PLANS FOR CONDUCTING MONITORING AND EVALUATION OF PROJECTS

| NO | CONSTITUENCY | PROJECT TO BE VISITED | ACTIVITY AND AMOUNT | BOARD’S DELIBERATION AND DATE | REMARKS |
| --- | --- | --- | --- | --- | --- |
| 1 | Chuka Igambang’ombe | Kibuga- Itugururu road | Gravelling of 10km road, Kshs. 3,348,275.87 | Conditional approval NGCDFC to submit a letter from KERRA indicating whether the road is National Government or the specific classification of the road The committee has also not discussed the specific road in the committee minute for purposes of okaying the resubmission Management to carry out verification visit(Board Paper of 11/12/2019) |  |
|  |  | All proposed projects are recommended for conditional approval subject to NG-CDFC revising the entire proposal with a view to ensuring that projects are allocated adequate funds Allocation of funds to Bursary, Emergency and Administration is recommended for approval |  |  | The Board management felt that they were a need to visit the constituency due to inadequate allocation of funds to the projects for 2019/20 F/Y |
| 2 | Isiolo North | All proposed projects are recommended for conditional approval apart from Administration, Bursary and Emergency which were approved subject to NG-CDFC revising its projects costing downward NG-CDFC to submit one BoQs for construction of classroom |  |  | The Board management felt that they were a need to visit the constituency due to inadequate allocation of funds to the projects for 2019/20 F/Y |
| 3 | Laisamis | NG-CDFC to revise cost of construction of a classroom from kshs.1,400,000 |  |  |  |
| 4. | Isiolo South | The management to visit the constituency to establish the delay in submission of the project proposal for 2019/20 F/y |  |  |  |