WEBUYE WEST NG-CDFC MEETING HELD ON 30TH JULY 2019 AT THE CDF BOARDROOM AT 9:00 AM.

NG-CDFC MEETING 3

PRELIMINARIES

1. Prayer

2. Introduction

3. Apologies

3. Adoption of Agenda

4. Chairman’s remarks

AGENDA

1. Reading and confirmation of previous minutes. 2. Matters arising. 3.Public participation report 4.Quater 1 report i)Complain reports ii)M&E report iii)PIS report iv)HIV repot v)Risk Management report 5.Asset status report 6.2019/2020 project proposals 7.Staff matters 8.Payments 9.Reallocation 10.Adjournment

MEMBERS PRESENT

1. PETER AMUTALLAH                             		CHAIRMAN

2. ESTHER SIMIYU			                       MEMBER

3. GEORGE SHIBANDA                			FAM

4. BENEAH 	NGOYA		           		SECRETARY

5. KIZITO KISIANG’ANI           		 	MEMBER

6. DORCAS N. MUNYOLE				MEMBER

7. MARY BUTASI				            MEMBER

8. LOTIATIA KIPKECH				DCC

IN ATTENDANCE

1. ANDREW NGEYWA                			COM

2. PETER SIFUNA			SUB COUNTY ACCOUNTANT

ABSENT WITH APOLOGY

1. EMMANUEL WANYONYI			MEMBER

NG-CDFC WBY.W/MIN-01/15/10/19 PRELIMINARIES

The meeting was called to order by the chairman at 11:00am, and a word of prayer was said by Mary Butasi

NG-CDFC WBY.W/MIN-02/15/10/19 READING AND CONFIRMATION OF

PREVIOUS MINUTES

The minutes of the previous meeting were read by the secretary and were proposed by Kizito Kisiang’ani who was seconded by Esther Simiyu as the true record of the deliberations.

NG-CDFC WBY.W/MIN-03/15/10/19 MATTERS ARISING

The bursary sub-com was asked to sit immediately and ask for all uncollected cheques and reallocate them.

The emergency fund for 18/19 was Kshs.5, 798,994 as confirmed by the manager. Kshs.5, 500,000 was allocated waiting for approval from the national board. Kshs.298, 994 had been used to do unihuts for the OCPD.

NG-CDFC WBY.W/MIN-04/15/10/19 PUBLIC PARTICIPATION REPORT

SITIKHO WARD

Milo,Mang’ana and Khalumuli projects were majorly on education and a few on security. There was also an issue of youth empowerment where they felt that CDF had not factored for them. On this, a way was to be found on how to empower youths by tendering and sports.

In Sitikho sublocation,Mwembula primary had almost all the classrooms condemned thus need support. Bituyu primary was as well under mud classrooms.

MATULO WARD

A Matulo girl looked critical since the students were sleeping in classrooms. The bursary committee was asked to be keen on documents. There was also an issue on representation of Kituni sublocation.

MISIKHU WARD

The major issue was Sirende ACK secondary whose girl’s dormitory had been condemned by the inspection team. Mungakha primary representative decried the shortage of fund in the school.

The principals appreciated how bursary for this year was distributed.

BOKOLI WARD

Milani primary was the issue with the highest number of challenges ranging from classrooms to toilets,so was St.Annes Maloho.

NG-CDFC WBY.W/MIN-05/15/10/19 QUARTER 1 REPORTS

(a). Complain Reports

There were complaints from;

- Fellow contractor limited.-Delay of variation at Makhonge primary. The variation team was asked to look at it from 15th of October 2019.

- Pambazuka construction limited.-Delayed payment over Ngwelo secondary project. To pays only upper advice of projects manager.

- George Makokha-Uncleared bursary cheque. The client mutilated the cheque by mistake.

- Ayub Barasa Karani-Brought a verbal complain about missing bursary award and he was advised to reapply.

(b).M&E report

The M&E report was read by the secretary;

- Chebosi girls-Committee to disburse remaining funds to avoid delay.

- SA Chebosi boy’s septic tank-There was a variation that needs to be discussed.

- Bokoli chief’s office-NGCDF to disburse the remaining balance to pay the contractor.

- Sambu PEFA primary-Needs additional 100,000 to complete the remaining works.

- Bokoli boys’ high school-School to wait for the reallocation letter to do a classroom.

- Matisi NGCDF office-NGCDF to follow up with telcom to supply laptops.

- St.Anthony school for the deaf-Has a variation that needs to be documented and discussed by NGCDF for approval.

- Township chief’s office-NGCDF neds to release funds for a septic tank.

- Misikhu friends’ boys’ high school-Was a variation that needs to be documented and discussed by NGCDF.

- Sirisia BOK-To check progress of land title deed processing.

- Brenda girls’ sec school-The school to wait for a reallocation letter to do a classroom.

- Manani sec-Contractor on site, job going on well.

- Ngwelo sec school-NGCDF commits to disburse the remaining funds to complete works for 18/19.

- Sitikho sec school-There was a variation that needs to be documented and discussed by NGCDF.

- Kuywa sec.-School to wait for a reallocation letter to do aclassroom.

In addition, the manager tabled a list of schools which had had bank balances since 14/15 FY. -The money amounted to Kshs. 2, 471,585.

It was agreed that the PMCs be called and asked to close the A/Cs using the little amounts remaining to take care of their need at individual levels but strictly on initial projects that the money was meant for.

For A/Cs that are below Kshs.1000 we write to them to close them.

(c).HIV Report

We are yet to do HIV training as per the goals of NGCDF Board.

(d). Risk Management report

The variation committee was turned into a risk management committee.

(e). Assets status report

The assets as at close to last year valued at Kshs.32, 512,086. They are:

- Land (office land)

- Buildings-valued at Kshs. 24,474,723 office & toilets

- Vehicle –Valued at Kshs. 4,616,600

- Office equip –Valued at Kshs. 10,003,621

- Computers

- ICT equipment

NG-CDFC WBY.W/MIN-06/15/10/19 2019/2020 PROJECT PROPOSALS

As per the circular number NG-CDFB/CEO/BOARD.CIRCULAR VOL.11 (014), the budget is Kshs.137, 367, 724. So as a committee we are required to identify projects through ward meetings. In addition, we are supposed to complete ongoing projects and have a strategic plan. We must also do a budget for staff and have an office.

Members felt money be found to do 3 classrooms at Bituyu primary school and it was agreed that it be prioritized in the next financial year ie. FY20/21.

The committee approved projects worth Ksh 137,367,724 for the financial year 19/20. The fund account manager was then tasked to submit the completed schedules as per the NGCDF act together with minutes from ward s Bokoli, Misikhu, Matulo and Sitikho together with the strategic plan.

The complete list of discussed and prioritized projects for submission to the board is as below

| WEBUYE WEST NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND PROJECT PROPOSALS 2019/20 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NO | Project Name | Original Cost | Cumulative allocation | Project activity | Balance to complete | Current Status |
|  |  | BOKOLI |  |  |  |  |
| 1 | Mahanga Pry School | 18,014,547.00 | 6,500,000.00 | Completion of 1 storey block of 6 classrooms Walling, Roofing, fittings and plasterworks | 9,000,000.00 | Ongoing |
| 2 | Maloho Pry School | 4,916,000.00 | 2,500,000.00 | Completion of 3 Classrooms-plasterworks, glazing Painting and finishes. | 2,416,000.00 | Ongoing |
| 3 | Chebini pry school | 800,000.00 | - | Purchase of one acre of land | 800,000.00 | New |
| 4 | St Marys Bokoli secondary school | 4,600,000.00 | 1,500,000.00 | Completion of 3 Classrooms-plasterworks, glazing Painting and finishes. | 3,100,000.00 | Ongoing |
| 5 | Chebosi Girls sec School | 1,000,000.00 | - | Furnishing of dormitory 320 beds metalic | 1,000,000.00 | Ongoing |
| 6 | Chebosi Girls sec School | 2,000,000.00 | - | Construction of septic tank 400 people capacity | 2,000,000.00 | Ongoing |
| 7 | Bokoli chiefs office | 5,500,000.00 | 4,600,000.00 | Completion of chiefs office roofing plastering, Floor screed | 900,000.00 | Ongoing |
| 8 | Miendo chiefs office | 5,000,000.00 | - | Construction of chiefs office upto walling level | 1,500,000.00 | New |
|  |  | MATULO |  |  |  |  |
| 9 | Matulo RC Primary | 4,642,180.00 | 2,500,000.00 | Completion of 3 Classrooms-plasterworks, glazing Painting and finishes. | 2,142,180.00 | Ongoing |
| 10 | St Anthony school for the deaf | 6,267,642.00 | 5,700,000.00 | Completion of adminstration block painting, firefighting equipments and finishes | 567,642.00 | Ongoing |
| 11 | Webuye DEB sec school | 1,400,000.00 | 1,200,000.00 | Completion of one classroom painting and finishes | 200,000.00 | Ongoing |
| 12 | Matulo Girls sec School | 43,000,000.00 | - | Construction of 320 capacity dorm substructure | 8,000,000.00 | new |
|  |  |  | MISIKHU |  |  |  |
| 13 | Manani pry sch | 18,509,166.00 | 9,000,000.00 | Completion of 1 storey block of 6 classrooms Roofing, plasterworks and glazing | 6,000,000.00 | Ongoing |
| 14 | Chengoli Pry School | 18,000,000.00 | 2,500,000.00 | Completion of 1 storey block of 6 classrooms walling and Roofing, | 7,500,000.00 | Ongoing |
| 15 | Misikhu Friends pry school | 2,400,000.00 | 1,300,000.00 | Completion of 2 Classrooms-plasterworks, and Painting | 361,172.01 | Ongoing |
| 16 | Makhonge Primary school | 4,643,654.00 | 4,000,000.00 | Completion of 3 classrooms painting and finishes | 643,654.00 | Ongoing |
| 17 | Bunjosi Pry School | 4,600,005.00 | 2,500,000.00 | Completion of 3 Classrooms-plasterworks, glazing Painting and finishes. | 2,100,005.00 | Ongoing |
| 18 | Sirende ACK Secondary school | 10,812,885.00 | - | Construction of 80 capacity dorm Subsstructure and walling | 4,350,000.00 | New |
| 19 | Lugulu Friends secoondary school | 18,000,000.00 | 2,500,000.00 | Completion of 1 storey block of 6 classrooms walling and Roofing, . | 9,000,000.00 | Ongoing |
|  |  | SITIKHO |  |  |  |  |
| 20 | Ngachi Pry School | 4,833,804.00 | 2,500,000.00 | Completion of 3 Classrooms-plasterworks, glazing Painting and finishes. | 2,333,804.00 | Ongoing |
| 21 | Ngachi Pry School | 350,000.00 | - | Purchase of half an acre of land | 350,000.00 | New |
| 22 | Bukunjangabo Pry Sch | 4,600,000.00 | 2,500,000.00 | Completion of 3 Classrooms-plasterworks, glazing Painting and finishes. | 2,100,000.00 | Ongoing |
| 23 | Khalala Primary School | 4,500,000.00 | - | Construction of 3 Classrooms-up to roof covering | 2,500,000.00 |  |
| 24 | Mwembula pry school | 9,500,000.00 | - | Construction of Six Classes, substructure and walling | 4,300,000.00 | New |
| 25 | Kuywa Primary School | 8,650,384.00 | 8,198,812.00 | Construction of adminstration block, substructure and walling | 4,000,000.00 | Ongoing |
| 26 | Khalumuli Secondary School | 2,000,000.00 | - | Completion of adminstration block roofing, plasterworks, painting and finishes. | 2,000,000.00 | New |
| 27 | Khalumuli ass Chiefs office | 1,000,000.00 | - | Purchase of land one acre | 1,000,000.00 | New |
|  |  |  | CONSTITUENCY |  |  |  |
| 28 | Secondary Bursaries | 17,000,000.00 | - | To cater for education bursary for needy and deserving secondary school students in the constituency | 17,000,000.00 | New |
| 29 | Tertiary Bursaries | 17,341,931.03 | - | To cater for education bursary for needy and deserving tertiary school students in the constituency | 17,341,931.03 | New |
| 30 | Employee salaries office admin | 5,720,763.00 | - | Payment of NG-CDF staff salaries and gratuity | 5,720,763.00 | New |
| 31 | Goods and services office admin | 1,801,820.00 | - | NG Advertisements, publications, and public awareness, office utility bills, stationery and motor vehicle operating costs | 1,801,820.00 | New |
| 32 | NSSF office admin | 118,080.00 | - | Payment of NSSF deductions | 118,080.00 | New |
| 33 | NHIF office admin | 101,400.00 | - | Payment of NHIF deductions | 101,400.00 | New |
| 34 | Committee expenses office admin | 500,000.00 | - | Payment of sitting allowances, transport and conferences | 500,000.00 | New |
| 35 | Emergency | 7,198,241.38 | - | Unallocated amount to be available for emergencies that may occur within the constituency | 7,198,241.38 | New |
| 36 | Monitoring and evaluation NG-CDFC/PMC capacity building | 2,621,031.72 | - | Monitoring & evaluation goods and services committee expenses NG-CDFC/PMC capacity building | 2,621,031.72 | New |
| 37 | Committee expenses | 500,000.00 | - | Payment committee sitting allowances, transport and conferences | 500,000.00 | New |
| 38 | Goods and services | 1,000,000.00 | - | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence | 1,000,000.00 | New |
| 39 | NGCDF office | 2,400,000.00 | - | Fencing of NGCDF compoound in Matisi with Chain link, barbed wire and concrete posts with a gate | 2,400,000.00 | New |
| 39 | Environment | 200,000.00 | - | Installation of 10,000lts tank on a well done concrete base, fixing of gutters 180LM at Yalusi primary school | 200,000.00 | New |
| 40 | Environment | 200,000.00 | - | Installation of 10,000lts tank on a well done concrete base, fixing of gutters 180LM at Sawa PCU pry school | 200,000.00 | New |
| 41 | Sports | 2,000,000.00 | 1,500,000.00 | Purchase of Equipments for winning teams in rugby tournaments Misikhu ward Team, Bokoli ward Team, Sitikho ward Team and Matulo ward Team | 500,000.00 | New |
|  | TOTAL |  |  |  | 137,367,724.14 |  |

NG-CDFC WBY.W/MIN-06/15/10/19 2019/2020 STAFF MATTERS

The committee unanimously agreed to pay the employees their entire gratuity as shown in the table. Kshs.1, 491,640.

| S/N | NAME | GRATUITY | PAYE | NET |
| --- | --- | --- | --- | --- |
| 1 | SAUL WEFWFWA | 278,504 | 66,880 | 211,624 |
| 2 | PETER WEKESA BARASA | 311,116 | 78,214 | 232,902 |
| 3 | PHILIS NAMASWA | 243,908 | 51,895 | 192,013 |
| 4 | PAMELA SITUMA | 243,908 | 40,365 | 203,543 |
| 5 | CATHERINE WAMOTO | 243,908 | 53,161 | 190,747 |
| 6 | GEORGE BARASA | 149,110 | 20,252 | 128,858 |
| 7 | PAMELA SIFUMA | 178,600 | 24,862 | 153,738 |
| 8 | ANTONY MUHINDI | 176,941 | 28,726 | 148,215 |
|  |  | 1,825,995 | 364,355 | 1,491,640 |

Going forward, the gratuity for George Barasa, Stephen Omulemule and John Barasa be charged at 10% of their salary.

NG-CDFC WBY.W/MIN-07/30/07/19 PAYMENT

The committee approved the following payments;

- Gratuity -Kshs. 1,491,640

- Webmar – Kshs. 100,000-Payment for fuel

- Muafrika printers – kshs 20,000-Printing of bursary forms.

- Sports – kshs 500,000-Purchase of sports equipments to the teams.

- Kenyatta university –ksh 9,000

- Mahanga pri ksh 1,500,000-Construction of 6 no classrooms.

- Beneah	 Ngoya ksh 15,000-Allowance for tender award meeting.

- Ezekiel mugita ksh 33,600-Per diem

- George shibanda ksh 33,600 Per diem

- Maseno University ksh 15,000

- Mmust ksh 15,000

- Mmust ksh 35,000

- St Mary’s mumias ksh 10,000

- Peter Barasa ksh 20,000

- CDF Office ksh 700,000-Completion of CDF office and installation of water tanks

- NGCDF Allowance ksh 64,000

- Peter Sifuna ksh 8,000

- Peter Barasa ksh 23,000-To facilitate KRA auditing exercise

- ICPAK Ksh 15,200

- ICPAK Ksh 25,000

- Peter Amutalla ksh 3,000-For monitoring and evaluation

- Seal honey ksh 32,599-Purchase of office toner.

- Mmust ksh 20,000

- George Shibanda ksh 20,000-Cash for office use

- Sigalagala National Polytechnic ksh 10,000

- East Africa School of Aviation ksh 5,000

- Macron fire equipment LTD. Kshs. 25,752-For refilling of fire units

- Central farmers Kshs. 41,861-For maintenance of GK 503G vehicle

- Central farmers Kshs. 41,106-For maintenance of GK 503G vehicle

- George Shibanda Kshs. 2,501-Photocopying of strategic plan booklet

- Abraham Injendi Kshs. 25,000-For office use

- Webmar – Kshs. 30,000-Payment for fuel

- Ezakiel Mugita Kshs.43,000-To facilitate project PMC training

- George Shibanda Kshs.17,150-Office use

- George Shibanda Kshs.27,000-Monitoring and evaluation at Chebosi girls secondary school

- Peter Sifuna Kshs.25,000-Per diem

- George Shibanda Kshs.25,000-Per diem

- Peter Amutallah Kshs.35,000-Per diem

- Inyanji Mmasava Kshs.20,000-Inspection and assesment of Sitikho secondary school.

- Pamellah Situma Kshs.28,500-For office use

- Postal corporation Kshs.16,000-Postal charges

- Beneah Ngoya Kshs. 24,500-Tender evaluation award

- Catherine Wamoto Kshs.5,000-Monitoring and evaluation allowance

- George Shibanda Kshs.50,000-For office use

- Peter Sifuna Kshs.15,000-Cash for office use

- George Shibanda Kshs.15000-Cash for office use

- George Shibanda Kshs.60,000-Cash for office use

- George Shibanda Kshs.5,000-Cash for office use

- George Shibanda Kshs.5,500-Cash for office use

- Peter Sifuna Kshs.10,000-Cash for office use

- George Shibanda Kshs.11,000-Cash for office use

- George Shibanda Kshs.26,200-Per diem

- George Shibanda Kshs.5,000-Cash for office use

- George Shibanda Kshs.40,000-Cash for office use

- Peter Amutallah Kshs.20,000-M&E Committee allowance

Payments of emergency 2018/19 allocation upon approval by CDF board

- Bokoli RC primary- 500,000

- St. Marys Bokoli sec- 1,500,000

- Lugulu day sec- 2,500,000

- CDF office- 700,000

- Bunang’eni primary- 200,000

- Sambu PEFA primary- 100,000

Bank balance at end of sep- 26,447,130.

NG-CDF WBY.W/MIN-09/30/19 REALLOCATION

The committee resolved to reallocate the following project;

| Reallocated from | Reallocated to | Amount | Reason |
| --- | --- | --- | --- |
| Cheng’oli primary school. Construction of three classrooms. | Cheng’oli primary school. Construction of a storey building of 6 classrooms. | 2,500,000 | Shortage of land. |

NG-CDFC WBY.W/MIN-08/30/07/19 ADJOURNMENT

There being no other business, the meeting was closed with a prayer from Dorcus N. Munyole

MINUTES SIGNED FOR CIRCULATION

NG-CDFC CHAIRMAN ………………………………    DATE………………………

NG- CDFC SECRETARY ……………………………      DATE………………………