0: INTRODUCTION OR BACKGROUND

0.1 About NG- CDF

The constituency development fund was established by the CDF act 2003 with the primary objective of dedicating a minimum of 2.5 percent of annual ordinary public revenue to grassroots development to eradicate poverty.The Act recognizes the constituency as a platform for identification, performance and implementation of the National Government function. The Act further provides for the participation of the people in the determination and implementation of the identified National Government development projects at the constituency level pursuant to article 10(2)(a) of the constitution. Over the years the Act has been amended with the recent amendment carried out in the year 2015 to align the Act with new constitution. The objective of the funds are now clearly provided for in the Act by clearly delineating the funds as specific to the National Government .It is now clearly specified that eligible projects under the NG-CDF Act are only those entailing works or services falling under the functions of the National Government. The Act further clearly specifies that the Fund is drawn from the National Government ‘s share of revenue in accordance with the Division of Revenue Act enacted pursuant to Article 218 of the constitution

0.2 About Mathira

Mathira constituency is one of the constituencies in Nyei County. The constituency covers an area of 389Km2 The Constituency borders Kieni Constituency to the west, Mount Kenya forest to the north, Ndia constituency to the east and Mukurweini constituency to the south.

The constituency comprises two Sub-counties namely Mathira East and Mathira West and 6 wards namely Kirimukuyu,Konyu ,Iriani ,Karatina,Magutu and Ruguru.

From financial Year 2013/2014 to financial year 2016/2017 Mathira Constituency has received a total of Ksh………………………….Which has been spent in various projects as set out in the attached schedule of projects.

EDUCATION

The committee is also happy to report an improvement in terms of education infrastructure through construction of classrooms, toilets, purchase of desks and improvement of already existing facilities. Almost all the primary schools have benefited from the CDF funds. Some new secondary schools have been initiated and supported by CDF and are now reporting great achievement in terms of enrollment and academic performance. Some of the education facilities include the following:

| EDUCATION SECTOR |  |  |
| --- | --- | --- |
| Project Name | Major Activities | Status |
| Kiamucheru Primary School | construction of two a classrooms and renovation of existing classrooms. | complete and in use |
| Karatina Urban Primary School | Construction of four classrooms to completion | complete and in use |
| Karatina Deb Primary School | Construction of Modern 20 door toilet block to completion | complete and in use |
| Hiriga primary school | Construction of additional 8 classrooms from foundation to completion and school gate | complete and in use |
| Kieni Secondary School | Rennovation of laboratory unit, classrooms and administration block. | complete |
| Gathehu Secondary School | construction of of a classroom to completion by roofing and plastering | complete |
| Gatundu Secondary School | construction of laboratory unit | complete |
| Giakabei secondary | construction of 2 additional classrooms co-funded by PTA | complete |
| Gitunduti secondary school | Construction of a storey classroom | complete |
| Hiriga Secondary School | construction of three classrooms from foundation to completion and Roofing of Administration block. The Project is co-funded by PTA | complete |
| Iruri Secondary School | Construction of a classroom and a laboratory unit | complete |
| Kabiruini Secondary School | construction of a dormitory | complete |
| Maganjo Sec School | Construction of 4 classrooms from foundation to completion and a laboratory unit | complete |
| Muthea Secondary School | Construction of a laboratory unit to completion | complete |
| Ndima- ini Secondary | Construction of classroom 4 classrooms | complete |
| Ragati secondary | Construction of a laboratory unit an two classrooms to completion | complete |
| Rititi Secondary school | Construction of a laboratory unit to completion | complete and in use |
| Mathira Technical Training Institute | Fencing of the compound, Gate Installation, ground leveling and land scaping to enable planting of trees and flowers. | Complete. Intake is in progree and teaching is set to start in January. |

The committee wishes to draw your attention to the following Education projects which are ongoing and require completion.

|  | Project Name | Major Activity | Status | Remarks |
| --- | --- | --- | --- | --- |
|  | SECONDARY SCHOOLS |  |  |  |
| 1 | Gaturiri secondary | purchase of computers and construction of foundation of multipurose hall | not started | Funds not yet received |
| 2 | Gitunduti secondary school | Construction of a storey classroom | ongoing | process ongoing |
| 3 | Icuga Secondary School | Construction of school administration block ,co-funded with PTA.CDF funds will be used for foundation and walling. | Ongoing | process ongoing |
| 4 | Kanyama secondary | Foundation and walling of lab unit, Completion of a laboratory Unit by roofing and fixing of doors and windows | Ongoing | requires more funding to complete |
| 5 | Kieni Secondary School | Fencing of school compound with Ksh 200,000 and renovation of 2 classroom by flooring, wall plastering and painting | phase allocated complete. | Requires more funding to construct classrooms |
| 6 | Maganjo Sec School | Construction of 4 classrooms from foundation to completion, Construction of a laboratory unit with Ksh 2,500,000 and completion of 2 ongoing classrooms by plastering, installation of doors and windows and painting | complete |  |
| 7 | Miiri Secondary School | Construction of the dining Hall | ongoing | need more funds to complete |
| 8 | Ngaini secondary | Construction of multipurpose hall | Complete |  |
| 10 | Rititi Secondary school | completion of laboratory unit by plastering windows and doors | complete |  |
| 11 | Tumutumu secondary | Roof replacement | Ongoing | process ongoing |
| 12 | Karatina Special School | Construction of dormitory a co-funded project by PTA.CDF to do foundation stage. | ongoing | Process ongoing |
| 13 | Ragati secondary school | Construction of two classrooms | complete | realocation from emergency REF: CDF BOARD/MATHIRA/VOL.1/8 |
|  | PRIMARY SCHOOL |  |  |  |
| 1 | Kianjeneni Primary School | Renovation of five (5)Classrooms by wall plastering, Flooring windows Panes installation | not started | cheque is read |
| 3 | Ngorano Primary School | Construction of 10 door toilets and renovation classrooms | ongoing | need more funds to complete |

The committee wishes to draw your attention to the following Security projects which are ongoing and require completion.

|  | SECURITY SECTOR |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Gaikuyu Police Post | Fencing of the police post | Not started | Waiting cheque disbursment |
| 2 | Karogoto AP Post | Construction Water tank and water connection. | Not started | Waiting cheque disbursment |
| 3 | Kiamachimbi Police Station | Construction of a social Hall | ongoing | need more funds to complete |
| 4 | Kiamwangi Police Post | Completion of offices and armory by plastering, wall painting electrical and plumbing works and fencing | complete | ongoing |
| 5 | Kiaruhiu Police post | Construction of administration block | Ongoing | need more funds to complete |
| 6 | Kirimara ACC's Office | Construction of an office | ongoing | process ongoing |
| 7 | Magutu ACC Office | Construction of an office | Not started | cheque not collected |

HEALTH SECTOR AND POLYTECHNICS

CDF has continued to support health sector. A number of health facilities have been initiated and completed and are helping the community to access good healthcare. It is important to note that the CDF Act was amended to align it with the new constitution in 2015.Among the changes that was brought about by the amendment was separation of projects done by the national government and those done by the county government. Health sector has since been put under the county Government. However before the amendment CDF iniated the following health projects and youth polytechnics project which are not complete and would wish the county Government to take them over to ensure completion and commissioning.

| LOCATION | NAME OF THE PROJECT | SCOPE OF WORK TO BE DONE (PENDING ACTIVITIES TO BE CLEARLY INDICATED) | PROJECT COST (AS PER WORKS OFFICERS’ CERTIFIED ESTIMATES | COST OF PROJECT COMPLETION (CERTIFIED) | CUMULATIVE EXPENDITURE TO DATE (CERTIFIED) | CURRENT STATUS OF THE PROJECT | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Kirimukuyu Ward | Gatiko Dispensary | Plastering, Fixing Door & Windows, Painting Sanitation Block Electrical works Basic equipment’s Furniture’s | 4,000,000 | 4,000,000 | 2,500,000 | The structure is complete only finishes | Dispensary is not operational |
| Ruguru Ward | Chieni Dispensary | Sanitation Block Basic Equipment & furniture’s | 4,000,000 | 1,500,000 | 3,500,000 | Dispensary structure complete ready for use. No Sanitation block | Pending works includes sanitation block, gate installation. Water connection not yet done. Basic furniture and equipments required. |
| Magutu Ward | Gathehu Dispensary | Basic Equipment Furniture | 2,500,000 | 1,000,000 | 1,450,000 | Complete only equipment’s remaining | Building ready for occupation. Basic furniture and equipments required. |
| Iriaini Ward | Kangocho Dispensary | Plastering And Painting Electrical works Basic equipment’s Furniture’s | 3,000,000 | 2,500,000 | 1,580,000 | Structure complete with no finishes. | Building ready for occupation |
| Konyu ward | Ndimai-ni dispensary | Maternity beds Basic equipment’s | 5,000,000 | 1,500,000 | 3,300,000 | Construction of maternity | Building ready for commissioning.Martenity beds and other equipments required |
| Kirimukuyu | Kaiyaba dispensary | Basic equipment Furniture’s Sanitation block | 2,000,000 | 2,000,000 | 800,000 | Construction of outpatient unit from foundation, walling & roofing | Renovation done on two classrooms done, one classroom remaining.Power and water connections pending. |
| Kirimukuyu ward | Karogoto Dispensary | Roofing, Finishes basic equipment’s Furniture’s & Sanitation Block | 4,000,000 | 2,500,000 | 1,700,000 | Roofing, wall plastering, fixing doors & windows. | More funds required to complete the project. Plastering,water connection, power installation, painting and fencing the compound.installing basic furnitures and Equipments |
| Kirimukuyu ward | Gachuiro Dispensary | Basic Equipment’s Furniture | 2,500,000 | 1,000,000 | 1,700,000 | Foundation Construction Painting & electricity installation | Dispensary building ready for operationing |
| Iriaini ward | Kiaruhiu Polytechnic | Basic Equipment Furniture & Sanitation Block | 4,000,000 | 2,000,000 | 2,000,000 | Classroom, sheds,& strong room complete | Sanitation block & equipments pending |
| Irianin ward | Mururu-ini Polytechnique | Basic Equipment Furniture | 3,000,000 | 1,500,000 | 2,500,000 | Roofing, Plastering & Construction of workshop is complete | Sanitation block & equipments pending |
| Kirimukuyu | Thamaru youth polytechnic | Basic Equipment Furniture &sanitation block | 2,500,000 | 2,500,000 | 1,300,000 | Project complete but no equipment’s. | Polytechnic still requires some equipments |
| Magutu | Kamunyuini Polytechnic | Equipment Furniture & Sanitation Block | 5,000,000 | 2,500,000 | 4,400,000 | Project complete but no equipment’s & sanitation block | Equipments required to operationalize the polytechnic |
| Konyu ward | Gachuku Polytechnic | Sanitation Block | 3,000,000 | 500,000 | 2,000,000 | Project complete but requires additional sanitation block |  |
| Kirimukuyu | Mung’aria Polytechnic | Equipment’s Furniture & sanitation block | 2,500,000 | 2,500,000 | 350,000 | Construction work complete but requires equipment’s | Equipments lacking |

- COMPLETED DEVOLVED PROJECTS THAT ARE COMPLETE

COUNTY: NYERI

| LOCATION | SECTOR | NAME OF THE PROJECT AND ACTIVITIES | CUMULATIVE EXPENDITURE TO DATE (CERTIFIED) | DATE OF COMPLETION OF THE PROJECT | REMARKS |
| --- | --- | --- | --- | --- | --- |
| Kirimukuyu ward | Health | Githima Dispensary | 2,300,000 | May 2014 | Project Complete |
| Karatina ward | Health | Gathumbi Dispensary | 1,000,000 | Jan 2015 | Project complete |

SECURITY PROJECT

Security has been a key priority area for funding by Mathira CDFC. Some key projects include;

|  | SECURITY SECTOR |  |  |
| --- | --- | --- | --- |
|  | Name | Major Activity | Status |
| 1 | Kariki Chiefs Camp | Construction of the chief’s office from foundation to completion and purchase of office furniture. | complete and in use |
| 2 | Kiamabara D.O office | Conversion of existing buildings to security office by partitioning of rooms, doors, windows installation, painting of the building and electricity installation. | complete and in use |
| 3 | Kiamariga/Ruguru D.O's Office | Construction of D.O's office from foundation to completion, constraction of toilets, fencing and gate installation. | complete |
| 4 | Mathaithi Police Post | Construction of reporting office and staff houses from foundation to completion. Construction of toilets and fencing of the police post. | complete and in use |
| 5 | Mathira West Police Headquarter | Conversion of existing buildings to security office by partitioning of rooms, doors, windows installation and painting of the building. | complete |
| 6 | Hombe Chiefs Camp | Conversion of a Nursery school to offices by partitioning of rooms ,wall and floor plastering ,installing doors and windows and painting | complete |
| 7 | Sagana AP Camp | Construction of one office and staff houses from foundation to completion | complete and in use |

NG-CDFC ASSETS:

The NG-CDFC Assets are as per the attached:

STAFF STABLISHMENT

The CDFC employees who are in office are as follows:

| NAME | ID NUMBER | DEGIGNATION | SALARY AMOUNT | ACCOUNT NUMBER |
| --- | --- | --- | --- | --- |
| Jeremiah Nyaga Wanjira | 24664111 | ACCOUNTANT | 35,000.00 | 01109059065600 |
| Simon Karanja Kamau | 0762892 | DRIVER | 21,034.00 | 01109410104700 |
| Samson Ngugi Njuguna | 29590814 | RECORDS OFFICER | 16,692.00 |  |
| Crispus Gathiaka Munuhe | 10845720 | PROJECT CO-ORDINATOR | 15,000.00 | 01116630787300 |
| Dorcas Njeri Wanjiru | 23381778 | CLEANER | 10,000 | 01116106332300 |

Liabilities:

Pending cheques:

The following cheques are held in the office awaiting the NG_CDFC decision on disbursement

| Name of the Project | Amount |
| --- | --- |
| Gaikuyu Police Post | 500,000.00 |
| Karogoto AP Post | 500,000.00 |
| Magutu ACC Office | 500,000.00 |

Other Liabilities

| Name of the supplier | Amount |
| --- | --- |

Other claims not verifiable by the office:

| Name of the supplier | Activity | Amount |
| --- | --- | --- |
| Stephen Magondu | Construction of bridge at Ihwagi | 150,000 |
| Stephen Magondu | Murraming of roads at Magutu,gathehu and Kirimukuyu | 1000,000 |
| Stephen Magondu | Construction of Boda Boda Sheds | 3,214,000 |

Financial position:

The constituency development fund is audited every year by the office of the Auditor General.The office is happy to report that there are no outstanding Audit issue and for the last two years the constituency has received  an unqualified(Clean) audit report.

The committee has received all the funding relating to financial year 2016/2017 and therefore there are no pending funds due from the board.

The bank balance as at 18/12/2017 is………………………………..

This amount includes unpresented cheques stated above .

The journey to this success has not been without challenges .Key among the challenges have been

- Inadequate funding to cater for all the projects prioritized by the constituents

- Some PMC have not been very honest and to some extent have misappropriated the funding.

- Lack of support from the various government departments in terms of technical advice and involvement. Many technical department site lack of enough personnel to facilitate proper involvement in CDF project implantation.

- Lack of sustainability of projects funded by the CDF especially Dispensaries which require to be taken over by the Ministry of health for staffing and medical supplies.

Despite all these challenges the outgoing CDFC wishes the incoming CDFC all the best as they embark on this noble calling of serving the people of Mathira. They have done their bit but believe that there is room for much more. The committee shall be at hand to assist in any way that may help to push Mathira constituency development Agenda to great heights.

WAY FORWARD.

The immediate activity that the committee is required to undertake is submission of 2017/2018 financial year project proposal.Project proposals submitted to the board shall be in compliance with Article 10 of the constitution which articulates the  National Values and Principles of Governance that includes democracy and participation of the people .Section 27(1)of the NG-CDF Act reqires that the chairperson of the constituency committee shall,within the first year of the commencement of a new parliament and atleast once every two years thereafter ,convene open forum public meeting in every ward in the constituency to deliberate on development matters in the ward and in the constituency.The Constituency committee shall thereafter deliberate on project proposal from all the wards and identify a list of priority projects.

In this regard, every constituency must ensure that the projects proposals are informed by the ward consultative forum reports.