| National Government Constituency Development Fund | Lamu East Constituency 2021 |  |
| --- | --- | --- |
| Minutes of the Meeting held on Thursday, August 30th, 2021 at Lamu East NG-CDF Office Boardroom. |  | Lamu East NG-CDF Committee |

MEMBERS PRESENT

| S/NO | NAMES | DESIGNATION |
| --- | --- | --- |
|  | Ali Kassim Msalam | Chairman |
|  | Khadija Swabir Mohamed | Secretary |
|  | Mohamed Hassan Swaleh | Member |
|  | Tima Abuu Bamkuu | Member |
|  | Yumbe Hassan Athman | Member |
|  | Khadija Mohamed Aboud | Member |
|  | Mohamed Farouq Kame | Member |
|  | Hassan Omar | Member |
|  | Josef Kumbatha | Fund Account Manager |

APOLOGY

- DCC Mohamud - Member

AGENDA

- Opening remarks by Chairperson

- Reading and Confirmation of Minutes of Previous Meeting

- Matters Arising

- Reports on the Public Ward Barazas

- Preparation and submission of Project Proposal Budget for FY 2021/2022

- Any Other Business (A.O.B).

PRELIMINARIES

The chairman called the meeting to order at 1123 hours with a word of prayer by Farouq Mohamed Kame.  He welcomed members to the day's session and thanked them for responding timely despite the short notice.

He wished all members fruitful deliberations.

The chairman went ahead to table the items of agenda as listed and urged members to participate actively in the deliberations of the day's business.

MIN 1/30/08/2021 - READING AND CONFIRMATION OF MINUTES OF PREVIOUS MEETING

Minutes of the previous sitting were read by the secretary, proposed by Tima Abuu, confirmed by Khadija Aboud and unanimously adopted by the committee as a true record of that day's deliberations.

MIN 2/30/08/2021 - MATTERS ARISING FROM PREVIOUS MINUTES

The chairman thanked members for the active role they played during the meet the people tour where the community had the opportunity to engage the committee one on one on matters of development, expectations, hearsay, future plans and feed back on implemented programs.

The committee was pleased that it was such a successful activity that gave a lot of insights to the programs being implemented by the committee.

MIN 3/30/08/2021 - REPORTS ON PUBLIC WARD BARAZAS

Reports of the public ward barazas conducted at the beginning of the month of August in readiness for the preparation of the project proposal budget for the financial year 2021/2022 as per the attached program of activities was tabled, discussed and endorsed by the committee as a true record of the views collected from the community.

PUBLIC WARD BARAZAS PROGRAM OF ACTIVITIES

| Date | Venue | Time | Villages Represented |
| --- | --- | --- | --- |
| 01/08/2021 | KIUNGA WARD |  |  |
|  | Kiunga Primary School grounds | 8:00am | Kiunga and Ishakani |
|  | Mkokoni Primary School | 2:00pm | Mkokoni |
| 02/08/2021 | KIUNGA WARD |  |  |
|  | Kiwayuu Primary School grounds | 8:00am | Kiwayuu Island |
|  | Ndau Primary School grounds | 2:00pm | Ndau Island |
| 03/08/2021 | FAZA WARD |  |  |
|  | Kizingitini Secondary School grounds | 8:00am | Kizingitini |
|  | Mbwajumwali Primary School grounds | 2:00pm | Mbwajumwali and Myabogi |
| 04/08/2021 | FAZA WARD |  |  |
|  | Tchundwa Primary School grounds | 8:00am | Tchundwa |
|  | Faza Secondary School grounds | 2:00pm | Faza |
| 05/08/2021 | FAZA WARD |  |  |
|  | Siyu Primary School grounds | 8:00am | Siyu and Shanga |
|  | Pate Primary School grounds | 2:00pm | Pate |
| 06/08/2021 | FAZA WARD |  |  |
|  | Mtangawanda Primary School grounds | 8:00am | Mtangawanda |
|  | BASUBA WARD |  |  |
|  | Mararani Primary School grounds | 2:00pm | Kiangwe, Mararani, Milimani, Mangai and Basuba |

REPORTS ON THE PUBLIC WARD BARAZAS

The ward meetings were conducted at all major villages in the Islands between 1 August 2021 and 6 August, 2021.

OBJECTIVE

- To conduct public forums and involve public participation in accordance to the NG-CDF ACT 2015 section 27(1)

- To sensitize the community on NG-CDF work and emerging issues

- To get customer feed-back on NG-CDF work

PLANNED ACTIVITIES

The planned activity was to convene open forum public meetings in each ward

TERMS OF REFERNCE

- To sensitize the community on NGCDF work done from 2013 to date

- Give a progress report on the work done since last Ward Forums in 2019

- Sensitize the community on new bursary policy and application forms

- Inform the community on eligible projects

- Invite members to give projects proposals and their priorities

- Address challenges and questions raised

- Meet with end user departments in Administration, Security and Education

THE TEAM

The team was composed of the following members

- Hon. Sharif Athuman - Chairman of the Constituency Oversight Committee

- Abuu Loo Mohamed - COC Member

- Hassan Omar - COC Member

- Ali Kassim – Chairman NGCDF Committee and Convener

- Tima Abuu - NGCDF Committee Member

- Yumbe Hassan - NGCDF Committee Member

- Mohamed Farouq Kame - NGCDF Committee Member

- Hassan Mohamed - NGCDF Committee Member

- Hassan Omar - NGCDF Committee Member

- Josef Kumbatha - Fund Account Manager

- Mwanamkuu Sheyumbe - NGCDF Office staff

- Respective Area Chiefs and Assistant Chiefs

- Security team

- The general public

- KIUNGA WARD – 1ST TO 2ND August, 2021

The projects for this area covered the frontier village of Ishakani bordering Somalia.

The following Projects were proposed for Kiunga Village of Kiunga Ward at 10.00AM:

- KIUNGA VILLAGE meeting held at Kiunga Primary School – Attendance 53 villagers

- Kiunga Primary School Kiunga additional classrooms and major Renovations on dilapidated structures that have rust iron sheets due to the salty humidity from the ocean, cracking walls and rough floor surfaces, School fence (preferable perimeter wall fence, desks, staff furniture and IT equipment

- Kiunga Sec Science Laboratory, School Fence, Lockers and chairs, Science laboratory, Library, Staff houses

- Furniture for Kiunga Chief Office

- Assistant County Commissioners offices and renovation of Kiunga Police Station

REJECTED PROJECTS

- Fishing boats and fishing equipment

- Social Hall

- Water Djabias

The following Projects were proposed for Ishakani Village of Kiunga Ward:

- ISHAKANI VILLAGE meeting held at Kiunga Primary School – Attendance 23 villagers

- Renovation of classrooms at Ishakani Primary School

- Extra Classrooms for Ishakani Primary School

- Block Toilets for the school

- Fencing of Ishakani Primary school

- MKOKONI VILLAGE meeting held at Mkokoni Primary School  at 2.00PM

- Attendance 76 villagers

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- School PTA

- Representatives from Basuba ward

- Village guard representative

- Primary and secondary schools Head Teachers

- Mkokoni Youth Group

- Fishermen representative

- Mangrove welfare group

PRELIMINARIES

The team met at Mkokoni Primary School and had an opportunity to monitor the on-going construction work of Mkokoni Chief’s Office  that was yet to take off due to village politicking

CONCERNS

The community was concerned that development agendas for the area were being interfered with by political interested rivalry groups that were incited to reject the implementation of community development projects

However, the community was grateful for, Police Post, desks and Mkokoni primary school Administration block

The following Projects were proposed for Mkokoni Village of Kiunga Ward:

- Mkokoni Primary School Fence

- Teacher’s staff quarters

- Administration block furniture

- School desks

- School public toilets

- Proposed Mkokoni  Secondary School

Projects Proposed but rejected

- Funding for Youth Groups, Welfare Groups and Mkokoni Cultural Activities which fall under County Government

- Renovation of Social Hall which also falls under County Government

- Street lighting which also falls under County Government

- Water Desalination Plant which also falls under County Government

- Training for life guards also falls under County Government

- KIUNGA WARD – KIWAYUU PRIMARY SCHOOL – 2ND August, 2021

- KIWAYUU VILLAGE:- Island of Kiwayuu  meeting held at Kiwayuu Primary School  at 10.00AM    – Attendance 54 villagers

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- Head teacher

- Representatives from Fishing Welfare

- School committee

- Opinion leaders

The following Projects were proposed for Kiwayuu Village of Kiunga Ward:

- Kiwayuu Primary School Fence

- Rehabilitation of Kiwayuu Chandani Feeder Primary School

- Additional Classrooms at Kiwayuu Chandani Feeder School

- Additional Classroms at Kiwayuu Primary School

- KIUNGA WARD – NDAU PRIMARY SCHOOL

- NDAU VILLAGE: Island of Ndau village meeting held at Ndau  Primary School  at 2.00 PM– Attendance 58 villagers

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- Head teacher

- Representatives from Water Association

- School committee

- Opinion leaders

The following Projects were proposed for Ndau Village of Kiunga Ward: People present are among others include:

- Furniture for the new Administration Offices i.e Ndau AP Post

- Proposed Construction of Ndau Secondary School

REJECTED PROJECTS

- Repossessing of the handed over water desalination plant from County Government – water company - LAWASCO

- Renovation of Ndau Dispensary

- FAZA WARD – KIZINGITINI SECONDARY SCHOOL – 3RD August, 2021

- KIZINGITINI VILLAGE meeting held at Kizingitini Secondary School at 8.00AM– Attendance 78 villagers

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- Head teacher

- Representatives of school management committee

- Kizingitini Boys and Kizingitini Girls Primary schools committee

- Water Association representative

- Religious leaders

- Opinion leaders

Security and Administration Proposed projects

- Sub County Amour

- ACC’s office and Chief’s office – Divisional offices

- Fencing of the Police Station

- Rehabilitation of Police Lines

Education Proposed projects

Kizingitini Secondary School

- Renovation of Science Laboratory, Administration block and classrooms of Kizingitini Secondary School

- Proposed construction of Perimeter wall fence

Kizingitini Girls Primary School

- Additional Classrooms at Kizingitini Girls Primary School

- Renovation of dilapidated classrooms

- Sea barrier wall for Kizingitini Girls Primary School

- Proposed perimeter wall fence for the girls primary school

Kizingitini Boys Primary School

- Additional classrooms at Kizingitini Boys Primary School

- Renovation of dilapidated classroom structures at Kizingitini Boys primary school

- Fencing and reclaiming the quarry next to the school

- FAZA WARD – MBWAJUMWALI PRIMARY SCHOOL – 2.00PM

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- Head teacher

- Representatives of Myabogi village

- School management committees

- MBWAJUMWALI VILLAGE

- Proposed Mbwajumwali Primary School perimeter wall fence

- Mbwajumwali Secondary School - completion of Multipurpose hall, installation of water harvesting facilities

- Proposed construction of Mbwajumwali Secondary school fence

- Proposed construction of Library at Mbwajumwali Secondary school

- Renovation of the dilapidated classrooms at Mbwajumwali primary school

- Expansion of Mbwajumwali AP Post

- Furnishing of Mbwajumwali Primary School Library

- MYABOGI VILLAGE

- Additional new classrooms at Myabogi Primary School

- Renovation of dilapidated classrooms at Myabogi primary school

- Furnishing of the new Administration block at Myabogi Primary School

- Proposed fence for Myabogi primary School

- FAZA WARD – TCHUNDWA VILLAGE AT 10.00AM – 4TH August, 2021

- TCHUNDWA VILLAGE meeting held at Tchundwa Primary School  at 9.00AM– Attendance 12 villagers

People present are among others include:

- Area Chief

- Retired Kadhi

- Current Kadhi

- Village elders

- Head teacher

- Representatives of women groups

- Representative of PLWD

- Opinion leaders

- Religious leaders

This was the most difficult session with heavy presence of police, activists and reporters after a police operation searching for a lost police officers who was found murdered. Police held a door to door operation searching for the murderers and lost loaded fire arm

Proposed projects

Security Projects –

- Toilets for Tchundwa Chief Office

- Proposed expansion of Tchundwa AP Post

Education Projects –

- Renovation of Tchundwa primary school dilapidated classrooms

- Proposed construction of school fence

- Proposed construction of Tchundwa secondary school

- FAZA WARD – FAZA SECONDARY SCHOOL AT 2.00PM– 4TH August, 2021

- FAZA VILLAGE meeting held at Faza Secondary School  at 11.00AM– Attendance 38 villagers

People present are among others include:

- Sub County Director of Education

- County Director of Education

- Knut officials

- Area Chief

- NGCDF REP

- Teachers

- Opinion leaders

- MUHURI representative

- PTA reps

- BoM REPS

- Religious leaders

Security and administration projects proposed

- OCPD and DCIOs offices

- Renovation of DCCs residence

- Administration Police Post

- Proposed renovation and purchase of Furniture for the ACC’s office Faza

- Construction of a Kadhi’s Court and a magistrate court

Education projects

Faza Secondary School

- Renovation of Science Laboratory

- Renovation of Girls and Boys Dormitories

- Rehabilitation of Water Djabia

- Rehabilitation of school fence

Rasini Girls Primary School

- Additional classrooms

- Renovation of dilapidated classroom structures

- Proposed construction of Administration Block

Faza Boys Primary School

- Additional classrooms and Fence

- Renovation of dilapidated classroom structures

Sub County Education

- Proposed construction of Sub County Education offices

- Proposed construction of KNUT offices

- FAZA WARD – SIYU PRIMARY AT 8.00AM – 5TH August, 2021

- SIYU VILLAGE meeting held at Siyu Primary School  at  8.00AM– Attendance 32

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- Head teacher

- Representatives of school management committee

- Two primary schools committee

- Opinion leaders

- Religious leaders

Proposed Projects

- Siyu Primary School library

- Renovation of dilapidated classroom structures for Siyu primary school

- Siyu primary school Teacher’s block of toilets

- Furnishing of the primary school laboratory

REJECTED PROJECT

- Repossession of the water Djabia from County Government Water Company - LAWASCO

- SHANGA VILLAGE  held at Siyu Primary School

- Additional Classrooms at Shanga Primary School

- Renovation of dilapidated classrooms at Shanga primary school

- Proposed construction of Administration Block at Shanga primary school

- Purchase and installation of water harvesting equipment at Shanga primary school

- FAZA WARD – PATE PRIMARY SCHOOL AT 2.00PM – 5TH August, 2021

- PATE VILLAGE meeting held at Pate Primary School – Attendance 36

People present are among others include:

- Area Chief

- Village Headman

- Village elders

- Head teacher

- Representatives of school management committee

- Primary school committee

- Opinion leaders

- Religious leaders

- Representatives from Mtangawanda village

- Representatives from Basuba Ward

Proposed Projects

PATE VILLAGE

- Patte Chief Office furniture

- Renovation of Administration Block at Patte Primary School

- Purchase and Installation of water harvesting plastic tanks for Patte Girls Sec School

- Rehabilitation of the Toilets Blocks at Primary School

- Fencing of Patte Girls Secondary School

- Grading of the access road to secondary school

- Proposed drilling of borehole for Patte Girls secondary school

- MTANGAWANDA VILLAGE AT MTANGAWANDA PRIMARY SCHOOL AT 8.00AM - 6TH August 2021

- Construction of armory at  Mtanagawanda Boarder Police Post

- Proposed construction of staff houses at Mtangawanda Boarder Police Post

- Fencing of Mtangawanda Primary School

- Renovation of dilapidated classroom structures at Mtangawanda primary school

- Proposed construction of Mtangawanda Secondary school

- New Administration Block at Mtangawanda Primary School

- BASUBA WARD

- KIANGWE VILLAGE AT MARARANI PRIMARY SCHOOL AT 2.00PM - 6TH August 2021

- Proposed construction of Acc offices at Kiangwe

- Proposed construction of chief offices at Kiangwe, Mangai, Milimani, Mararani and Basuba

- Proposed construction of toilet block at Kiangwe AP Post

- Fencing of all primary schools of Kiangwe, Mangai , Milimani, Mararani and Basuba

- Renovation of all vandalized primary school structures

- Proposed construction of a secondary school in Basuba Ward

REJECTED PROJECTS

- Feeding programme for school children

- Provision of uniforms for school children

- Boat and fuel for emergency cases

- Provision of medicines and medical equipment

- CONCLUSION: NGCDF Committee – LAMU EAST CONSTITUENCY

The committee members observed that most proposed projects are in line with the constituency strategic plan. The committee noted that the current year projects proposal are to be prioritized in accordance with emerging issues in alignment to the Constituency Strategic Plan, Medium Term Plans, The President’s big four agendas among other prevailing treaties and conventions.

The committee proposed the funding of Lamu East Technical Training Institute (TTI) that was initially co-financed by the Ministry of Education, Science and Technology, and the NGCDF Lamu East Constituency but works had stalled due to rising cost variations encountered in unprecedented high costs of ferrying building materials to site, change of building materials from steel and metallic to hard wood so as to avoid corrosion resulting from salty humidity from the ocean, change from hardboard ceiling to upvc, introduction of septic tank and soak pit that had not been included in initial plan and design.

The NGCDF Committee, through the Chairman of the Constituency Oversight Committee had written to the Ministry of Education, Science and Technology asking for guidance and way-forward for the pending works to be completed so as to enable the constituents benefit from the services of the institution and the ministry had advised the NGCDF Committee Lamu East Constituency to put in place mechanisms that would see the remaining works completed and the project put into use.

- In addition, the NGCDF Committee proposed the construction of underground Water Reservoir for the newly constructed Lamu East Sub-county Head Quarters at Faza and erection of water towers to hold storage plastic water tanks that would be used to supply water into the offices once pumped from the underground water reservoir

CHALLENGES ENCOUNTERED DURING THE WHOLE EXERCISE

- Rough seas: The ocean was an usual rough and it was by sheer luck of having hired a bigger boat

- Fuel consumption: fuel consumption was higher because of bigger waves, we also had to take longer routes avoiding open seas

- The projects proposed were far too many

- Most villagers had issues with previous projects which they proposed and never implemented

- The other challenge was culture where women could not participate in public forums with men though we carried women in our team, it did not help

- Security scare with the death of a police officer, disappearance of a businessman, and massacred chief and assistant chief.

- Political divisions were also witnessed where members opposed to the area MP participated in the proceedings but refused to register their presence, while heckling contributors eg at Mkokoni village

- Others questioned the presence of the area MP in the team soliciting views on project implementation for ignorance that the MP was participating in his capacity as the Chairman of the Constituency Oversight Committee

- Ward forums are done per ward in Lamu East; they are held in every village and major Islands which pose a challenge of the convenient means of transport noting that most islands have no motor vehicle except Patte island and the Kiunga mainland though with security scares

MIN 4/30/08/2021 – PREPARATION AND SUBMISSION OF PROJECT PROPOSAL BUDGET  FOR FINANCIAL YEAR 2021/2022

The chairman informed the committee that a circular dated 26th August 2021 from the NGCDF Board referenced NGCDFB/CEO/BOARD CIRCULARS VOL II (30) is calling for preparation and submission of Project Proposals for each constituency for the 2021/2022 Financial Year.

In the circular, Lamu East constituency has been allocated kshs.137,088,879 for the financial year 2021/2022 project proposal budget.

The committee was satisfied with its futuristic forecast where it had already conducted the public ward barazas in the constituency to collect views from the constituents in readiness for the preparation of the project proposal budget for the financial year 2021/2022.

Guided by the views gathered during the public ward barazas together with the constituency strategic plan (2018-2022) and relevant circulars on emerging issues, the committee compiled a Project Proposal Budget for the Financial Year 2021/2022 as follows;

FINANCIAL YEAR 2021/2022 PROJECT PROPOSAL BUDGET

| Project Name | Original Cost | Cumulative Allocation | Project activity | Amount Allocated | Current Status |
| --- | --- | --- | --- | --- | --- |
| ADMINISTRATION AND RECURRENT (6%) |  |  |  |  |  |
| Employees Salaries | 4,195,000 | 0 | Compensation of Employees - Basic wages of Contractual employees, Basic wages of Casual labour, house allowance, transport allowance, leave allowance and gratuity | 4,195,000 | New |
| NSSF | 105,000 | 0 | Employer Contribution of NSSF Deductions | 105,000 | New |
| Goods and Services | 924,672.00 | 0 | Use of Goods and Services - Office and general supplies, Utilities, supplies and services, office rent, printing, communication, fuel, oils and lubricants, routine maintenance of equipment and machinery | 924,672 | New |
| Committee Expenses | 3,000,000 | 0 | Payment of Committee sitting allowances, transport, conferences | 3,000,000 | New |
| Sub-total |  |  |  | 8,224,672 |  |
| MONITORING & EVALUATION AND CAPACITY BUILDING (3%) |  |  |  |  |  |
| Committee Expenses | 2,500,000 | 0 | Payment of Committee sitting allowances, transport, conferences | 2,500,000 | New |
| NGCDFC/PMC Capacity Building | 1,612,000 | 0 | Undertake Training of the PMCs, CDFCs and Office Staff on NG-CDF Related issues | 1,612,000 | New |
| Sub-total |  |  |  | 4,112,000 |  |
| EMERGENCY (5%) |  |  |  |  |  |
| Emergency | 7,192,207 | 0 | To cater for any unforeseen occurrences in the constituency during the financial year | 7,192,207 | New |
| SPORTS (2%) |  |  |  |  |  |
| Lamu East Constituency Sports Committee | 2,730,000 | 0 | To carry out Sports Tournaments and award winning teams with trophies, balls and uniforms where the tournament facilitation budget is kshs.1,000,000 and purchase of sports wear, sporting gear, sporting equipment and trophies is kshs.1,730,000 | 2,730,000 | New |
| ENVIRONMENT (2%) |  |  |  |  |  |
| Mbwajumwali Secondary School | 700,000 | 0 | Purchase, transport and installation to completion of 3no plastic water tanks each of 10,000 litres capacity installed on concrete slab base and construction of water collection gutters to harvest rain water | 700,000 | New |
| Kiangwe Police Post | 630,000 | 0 | Construction to completion of a single pit compartment - 4 door pit-latrine in which one cubicle is designed to cater for PLWD with ramp, holding rails and necessary supporting accessories | 630,000 | New |
| Shanga Primary School | 700,000 | 0 | Purchase, transport and installation to completion of 3no plastic water tanks each of 10,000 litres capacity installed on concrete slab base and construction of water collection gutters to harvest rain water | 700,000 | New |
| Patte Girls Secondary School | 700,000 | 0 | Purchase, transport and installation to completion of 3no plastic water tanks each of 10,000 litres capacity installed on concrete slab base and construction of water collection gutters to harvest rain water | 700,000 | New |
| Sub-total |  |  |  | 2,730,000 |  |
| BURSARY (35%) |  |  |  |  |  |
| Bursary Secondary Schools | 24,000,000 | 0 | Cater for bright and needy students in secondary schools | 24,000,000 | New |
| Bursary Tertiary Schools | 23,000,000 | 0 | Cater for bright and needy students in tertiary institutions | 23,000,000 | New |
| Sub-total |  |  |  | 47,000,000 |  |
| EDUCATION: PRIMARY SCHOOLS |  |  |  |  |  |
| Shanga Primary School | 4,000,000 | 0 | Renovation to completion of 10no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 4,000,000 | New |
| Siyu Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Mbwajumwali Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Kizingitini Girls Primary School | 2,400,000 | 0 | Construction of 2no classrooms to completion | 2,400,000 | New |
| Kizingitini Girls Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Myabogi Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Rasini Girls Primary School | 3,000,000 | 0 | Renovation to completionof 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Faza Boys Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Patte Primary School | 2,200,000 | 0 | Renovation to completion of a 7no roomed Administration block comprising of Principal's and Deputy principal's offices, Secretary's and Bursar's cubicles, Staff-room, mini-kitchen and Reception (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, replacement of broken door shutters, windows, and painting) | 2,200,000 | New |
| Kiunga Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Kizingitini Boys Primary School | 3,000,000 |  | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 |  |
| Tchundwa Primary School | 3,000,000 | 0 | Renovation to completion of 7no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 3,000,000 | New |
| Sub-total |  |  |  | 35,600,000 |  |
| EDUCATION: SECONDARY SCHOOLS |  |  |  |  |  |
| Kizingitini Secondary School | 4,000,000 | 0 | Renovation to completion of 10no classrooms (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 4,000,000 | New |
| Faza Secondary School | 2,000,000 |  | Renovation to completion of science laboratory with a 500 students holding capacity per session (Replacement of worn-out roof, repair and plastering of cracking walls, flooring of damaged floors, fitting of doors and windows, and painting) | 2,000,000 | New |
| Mbwajumwali Secondary School | 2,000,000 | 0 | Completion of multipurpose hall comprising of dining hall and kitchen with capacity to accommodate 500 students per session = kshs.1,000,000 and purchase of dinning hall furniture = kshs.1,000,000 | 2,000,000 | New |
| Sub-total |  |  |  | 8,000,000 |  |
| EDUCATION: TERTIARY INSTITUTIONS |  |  |  |  |  |
| Lamu East Technical Training Institute | 12,000,000 | 0 | Completion of TTI building - (Finishes) plumbing and drainage works, fittings, electrical and mechanical works, flooring and plastering, ceiling and painting | 12,000,000 | On going |
| Sub-total |  |  |  | 12,000,000 |  |
| SECURITY |  |  |  |  |  |
| Lamu East Sub-county Head Quarter | 2,000,000 | 0 | Construction of underground concrete water reservoir of 50,000 litres capacity of water and erection of water tower to hold 2no plastic water tanks of 5,000 litres capacity of water | 2,000,000 | New |
| Kizingitini ACC Office | 1,000,000 | 0 | Floor tiling of 5no room Administration office block to completion comprising of 2no offices, secretary office, reception, boardroom and store = kshs.500,000 and Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 1,000,000 | On going |
| Faza ACC Office | 1,000,000 | 0 | Floor tiling of 5no room Administration office block to completion comprising of 2no offices, secretary office, reception, boardroom and store = kshs.500,000 and Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 1,000,000 | New |
| Kizingitini Chief Office | 3,500,000 | 0 | Construction of 5no room Administration office block to completion comprising of 2no offices, secretary office, reception, boardroom and store = kshs.3,000,000 and Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 3,500,000 | New |
| Siyu AP Post | 500,000 | 0 | Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 500,000 | New |
| Patte Chief's Office | 500,000 | 0 | Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 500,000 | New |
| Siyu Chief's Office | 500,000 | 0 | Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 500,000 | New |
| Kiunga Chief's Office | 500,000 | 0 | Purchase of Office furniture - 2no Executive office desks, 10no Executive office chairs 1no Boardroom executive table and 14no Boardroom chairs = kshs.500,000 | 500,000 | New |
| Sub-total |  |  |  | 9,500,000 |  |
| Total |  |  |  | 137,088,879 |  |

MIN 05/30/08/2021 - ANY OTHER BUSINESS (A.O.B)

The committee observed that attendance of the public ward barazas was widely affected by the prevailing Covid 19 scare that demand physical - social distancing, controllable sizes of  gatherings, strictly use of Covid 19 control measures among other unavoidable challenges.

However, the views obtained gave a true and fair presentation of the constituents needs and aspirations.

There being no other business for deliberation, the meeting adjourned at 1519 hours with a word of prayer by Hassan Swaleh.

Minutes taken by Secretary________________________Date____________________

Minutes confirmed by Chairman _________________________Date___