MINUTE OF THE MOYALE NATIONAL GOVERNMENT CONSITUTIECY DEVELOPMENT FUND COMMITTEE HELD ON TUESDAY, 10th OCTOBER 2019 AT NGCDFC BOARDROOM AT 8.00 AM.

PRESENT:

| 1. | DENGE TULU | CHAIR NGCDFC |
| --- | --- | --- |
| 2. | ABDIKADIR HUQA | SECRETARY NGCDFC |
| 3. | SULEIMAN GUYO | FUND MANAGER |
| 4. | MAHAD MOHAMED | MEMBER |
| 5. | HUSSEIN KONSE ALI | MEMBER |
| 6. | AMINA TURE KALICHA | MEMBER |
| 7. | KHADIJA ABDI HUSSEIN | MEMBER |
| 8. | BUKE GALM BORU | MEMBER |
| 9. | MOHAMMED HUSSEIN FOFLE | MEMBER |
| 10. | PATRICK B. MUMALI | MEMBER |

AGENDA:

- Confirmation of previous Minute

- Status of the Previous Year 2018/19 Projects

- NGCDFC Office

- Priority Projects for the Year 2019/2020

MIN 1/10/10/2019: CONFIRMATION OF PREVIOUS MINUTE

The Proceedings of the previous minute was read for the members who confirmed that the minute represented the true picture of what was discussed during the meeting.

MIN 2/10/10/2019: STATUS OF THE PREVIOUS YEAR 2018/19 PROJECTS

The NGCDFC Chairman Mr. Denge Tullu informed the committee that the purpose of the day’s meeting was to finalize the priority projects to be funded for the year 2019/2020 after the various proposals were received from the just concluded Public Forum.

The Chairman also informed the committees that in line with the NGCDFB Regulations and NGCDF Act 2016, Projects funded during the previous year and not completed due to inadequate budget are to be given the priorities before others.

The Committee deliberated and agreed that the following are the ongoing projects for the previous year which requires funding as indicated:

| Project Names | Activities to be funded | Budget Amount required |
| --- | --- | --- |
| Uran Chiefs Office | Superstructure walling, roofing and plastering, painting and fixing doors and windows | 2,200,000.00 |
| Watiti Primary School | Completion of Administration Block Consisting of Two Offices and a staff room: Roofing, Plastering and Painting works | 500,000.00 |
| Moyale Prison | Completion of 30 persons capacity Dining Hall; Roofing, Plastering and Painting works | 510,000.00 |

MIN 3/10/10/2019: NGCDFC OFFICE RENOVATION

The Committee deliberated on the need to renovate the NGCDFC Offices in Moyale. The NGCDFC agreed they should fund the following activities at the office during the year 2019/2020.

| Project Names | Activities to be funded | Budget Amount required |
| --- | --- | --- |
| Moyale NGCDFC Office | Renovation of the Toilets and 8 roomed Office Building- Gutters; Plastering and Painting works; Construction of Bio-Digester for the Office Toilets for Kshs 1,047,354.48 and Purchase of Three Executive Tables for Kshs 300,000; Two Safety Boxes for Kshs 220,000; Two HP Printers and a Photocopies and the accessories for Ksh 320,000; Six piece Metallic Seats for Kshs 200,000 and Five Executive Leather seats for Ksh 250,000; | 2,337,354.48 |

The NGCDF Discussed on the requests from the Civil Registration Office Bay at the Moyale Registration of Persons Office. The Committee deliberated to fund the requests from the Civil registration office for a waiting bay to ensure those members of the public seeking government services are not subjected to hot weather and long-standing hours. The Committee agreed to fund the bay at a budget of Ksh 600,000.

MIN 4/10/10/2019: PRIORITY PROJECTS  2019-2020 BY WARD AND SECTOR

The NGCDFC conducted a five day public forums in all the wards in the constituency and obtained a ward report detailing the projects proposed by the community during the forum. The Report was tabled before the committee and after a lengthy deliberation it was resolved that the following projects be funded for the Year 2019/2020 as per indicated wards:

STATUTORY VOTES: ADMINISTRATION

| Employee Salaries | 4-010-45-2110000-100-2019/20-001 | 3,599,880.00 | 3,599,880.00 | Payment of staff salaries and Gratuity | 3,599,880.00 | Ongoing |
| --- | --- | --- | --- | --- | --- | --- |
| NHIF | 4-010-45-2120101-100-2019/20-001 | 99,600.00 | 99,600.00 | NHIF Deductions | 99,600.00 | Ongoing |
| Goods and Services | 4-010-45-2210000-100-2019/20-001 | 3,013,303.45 | 3,013,303.45 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, Air time, Electricity, Rent, Bank charges, Postal charges, Insurance Costs | 3,013,303.45 | Ongoing |
| NSSF | 4-010-45-2120101-100-2019/20-001 | 161,280.00 | 161,280.00 | Payment of NSSF Deductions | 161,280.00 | Ongoing |
| Committee Expenses | 4-010-45-2210802-100-2018/19-001 | 1,368,000.00 | 1,368,000.00 | Payment of Committee sitting allowances, transport, conferences | 1,368,000.00 | Ongoing |

MONITORING AND EVALUATION VOTES:

| Goods and Services | 4-010-045-2210000-111-2019/20-001 | 1,585,031.72 | 1,585,031.72 | Purchase of fuel, printing, stationery, telephone, travel and subsistence, office tea, Air time, Electricity, Rent, Bank charges, Postal charges | 1,585,031.72 | Ongoing |
| --- | --- | --- | --- | --- | --- | --- |
| Committee Expenses | 4-010-045-2210802-111-2019/20-001 | 1,036,000.00 | 1,036,000.00 | Payment of Committee sitting allowances, transport, conferences | 1,036,000.00 | Ongoing |
| NG-CDFC/PMC Capacity Building | 4-010-045-2210700-111-2019/20-001 | 1,500,000.00 | 1,500,000.00 | Undertake Training of the NGCDFC Staffs, PMCs/NG-CDFCs on ng-CDF Operations, Cross cutting Issues and Capacity Building activities | 1,500,000.00 | Ongoing |

EMERGENCY VOTES:

| Emergency | 4-010-045-2640200-101-2019/20-001 | 7,198,241.38 | 7,198,241.38 | To cater for any unforeseen occurrences in the constituency during the financial year | 7,198,241.38 | New |
| --- | --- | --- | --- | --- | --- | --- |

SPORTS PROJECTS:

| Project Name | Codes | Activities to be undertaken | Budget | Status |
| --- | --- | --- | --- | --- |
| Sports Projects | 4-010-045-2640509-112-2019/20-001 | Purchase of Balls and Sport Skits for 8 Volleyball Teams @ Kshs 84,000 per Team; The Teams- Star Ladies, Sololo Bilitu, Sololo Queens, Obbu Starlets, Darara stars, Warriors, Sharks, Biqila, Moyale United and Red Soil; Purchase of 12 Sport Skits for each of 8 Sec School @ Kshs 77,000 per School; Purchase of Costumes for Music Festivals for 8 Secondary Schools @ Kshs 56,419.31 per school; Sec Schools- Butiye Mixed, Manyata Mixed, Dabel, Dr Guracha, Sololo Boys, Walda Complex , Odda Mixed and Heilu Mixed. | 2,747,354.48 | Ongoing |

BURSARIES /MOCKS AND CATS

| Project Name | Codes | Activities to be undertaken | Budget | Status |
| --- | --- | --- | --- | --- |
| Bursary Secondary Schools | 4-010-045-2640101-103-2019/20-001 | Pay School fees for needy and Poor Students in Secondary Schools | 28,178,703.45 | Ongoing |
| Bursary for Colleges/Universities | 4-010-045-2640101-103-2019/20-002 | Pay School fees for needy and Poor Students in Colleges/Universities Schools | 17,000,000.00 | Ongoing |

PRIMARY SCHOOL PROJECTS FOR 2019/2020:

| Project Name | Project Code | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- |
| Muslim Primary School | 4-010-045-2630204-104-2019/20-001 | Renovations of 4 Classrooms: Fixing of Windows and Doors, Floors, Plastering and Painting works. | 1,200,000.00 | New |
| Manyatta Primary School | 4-010-045-2630204-104-2019/20-002 | Renovation works of 6 Classroom: Fixing Windows and doors, Floor repairs, Painting works | 1,400,000.00 | New |
| Kuro Girls Primary School | 4-010-045-2630204-104-2019/20-003 | Fencing works using Metallic posts, Chain link and Barbed wire covering 950m | 1,300,000.00 | New |
| Holale Primary School | 4-010-045-2630204-104-2019/20-004 | Renovations of Four Classrooms: Fixing Windows and Doors; Floors and Painting works | 1,260,000.00 | New |
| El Raya Primary School | 4-010-045-2630204-104-2019/20-005 | Construction of 1 No. Class room to Completion. | 1,260,000.00 | New |
| Antut Primary School | 4-010-045-2630204-104-2019/20-006 | Construction of One Classroom for Ksh 1,260,000 and Construction of Two roomed- One Ordinary Staff House for Kshs 640,000. | 1,900,000.00 | New |
| Harosa Primary School | 4-010-045-2630204-104-2019/20-007 | Construction of Three door Pit Latrine to completion. | 630,000.00 | New |
| Yaballo Primary School | 4-010-045-2630204-104-2019/20-008 | Construction of Three door Pit Latrine to completion. | 630,000.00 | Ongoing |
| Dabel Primary School | 4-010-045-2630204-104-2019/20-009 | Renovations of Three Classrooms: Fixing Windows and Doors; Floors and Painting works | 1,000,000.00 | New |
| Nana Primary School | 4-010-045-2630204-104-2019/20-010 | Renovations of Three Classrooms: Fixing Windows and Doors; Floors and Painting works | 900,000.00 | New |
| Qoloba Primary School | 4-010-045-2630204-104-2019/20-011 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Misa Primary School | 4-010-045-2630204-104-2019/20-012 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Godoma Didiqo Primary School | 4-010-045-2630204-104-2019/20-013 | Construction of Three door Pit Latrine to completion. | 630,000.00 | New |
| Iladhu Primary School | 4-010-045-2630204-104-2019/20-014 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Mukh Gura Primary School | 4-010-045-2630204-104-2019/20-015 | Purchase and Installation of solar panels on Staff room and Two Classrooms: Wiring for Kshs 150,000; 11-120w Solar Panels for Kshs 330,000 ; Three Inverters Kshs 60,000; Three Charge Controllers for Ksh 90,000 ; Six Batteries for Ksh 120,000 | 750,000.00 | New |
| Kukub Primary School | 4-010-045-2630204-104-2019/20-016 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Makutano Primary Sch | 4-010-045-2630204-104-2019/20-017 | Construction of Three door Pit Latrine to completion. | 630,000.00 | New |
| Amballo Primary School | 4-010-045-2630204-104-2019/20-018 | Renovations of Four Classrooms: Fixing Windows and Doors; Floors and Painting works for Kshs 1,200,000 and Construction of three door VIP Latrines for Kshs 787,500 | 1,987,500.00 | New |
| Kukub Primary School | 4-010-045-2630204-104-2019/20-019 | Construction of Administration Block to Completion ( Staff room, Head Teachers Office and Deputy Head teachers Office and a store | 2,000,000.00 | New |
| Gadha Korma Primary School | 4-010-045-2630204-104-2019/20-020 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Golole Primary School | 4-010-045-2630204-104-2019/20-021 | Water Piping Works covering 2.0 km from the Community Borehole to the School for Kshs 1,300,000; Purchase of Two-10,000 Litre Tanks for Ksh 200,000; Raised Two Metal stands for the tanks for Ksh 540,000; Fixing Six Taps for Ksh 60,000 and Construction of Washing Basins for Ksh 180,475. | 2,380,475.00 | New |
| Watiti Primary School | 4-010-045-2630204-104-2019/20-022 | Completion of an Administration Block; roofing, plastering and painting. | 500,000.00 | Ongoing |
| Sololo Primary School | 4-010-045-2630204-104-2019/20-023 | Construction of Kitchen including a Stores and Oven to completion for Kshs 1,400,000.18. | 1,400,000.18 | New |
| Elle Dimtu Primary School | 4-010-045-2630204-104-2019/20-024 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Walda Primary School | 4-010-045-2630204-104-2019/20-025 | Renovation of Four Classrooms: Painting; Flooring and Fixing doors and windows. | 1,370,000.00 | New |
| Sololo Primary School | 4-010-045-2630204-104-2019/20-026 | Construction of a 300 Capacity Library at Sololo Primary School; Foundation; Superstructure Walling, Lintel and roofing. | 3,045,000.00 |  |
| Purchase of Furniture for Primary Schools in Moyale | 4-010-045-2630204-104-2019/20-027 | Purchase of 80 Lockers and 80 Chairs for each of these schools: Golole Pry Sch; Uran Primary School; Elle Bor Primary School; Sololo Primary School; Anona Primary School; Dambala Fachana Pry School; Dadach Lakole Primary School; Odda Primary School; Dabel Primary School; Watiti Primary School; Somare Primary School; Heilu Primary School and 40 Lockers and Chairs for Karbururi Primary School. | 5,000,000.00 | New |

SECONDARY SCHOOL PROJECTS FOR 2019/2020:

| Project Name | Project Code | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- |
| St Mary's Secondary School | 4-010-045-2630205-104-2019/20-001 | Construction of Two one storey Classrooms upto the Shutter level; Foundation Slab, Walling and Shuttering. | 4,250,000.00 | New |
| Sololo Mixed Secondary School | 4-010-045-2630205-104-2019/20-002 | Renovation of 100 Capacity Dining hall: Roofing repairs, Walls repairs and Floor repairs, Fixing Doors & Windows and Painting works for Kshs 1,315,000 and Equipping with 10 Dining tables for Ksh 200,000 and 120 Dining Chairs for Ksh 360,000. | 1,875,000.00 | New |
| Dr. Guracha Memorial Girls Secondary School | 4-010-045-2630205-104-2019/20-003 | Construction of a Science Laboratory with a Capacity of 100 Students to completion for Kshs 2,400,000 and equipping with 50 Lab stools for Ksh 200,000 and 50 lab Chairs for Ksh 200,000 | 2,800,000.00 | New |
| Sessi Mixed Day Secondary School | 4-010-045-2630205-104-2019/20-004 | Construction of an Administration Block to completion for Kshs 2.5 M and Equipping with Nine Tables for Kshs 135,000 and 9 Chairs for Kshs 180,000 | 2,815,000.00 | New |
| Butiye Mixed Day Secondary School | 4-010-045-2630205-104-2019/20-005 | Construction of a Science Laboratory with Capacity of 100 students for Kshs 2,300,000 to Completion and Equipping with 100 Chairs for Kshs 250,000 and 50 Lab Stools for Kshs 500,000. | 3,050,000.00 | New |
| Bori Junction Mixed Day Sec School | 4-010-045-2630205-104-2019/20-006 | Construction of 1 No. Classroom to Completion | 1,260,000.00 | New |
| Uran Mixed Day Secondary School | 4-010-045-2630205-104-2019/20-007 | Fencing works: Metallic posts, chain link and barbed wires covering 1000 metres | 1,500,000.00 | New |

SECURITY PROJECTS FOR THE 2019/2020:

| Project Name | Project Code | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- |
| Madho Adhi Chief’s Office | 4-010-045-2640507-108-2019/20-001 | Construction of a Chiefs Office: Two Office rooms; a store and Board room. | 2,355,000.00 | New |
| Manyatta Chief’s Office | 4-010-045-2640507-108-2019/20-002 | Fencing and Gate Construction works 350m: Metallic Posts, Chain link and Barbed wires covering 200 m | 900,000.00 | New |
| Heilu Chief’s Office | 4-010-045-2640507-108-2019/20-003 | Construction of One Double door VIP Latrines for Kshs 630,000 to completion and Supply of Furniture: One Boardroom Table for Ksh 85,000; Two Executive Tables for Kshs 100,000; Two executive Chairs for Ksh 90,000 and 30 plastic chairs for Kshs 45,000. | 950,000.00 | New |
| Funan Qumbi AP Camp | 4-010-045-2640507-108-2019/20-004 | Construction Three -Two Door staff Houses to Completion. | 1,800,000.00 | New |
| Moyale Prison | 4-010-045-2640507-108-2019/20-005 | Completion of the 30 persons capacity Dining Hall: Roofing, Plastering and Painting works | 510,000.00 | Ongoing |
| Uran Chief’s Office | 4-010-045-2640507-108-2019/20-006 | Construction of Chief’s Office; Office room, Asst Chiefs Room and Board room. | 2,200,000.00 | New |

ENVIRONMENTAL PROJECTS FOR 2019/2020:

| Project Name | Project Code | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- |
| Kukub Primary School | 4-010-045-2640510-104-2019/20-001 | Purchase of 50 tree seedlings and Planting works for Kshs 100,000; Purchase of two -10,000 Litre Plastic Water Tanks for Kshs 180,000 and Construction of the tank base for Kshs 165,000. | 445,000.00 | New |
| Heilu Mixed Sec School | 4-010-045-2640510-104-2019/20-002 | Fencing to Protect School Environment covering 320m using barbed wire, chain-link and metallic posts | 900,000.00 | New |
| Nana Primary School | 4-010-045-2640510-104-2019/20-003 | Construction of Gabions to Control Gulley Erosion in the school | 600,000.00 | New |

MIN 4/10/10/2019: ANY OTHER BUSINESS

There being no other Business, the Meeting was adjourned at 12.30 pm.

Minute taken by:	Minute Confirmed By:

………………………….	                                                 ………………………….

NGCDFC Secretary	                                                                NGCDFC Chairman