MINUTE OF MOYALE NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND COMMITTEE HELD ON 23rd SEPTEMBER 2020 AT MOYALE NG-CDFC BOARD ROOM AT 9.00 AM

PRESENT

| No. | NAMES | DESIGNATION |
| --- | --- | --- |
| 1. | Denge Tulu Racha | NGCDFC Chairman |
| 2. | Abdulkadir Huqa | NGCDFC Secretary |
| 3. | Hussein Konse Ali | Member |
| 4. | Patrick B. Mumali | Member |
| 5. | Buke Galma Boru | Member |
| 6. | Amina Ture Kalicha | Member |
| 7. | Mohamed Hussein Fofle | Member |
| 8. | Mahad Mohamed Dida | Member |
| 9. | Suleiman Guyo Roba | Fund Manager |
| 10. | Khadija Abdi Hussein | Member |

AGENDA:

- Preliminaries

- Incomplete and Ongoing Projects FY 2019/2020

- Proposed Projects for FY 2020/2021

- A.O.B

Min 1/23/09/2020: Preliminaries

The Meeting started at 10.30 am in the Morning with a word of prayer from Mr. Denge Tullu. Mr. Denge read the agenda of the meeting for the members and invited a fruitful session where every member of the committee shall contribute to the proposals before the committee.

Min 2/23/09/2020: ONGOING PROJECTS FOR FUNDING IN 2020/2021

The Fund Manager informed the committee that as a requirement from the Board, priorities have to be given to the ongoing projects which have not been fully funded during the previous years. The Committee deliberated on the incomplete projects across all wards and it was noted that only two such projects exists.

Mr. Hussein identified St Mary’s Secondary School Complex which requires additional Ksh 2 Million funding from the NG-CDF as per the Bill of Quantities provided by the Public Works. It was also noted by Mr. Huqa that Sololo Primary School Library has not been fully funded. Mr. Huqa suggested that the Library requires additional funding for Plastering, Painting, Shelves Construction, Flooring, Electrification and Ceiling works for it to be fully completed.

The Committee did the budgeting and arrived at some Kshs 2,150,000 for the completion of the library Block.

The Committee unanimously agreed to fund both the projects during the Financial Year 2020/2021.

| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| Sololo Primary School | 5,195,000.00 | 5,195,000.00 | Completion of a 300 Capacity Library Block; Plastering, Painting, Wiring, Ventilations, Ceiling for Kshs 650,000; Construction of Shelves for Ksh Kshs 500,000 and Equipping with 200 chairs for Ksh 750,000 and 20 Reading Tables for Kshs 300,000 | 2,150,000.00 | Ongoing |
| St Mary's Secondary School | 6,250,000.00 | 4,250,000.00 | Completion of a two-one storey classroom; Plastering, Paintings, Roofing, wiring and ceilings for Ksh 2,000,000. | 2,000,000.00 | Ongoing |

Min 3/23/09/2020: PROPOSED PROJECTS 2020/2021

The fund Manager informed the committee that some Kshs 137,088,879.31 was allocated to the constituency during the financial Year 2020/2021. He further gave the committee the breakdowns for the statutory budgets inform of percentages and figures as per the Circular of the Board referenced NG-CDFB/CEO/BOARD CIRCULARs/Vol II (024).

| No. | Statutory Budget Items | Percentage provided | Amount in Kshs |
| --- | --- | --- | --- |
| 1. | Admin/Recurrent | 6% | 8,225,332.76 |
| 2. | Monitoring and Evaluation | 3% | 4,112,666.38 |
| 3. | Sports | 2% | 2,741,777.59 |
| 4. | Environment | 2% | 2,741,777.59 |
| 5. | Emergency | 5% | 7,192,206.90 |
| 6. | Bursaries | 35% | 47,981,107.76 |

Having received the figures for the statutory budgets, the committee decided to reduce the Bursary Vote to Some Kshs 30,000,000 where Ksh 14,500,000 was allocated to Colleges and Universities and Kshs 15,500,000 was allocated to Secondary Schools. The Reduction was agreed to fund New Projects in the Constituency.

| No. | Budget Item | Project Name | Project Details | Budget Amount in Kshs |
| --- | --- | --- | --- | --- |
| 1. | Bursaries | Bursaries for Secondary Schools | Payment of bursary to needy students in Secondary Schools | 15,500,000.00 |
|  |  | Bursaries for Colleges and Universities | Payment of bursary to needy students in Tertiary Institutions | 14,500,000.00 |

After the Deliberations on the needs of the NG-CDFC Office at the Constituency, the Committee decided to come up with the following specific budgets for the other statutory items:

| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| Administration/Recurrent |  |  |  |  |  |
| Employee Salaries | 3,142,000.00 |  | Payment of staff salaries and Gratuity | 3,142,000.00 | New |
| Employee NHIF | 88,000.00 |  | Payment of NHIF Deductions | 88,000.00 | New |
| Goods and Services | 3,507,332.76 |  | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, Air time, Electricity, Rent, Bank charges, Postal charges, Insurance Costs | 3,507,332.76 | New |
| Employee NSSF | 120,000.00 |  | Payment of NSSF Deductions | 120,000.00 | New |
| Committee Expenses | 1,368,000.00 |  | Payment of Committee sitting allowances, transport, conferences | 1,368,000.00 | New |

| Monitoring and Evaluation/ Capacity Building |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| Goods and Services | 1,595,000.00 |  | Purchase of fuel, printing, stationery, telephone, travel and subsistence, office tea, Air time, Electricity, Rent, Bank charges, Postal charges | 1,595,000.00 | New |
| Committee Expenses | 1,144,000.00 |  | Payment of Committee sitting allowances, transport, conferences | 1,144,000.00 | New |
| NG-CDFC and PMC Capacity Building | 1,373,666.38 |  | Undertake Training of the NG-CDFC Staffs, PMCs and NG-CDFCs on NG-CDF Operations, Cross cutting Issues and Capacity Building activities | 1,373,666.38 | New |

| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| Emergency | 7,192,206.90 |  | To cater for any unforeseen occurrences in the constituency during the financial year | 7,192,206.90 | New |
| Sports Projects |  |  |  |  |  |
| Sports Projects | 2,741,777.59 |  | Carry out Constituency sports tournament and the winning teams / schools to be awarded with trophy ,balls and sports kits | 2,741,777.59 | New |

| Bursaries |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| Bursary Secondary Schools | 15,500,000.00 |  | Payment of bursary to needy students in Secondary Schools | 15,500,000.00 | New |
| Bursary Tertiary Institutions | 14,500,000.00 |  | Payment of bursary to needy students in Tertiary Institutions | 14,500,000.00 | New |
| Environmental Projects |  |  |  |  |  |
| Kukub Primary School | 1,750,000.00 |  | Fencing of the school compound covering 900 metres using metallic posts, barbed wires and chain link to protect trees and the environment to Completion for Kshs 1500,000 and Gate Construction of Kshs 250,000. | 1,750,000.00 | New |
| Qate Primary School | 791,777.59 |  | Fencing of the school compound covering 500 metres using metallic posts, barbed wires and chain link to protect trees and the environment to completion. | 791,777.59 | New |

The NG-CDFC Chairman, Mr. Denge further tabled the list of the projects chosen by the communities in various wards during the public forums before the committee for deliberations. Mr. Denge also stated that some of the projects have been selected from the proposals forwarded to the NG-CDFC Office by the local schools and security Institutions. The Committee discussed the proposals at length and came up with the following priority projects based on the Ward needs:

- PRIMARY SCHOOL PROJECTS

| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| Sololo Primary School | 5,195,000.00 | 3,045,000.00 | Completion of a 300 Capacity Library Block; Plastering, Painting, Wiring, Ventilations, Ceiling for Kshs 650,000; Construction of Shelves for Kshs 500,000 and Equipping with 200 chairs for Kshs 750,000 and 20 Reading Tables for Kshs 300,000 | 2,150,000.00 | Ongoing |
| Funan Qumbi Primary School | 1,500,000.00 |  | Fencing School Compound covering 900 metres using Metallic Posts, Barbed wires and Chain Link to completion. | 1,500,000.00 | New |
| Qonqoma Primary School | 2,500,000.00 |  | Construction of two Classrooms to completion | 2,500,000.00 | New |
| Godoma Didiqo Primary School | 630,000.00 |  | Construction of Two Door Ventilated Improved Pit Latrines to completion | 630,000.00 | New |
| Uran Godha Primary School | 1,000,000.00 |  | Fencing of the school compound covering 600 metres using Metallic Posts, Chain Link and Barbed Wire to completion. | 1,000,000.00 | New |
| Madho Adhi Primary School | 630,000.00 |  | Construction of Two Door Ventilated Improved Pit Latrines to completion | 630,000.00 | New |
| Waye Godha Primary School | 1,345,000.00 |  | Construction of a Three roomed Staff House to Completion | 1,345,000.00 | New |
| Sololo Makutano Primary School | 1,175,000.00 |  | Renovation of Eight Classrooms; Reroofing to completion. | 1,175,000.00 | New |
| Madho Adhi Primary School | 1,180,000.00 |  | Renovation of a 20 staffs capacity Administration Block- Painting, Fixing Doors and Windows, Flooring and Ceilings. | 1,180,000.00 | New |
| Heilu Primary School | 1,416,000.00 |  | Fencing of the school compound covering 850 metres using Metallic Posts, Chain Link and Barbed Wire to completion. | 1,416,000.00 | New |
| Yaballo Primary School | 680,000.00 |  | Renovations of Three Classrooms; Fixing Doors and Windows, Painting, Flooring to completion. | 680,000.00 | New |
| Moyale Special School for Hearing Impaired. | 950,000.00 |  | Renovations of Five Classrooms; Fixing Doors and Windows, Painting, Flooring to completion. | 950,000.00 | New |
| Al Huda Primary School | 1,550,000.00 |  | Construction of a School Kitchen with a Store for Kshs 1,250,000 and Installation of Energy Saving Jiko for Kshs 300,000 to Completion | 1,550,000.00 | New |
| Dadacha Lakole Primary School | 2,529,000.09 |  | Grading and Bush Clearing of Dadacha Lakole Primary Access Road Covering 1km to completion. | 2,529,000.09 | New |
| Qoloba Primary School | 1,260,000.00 |  | Construction of One Classroom to completion | 1,260,000.00 | New |
| Moyale Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Iladhu Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Sololo Makutano Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Kukub Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Bori Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Kuro Girls Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Sessi Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Butiye Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Amballo Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Misa Primary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |

- SECONDARY SCHOOL PROJECTS

| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| St Mary's Secondary School | 6,250,000.00 | 4,250,000.00 | Construction of one storey building with four Classrooms; Plastering, Paintings, Roofing, wiring and ceilings for Kshs 2,000,000. | 2,000,000.00 | Ongoing |
| Moyale Boys Secondary School | 7,452,250.00 |  | Purchase of a 49 seater Isuzu School Bus | 7,452,250.00 | New |
| Bori Junction Mixed Day Secondary School | 1,475,000.00 |  | Construction of one Classroom to Completion | 1,260,000.00 | New |
| Kinisa Mixed Day Secondary School | 1,260,000.00 |  | Construction of One Classroom to completion | 1,260,000.00 | New |
| Bori Junction Mixed Day Secondary School | 3,900,000.00 |  | Construction of a 200 Student capacity Science Laboratory for Kshs 2,350,000 to completion and Equipping with 100 chairs for Kshs 350,000 and 20 lab tables for Kshs 300,000; | 3,000,000.00 | New |
| Sololo Mixed Secondary School | 2,396,000.00 |  | Grading and Murraming of 700m Sololo Mixed Sec Access Road (Main High Way to the School Gate) to completion. | 2,396,000.00 | New |
| Walda Complex Secondary School | 1,500,000.00 |  | Fencing works of the School Compound covering 900m using chain link, barbed wire and metallic Posts to completion. | 1,500,000.00 | New |
| Sessi Mixed Day Secondary Sch | 700,000.00 |  | Fencing works of the School Compound covering 400m using chain link, barbed wire and metallic Posts to completion. | 700,000.00 | New |
| Moyale Girls Secondary School | 3,095,000.00 |  | Construction of an Administration Block comprising of a Staff room, Head Teachers Office with Secretary Space, D/H Office and Bursar Office for Ksh 2,775,000 to completion and Purchase and Supply of Four Executive Tables for Kshs 200,000 and 16 Metallic Chairs for Kshs 120,000 | 3,095,000.00 | New |
| Bori Junction Mixed Day Secondary School | 1,950,000.00 |  | Fencing works of the School Compound covering 1000m using chain link, barbed wire and metallic Posts to completion for Kshs 1,600,000 and Gate Construction of Kshs 350,000. | 1,950,000.00 | New |
| Moyale Girls Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Moyale Boys Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Heilu Mixed Day Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Manyatta Mixed Day Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Butiye Mixed Day Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Sessi Mixed Day Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Township Mixed Day Secondary | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Bori Junction Mixed Day Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Uran Mixed Day Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |
| Walda Complex Secondary School | 625,000.00 |  | Purchase and Supply of 100 Lockers and 100 Chairs | 625,000.00 | New |

- SECURITY PROJECTS

| Project Name | Original Costs | Cumulative Costs | Project Activities | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| Golole Police Post | 1,875,000.00 |  | Construction of a Three- Two roomed Staff Houses to Completion. | 1,875,000.00 | New |
| Uran Lataka Chief's Office | 1,603,000.00 |  | Construction of a Chief's Office comprising of Two Office rooms to completion | 1,603,000.00 | New |
| Funan Idha Administration Police Camp | 1,875,000.00 |  | Construction of a Three- Two roomed Staff Houses to Completion. | 1,875,000.00 | New |
| Badhan Rero Police Post | 1,875,000.00 |  | Construction of a Three- Two roomed Staff Houses to Completion. | 1,875,000.00 | New |
| Elle Dimtu Administration Police Camp | 1,875,000.00 |  | Construction of a Three- Two roomed Staff Houses to Completion. | 1,875,000.00 | New |
| Sololo Police Post | 850,000.00 |  | Fencing Works covering 500 metres using metallic posts, chain link and barbed wires to completion. | 850,000.00 | New |
| Amballo Police Post | 1,830,000.00 |  | Construction of a One Door Ventilated Improved Pit Latrine and one Door Bathroom for Kshs 630,000 to completion; Fencing works covering 350m for Ksh 600,000 to completion and renovation of Three roomed staff house- Plastering, Wiring, fixing doors and windows for Kshs 600,000. | 1,830,000.00 | New |
| Dabel Chief's Office | 2,375,000.00 |  | Construction of a Chief's Office comprising of Chief’s Office, Assistant Chief's Office and a Board Room to completion. | 2,375,000.00 | New |
| Godoma Police Post | 787,500.00 |  | Construction of a Two Door Ventilated Improved Pit Latrine and One Door Bathroom for Kshs 787,500 to completion. | 787,500.00 | New |
| Township Chief Office | 2,175,000.00 |  | Construction of a Chief's Office; Chief's Office, Assistant Chief's Office and a Board Room to completion. | 2,175,000.00 | New |
| Funan Qumbi-Funan Idha Security Road | 3,977,868.09 |  | Opening Up of Security Road Covering 8Km-Bush Clearing and Removal of Boulders to completion | 3,977,868.00 | New |
| Lami Chief Office | 2,275,000.00 |  | Construction of a Chief's Office; Chief's Office, Assistant Chief's Office and a Board Room to completion. | 2,275,000.00 | New |

- OTHER PROJECTS

The NG-CDF noted that the Sololo Based NG-CDFC Office is in pathetic condition and needs to be rehabilitated. Mr. Huqa suggested that the Office which was built about 10 years ago is situated in Sololo town to serve the vast Constituency and as at the moment it has been shut down due to its bad condition.

The Committee agreed to allocate Ksh 1,293,500.00 to rehabilitate the office Building which is in bad condition.

Min 4/23/09/2020: ANY OTHER BUSINESS

There being no other business the meeting was closed at 4.30 pm.

- Minute taken by:	Minute Confirmed by:

NGCDFC Secretary                                                                    NGCDFC Chairman