|  |  |
| --- | --- |
| CDF logo 4 MsWord  **NG-CDF** | **National Government Constituencies Development Fund**  **Maara Consitituency**  **P.O Box 301-60401**  **Chogoria**  **Email:cdfmaara@ngcdf.go.ke** | |

REF:MAARANGCDF/Date: 15/11/2019

THE CEO

NGCDF BOARD

P.O BOX 46682-00100

NAIROBI.

RE: PROJECT PROPOSALS 2019/2020 FINANCIAL YEAR

Attached find NGCDFC minutes,ward report and strategic plan implementation matrix in support of Maara NGCDF 2019/2020 project proposals.

The proposals have beenprepared in adherence to the CEO circular ref:NGCDFB/CIRCULARS Vol. II(014) dated 24th September 2019.

ANTHONY MUCHANGI KARIUKI

FUND ACCOUNT MANAGER

MAARA NGCDF

**MINUTES OF MAARA NATIONAL GOVERNMENT CONSTIYUENCY DEVELOPMENT FUND COMMITTEE MEETING HELD ON 12THNOVEMBER 2019**

MEMBERS PRESENT

1. JASPER KIAMBI M’RITHAA CHAIRMAN
2. MERCY GACERI MATI SECRETARY
3. JAMES WAMBUA MEMBER(DCC)
4. CATHERINE NDIGA MEMBER
5. DOMINIC MWITI MEMBER
6. JASPER NYAGA MEMBER
7. EMIS KAARI MUKWANJERU MEMBER
8. ARNEST MURITHI KITHINJI MEMBER
9. HUMPHREY MAGUTA MEMBER
10. ANTHONY M. KARIUKI FAM

PRESENT BY INVITATION

1. TITUS NABEA DISTRICT ACCOUNTANT
2. TIMOTHY KINEGENI PA MNA

AGENDAS

1. PRELIMINARIES
2. READING AND CONFIRMATION OF THE PREVIOUS MEETING MINUTES

3. MATTERS ARISING FROM THE MINUTES

4. PROJECT PROPOSALS FOR 2019/2020 FINANCIAL YEAR

5. POSTA PROPOSAL TO DELIVER BURSARY CHEQUES

6 . AOB

**NGCDFC MIN 1-12/11/2019 PRELIMINARIES**

With a quorum present the chairman called the meeting to order at 3.15 PM. Opening prayers were led by Humphrey Maguta. The chairman thanked members for availing themselves on short notice and for being punctual.

**NGCDFC MIN 2-29/11/2018 READING AND CONFIRMATION OF THE PREVIOUS MEETING MINUTES**

Having been circulated the minutes of the previous meeting held on 12th October 2019 were read and confirmed as a true record of the said meeting. They were proposed and seconded by Arnest murithi and Catherine Ndiga respectively.

**NGCDFC MIN 3-299/11/2018 MATTERS ARISING FROM THE MINUTES**

There were no matters arising.

**NGCDFC MIN 4-29/11/2018 PROJECT PROPOSALS FOR 2018/2019 FINANCIAL YEAR**

Members were informed that the allocation for the financial year is kshs 137,367,724.10. Members were taken through the CEO circular ref:NGCDFB/CIRCULARS Vol. II(014) dated 24th September 2019. Members deliberated on the projects to benefit under the financial year and in considering incomplete projects, ward priorities, statutory projects and those cutting across the constituency as well as constituency projects .

On ongoing projects the committee allocated them funds and observed the following.

* NGCDFC office- the project is yet to start as there is a dispute on allocation of land where the Prisons department has fenced the piece of land earmarked for construction of the office and other government departments offices. The office project is to be allocated more funds once the dispute is resolved.
* Nguruki day secondary- the project was allocated funds for completion under 2018/2019 Financial year.
* Kieni Day secondary school- the project was allocated funds for completion under 2018/2019 Financial year.
* Maara mixed boarding- the project was allocated funds for completion under 2018/2019 Financial year.
* Kiraro primary-the project is complete
* Kiraro day secondary- dormitory complete
* Ndintune day secondary- the project was allocated funds for completion under 2018/2019 Financial year.

The committee after considering the above mentioned issues came up with the following proposals:

|  |  |  |  |
| --- | --- | --- | --- |
| **PROJECT NAME** | **ACTIVITIES** |  | status |
| **Administration and recurrent** |  |  |  |
| Employees Salaries | Payment of staff salaries and gratuity | **2,200,000.00** | ongoing |
| Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence and office tea. | **2,730,611.22** | ongoing |
| NSSF | Payment of NSSF Deductions | **129,600.00** | ongoing |
| NHIF | Payment of NHIF Deductions | **51,600.00** | ongoing |
| Committee Expenses | Payment of Committee sitting allowances, transport, conferences | **3,000,000.00** | ongoing |
| Monitoring and Evaluation |  |  |  |
| Goods and Services | Purchase of fuel , maintenance, printing, stationery, Airtime, travel and subsistence. | **500,000.00** | ongoing |
| Committee Expenses | Payment of Committee sitting allowances, transport, conferences, monitoring and evaluation expenses. | **2,121,031.70** | ongoing |
| NGCDFC/PMC Capacity Building | Undertake Training of the PMCs/NGCDFC on NGCDF Related issues. | **1,500,000.00** | ongoing |
| **BURSARY** |  |  |  |
| Bursary Secondary Schools | Payment of bursary to needy student | **17,000,000.00** | ongoing |
| Bursary Tertiary Schools | Payment of bursary to needy student | **17,341,931.00** | ongoing |
|  |  |  |  |
| **SPORTS** | Organize a sports tournament with winning teams being awarded uniforms and trophies. | 2,747,354.40 | ongoing |
| **ENVIRONMENT** |  |  |  |
| IGANGARA SECONDARY SCHOOL | Water harvesting- installation of gutters(Kshs.120,000) and purchase of water tank(10,000litres) Kshs.80,000. Purchase and planting 1,000 tree seedlings(Kshs.100,000) | 300,000.00 | ongoing |
| NTAKANI PRIMARY SCHOOL | Water harvesting- installation of gutters(Kshs.120,000) and purchase of water tank(10,000litres) Kshs.80,000 | 200,000.00 | ongoing |
| MUKUI PRIMARY SCHOOL | Water harvesting- installation of gutters(Kshs.120,000) and purchase of water tank(10,000litres) Kshs.80,000. | 200,000.00 | ongoing |
| MAKENGI PRIMARY SCHOOL | Water harvesting- installation of gutters(Kshs.120,000) and purchase of water tank(10,000litres) Kshs.80,000. Purchase and planting 1,000 tree seedling(Kshs.100,000) | 300,000.00 | ongoing |
| Ndumbini primaryschool | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Kamachuku primary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Giampampo primary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Wiru day secondary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Itara day secondary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Gituja day secondary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Kieganguru primary | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Ikumbo day secondary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Kauuni primary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Kanini primary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Kiurani primary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Munga primary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
| Iruma day secondary school | Purchase and planting 1,000 tree seedlings | 100,000 | ongoing |
|  |  |  |  |
| EMERGENCY | To cater for any unforeseen occurrences in the constituency during the financial year | **7,198,241.38** | ongoing |
| **PRIMARY SCHOOLS** |  |  |  |
| Giampampo Primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Kiini primary school | Construction of a kitchen with cooking area,serving area and store from foundation to completion | 400,000.00 | new |
| Kiini Boarding primary school | Renovation of 3 classes- fixing floor, windows and doors, and plasteringto completion | 400,000.00 | new |
| Giankanja primary school | Construction of two classrooms from walling to completion(foundation done by parents) | 1,000,000.00 | new |
| Ikame primary school | Renovation of 2 classes- fixing floor, windows and doors to completion(300,000), and plastering and construction of 1 classroom from foundation to completion(600,000). | 900,000.00 | new |
| Karimba primary school | construction of four roomed administration block from foundation to completion to serve 24 teachers. | 1,000,000.00 | new |
| Mikuu primary school | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | 300,000.00 | new |
| Kamachuku primary school | Renovation of 3 classes- fixing floor, windows and doors, and plastering to completion. | 400,000.00 | new |
| Ntakani primary school | construction of pit latrines with four doors to completion. | 300,000.00 | new |
| Kanoro primary school | Renovation of three classrooms- replacement of iron sheets to completion | 400,000.00 | new |
| Gituja primary school | Renovation of 2 classes- fixing floor, verandah, windows and doors, and plastering to completion. | 400,000.00 | new |
| Iriga DEB primary school | Dinning hall construction-plastering ,fixing floor, windows and doors to completion. To accommodate 300 students. | 500,000.00 | ongoing |
| Kajiunduthi primary school | construction of a girl’s dormitory from foundation to completion. To accommodate 80 pupils. | 1,000,000.00 | new |
| Kagongo primary school | Renovation of three classrooms- replacement of iron sheets to completion | 300,000.00 | new |
| Rurea primary school | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | 300,000.00 | new |
| NICA Bishop Ezekiel primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Muthambi primary school | Renovation of 3 classrooms)- fixing floor, verandah, windows and doors, and plastering to completion | 600,000.00 | new |
| Maatha primary school | Renovation of 2 classes- fixing floor, windows and doors, and plastering to completion. | 300,000.00 | new |
| Karigini primary school | Renovation of 3 classrooms- fixing floor, verandah, windows and doors, and plastering to completion | 600,000.00 | new |
| ntatua primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Muraga primary school | construction of pit latrines with four doors to completion. | 300,000.00 | new |
| gaketha primary school | Renovation of 3 classrooms- fixing floor, windows and doors, and plastering to completion. | 500,000.00 | new |
| Kairuni primary school | renovation of 4 classrooms- roof replacement and plastering to completion. | 600,000.00 | new |
| Kieganguru primary school | completion of adining hall and kitchen-plastering, fixing floor and painting. To accommodate 300 students | 1,000,000.00 | ongoing |
| Kiraro primary school | renovation of 4 classess- roof replacement and plastering to completion. | 600,000.00 | new |
| Nturiri primary school | fencing of school compound with concrete posts and barbed wire and chain link . an area of about 4 acres(500,000), renovations(500,000)painting of iron sheets,plastering,fixing floor of 3 classrooms | 1,000,000.00 | new |
| wiru primary school | Completion of an administration block-plastering,painting,fixing floor,ceiling and wiring. To accommodate 30 teachers. | 500,000.00 | new |
| Katharaka primary school | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | 300,000.00 | new |
| Kiriani primary school | Renovation of 2 classrooms- fixing floor, verandah, fixing of windows and doors, and plastering and painting of iron sheets to completion | 600,000.00 | new |
| Munga primary school | Renovation of 3 classrooms- fixing floor, verandah, windows and doors, and plastering to completion | 500,000.00 | new |
| Kimuchia primary school | completion of dinning hall-plastering,fixing floor and painting to serve 250 students. | 300,000.00 | ongoing |
| Thigaa primary school | Replacing Asbestos Iron sheets for 4 classrooms | 500,000.00 | new |
| St Augustine Majira primary school | completion of dinning hall-plastering,fixing floor and painting to serve 250 students. | 300,000.00 | ongoing |
| Mbogori primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Makuri primary school | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000). | 700,000.00 | new |
| Kianjagi primary school | construction of flushing ablution block with 12doors (700,000), septic tank(300,000). | 1,000,000.00 | new |
| Chogoria complex primary school | construction of flushing ablution block with 12doors (700,000), septic tank(300,000). | 1,000,000.00 | new |
| Mutindwa primary school | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | 300,000.00 | new |
| Gitare primary school | Construction of teachers pit latrines block with 4 doors to completion. | 300,000.00 | new |
| Kirumi primary school | fencing with concrete posts, chain link and barbed wire approximately 3 acres | 300,000.00 | new |
| Kagira primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Ukuruni primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion | 500,000.00 | new |
| Ikumbo primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion | 500,000.00 | new |
| Ntumu Boys Boarding primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Nkangani primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Murunga primary school | Construction of flushing ablution block with 6 doors(Kshs.400,000) and septic tank(Kshs.300,000) to completion. | 700,000.00 | new |
| Mukui primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion | 500,000.00 | new |
| Ngaita primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion | 500,000.00 | new |
| Kiamaogo primary school | Renovation of 2 classrooms-plastering, fixing floor,doors and painting to completion | 400,000.00 | new |
| Ngeru primary school | construction of flushing ablution block with 6 doors(400,000), connections to septic tank(100,000) to completion | 500,000.00 | new |
| St peter Keriani primary school | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000) to completion. | 700,000.00 | new |
| Kianjuki primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Kanoa primary school | Construction of a pit latrine block with 4 doors to completion. | 200,000.00 | new |
| Kaare primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Kieni primary school | Completion of six roomed administration block -fixing floor, flash washrooms and verandah.. | 400,000.00 | ongoing |
| Karumbi primary school | Three roomed Administration block construction from foundation to completion. to accommodate 20 teachers. | 700,000.00 | new |
| Kabaikubu primary school | construction of flash ablution block with 6 doors(400,000), septic tank(300,000) to completion. | 700,000.00 | new |
| Ndintune primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Kanini primary school | Completion of 12 doors flush toilet-plastering,fixing floor and painting to fully completion | 300,000.00 | ongoing |
| Nguruki primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | 400,000.00 | new |
| Mautini primary school | Kitchenconstruction from foundation to completion with serving room,cooking area and store. | 400,000.00 | new |
| Iruma primary school | construction of a four roomedAdministration block from foundation to completion. Toaccommodate 24 teachers. | 1,000,000.00 | new |
| Makengi primary school | Construction of Teachers pit latrine with 4 doors to completion. | 300,000.00 | new |
| Maguma primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | 500,000.00 | new |
| Iruri primary school | Renovation of 2 classrooms-plastering, fixing floor,doors and painting to completion | 600,000.00 | new |
| Rugongoni primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| m/ekorani primary school | Renovation of 2 classrooms-plastering, fixing floor,doors and painting to completion. | 400,000.00 | new |
| Kirindini primary school | Construction of Girls pit latrine block with 6 doors to completion. | 400,000.00 | new |
| Kithitu primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | 500,000.00 | new |
| Kiairugu primary school | Construction of a classroom from foundation to completion. | 600,000.00 | new |
| Kabui primary school | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | 500,000.00 | new |
| SECONDARY SCHOOLS |  |  |  |
| Kamwangu Day secondary school | Renovation of 2 classes- fixing floor, verandah, windows and doors, and plastering to completion. | 500,000.00 | New |
| St Bonaventure Mumbuni secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Muraga secondary school | Construction of a twin dormitory from roofing to completion-Has a capacity of 160 students.  (foundation and walling done by parents) | 1,000,000.00 | New |
| Karigini day secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Muthambi girls secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Mutiiguru Day Sec sch secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Itara secondary school | Construction of a girls dormitory from foundation to completion with a capacity of 120 students. | 2,000,000.00 | New |
| Igangara secondary school | Construction of a girls dormitory from foundation to completion with a capacity of 80 students. (The amount will be able to complete the dormitory) | 1,000,000.00 | New |
| st Augustine Ruguta Secondary school | Completion of asix roomed administration block to completion-plastering, fixing floor and toilets . has a capacity of 30 teachers | 500,000.00 | ongoing |
| Ndumbini Day secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Gituntu Sec secondary school | Phase one construction of administration block(foundation,walling, plastering and painting of 3 offices to completion) | 1,000,000.00 | New |
| Karimba Day Sec secondary school | construction pit latrine block with four doorsto completion. | 300,000.00 | New |
| Kiraro day secondary school | Phase one construction of administration block(foundation,walling, plastering and painting of 3 offices to completion) | 1,000,000.00 | New |
| Nturiri boys secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Wiru Day secondary school | Construction of six roomed administration block from walling to completion with a capacity of 24 teachers(Kshs.2,100,000),(foundation was done by NG-CDF)  Construction of 6 doors flush toilet to completion- plastering painting ,water system and fixing toilets(400,000) | 2,500,000.00 | ongoing |
| Gianchuku secondary school | Phase one construction of administration block(foundation,walling, plastering and painting of 3 offices to completion) | 1,000,000.00 | New |
| Kianjagi day secondary school | Purchasing and installation of 2 energy saving jikos(300,000)and completion of dining hall–wiring,fixing teraso and painting(200,000) has a capacity of 300 students | 500,000.00 | ongoing |
| Mutindwa Day secondary school | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000) to completion | 700,000.00 | New |
| Kalewa secondary school | Dinning hall completion- fixing 6 windows, partitioning of kitchen and verandahhas a capacity of 200 students. | 400,000.00 | ongoing |
| St.Anne girls Kariakomo secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Ikumbo secondary school | Construction of a dormitory from lintel to completionwith a capacity of 80 students.  (Dormitory started by parents) | 747,354.40 | new |
| Mukui Day secondary school | Construction of three classrooms from foundation to completion. | 1,800,000.00 | New |
| Iruma day secondary school | construction of a Dinning hall from foundation to completion with a capacity of 200 students. | 700,000.00 | new |
| Nguruki day secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Nditune day secondary school | Construction of a classroom from foundation to completion. | 600,000.00 | New |
| Kiurani secondary school | Phase one construction of adormitory block(foundation,walling, plastering and painting completion) with a capacity of 120 students | 1,000,000.00 | New |
| Kiurani Girls secondary school | construction of a pit latrine block to completion with 6 doors(500,000),electricity installation (100,000) | 600,000.00 | New |
| Igakiramba day secondary school | Construction of a six roomed administration block-fixing floor, plastering and painting to completion with a capacity of 24 teachers | 400,000.00 | ongoing |
| Munga day secondary school | Construction of a dinning hall-fixing floor,painting and plastering to completion. Has a capacity of 180 students. | 400,000 | ongoing |
| **TERTIARY INSTITUTIONS** |  |  |  |
| Muraga TTI | Construction of two classrooms from foundation to completion. | 1,200,000.00 | New |
| Chuka University chogoria campus | Construction of four lecture halls with lecturer offices from foundation to completion. Can accommodate 200 students. | 10,000,000.00 | New |
| SECURITY |  |  |  |
| Mwimbi ACCs office | construction of pit latrine block with 6 doors to completion. | 500000 | New |
| Kiera chiefs office | Construction of an office block with three roomsfrom foundation to completion. | 700000 | New |
| **Ikumbo Assistant chiefs office** | Completion of office block with three rooms-fixing floor, plastering ,window panes, verandah and painting of an office block. | 200000 | ongoing |
| Ganga ACC'S office | Renovation of 4 rooms of Accs offices and house- fixing ceiling,water connections, plastering,installation of water and electricity to completion. The house has three bedrooms and the offices has a capacity of 30 people. | 800000 | New |
| Gakui Assistant chief office | Completion of office block with three rooms-fixing floor, plastering , verandah and painting | 200000 | ongoing |
| Muthambi police station | Construction of four rooms office block from foundation to completion. | 2,000,000 | New |
| Mitheru ACC'S office | Renovation of Accs office with five rooms - fixing doors,partitioning,water connections, plastering,installation of water and electricity to completion. | 1,000,000 | New |
|  | **GRAND TOTAL** | 137,367,724.10 |  |

**NGCDFC MIN 5-29/11/2019 POSTA PROPOSAL TO DELIVER BURSARY CHEQUES**

Members were taken through a proposal by posta corporation of Kenya for delivery of bursary cheques which they deliberated on at length. They proposed that for bursary cheques within the county and neighboring counties the cheques can be hand delivered and the rest to be delivered by posta.

There being no other business the chairman declared the meeting adjourned at 2.25PM until the next meeting. Closing prayers were led by Catherine Ndiga.

Minutes prepared by confirmed by:

Mercy gaceri mate(secretary) Jasper Kiambi M’Rithaa(chairman)

Signature………………………………… signature……………………………………………..

Date …………………………………………….. Date ……………………………………………….

**MAARA**

**IEBC NUMBER 060**

**CONSTITUENCY DEVELOPMENT FUND**

**WARD REPORT**

**2019/2020 FINANCIAL YEAR**

**SUBMITTED**

**NOVEMBER 2019**

1.0 Introduction or Background

* 1. About NG-CDF

NG-CDF was initiated in the year 2003 with an aim of alleviating poverty at the grassroot level. It has been administered using the CDF Act of 2003, CDF Amendment Act 2007,CDF ACT 2013 and currently NGCDF Act 2015. It has an allocation of 2.5% of the National government revenue.

1.2 About Maara

Maara constituency is located in Tharaka Nithi County Maara south sub county. It has a total of 5 wards, 14 locations and 43 sub locations. It came into being after the split of the then Nithi constituency in 2013. The constituency has greatly benefitted from NG-CDF notably in the sectors of Education, sports, environment conservation, among many other areas.

1. Projects funding in the previous financial year

2.1 Sectoral analysis of complete and ongoing projects

In the 2018/2019 financial year, the constituency was allocated kshs 109,040,875.50.

1. **Number/allocation of completed projects 2016/2017 financial year**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sector** | **Ward** | **Number of completed projects** | **Cost** | **Remarks** |
| Education |  | 93 |  |  |
| SECURITY |  | 0 |  |  |
| sports |  | 1 | 2180817.50 |  |
| environment |  | 1 | 2180817.50 |  |

1. **Number/allocation of ongoing projects 2018/2019 financial year**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sector** | **Ward** | **Number of ongoing projects** | **Cost** | **Remarks** |
| Education | all | 9 |  |  |
| SECURITY | all | 10 |  |  |

1. **Amount of money used for bursaries, number of beneficiaries and criteria used for 2016/2017 financial year**

|  |  |  |  |
| --- | --- | --- | --- |
| **constituency** | **No. of beneficiaries** | **Amount allocated** | **Remarks (mention creteria** |
| Maara constituency | 4,242 | 26,557,500 | Forms distributed through chiefs, filled, signed by the beneficiaries,vetted by sublocation bursary committee and forwarded to bursary sub committee for approval and cheques writing |

.

3.0 Documentation of the ward reports.

The documents used during the ward meetings can be traced in the NG-CDFC file reference NG-CDF/060/wardreport2019

1. Ward meetings
   1. **Mitheru ward Ward** 
      1. When and where was the meeting conducted

The meeting was held at Mitheru divisional headquarters on 18th September 2019.

* + 1. Who were present

The residents,chiefs and assistant chiefs were present.

* + 1. Who graced the occasion

The occasion was graced by the Mp representative and the DCC..

* + 1. Comments by DC/Chief/Assistance/Mp/

Mp representative

The mp representative emphasized on the need to fund projects to completion and ownership by the residents. He also encouraged the residents to support their leaders to enable them serve the residents better.

DCC

The DCC reminded the residents that the government was committed to ensure developments was realized to all community members. He called upon the residents to ensure that they adhere to the Government policy of eradicating local and substandard brews.

* + 1. Comments by FAM on the nature of projects in respect to NGCDF Act

The FAM took enlighted members on eligible projects

* + 1. Comments by FAM/Chairman on bursary and environment

The FAM and the chairman reminded the community on the need to conserve the environment as well as to ensure needy and bright students are considered for bursary funding. They were reminded that bursary was a project hence the need to continue funding identified beneficiaries until they complete their studies.

* + 1. Projects priorities identified in the Ward

|  |  |
| --- | --- |
| Gaketha Pry sch | 1. Fencing & Gate |
|  | **2. kitchen and dining hall** |
|  | **3. furniture** |
|  | 4. Administartion block |
|  | 4. Boys & Girls toillets |
|  |  |
|  |  |
| Giampampo pry sch | 1. Gate and fencing |
|  | 2. Administration block construction |
|  | 3. Modern sanitation block |
|  | **4. Furniture** |
|  |  |
| Giampampo Day Sec sch | 1.Classroom construction |
|  | 2. Administration block |
|  | 3. laboratory |
|  |  |
| Ruguta pry sch | **1. Kitchen and dinning hall** |
|  | **2. Gate and fencing** |
|  | **3. Renovations of 3 classe** |
|  | 4. Furniture |
|  |  |
|  |  |
| st Augustine Ruguta Sec Sch | **1. Completion of 1st floor of administration block** |
|  | **2. Girls dormitory** |
|  | **3. Fencing** |
|  |  |
|  |  |
|  |  |
| Minugu Pry Sch | **1. Renovation of 3 classes, plastering** |
|  | **2. Admin block** |
|  | **3. Gate and fencing** |
|  |  |
| Kiaibio pry sch | 1. Construction of 3 classrooms |
|  | 2. Admin block |
|  | 3. Kitchen and dining hall |
|  | 4. Sanitation block |
|  |  |
| Kiini pry sch | **1. Kitchen and dining hall** |
|  | **2. Fencing and furniture** |
|  |  |
| Kiini sec sch | 1. sanitation block |
|  | 2. dormitory |
|  | 3. library |
|  |  |
|  |  |
| Kiini Boarding | **1. Renovations of 5 classrooms** |
|  | **2. completion of comp lab** |
|  | **3.sanitation block** |
|  | **3. Fencing** |
|  |  |
| Kiini Industrial TTI | 1.Admin block |
|  | 2. dormitories |
|  | 3. Workshop |
|  |  |
| Giankanja pry sch | 1. Construction of 1st floor storey classes with slab |
|  | 2. Modern sanitation block |
|  | 3. Kitchen and didning hall |
|  | 4. admin block |
|  |  |
|  |  |
|  |  |
| Ikame Pry Sch | 1.Administration block construction |
|  | 2. Sanitation block and septic tank |
|  | **3. Gate and furniture** |
|  | **4. renovations** |
| Ikame Day Sec Sch | **1. 2 new classes** |
|  | **2. Furniture** |
|  |  |
| Mugona Pry Sch | 1. Roofing 2 class |
|  | **2. Kitchen anad dining hall** |
|  | 3. Gate and fencing |
|  |  |
|  |  |
| Mugona Girls | 1. completion of dormitory, |
|  | 2.complete sanitation block |
|  |  |
|  |  |
| Magundu pry sch | 1. Sanitation block and septic tank |
|  | 2. Furniture |
|  | 3. kitchen and dining hall |
|  | 4. Admin block |
|  |  |
| Magundu sec sch | 1. dormitory |
|  | 2. Sanitation block |
|  | 3. admin block |
|  |  |
| Nkururu pry sch | **1. Construction of 1 classroom** |
|  | **2. Furniture** |
|  | 2. Gate and fencing |
|  | 3. Admin block |
|  |  |
| Karimba Day Sec | 1.Phase I Construction of Administration block |
|  | 2. kitchen and dining hall |
|  | 3. Sanitation block |
|  | **5. Laboratory** |
|  |  |
|  |  |
| Karimba pry sch | **1. Admin block** |
|  | **2. Kitchen and didning hall** |
|  | **3. sanitation block** |
|  | 4.Sanitation block and septic tank |
|  |  |
| Kagongo Gaceke | 1.Furniture |
|  | **2. reroofing of 8 classes** |
|  | **3. Gate and fencing** |
|  | **4. admin block** |
|  | 5. kitchen and dining hall |
|  |  |
|  |  |
| Kathangawe Pry Sch | 1. Sanitation block |
|  | 2. Furniture |
|  | 3. renovation of 5 classes |
|  | 4. Gate and fencing |
|  | 5. Kitchen and dining hall |
|  |  |
| Ndumbini Day | 1. construction of admin block |
|  | **2.Construction of 2 classes** |
|  | 3. D.hall and kitchen completion |
|  | 4. Sanitation block |
|  |  |
| Ndumbini pry | 1.Furniture |
|  | 2. Admin block |
|  | 3. Gate and fencing |
|  | 4. Dining hall |
|  |  |
|  |  |
| Muragara pry | 1.Construction of 2 classroom |
|  | 2.furniture and gate |
|  | 3. Administration block |
|  |  |
| Kaganjo pry sch | **1.Construction of 2 new classroom** |
|  | 2.Renovation of 3 classroom |
|  | 3. Kitchen and Dining hall |
|  | 4. Water storage tanks |
|  |  |
| Igangara Sec Sch | 1. Boys dormitory |
|  | **2. Phase I Administration block** |
|  | 3.Kitchen and dining hall |
|  | 4. water harvesting and storage |
|  | 5. Sanitation block |
|  |  |
|  |  |
| Gituntu pry Sch | 1.Furniture |
|  | **2. Amin block** |
|  | 3. Kitchen and Dining hall |
|  |  |
| Gituntu Sec Sch | 1 .Lab construction |
|  | **2. Admin block** |
|  | 3. library construction |
|  | 4. girls dormitory |
|  |  |
| Mikuu Pry Sch | 1. furniture |
|  | 2.Fencing & Gate |
|  |  |
|  |  |
| Kamachuku pry sch | **1. Renovations of 6 classes** |
|  | **2. Gate and fencing** |
|  | **3. Admin block** |

* 1. **Muthambi Ward** 
     1. When and where was the meeting conducted

The meeting was held at Muthambi divisional headquarters on 18th September 2019.

* + 1. Who were present

The residents,chiefs and assistant chiefs were present.

* + 1. Who graced the occasion

The occasion was graced by the Mp representative and the DCC..

* + 1. Comments by DC/Chief/Assistance/Mp

Mp representative

The mp representative emphasized on the need to fund projects to completion and ownership by the residents. He also encouraged the residents to support their leaders to enable them serve the residents better.

DCC

The DCC reminded the residents that the government was committed to ensure developments was realized to all community members. He called upon the residents to ensure that they adhere to the Government policy of eradicating local and substandard brews.

* + 1. Comments by FAM on the nature of projects in respect to NGCDF Act

The FAM took enlighted members on eligible projects

* + 1. Comments by FAM/Chairman on bursary and environment

The FAM and the chairman reminded the community on the need to conserve the environment as well as to ensure needy and bright students are considered for bursary funding. They were reminded that bursary was a project hence the need to continue funding identified beneficiaries until they complete their studies.

* + 1. Projects priorities identified in the Ward

|  |  |
| --- | --- |
| Kamwangu Day Sch | 1.completion of 2 classes |
|  | 2. kitchen and dining hall |
|  | 3. modern sanitation block |
|  | 4. furniture |
|  | 5. Admin block |
|  |  |
| Ntakani Pry Sch | 1. modern sanitation block |
|  | 2.Fencing & Gate |
|  | 3. furniture |
|  | 4. kitchen and dining hall |
|  |  |
| Kanoro Pry Sch | **1. Renovation of 3 classes,-rerofing)** |
|  | **2. Gate and fencing** |
|  | 3. Furniture |
|  | 4.Kitchen, Dining hall |
|  |  |
| Maatha Pry sch | **1.Renovation of 2 classrooms, floor, plaster, windows, doors** |
|  | 2. sanitation block |
|  | 3.Fencing and gate |
|  | 4. Furniture |
|  | 4.Kitchen and dining hall |
|  |  |
| St Bonaventure Mumbuni Sec Sch | 1. kitchen and dining hall |
|  | 2. admin block |
|  | **3. Sanitation block** |
|  | 1. Construction of 2 classrooms |
| Mumbuni Pry Sch |  |
|  | 2. Admin block |
|  | 3. lockers & chairs |
|  | **4. Gate and fencing** |
|  | **5. sanitaion block** |
|  |  |
| Kajiambaki pry sch | 1. 1 new class |
|  | **2. Renovation of 3 classes** |
|  | 3. furniture |
|  | 4. kitchen and dining hall |
|  | 5. Modern sanitation block |
|  |  |
|  |  |
| Ikindu pry sch | **1.Renovation of 3 Classrooms** |
|  | 2.school fencing&gate |
|  | 3.School kitchen & dinning hall |
|  | 4.Pupils locker&chairs |
|  |  |
| NICA Bishop Ezekiel pry sch | **1.construction of 2 new class** |
|  | 2. completion of 2 classes, floor, plaster, windows |
|  | 3.Administration block (Staffroom) |
|  | 3.Furniture |
|  | 4.Kitchen and d. hall |
|  | 5.Gate and fencing |
|  |  |
| Kariani Pry Sch | 1. Gate and fencing |
|  | 2.Furniture |
|  |  |
| Willys Pry school | 1. sanitation block |
|  | 2. Kitchen and dining hall |
|  |  |
| St Anselim Mururi B SCH | 1. Comp lab and library |
|  |  |
| Muraga Sec | 1. Twin dormitory |
|  | 2. Sanitation block |
|  |  |
| Nkundi Pry Sch | **1. Renovation of 3 classes,** |
|  | 2. Administration block |
|  | 3. Gate and fencing |
|  | 3. modern sanitation block |
|  | 4. Kitchen and d hall |
|  | 5. water harvesting and storage |
|  |  |
| Karigini day sec sch | 1.Lab completion; benches, water &gas installation |
|  | **2.Construction of 1 class** |
|  | 3.Administration block |
|  | 4. water harvesting and storage |
|  |  |
|  |  |
| Karigini Pry Sch | **1.Renovation of 3 classes** |
|  | 2. modern sanitation block |
|  | **3. Reroofing classes** |
|  | **4. Furniture** |
|  |  |
|  |  |
| marima primary sch | 1..reroofing of 10 classes |
|  | **2. furniture** |
|  | 3. modern saniation block |
|  | **4. Kitchen and dining hall** |
|  |  |
|  |  |
| ntatua primary | 1. Construction of a new class |
|  | 2. Furniture |
|  | 3.construction of a kitchen and dining hall |
|  | 4. Gate and fencing |
|  |  |
| Muraga day & Boarding pry | 1. Dining hall/Kitchen |
|  | 2. 3 new Classrooms |
|  | **3. Administration block construction to completion** |
|  |  |
|  |  |
| Muraga Pry Sch | 1. School gate, fencing and furniture |
|  | **2. Admin block** |
|  | 3.modern Sanitation blocks |
|  |  |
| Muraga TTI | 1.Cabros flooring |
|  | 2.Tuition block |
|  | 3. Electrical and electronics Workshop |
|  |  |
| Mutiiguru pry sch |  |
|  | 2. Renovations of all classes |
|  | 3. Sanitation block |
|  | 4. Furniture |
|  |  |
|  |  |
| Mutiiguru Day Sec sch | **1.1st floor 2 classes** |
|  | 2. Admin block |
|  | 3. Laboratory |
|  | 4. kitchen and dining hall |
|  |  |
| Gituja day sec sch | 1.Construction of kitchen and dinning hall |
|  | 2.Construction of administration block |
|  | 2.Gate, fencing and furniture |
|  |  |
|  |  |
| Gituja Pry Sch | **1.Renovation of 3 classroom ;** |
|  | 2. Gate, fencing and furniture |
|  | 3. Kitchen and dining hall |
|  |  |
| Iriga DEB Pry Sch | **1.Renovation of 3 classrooms** |
|  | 2.Construction of administration block |
|  | 3. Completion of dining hall |
|  | 4. Gate and fencing |
|  |  |
| Kajiunduthi Sec | 1. Dormitory- Multi storied building |
|  |  |
| Kajiunduthi pry sch | 1. Girls dormitory |
|  | 2. Kitchen and didning hall |
|  | 3. Gate and fencing |
|  |  |
| Itara Primary sch | **1.Reroofing 8 leaking classrooms** |
|  | 2. modern sanitation block and septic tank |
|  |  |
|  |  |
| Itara Sec sch | **1. Science lab** |
|  | **2. Admin block** |
|  | 3. GIRLS DORMITORY |
|  |  |
| Kagongo pry sch | 1.Roofing of 3 classrooms |
|  | 2.Furnitures (students&Teachers) |
|  | 3.Kitchen and dining hall |
|  | 4.Administration block |
|  | 5. Gate and fencing |
|  |  |
| Rurea pry sch | 1.Furnitures |
|  | 2. modern sanitation block |
|  | **3. Kitchen and didning hall** |
|  | 4.Administration block |
|  |  |
| Muthambi Girls | 1. 2 new classes |
|  | 2. Septic tank |
|  |  |
| muthambi boys | 1. modern sanitation block |
|  | 2. multipurpose block |
|  |  |
| Muthambi pry sch | **1.Renovation of 8 classrooms** |
|  | **2. Furniture** |
|  | **3. Sanitation** |
|  | 4. Gate and fencing |

* + 1. Challenges

-funds allocated to the constituency which was inadequate to cater for the pressing needs of the community

-the community was at times unaware of government opportunities they could benefit from

-lack of awareness between National Government functions and County functions

* + 1. Way-forward

-continous awarenwss campaigns on government opportunities and National and devolved fuctions

* 1. **Ganga Ward**
     1. When and where was the meeting conducted

The meeting was held at Ganga divisional headquarters on 20th September 2019.

* + 1. Who were present

The residents,chiefs and assistant chiefs were present.

* + 1. Who graced the occasion

The occasion was graced by the Mp representative and the DCC..

* + 1. Comments by DC/Chief/Assistance/Mp

Mp representative

The mp representative emphasized on the need to fund projects to completion and ownership by the residents. He also encouraged the residents to support their leaders to enable them serve the residents better.

DCC

The DCC reminded the residents that the government was committed to ensure developments was realized to all community members. He called upon the residents to ensure that they adhere to the Government policy of eradicating local and substandard brews.

* + 1. Comments by FAM on the nature of projects in respect to NGCDF Act

FAM informed members on eligible projects

* + 1. Comments by FAM/Chairman on bursary and environment

The FAM and the chairman reminded the community on the need to conserve the environment as well as to ensure needy and bright students are considered for bursary funding. They were reminded that bursary was a project hence the need to continue funding identified beneficiaries until they complete their studies.

* + 1. Projects priorities identified in the Ward

|  |  |
| --- | --- |
| Igwanjau sec | 1. boys dormitory |
|  |  |
| Kirumi primary | 1. sanitation block |
|  | 2. fencing and gate |
|  | 3. kitchen/DH |
|  |  |
| Kauuni pry sch | 1.Renovation of 4 classrooms |
|  | 2. Furniture |
|  | 3. Gate and fencing |
|  | 4. Kitchen and dining hall |
|  | 5. Admin block |
|  |  |
| Kagira pry sch | **1.Construction of 2 classrooms** |
|  | 2.Construction of adminstration block |
|  | 3.construction of modern saniation blocks |
|  | 4.Fencing, gate and furniture |
|  | 5. Kitchen and dining hall |
|  |  |
| Ukuruni pry sch | 1.Renovations of classes (8) floor,plastering, valendar |
|  | **2. Modern Boys sanitation block, 4 doors with septic tank** |
|  | 3. construction of kitchen and dining hall |
|  | 4.Construction ofn adminstration block |
|  | 5. furniture |
|  |  |
|  |  |
| Ikumbo pry sch | **1.Renovation of (3) classrooms, plastering, floor, walls,** |
|  | **windows and varendah** |
|  | **2. Furniture** |
|  | 3.Modern teachers latrine |
|  | 4. kitchen and dining hall |
|  | 5. Water harvesting |
|  |  |
| Ikumbo sec sch | 1.Dormitory girls & boys |
|  | 2. sanitation block and septic tank |
|  | 3.Teachers houses |
|  | 4. Kitchen and dining hall |
|  |  |
| Ntumu Boys Boarding | 1. replace timber classes 4 |
|  | **2. boys sanitation block** |
|  | 3. replace asbestos iron sheets |
|  |  |
| Nkangani pry sch | 1. sanitation block |
|  | **3. 3 new classes** |
|  |  |
|  |  |
|  |  |
| Mbironi pry sch | 1. Gate and fencing |
|  | 2. Furniture |
|  | 3. Sanitation block |
|  |  |
|  |  |
| Murunga Pry Sch | 1. Modern sanitation block |
|  | 2.Completion of administration block; keying&painting |
|  | **3. Furniture** |
|  | **4. Fencing and gate** |
|  | 5.Kitchen, Fencing & gate |
|  | 6. Roofing of 1 classroom |
|  |  |
| Mukui pry sch | 1.Renovation of 5 classes |
|  | 2. Furniture |
|  | 3. Fencing and gate |
|  |  |
| Kajiethetu pry sch | 1. Construction of 2 new classroom |
|  | 2. gate and fencing |
|  | 3. Kitchen |
|  | 4. Water harvesting and storage facility |
|  |  |
|  |  |
| Ngaita pry sch | **1.Renovation of (3) classes** |
|  | 2. Modern sanitation block for boys&Girls |
|  | 3. Gate and fencing |
|  | **4. Furniture** |
|  | **5. Kitchen and didning hall** |
|  |  |
| Ngaita Sec Sch | **1. new class** |
|  | 2. Admin block |
|  |  |
| Kiamaogo sec | 1. Sanitation block |
|  |  |
|  |  |
| Kiamaogo pry | **1. Gate and fencing** |
|  | **2. Renovations of classes** |
|  | **3. Kitchen and dining hall** |
|  | 4.Furniture |
|  |  |
| Maara Mixed Day and Boarding | 1. Girls dormitory |
|  | **2. Fencing** |
|  | 2. Administration Block |
|  |  |
| Ngeru pry sch | 1. Modern sanitation block (special, teachers, other pupils |
|  | **2. Renovation of classes** |
|  | **3. Kitchen and dining hall** |
|  |  |
| Ngeru Elite | **1. Kitchen and dining hall** |
|  | **2. Modern sanitation block** |
|  |  |
|  | 4.Gate and fencing |
|  |  |
| Ngeru Sec | **1. Renovations of classes** |
|  | 2. Admin block |
|  | 3. Fecing |
|  |  |
| Ndunguri pry sch | 1. modern sanitation block |
|  |  |
| Kariakomo pry sch | **1. Furniture** |
|  | **2. Gate and fencing** |
|  |  |
| St peter Keriani pry | 1.Construction of modern toilets; teachers & pupils |
|  | 2.Class construction for special pupils |
|  | 3.Gate & fencing |
|  | 6.Electricity wiring |
|  | 7.Kitchen |
|  | 8.Furniture |
|  |  |
| St.Anne girls Kariakomo | 1. 1st phase dormitory |
|  | 2. Perimeter wall |
|  | **3.Construction of 1 Classroom** |
|  |  |
|  |  |
| Mukui Day Sec | 1. 3 new classes |
|  | 1. sanitation block |
|  | 2. Kitchen and dining hall |

* + 1. Challenges

-funds allocated to the constituency which was inadequate to cater for the pressing needs of the community

-the community was at times unaware of government opportunities they could benefit from

-lack of awareness between National Government functions and County functions

* 1. **Mwimbi Ward**
     1. 4.4.1 When and where was the meeting conducted

The meeting was held at Mwimbi divisional headquarters on 20th September 2019.

* + 1. Who were present

The residents,chiefs and assistant chiefs were present.

* + 1. Who graced the occasion

The occasion was graced by the Mp representative and the DCC..

* + 1. Comments by DC/Chief/Assistance/Mp

Mp representative

The mp representative emphasized on the need to fund projects to completion and ownership by the residents. He also encouraged the residents to support their leaders to enable them serve the residents better.

DCC

The DCC reminded the residents that the government was committed to ensure developments was realized to all community members. He called upon the residents to ensure that they adhere to the Government policy of eradicating local and substandard brews.

* + 1. Comments by FAM on the nature of projects in respect to NGCDF Act

The FAM took enlighted members on eligible projects

* + 1. Comments by FAM/Chairman on bursary and environment

The FAM and the chairman reminded the community on the need to conserve the environment as well as to ensure needy and bright students are considered for bursary funding. They were reminded that bursary was a project hence the need to continue funding identified beneficiaries until they complete their studies.

* + 1. Projects priorities identified in the Ward

|  |  |
| --- | --- |
| Kianjuki pry sch | **1. Construction of 3 new classroom** |
|  | 2.Construction of adminstration block |
|  | 3.construction of modern sanitation block |
|  |  |
| Kanoa Pry | 1. Administration block |
|  | 2. Furniture and sanitation block |
|  | 3. sanitation |
|  |  |
| Kaare pry sch | **1.Construction of 3 classrooms,** |
|  | **2. fencing** |
|  |  |
| Kaare sec sch | 1.Dinning Hall and kitchen |
|  | 2. Modern sanitation block |
|  | 3. admin block |
|  |  |
| Kieni Pry School | **1. Construction of kitchen and dining hall** |
|  | **2. Fencing and furniture** |
|  | 3.Wiring & electricity |
|  | 4.Construction of boys & teachers sanitation block |
|  | finishing of admin and electricit/furniture |
|  |  |
| Karumbi pry sch | 1.Administration block |
|  | 2.Construction of kitchen and dining hall |
|  | 3.Sanitation block for boys & girls |
|  | 4.Fencing & gate |
|  |  |
|  |  |
| Kabaikubu pry sch | 1. Completion of 4 classes, plastering, windows, window panes |
|  | 2.Sanitation block |
|  | 3.Wiring and electricty of the administration block |
|  |  |
|  |  |
| Ndintune pry sch | **1. Construction of a new class** |
|  | 2.Teachers/pupils sanitation block |
|  | 3. kitchen and dining hall |
|  |  |
|  |  |
| Kanini pry sch | 1. Renovations of 2 classes |
|  | 2.Adminstration block |
|  | 3. Furniture |
|  | 4. Gate and fencing |
|  | /FINISHING OF SANITATION |
| Kieni sec sch | 1.Dormitory for girls completion |
|  | 2. Construction of sanitation block |
|  | 3. Kitchen and dining hall |
|  |  |
| Nguruki day sch | 1.Dining hall/Kitchen store |
|  | **2. Construction of 3 new classes** |
|  | 3.Modern washrooms |
|  |  |
| Nguruki pry sch | **1.Renovation of (5) classrooms,** |
|  | 2.Construction of 2 classrooms |
|  | 3.modern administration block |
|  |  |
| Nditune day sec | **1. Construction of 2 new classes** |
|  | 2.Construction of a dinning hall/Kitchen |
|  | 3. Admin block |
|  |  |
| Maguma Day sec | 1. Construction of 1 classrooms |
|  | 3. A dinning hall/Kitchen |
|  | 4. sanitation block |
|  | 5. Admin block |
|  |  |
| Kiurani pry sch | 1.Classroom renovation (8) classes, plaster, floor, painting |
|  | 2. Modern sanitation block |
|  | 3. Admin block |
|  |  |
| Jediel Kiraithe pry | **1. Construction of (1) classroom** |
|  | **2.Construction of Dinning Hall and kitchen to completion** |
|  | 3.Administration block |
|  | 4.Completion of boys dormitory |
|  | 5. modern sanitation block with septic tank |
|  |  |
| Mautini pry sch | 1.Kitchen, Dining hall and store |
|  | 2.School gate and fencing |
|  | 3. furniture |
|  | 4.Completion of classroom |
|  | 5. modern sanitation block |
|  | 6.Leveling of school field |
|  | 7.water storage facility |
|  |  |
|  |  |
| Iruma pry sch | **1.Construction of administartion block** |
|  | 2.Sanitation block with septic tank |
|  |  |
| Iruma day sch | 1. Dining hall |
|  | 2. 4 new classes |
|  | 3. Library |
| Iruma girls sec sch | 1.Completion of girls dormitory |
|  |  |
| Makengi pry sch | 1. Fencing |
|  | 2.Kitchen and dining hall |
|  | 3. Modern teachers sanitation block |
|  |  |
|  | 5.Library and ICT room |
|  | 6. water storage facility |
|  |  |
|  | **7. 100 Lockers and Chairs for students** |
|  |  |
| Maguma pry sch | 1. renovation of 3 classes/ WIRING |
|  | **2. Wiring** |
|  | 2.Construction of adminstration block |
|  |  |
| Iruri pry sch | **1.Renovation of (2) classrooms, plaster, wind0ws, floor** |
|  | 2. 2 new classes |
|  | 3.Construction of administration block |
|  |  |
| Scotia High school | 1. furniture |
|  |  |
| Rugongoni pry sch | **1.construction of (2)new permanent class** |
|  |  |
| m/ekorani pry sch | **1.renovation of classes (4) classrooms,** |
|  | 2. Admin block |
|  | 3.Gate and fencing |
|  |  |
|  | **i) plaster, painting, floor** |
|  |  |
|  | 4.Kitchen and dining hall |
|  |  |
|  | 6. construction of a new class |
|  | 7. water harvesting and storage facilities |
|  |  |
| Kirindini pry sch | 1. Girls sanitation block |
|  | 2. urniture and fencing |
|  |  |
| Egakiramba pry | **1.Renovation of (3) classrooms** |
|  | **2. Furniture** |
|  | 3. modern sanitation block |
|  |  |
| Kithitu pry sch | **1. staff pit latrines** |
|  | 2. renovation of 5 classes |
|  |  |
| Kiairugu PEFA Pry sch | 1. Construction of 4 new classes |
|  |  |
| Kiairugu pry sch | **1.Construction of (3) new classrooms** |
|  | 5.Gate and fencing |
|  | 4. modern sanitation block |
|  |  |
| Kabui Pry sch | 1.Renovations of classes and adminitration block |
|  | 2. furniture |
|  | 2. Administration block |
|  | 3. Gate and fencing |
|  |  |
| Kabui sec sch | 1. Construction of 2 new classes |
|  | 2. Expansion of girls dormitory |
|  |  |
| Kiurani Sec Sch | 1.Boys dormitory |
|  | 2.New Classrooms (3) |
|  | 3. Kitchen and didning hall |
|  |  |
|  | 5. Library and ICT room |
|  | 6. Modern Sanitation block |
|  | 7.Three teachers houses |
|  | 8.Basket ball court |
|  |  |
| Kiurani Girls Sec | **1. Construction of 2 new classrooms from foundation to completion** |
|  | **2. Modern sanitation block** |
|  | **3. Admin block** |
|  |  |
| Igakiramba day | **1. completion of admin block** |
|  | 1.Kitchen/dinning hall |
|  | 2. Modern sanitation block |
|  | 5. Library and ICT |

* + 1. Challenges

-funds allocated to the constituency which was inadequate to cater for the pressing needs of the community

-the community was at times unaware of government opportunities they could benefit from

-lack of awareness between National Government functions and County functions

* + 1. Way-forward

-continous awarenwss campaigns on government opportunities and National and devolved fuctions

* 1. **Chogoria Ward**
     1. When and where was the meeting conducted

The meeting was held at Kairuni stadium on 21st September 2019.

* + 1. Who were present

The residents,chiefs and assistant chiefs were present.

* + 1. Who graced the occasion

The occasion was graced by the Mp representative and the DCC..

* + 1. Comments by DC/Chief/Assistance/Mp

Mp representative

The mp representative emphasized on the need to fund projects to completion and ownership by the residents. He also encouraged the residents to support their leaders to enable them serve the residents better.

DCC

The DCC reminded the residents that the government was committed to ensure developments was realized to all community members. He called upon the residents to ensure that they adhere to the Government policy of eradicating local and substandard brews.

* + 1. Comments by FAM on the nature of projects in respect to NGCDF Act

The FAM took enlighted members on eligible projects

* + 1. Comments by FAM/Chairman on bursary and environment

The FAM and the chairman reminded the community on the need to conserve the environment as well as to ensure needy and bright students are considered for bursary funding. They were reminded that bursary was a project hence the need to continue funding identified beneficiaries until they complete their studies.

* + 1. Projects priorities identified in the Ward

|  |  |
| --- | --- |
| Kairuni pry sch | 1. Renovations of 7 classes |
|  | 2. Kitchen and Dining hall |
|  | 3. Adm block |
|  |  |
|  | **4. reroofing and painting of 4 classes** |
|  | **i) plastering, painting** |
|  |  |
| Kairuni mentally sch | 1.kitchen and dining hall construction |
|  |  |
|  | 2. Girls Dormitory |
|  | 3. Fencing |
|  |  |
| Kieganguru girls | **1.Completion of library block** |
|  | **2. Water Storage tanks** |
|  | **3. Fencing** |
|  |  |
| Kieganguru Pry | **1. Completion of kitchen and dining hall** |
|  | **2. Modern sanitation block** |
|  | 3. Library |
|  |  |
| Kiraro pry | **1.Renovations of 5 classes** |
|  | **i) painting, doors, plaster, windows and verandah** |
|  |  |
|  | 2. furniture and Fencing |
|  |  |
| Kiraro day Sec Sch | 1. Modern admin block with slab |
|  |  |
|  | **2. ICT laboratory** |
|  |  |
|  | 3. completion of staff quarters |
|  |  |
| Nturiri boys | 1. 1 New classroom |
|  |  |
|  |  |
| Nturiri pry | **1. Fencing of school compound/ sanitation** |
|  |  |
|  | 2. modern sanitation block |
|  |  |
|  |  |
| Wiru pry sch | 2. Kitchen and Dining hall |
|  | 3.Modern sanitation block |
|  | **ADMINISTRATION BLOCK** |
|  |  |
|  |  |
|  |  |
| Wiru Day Sec School | 1. ad,min block-COMPLETION |
|  | **1. Modern sanitation block** |
|  | 2. 4 new classrooms |
|  | 3. Laboratory |
|  |  |
| Katharaka pry sch | **1. Administartion block** |
|  | **2. furniture** |
|  | 3. dining hall |
|  |  |
|  |  |
| Kiriani boys | **1.Completion of dormitory** |
|  | **i.Roofing of first floor,** |
|  | **ii.Plastering, window frames, sanitation system** |
|  |  |
| Kiriani pry sch | 1. finishing admin block |
|  | **CLASS RENOVATIONS( 2 CLASSES)** |
|  |  |
| Kiriani day sch | **1. Construction of Administration block to completion** |
|  |  |
|  |  |
| Munga pry sch | 1. Renovations of classes |
|  | 2. Furniture and fencing |
|  |  |
| Munga Day sch | **completion of dining hall** |
|  | **2. science lab** |
|  |  |
| Kimuchia pry sch | 1.completion of dining hall and furniture |
|  | 2.Reconstruction of the 4 mabati classes |
|  |  |
| Kimuchia day sch | **1. equip schience lab** |
|  | **2. quip library** |
|  | **3. equip comp lab** |
|  |  |
| Thigaa pry sch | 1. Replacing Asbestos Iron sheets |
|  | 2. Kitchen and Dining Hall |
|  | 3.Fencing & gate |
|  |  |
| Thigaa Sec Sch | 1. Multipurpose hall |
|  | 2. Perimeter wall |
|  | 3. Boys Dormitory |
|  | 4. Day Time Sanitation Block |
|  |  |
|  |  |
| St Augustine Majira | 2.Adminstration block |
|  | 3.Modern Sanitation block and septic tank |
|  | 4.Fencing & gate |
|  | kitchen/ DH completion |
|  |  |
| Mbogori pry sch | **1. Construction of 3 new classes** |
|  | 2.Construction of adminstration block |
|  | **3. gate and fencing** |
|  |  |
|  |  |
| Chogoria Boys Boarding Pry | 1. modern toilets |
|  | 2. tiles and dining furniture |
|  | 3.painting of old buildings |
|  | 4. perimeter wall |
|  |  |
| Gianchuku Pry | 1.Renovation of classrooms |
|  | i)roof painting, doors, plastering, windows and window panes |
|  | 2.Adminstration block |
|  |  |
| Gianchuku Sec Sch | 1. construction of administration block |
|  | 2. Computer lab and library |
|  |  |
| Makuri pry sch | **1. sanitation block 7 doors for boys and septic tank** |
|  | **2. Furniture** |
|  | 3.Kitchen and Dinning hall |
|  |  |
| Kianjagi day | 1. 2 energy saving jikos and completion of dining hall |
|  |  |
|  |  |
| Kianjagi pry | **1. Administration block** |
|  | **2. Dining hall** |
|  | 3. fencing and furniture |
|  |  |
| Mwimbi boarding | 1. 1st floor of boys dormitory |
|  | 2. modern sanitation and septic |
|  |  |
|  |  |
| Chogoria G boarding | 1.School fencing |
|  | 2.Dormitory |
|  | 3. sanitation block |
|  |  |
| Chogoria complex | 1. sanitation block with 6 floors |
|  | 2. administration block |
|  |  |
| Chogoria girls High school | 1.Additional 4 new classrooms |
|  | 2. Perimeter wall reconstruction |
|  |  |
|  |  |
| Chogoria boys High | RENOVATION OF CLASSES |
|  |  |
| Chief Mbogori Girls | **1. Construction of 2 new classes** |
|  | **2. Dormitory 1 st floor** |
|  | 3. library |
|  |  |
| Makuri Girls | 1. students washrooms |
|  | 2. fencing |
|  | 3. store for school furniture |
|  |  |
| Mutindwa Pry sch | 1. furniture |
|  |  |
| Mutindwa Day Sec | 1. modern sanitation block, 12 doors and septic tank |
|  | 2. 3 new classes |
|  |  |
| Kalewa Sec Sch | 1. completion of dining hall and admin block |
|  | 2.Construction of a ICT lab and library |
|  |  |
| Kalewa Pry sch | 1. Sanitation block |
|  | 2admin block |
|  | 3. Kitchen and dining hall |
|  |  |
| Gitare pry | 1. dining hall |
|  | 1. teachers toilets |
|  | 2. gate and fencing |

* + 1. Challenges

-funds allocated to the constituency which was inadequate to cater for the pressing needs of the community

-the community was at times unaware of government opportunities they could benefit from

-lack of awareness between National Government functions and County functions

* + 1. Way-forward

-Increase of CDF fundinf from the current 2.5% to atleast 5%.

-continous awarenwss campaigns on government opportunities and National and devolved fuctions

|  |  |
| --- | --- |
|  |  |
| **SECURITY** | **1. Kaare Police post- electricty,furniture** |
|  | **2.Ntuneni Asst chiefs office-renovations, fencing, furniture** |
|  | 3. Muragara Asst chiefs ofice-Office Block |
|  | 4. Kaare Loc chiefs office-fencing, furniture |
|  | 5. Magutuni Police station-wards, expamnsion, furniture, fencing |
|  | 6. Mwimbi ACCs office-Expansion, sanitation |
|  | 7. Kiera Chiefs office-office block, water, electricity |
|  | 8. Magutuni Asst Chiefs office-sanitation, water, electricity |
|  | 9. Karii Asst Chiefs office-office block,Sanitation, fencing |
|  | 10. Kathingithiu Asst Chiefs office |
|  | 11. Kiroo Asst chiefs office-electricity |
|  | 12. Thigaa ASST chiefs office-Office block and furniture |
|  | 13. Maara Loc Chiefs office-Hall, sanitation block, AP line |
|  | 14.Ikuu asst chief office-furniture |
|  | 15.Iruma asst chiefs office-furniture, electricity, gate and fencinh |
|  | 16. Iruma Chiefs office |
|  | 17. Makengi PRISON-WARDS, KITCHEN |

* 1. **Conclusion/way forward**

The entire exercise was a success and the residents were optimistic that the fund will continue so as to be able to enjoy more development opportunities.

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Signed (Chairman)**

**Date**

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Signed (Fund Account Manager) Date**

# ANNEX I: STRATEGIC PLAN IMPLEMENTATION MATRIX

| **No** | **Strategic Theme** | **Strategic Objective** | **Strategies/Activities** | **Output Indicators** | **Total in Five Years** | **Expected Output** | | | | | **Resources**  **(Kshs. Millions)** | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Y1** | **Y2** | **Y3** | **Y4** | **Y5** | **Y1** | **Y2** | **Y3** | **Y4** | **Y5** |
|  | Access to quality education | To improve access to quality education | Expansion of schools through rehabilitation/  renovation/construction of classrooms in various primary and secondary schools in the constituency | No. of class rooms (‘0') rehabilitated/renovated (On average 2 per school-both primary and secondary) | 150[[1]](#footnote-2) | 30 | 30 | 30 | 30 | 30 | 8.4 | 8 | 8 | 8 | 8 |
| Rehabilitation of ‘***Very Needy Primary Schools*** | No. of classrooms constructed (6 each school) | 300[[2]](#footnote-3) | 60 | 60 | 60 | 60 | 60 | 18 | 18 | 18 | 18 | 18 |
| No. of Kitchen and Dining Halls Constructed | 54[[3]](#footnote-4) | 14 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 |
| No. of schools fenced and gated | 50[[4]](#footnote-5) | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 |
|  |  |  |  |  |  |  |  |  |  |  |  |
| No. of staff quarters (3-door units) | 25 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 |
| No. of dormitories constructed (for boys and girls) | 20 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 |
| No. of administration[[5]](#footnote-6) blocks constructed | 48 | 8 | 10 | 10 | 10 | 10 | 3 | 3 | 3 | 3 | 3 |
| Completion of day secondary schools[[6]](#footnote-7) | No. of classrooms constructed (2 each school) | 20 | 4 | 4 | 4 | 4 | 4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 |
| No. of dormitories constructed | 20 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 |
|  |  |  |  |  |  |  |  |  |  |  |  |
| No. of Administration blocks constructed | 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |
| No. of laboratories | 10 | 3 | 3 | 3 | 1 | - | 3.6 | 3.6 | 3.6 | 1.2 | - |
| No. of staff quarters (3-door units) | 10 | 3 | 3 | 3 | 1 | - | 1.8 | 1.8 | 1.8 | 0.6 | - |
| Construction and equipping of special units in primary schools[[7]](#footnote-8) | No. of class rooms constructed (2 per school) | 8 | 4 | 4 | - | - | - | 2.4 | 2.4 | - | - | - |
| No. of workshops constructed | 4 | 2 | 2 | - | - | - | 1.2 | 1.2 | - | - | - |
| No. of assessment rooms constructed | 4 | 2 | 2 | - | - | - | 1.2 | 1.2 | - | - | - |
| No. of dormitories | 8 | 4 | 4 | - | - | - | 12 | 12 | - | - | - |
| No. of toilets (3-door units) | 24 | 6 | 6 | 6 | - | - | 1.2 | 1.2 | 1.2 | - | - |
| Supply of laboratory equipment to secondary schools | No. of laboratories equipped | 10 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 |
| Construction of computer labs/classes in primary schools | No. of computer labs/classes constructed | 166[[8]](#footnote-9) | 34 | 33 | 33 | 33 | 33 | 20.4 | 20 | 20 | 20 | 20 |
| Rehabilitation/  Renovation/Construction of multipurpose halls in day secondary schools | No. of Multipurpose halls constructed | 10 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 |
| Rehabilitation/  Renovation/Construction of libraries in day secondary schools | No. of libraries constructed | 10 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 |
| Rehabilitation/  Renovation/Construction of toilet blocks in both primary and secondary schools | No. of four-door toilets (166 primary schools and 10 day secondary schools) | 176[[9]](#footnote-10) | 36 | 35 | 35 | 35 | 35 | 7.2 | 7 | 7 | 7 | 7 |
| Leveling of playing fields in both primary and secondary schools | No. of schools with leveled playing grounds (166 primary schools and 10 day secondary schools) | 176[[10]](#footnote-11) | 36 | 35 | 35 | 35 | 35 | 7.2 | 7 | 7 | 7 | 7 |
| Provision of bursary to needy and bright secondary school/tertiary institutions’ students | Amount of funds disbursed (Kshs. millions) | 135 | 25 | 26 | 27 | 28 | 29 | 25 | 26 | 27 | 28 | 29 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction of adult education classes | No. of adult education classes constructed (in each location) | 45 | 9 | 9 | 9 | 9 | 9 | 5.4 | 5.4 | 5.4 | 5.4 | 5.4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |
| Water Harvesting | No. of water tanks[[11]](#footnote-12) (10,000 lts) | 250 | 50 | 50 | 50 | 50 | 50 | 5 | 5 | 5 | 5 | 5 |
|  | Youth and Sports | To empower the youth and harness their talent | Conducting campaigns on drugs and substance abuse and on HIV and AIDS | No. of forums held | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Creating awareness among the youth on the establishment of youth groups, and accessing devolved funds | No. of forums held | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Funding of youth sporting initiatives (e.g. Zone Marathon) | No. of sporting initiatives supported | 5 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 |
|  | Emergency Support | To cater for any unforeseen occurrences in the constituency | Catering for any unforeseen occurrences in the constituency | Amount of money earmarked for emergency projects/initiatives support | 5.4 | - | - | - | - | - | 5.4 | 5.4 | 5.4 | 5.4 | 5.4 |
|  | Environment | To promote environmental sustainability | Organizing tree planting days and cleaning days in towns within the constituency | No. of tree planting days held | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
|  | Security | To enhance security in the constituency | Rehabilitation/  Renovation/Construction of National Government Administration offices and residential houses | No. of Ass. chief's offices constructed (Weru; Gituja; Kiraro; Makuri; Kandungu; Kthitu; Mutindwa; Gitombani; Murugi West; Mugumango; Kathingithu; | 12 | 4 | 4 | 4 | 4 | - | 1.8 | 1.8 | 1.8 | - | - |
| Construction/rehabilitation of Police Stations/AP Offices and police/AP houses | No. of administration blocks for police stations (Kaare Police Station) | 1 | - | 1 | - | - | - | - | 1.5 | - | - | - |
| % completion of civil works in Muthambi and Kieganguru Police post | 100 | - | 100 | - | - | - | - | 5 | - | - | - |
| No. of administration blocks for AP posts | 11 | 3 | 3 | 3 | 2 | - | 1.8 | 1.8 | 1.8 | 1.2 | - |
| No. of AP posts fenced | 11 | 3 | 3 | 3 | 2 | - | 6 | 6 | 6 | 4 | - |
|  | Tracking of results | To improve tracking of implementation NG-CDF programmes | Capacity Building of NGCDFC's and PMC's | No. of staff/NGCDFC/PMCs capacity building forums | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Organizing regular projects monitoring field visits | No. of monitoring and evaluation reports prepared | 20 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 |
|  | Institutional Strengthening | To promote performance management and smooth running of the NG-CDF office | Purchase of working tools and equipment | Employee satisfaction index | 2 | 1 | - | - | - | 1 | 1 | - | - | - | 1 |

**MAARANational Government Constituency Development Fund**

**Project Proposal 2019/2020 Financial Year**

**Codelist**

**FINANCIAL YEAR:…2019 1ST JULY TO 30TH JUNE……2020**

| **Project Name** | | **Project Number** | **Original Cost** | **Cumulative allocation** | **Project activity** | **Amount Allocated** | | **Current Status** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Employees Salaries |  | | **2,200,000.00** | 0 | Payment of staff salaries and gratuity | | **2,200,000.00** | ongoing | |
| Goods and Services |  | | **2,730,611.22** | 0.00 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence and office tea. | | **2,730,611.22** | ongoing | |
| NSSF |  | | **129,600.00** | 0 | Payment of NSSF Deductions | | **129,600.00** | ongoing | |
| NHIF |  | | **51,600.00** | 0 | Payment of NHIF Deductions | | **51,600.00** | ongoing | |
| Committee Expenses |  | | **3,000,000.00** | 0 | Payment of Committee sitting allowances, transport, conferences | | **3,000,000.00** | ongoing | |
| Monitoring and Evaluation |  | |  | 0 |  | |  |  | |
| Goods and Services |  | | **500,000.00** | 0 | Purchase of fuel , maintenance, printing, stationery, Airtime, travel and subsistence. | | **500,000.00** | ongoing | |
| Committee Expenses |  | | **2,121,031.70** | 0 | Payment of Committee sitting allowances, transport, conferences, monitoring and evaluation expenses. | | **2,121,031.70** | ongoing | |
| NGCDFC/PMC Capacity Building |  | | **1,500,000.00** | **0.00** | Undertake Training of the PMCs/NGCDFC on NGCDF Related issues. | | **1,500,000.00** | ongoing | |
| **BURSARY** |  | |  | **0** |  | |  |  | |
| Bursary Secondary Schools |  | | **17,000,000.00** | 0 | Payment of bursary to needy student | | **17,000,000.00** | ongoing | |
| Bursary Tertiary Schools |  | | **17,341,931.00** | 0 | Payment of bursary to needy student | | **17,341,931.00** | ongoing | |
|  |  | |  | 0 |  | |  |  | |
| **SPORTS** |  | | 2,747,354.40 | 0 | Organize a sports tournament with winning teams being awarded uniforms and trophies. | | 2,747,354.40 | ongoing | |
| **ENVIRONMENT** |  | |  |  |  | |  |  | |
| IGANGARA SECONDARY SCHOOL |  | | 300,000.00 | 0 | water harvesting- installation of gutters(120,000) and purchase of water tank(10,000litres) 80,000. Purchase and plant 1,000 trees(100,000) | | 300,000.00 | ongoing | |
| NTAKANI PRIMARY SCHOOL |  | | 200,000.00 | 0 | water harvesting- installation of gutters(120,000) and purchase of water tank(10,000litres) 80,000 | | 200,000.00 | ongoing | |
| MUKUI PRIMARY SCHOOL |  | | 200,000.00 | 0 | water harvesting- installation of gutters(120,000) and purchase of water tank(10,000litres) 80,000. | | 200,000.00 | ongoing | |
| MAKENGI PRIMARY SCHOOL |  | | 300,000.00 | 0 | water harvesting- installation of gutters(120,000) and purchase of water tank(10,000litres) 80,000. Purchase and plant 1,000 trees(100,000) | | 300,000.00 | ongoing | |
| Ndumbini primaryschool |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Kamachuku primary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Giampampo primary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Wiru day secondary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Itara day secondary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Gituja day secondary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Kieganguru primary |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Ikumbo day secondary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Kauuni primary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Kanini primary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Kiurani primary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Munga primary school |  | | 100,000 | 0 | Purchase and plant 1,000 trees | | 100,000 | ongoing | |
| Iruma day secondary school |  | | 100,000 | 0 | Purchase and plant 1000 trees | | 100,000 | ongoing | |
|  |  | |  | 0 |  | |  |  | |
| EMERGENCY |  | | **7,198,241.38** | 0 | To cater for any unforeseen occurrences in the constituency during the financial year | | **7,198,241.38** | ongoing | |
| **PRIMARY SCHOOLS** |  | |  | 0 |  | |  |  | |
| Giampampo Primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Kiini primary school |  | | 400,000.00 | 0 | construction of a kitchen with cooking area,serving area and store from foundation to completionto serve 200 students. | | 400,000.00 | new | |
| Kiini Boarding primary school |  | | 400,000.00 | 0 | Renovation of 3 classes- fixing floor, windows and doors, and plasteringto completion | | 400,000.00 | new | |
| Giankanja primary school |  | | 1,000,000.00 | 0 | construction of two classrooms from walling to completion | | 1,000,000.00 | new | |
| Ikame primary school |  | | 900,000.00 | 0 | Renovation of 2 classes- fixing floor, windows and doors to completion(300,000), and plastering and construction of 1 classroom from foundation to completion(600,000). | | 900,000.00 | new | |
| Karimba primary school |  | | 1,000,000.00 | 0 | construction of four roomed administration block from foundation to completion to serve 24 teachers. | | 1,000,000.00 | new | |
| Mikuu primary school |  | | 300,000.00 | 0 | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | | 300,000.00 | new | |
| Kamachuku primary school |  | | 400,000.00 | 0 | Renovation of 3 classes- fixing floor, windows and doors, and plastering to completion. | | 400,000.00 | new | |
| Ntakani primary school |  | | 300,000.00 | 0 | construction of pit latrines with four doors to completion. | | 300,000.00 | new | |
| Kanoro primary school |  | | 400,000.00 | 0 | Renovation of three classrooms- replacement of iron sheets | | 400,000.00 | new | |
| Gituja primary school |  | | 400,000.00 | 0 | Renovation of 2 classes- fixing floor, verandah, windows and doors, and plastering to completion. | | 400,000.00 | new | |
| Iriga DEB primary school |  | | 1,300,000.00 | 800,000 | Dinning hall construction-plastering ,fixing floor, windows and doors to completion. To accommodate 300 students. | | 500,000.00 | ongoing | |
| Kajiunduthi primary school |  | | 1,000,000.00 | 0 | construction of a girl’s dormitory from foundation to completion. To accommodate 80 pupils. | | 1,000,000.00 | new | |
| Kagongo primary school |  | | 300,000.00 | 0 | Renovation of three classrooms- replacement of iron sheets | | 300,000.00 | new | |
| Rurea primary school |  | | 300,000.00 | 0 | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | | 300,000.00 | new | |
| NICA Bishop Ezekiel primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Muthambi primary school |  | | 600,000.00 | 0 | Renovation of 3 classrooms)- fixing floor, verandah, windows and doors, and plastering to completion | | 600,000.00 | new | |
| Maatha primary school |  | | 300,000.00 | 0 | Renovation of 2 classes- fixing floor, windows and doors, and plastering to completion. | | 300,000.00 | new | |
| Karigini primary school |  | | 600,000.00 | 0 | Renovation of 3 classrooms- fixing floor, verandah, windows and doors, and plastering to completion | | 600,000.00 | new | |
| ntatua primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Muraga primary school |  | | 300,000.00 | 0 | construction of pit latrines with four doors to completion. | | 300,000.00 | new | |
| gaketha primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms- fixing floor, windows and doors, and plastering to completion. | | 500,000.00 | new | |
| Kairuni primary school |  | | 600,000.00 | 0 | renovation of 4 classrooms- roof replacement and plastering to completion. | | 600,000.00 | new | |
| Kieganguru primary school |  | | 2,300,000.00 | 1,300,000 | completion of adining hall and kitchen-plastering, fixing floor and painting. To accommodate 300 students | | 1,000,000.00 | ongoing | |
| Kiraro primary school |  | | 600,000.00 | 0 | renovation of 4 classess- roof replacement and plastering to completion. | | 600,000.00 | new | |
| Nturiri primary school |  | | 1,000,000.00 | 0 | fencing of school compound with concrete posts and barbed wire and chain link . an area of about 4 acres(500,000), renovations(500,000)painting of iron sheets,plastering,fixing floor of 3 classrooms | | 1,000,000.00 | new | |
| wiru primary school |  | | 1500000 | 100000 | Completion of an administration block-plastering,painting,fixing floor,ceiling and wiring. To accommodate 30 teachers. | | 500,000.00 | new | |
| Katharaka primary school |  | | 300,000.00 | 0 | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | | 300,000.00 | new | |
| Kiriani primary school |  | | 600,000.00 | 0 | Renovation of 2 classrooms- fixing floor, verandah, windows and doors, and plastering(300,000), painting of iron sheets (300,000) | | 600,000.00 | new | |
| Munga primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms- fixing floor, verandah, windows and doors, and plastering | | 500,000.00 | new | |
| Kimuchia primary school |  | | 1,400,000.00 | 1,100,000 | completion of dinning hall-plastering,fixing floor and painting to serve 250 students. | | 300,000.00 | ongoing | |
| Thigaa primary school |  | | 500,000.00 | 0 | Replacing Asbestos Iron sheets for 4 classrooms | | 500,000.00 | new | |
| St Augustine Majira primary school |  | | 1,600,000.00 | 1,300,000 | completion of dinning hall-plastering,fixing floor and painting to serve 250 students. | | 300,000.00 | ongoing | |
| Mbogori primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Makuri primary school |  | | 700,000.00 | 0 | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000). | | 700,000.00 | new | |
| Kianjagi primary school |  | | 1,000,000.00 | 0 | construction of flushing ablution block with 12doors (700,000), septic tank(300,000). | | 1,000,000.00 | new | |
| Chogoria complex primary school |  | | 1,000,000.00 | 0 | construction of flushing ablution block with 12doors (700,000), septic tank(300,000). | | 1,000,000.00 | new | |
| Mutindwa primary school |  | | 300,000.00 | 0 | purchase of furniture- 75 lockers each at 2500 and 75 chairs each at 1500. | | 300,000.00 | new | |
| Gitare primary school |  | | 300,000.00 | 0 | Construction of teachers pit latrines block with 4 doors | | 300,000.00 | new | |
| Kirumi primary school |  | | 300,000.00 | 0 | fencing with concrete posts, chain link and barbed wire approximately 3 acres | | 300,000.00 | new | |
| Kagira primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Ukuruni primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting | | 500,000.00 | new | |
| Ikumbo primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting | | 500,000.00 | new | |
| Ntumu Boys Boarding primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Nkangani primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Murunga primary school |  | | 700,000.00 | 0 | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000). | | 700,000.00 | new | |
| Mukui primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting | | 500,000.00 | new | |
| Ngaita primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting | | 500,000.00 | new | |
| Kiamaogo primary school |  | | 400,000.00 | 0 | Renovation of 2 classrooms-plastering, fixing floor,doors and painting | | 400,000.00 | new | |
| Ngeru primary school |  | | 500,000.00 | 0 | construction of flushing ablution block with 6 doors(400,000), connections to septic tank(100,000) | | 500,000.00 | new | |
| St peter Keriani primary school |  | | 700,000.00 | 0 | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000). | | 700,000.00 | new | |
| Kianjuki primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Kanoa primary school |  | | 200,000.00 | 0 | Construction of a pit latrine block with 4 doors to completion. | | 200,000.00 | new | |
| Kaare primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Kieni primary school |  | | 1,900,000.00 | 1,500,000 | six roomed administration block completion-fixing floor, flash washrooms and verandah. | | 400,000.00 | ongoing | |
| Karumbi primary school |  | | 700,000.00 | 0 | Three roomed Administration block construction from foundation to completion. to accommodate 20 teachers. | | 700,000.00 | new | |
| Kabaikubu primary school |  | | 700,000.00 | 0 | construction of flash ablution block with 6 doors(400,000), septic tank(300,000) to completion. | | 700,000.00 | new | |
| Ndintune primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Kanini primary school |  | | 800,000.00 | 500,000 | sanitation block completion(flash)-plastering,fixing floor and painting | | 300,000.00 | ongoing | |
| Nguruki primary school |  | | 400,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | | 400,000.00 | new | |
| Mautini primary school |  | | 400,000.00 | 0 | Kitchenconstruction from foundation to completion with serving room,cooking area and store. | | 400,000.00 | new | |
| Iruma primary school |  | | 1,000,000.00 | 0 | construction of a four roomedAdministration block from foundation to completion. Toaccommodate 24 teachers. | | 1,000,000.00 | new | |
| Makengi primary school |  | | 300,000.00 | 0 | Construction of Teachers pit latrine with 4 doors to completion. | | 300,000.00 | new | |
| Maguma primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | | 500,000.00 | new | |
| Iruri primary school |  | | 600,000.00 | 0 | Renovation of 2 classrooms-plastering, fixing floor,doors and painting to completion | | 600,000.00 | new | |
| Rugongoni primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| m/ekorani primary school |  | | 400,000.00 | 0 | Renovation of 2 classrooms-plastering, fixing floor,doors and painting to completion. | | 400,000.00 | new | |
| Kirindini primary school |  | | 400,000.00 | 0 | Construction of Girls pit latrine block with 6 doors to completion. | | 400,000.00 | new | |
| Kithitu primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | | 500,000.00 | new | |
| Kiairugu primary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | new | |
| Kabui primary school |  | | 500,000.00 | 0 | Renovation of 3 classrooms-plastering, fixing floor,doors and painting to completion. | | 500,000.00 | new | |
| SECONDARY SCHOOLS |  | |  | 0 |  | |  |  | |
| Kamwangu Day secondary school |  | | 500,000.00 | 0 | Renovation of 2 classes- fixing floor, verandah, windows and doors, and plastering to completion. | | 500,000.00 | New | |
| St Bonaventure Mumbuni secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Muraga secondary school |  | | 1,000,000.00 | 0 | Construction of a twin dormitory from roofing to completion-Has a capacity of 160 students.  (foundation and walling done by parents) | | 1,000,000.00 | New | |
| Karigini day secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Muthambi girls secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Mutiiguru Day Sec sch secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Itara secondary school |  | | 2,000,000.00 | 0 | Construction of a girls dormitory from foundation to completion with a capacity of 120 students. | | 2,000,000.00 | New | |
| Igangara secondary school |  | | 1,000,000.00 | 0 | Construction of a girls dormitory from foundation to completion with a capacity of 80 students. (The amount will be able to complete the dormitory) | | 1,000,000.00 | New | |
| st Augustine Ruguta Secondary school |  | | 800,000.00 | 300,000 | Completion of asix roomed administration block to completion-plastering, fixing floor and toilets . has a capacity of 30 teachers | | 500,000.00 | ongoing | |
| Ndumbini Day secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Gituntu Sec secondary school |  | | 1,000,000.00 | 0 | Phase one construction of administration block(foundation,walling, plastering and painting of 3 offices to completion) | | 1,000,000.00 | New | |
| Karimba Day Sec secondary school |  | | 300,000.00 | 0 | construction pit latrine block with four doorsto completion. | | 300,000.00 | New | |
| Kiraro day secondary school |  | | 1,000,000.00 | 0 | Phase one construction of administration block(foundation,walling, plastering and painting of 3 offices to completion) | | 1,000,000.00 | New | |
| Nturiri boys secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Wiru Day secondary school |  | | 3,900,000.00 | 1,400,000 | construction of six roomed administration block from walling to completionwith a capacity of 24 teachers(2,100,000),(foundation was done by NGCDF)  construction of ablution block to completion- plastering painting ,water system and fixing toilets(400,000) | | 2,500,000.00 | ongoing | |
| Gianchuku secondary school |  | | 1,000,000.00 | 0 | Phase one construction of administration block(foundation,walling, plastering and painting of 3 offices to completion) | | 1,000,000.00 | New | |
| Kianjagi day secondary school |  | | 1,500,000.00 | 1,000,000 | Purchasing and installation of 2 energy saving jikos(300,000)and completion of dining hall–wiring,fixing teraso and painting(200,000) has a capacity of 300 students | | 500,000.00 | ongoing | |
| Mutindwa Day secondary school |  | | 700,000.00 | 0 | construction of flushing ablution block with 6 doors(400,000), septic tank(300,000) to completion | | 700,000.00 | New | |
| Kalewa secondary school |  | | 2,400,000.00 | 2,000,000 | Dinning hall completion- fixing 6 windows, partitioning of kitchen and verandahhas a capacity of 200 students. | | 400,000.00 | ongoing | |
| St.Anne girls Kariakomo secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Ikumbo secondary school |  | | 747,354.40 | 0 | Construction of a dormitory from lintel to completionwith a capacity of 80 students.  (Dormitory started by parents) | | 747,354.40 | new | |
| Mukui Day secondary school |  | | 1,800,000.00 | 0 | Construction of three classrooms from foundation to completion. | | 1,800,000.00 | New | |
| Iruma day secondary school |  | | 700000 | 0 | construction of a Dinning hall from foundation to completion with a capacity of 200 students. | | 700,000.00 | new | |
| Nguruki day secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Nditune day secondary school |  | | 600,000.00 | 0 | Construction of a classroom from foundation to completion. | | 600,000.00 | New | |
| Kiurani secondary school |  | | 1,000,000.00 | 0 | Phase one construction of adormitory block(foundation,walling, plastering and painting completion) with a capacity of 120 students | | 1,000,000.00 | New | |
| Kiurani Girls secondary school |  | | 600,000.00 | 0 | construction of a pit latrine block to completion with 6 doors(500,000),electricity installation (100,000) | | 600,000.00 | New | |
| Igakiramba day secondary school |  | | 2,400,000 | 2,000,000 | Construction of a six roomed administration block-fixing floor, plastering and painting to completion with a capacity of 24 teachers | | 400,000.00 | ongoing | |
| Munga day secondary school |  | | 1,900,000 | 1,500,000 | Construction of a dinning hall-fixing floor,painting and plastering to completion. Has a capacity of 180 students. | | 400,000 | ongoing | |
| **TERTIARY INSTITUTIONS** |  | |  | 0 |  | |  |  | |
| Muraga TTI |  | | 1,200,000.00 | 0 | Construction of two classrooms from foundation to completion. | | 1,200,000.00 | New | |
| **Chuka University chogoria campus** |  | | **10,000,000.00** | 0 | Construction of four lecture halls with lecturer offices from foundation to completion. Can accommodate 200 students. | | 10,000,000.00 | New | |
| SECURITY |  | |  | 0 |  | |  |  | |
| Mwimbi ACCs office |  | | 500000 | 0 | construction of pit latrine block with 6 doors to completion. | | 500000 | New | |
| Kiera chiefs office |  | | 700000 | 0 | Construction of an office block with three roomsfrom foundation to completion. | | 700000 | New | |
| **Ikumbo Assistant chiefs office** |  | | 700000 | 500,000 | Completion of office block with three rooms-fixing floor, plastering ,window panes, verandah and painting of an office block. | | 200000 | ongoing | |
| Ganga ACC'S office |  | | 800000 | 0 | Renovation of 4 rooms of Accs offices and house- fixing ceiling,water connections, plastering,installation of water and electricity to completion. The house has three bedrooms and the offices has a capacity of 30 people. | | 800000 | New | |
| Gakui Assistant chief office |  | | 800000 | 600000 | Completion of office block with three rooms-fixing floor, plastering , verandah and painting | | 200000 | ongoing | |
| Muthambi police station |  | | 2000000 | 0 | Construction of four rooms office block from foundation to completion. | | 2,000,000 | New | |
| Mitheru ACC'S office |  | | 1000000 | 0 | Renovation of Accs office with five rooms - fixing doors,partitioning,water connections, plastering,installation of water and electricity to completion. | | 1,000,000 | New | |
| Total |  | |  |  |  | | 137,367,724.10 |  | |

1. Gaketha Pry sch, St Augustine Ruguta pry sch, Ruguta Sec Sch, Minugu Pry Sch, Kiaibio pry sch, Kiini pry sch, Ikame Pry Sch, Mugona Pry Sch, Nkururu pry sch, Karimba pry sch, Kagongo Gaceke, Kathangawe Pry Sch, Ndumbini pry, Muragara pry, Kaganjo pry sch, Gituntu pry Sch, Mikuu Pry Sch Ntakani Pry Sch, Kanoro Pry Sch, Maatha Pry sch, Mumbuni Pry Sch, Kajiambaki pry sch, Muraga Pry Sch , Mutiiguru pry sch, Karigini Pry Sch, Iriga DEB Pry Sch, Itara Primary sch, Kagongo pry sch, Rurea pry sch, Muthambi pry sch, Kairuni pry sch Kiraro pry, Nturiri pry Katharaka pry sch, Kiriani pry sch Munga pry sch Mbogori pry sch, Gianchuku Pry, Kianjagi pry, Kauni pry sch, Ukuruni pry sch, Ikumbo pry sch Nkangani pry sch, Mbironi pry sch Murunga Pry Sch Mukui pry sch, Ngaita pry sch, Ngeru pry sch, Ndunguri pry sch, Kariakomo pry sch, St peter Keriani pry, Kieni pry sch, Karumbi pry sch, Kabaikubu pry sch, Kanini pry sch, Nguruki pry sch, Kiurani pry sch, Iruma pry sch, Iruri pry sch, Mekorani pry sch, Egakiramba pry [↑](#footnote-ref-2)
2. Giampampo pry sch, Giampampo Day Sec sch, Giankanja pry sch, Nkururu pry sch, Karimba Day Sch, Mumbuni Pry Sch, Kajiambaki pry sch, Kanoro Pry Sch, Maatha Pry sch, Mumbuni Pry Sch, Kajiambaki pry sch, Ikindu pry sch, Bishop Ezekiel pry sch, Nkundi Pry Sch, Muraga day & Boarding pry , ntatua primary, Rurea pry sch, Thigaa pry sch St Augustine Majira, Nkangani pry sch, Kianjuki pry sch, Kaare pry sch, Kabaikubu pry sch, Ndintune pry sch, Nguruki pry sch, Kiurani pry sch ,Mautini pry sch, Iruma pry sch, Makengi pry sch, Maguma pry sch, Iruri pry sch, Rugongoni pry sch, m/ekorani pry sch, Egakiramba pry, Kithitu pry sch, Kiairugu pry sch, [↑](#footnote-ref-3)
3. Giankanja pry sch, Magundu pry sch, Kagongo Gaceke, Kathangawe Pry Sch, Kaganjo pry sch, Igangara Sec Sch, Gituntu pry Sch, Ntakani Pry Sch , Muraga Pry Sch, Nkundi Pry Sch, ntatua primary, Muraga day & Boarding pry, Muraga Pry Sch, Gituja Pry Sch, Iriga DEB Pry Sch, Kajiunduthi pry sch, Kagongo pry sch ,Kieganguru Pry, Wiru pry sch, St Augustine Majira Gianchuku Pry, Makuri pry sch, Kirumi primary, Kauni pry sch Kagira pry sch, Ukuruni pry sch Ikumbo pry sch, Mukui pry sch, Kajiethetu pry sch Ngaita pry sch, Ndunguri pry sch, Ngaita pry sch,Kariakomo pry schSt Kiurani pry sch peter Keriani pry,Kaare pry sch,Kieni pry sch,Karumbi pry sch,Karumbi pry sch,Kabaikubu pry sch,Ndintune pry sch,Kanini pry sch,Nguruki pry sch, Mautini pry sch, Iruma pry sch, Makengi pry sch, Maguma pry sch, Rugongoni pry sch, m/ekorani pry sch, Kirindini pry sch, Egakiramba pry, Kithitu pry sch, Kiairugu pry sch, [↑](#footnote-ref-4)
4. Muraga Pry Sch ,Thigaa pry sch, St Augustine Majira, Kirumi primary, Kagira pry sch, Kajiethetu pry sch, Ngaita pry sch, Ngeru pry sch, St peter Keriani pry Kianjuki pry sch, Kaare pry sch, Karumbi pry sch, Kabaikubu pry sch, Ndintune pry sch, Mautini pry sch, Maguma pry sch, Iruri pry sch, Rugongoni pry sch, m/ekorani pry sch, Kirindini pry sch, Kithitu pry sch, Kiairugu pry sch [↑](#footnote-ref-5)
5. Giampampo pry sch, St Augustine Ruguta pry sch, Ruguta Sec Sch, Kiaibio pry sch, Kiini Boarding, Ikame Pry Sch, Karimba Day Sch, Kathangawe Pry Sch, Muragara pry, Ntakani Pry Sch, Ntakani Pry Sch Kagongo pry sch, Rurea pry sch, Rurea pry sch Kiriani pry sch, Thigaa pry sch Thigaa pry sch St Augustine Majira, Mbogori pry sch, Gianchuku Pry, Kagira pry sch, Ukuruni pry sch, Mbironi pry sch Mukui pry sch, St peter Keriani pry Kianjuki pry sch, Kaare pry sch, Karumbi pry sch, Ndintune pry sch, Kanini pry sch, Nguruki pry sch, Mautini pry sch, Makengi pry sch, Maguma pry sch, Iruri pry sch, Rugongoni pry sch, Kirindini pry sch, Kithitu pry sch, Kiairugu pry sch [↑](#footnote-ref-6)
6. Karimba Day Sch, Ndumbini Day, Igangara Sec Sch , Gituntu Sec Sch , Kamwangu Day Sch, St Bonaventure Mumbuni Sec Sch, Karigini day sec sch, Gituja day sec sch, Mutiiguru day sec, Kieganguru girls, Kiraro day girls, Nturiri boys, kiriaini boys, Kiriani day sch, Munga Day sch, Kimuchia day sch, Gianchuku Sec Sch, Kianjagi day, Mutindwa Day Sec, Kalewa Sec Sch, Igwanjau sec, Ikumbo sec sch Kiamaogo sec, St. Anne girls, Mukui Day Sec, Kaare sec sch, Kieni sec sch, Nguruki day sch, Nditune day sec, Maguma Day sec, Iruma day sch, Iruma girls sec sch, Kabui sec sch, Kiurani Sec Sch, Igakiramba day. [↑](#footnote-ref-7)
7. Kairuni mentally sch, Ngeru pry sch ,St peter Keriani pry and Kithitu pry sch [↑](#footnote-ref-8)
8. Munga pry schChogoria G boarding and Mwimbi boarding [↑](#footnote-ref-9)
9. Kiini pry sch, Giankanja pry sch, Ikame Pry Sch, Mugona Pry Sch, Magundu pry sch, Karimba pry sch, Kagongo Gaceke, Gituntu pry Sch, Kamachuku pry sch, Ntakani Pry Sch, Kanoro Pry Sch, Maatha Pry sch, Iriga DEB Pry Sch, Kajiunduthi pry sch ,Itara Primary sch, Rurea pry sch Nturiri pry, Kimuchia pry sch Thigaa pry sch St Augustine Majira, Makuri pry sch, Kianjagi pry Mutindwa Pry sch, Kirumi primary, Kagira pry sch, Ukuruni pry sch, Ikumbo pry sch, Nkangani pry sch Mbironi pry sch, Murunga Pry Sch Kajiethetu pry sch, Ngaita pry sch Kiamaogo pry, Ngeru pry sch, Ndunguri pry sch, Kariakomo pry sch, St peter Keriani pry Kaare pry sch, Kieni pry sch, Kabaikubu pry sch, Nguruki pry sch, Kiurani pry sch, Jediel Kiraithe pry, Mautini pry sch, Iruma pry sch, Makengi pry sch, Maguma pry sch, m/ekorani pry sch, Kirindini pry sch, Egakiramba pry, Kithitu pry sch, Kiairugu pry school [↑](#footnote-ref-10)
10. Magundu pry sch, Karimba pry sch, Mautini pry sch, Maguma pry sch, Iruri pry sch, Kirindini pry sch, Kithitu pry sch, [↑](#footnote-ref-11)
11. For schools and National Government Administration Offices [↑](#footnote-ref-12)