NANDI HILLS

IEBC NUMBER 153

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND

PROJECT PROPOSAL

2017/2018 FINANCIAL YEAR

SUBMITTED

FEBRUARY 2018

MINUTES OF CDFC MEETING HELD AT THE NG - CDF BOARDROOM ON 9/02/2018 AT 9.00 AM

MEMBERS PRESENT

- Charles Limo			Chairman

- Mary Mwaki			Fund Account Manager

- Talam Tiony			Secretary

- Leah Ng’eno 			Member

- Victor Kipkogei			Member

- Elizabeth Chelang’at		Member

- Sarah Melly 			Member

- Ezekiel Yego			Member

- Solomon Kitayi			Assistant County Commissioner

- Joseph Rotich			Sub-County Accountant

AGENDA

- PRAYER

- READING AND CONFIRMATION OF PREVIOUS MINUTES

- CHAIRMAN’S REMARK

- SUBMISSION OF PROPOSALS FOR 2017/2018.

- A.O.B

MIN1/NANDI/01/2018 PRAYER

The meeting started at 10.32 am with a word of prayer from Leah.

MIN2/ NANDI /01/2018 READING AND CONFIRMATION OF PREVIOUS MINUTES

The chairman called upon the secretary to read the previous meeting minutes which were proposed and confirmed by Elizabeth and Ezekiel consecutively to be a true copy of original.

MIN3/ NANDI /01/2018 CHAIRMAN’S REMARKS

The chairman welcomed members to the meeting and thanked them for the good work they have been doing informed members about the allocations of financial year 2017/2018 and cautioned members that no devolved functions will be funded, he also insisted on closer supervision of the projects with the line ministries like the public works, public health officer, Ministry of education among others. He further thanked the Area Member of Parliament for sacrificing his time and accompanying them whenever they needed him during public opinions on proposal collections in Wards.

He further ushered in the Funds Manager, Funds Manager thanked the committee for the work they are doing and encouraged them to keep trying despite of challenges but they should keep on trying to see that they are among the top ten in terms of development country wide

MIN4/ NANDI /01/2018 SUBMISSION OF PROPOSALS

The Secretary Mr. Talam took the members through the proposed projects as compiled by the Fund Account Manager for confirmation and approval. The proposal was approved as below:-

| Project Name | Project Number | Original Cost | Activity | Amount | Status |
| --- | --- | --- | --- | --- | --- |
| Administration/ Recurrent AP1 |  |  |  |  |  |
| Employees’ Salaries | 4-029-153-2110000-100-2017/18-001 | 2,000,000 | Payment of staff salaries and gratuity | 2,000,000 | Ongoing |
| Goods and Services | 4-029-153-2210000-100-2017/18-002 | 1,085,420.69 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, etc. | 1,085,420.69 | Ongoing |
| Office Laptops | 4-029-153-2210000-100-2017/18-002 | 400,000.00 | Purchase of office laptops for Manager, CDFC Chairman and secretary. | 400,000.00 | New |
| NSSF | 4-029-153-2120101-100-2017/18-003 | 50,000.00 | Payment of NSSF Deductions | 50,000.00 | Ongoing |
| NHIF | 4-029-153-2120201-100-2017/18-0z04 | 50,000.00 | Payment of NHIF Deductions | 50,000.00 | Ongoing |
| Committee Expenses | 4-029-153-2210802-100-2017/18-005 | 1,623,200.00 | Payment of Committee sitting allowances, transport, conferences | 1,623,200.00 | Ongoing |
|  |  | 5,208,620.69 |  |  |  |
| Project Name | Project Number | Original Cost | Activity | Amount | Status |
| Monitoring & evaluation AP2 |  |  |  |  |  |
| ` Goods and Services | 4-029-153-2210000-111-2017/18-001 | 404,154.30 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence, | 404,154.30 | Ongoing |
| office photo computers for | 4-029-153-2210000-111-2017/18-001 | 200,000.00 | Purchase of staplers paper punch and photocopier to replace the old ones that has broken down | 200,000.00 | New |
| Committee Expenses | 4-029-153-2210802-111-2017/18-002 | 780,000.00 | Payment of Committee sitting allowances, transport, conferences | 780,000.00 | Ongoing |
| CDFC/PMC Capacity Building | 4-029-153-2210700-111-2017/18-003 | 1,220,156.00 | Undertake Training of the PMCs/CDFCs/Staff on CDF Related issues | 1,220,156.00 | Ongoing |
|  |  | 2,604,310.30 |  |  |  |
| Strategic plan |  |  |  |  |  |
| Constituency Strategic Plan | 4-029-153-2211310-108-2017/18-001 | 3,000,000.00 | To develop a five year strategic plan and website for the constituency | 3,000,000.00 | New |
| ICT HUB |  |  |  |  |  |
| ICT HUB | 4-029-153-2211310-108-2017/18-002 | 4,677,027.20 | Establish Constituency innovation hub in partnership with Ministry of ICT through Telcom Kenya in Siwo Secondary, Koilot Day Secondary, Kimugul Primary School and Jean Marie Seronei Secondary School. | 4,677,027.20 | New |
| Emergency |  |  |  |  |  |
| Emergency | 4-029-153-2640200-101-2017/18-001 | 4,568,965.52 | To cater for any unforeseen occurrences in the constituency during the financial year | 4,568,965.52 | Ongoing |
| Environmental |  |  |  |  |  |
| Nandi hills constituency Environment | 4-029-153-2640509-110-2017/18-001 | 1,536,206.90 | Purchase and installation of water tanks distributions in Chesirikan Primary, Taboiyat Secondary, Timobo and Tereno Primary schools. | 1,536,206.90 | Ongoing |
| Project Name | Project Number | Original Cost | Activity | Amount | Status |
| Sports |  |  |  |  |  |
| Nandi hills constituency sports | 4-029-153-2640509-112-2017/18-001 | 1,536,206.90 | Organizing constituency sports tournament where sports kits will be awarded to winning teams. | 1,536,206.90 | Ongoing |
| Bursary |  |  |  |  |  |
| Bursary Secondary Schools | 4-029-153-2640101-103-2017/18-001 | 10,002,000.00 | Payment of bursary to needy student | 10,002,000.00 | Ongoing |
| Bursary Tertiary Schools | 4-029-153-2640101-103-2017/18-002 | 11,700,758.00 | Payment of bursary to needy student | 11,700,758.00 | Ongoing |
|  |  |  |  | 21,702,758.00 |  |
| SECONDARY SCHOOLS |  |  |  |  |  |
| Ainapngetuny Secondary | 4-029-153-2630205-104-2017/18-001 | 2,000,000 | Completion of two classrooms (storeyed) slab and plastering | 2,000,000 | ongoing |
| Chepngetuny Secondary | 4-029-153-2630205-104-2017/18-002 | 700,000 | Purchase of one acre of land | 700,000 | Ongoing |
| Choimim Secondary school | 4-029-153-2630205-104-2017/18-003 | 1,000,000 | Purchase of one acre of land | 1,000,000 | New |
| Jean Marie Secondary School | 4-029-153-2630205-104-2017/18-004 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | ongoing |
| Kapkoros Secondary Bus | 4-029-153-2630205-104-2017/18-005 | 7,000,000 | Purchase of 52 seater school bus | 7,000,000 | New |
| kaplelmet secondary (classroom) | 4-029-153-2630205-104-2017/18-006 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | Ongoing |
| Kaptien Secondary (Classrooms) | 4-029-153-2630205-104-2017/18-007 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | ongoing |
| Keben secondary (Classroom) | 4-029-153-2630205-104-2017/18-008 | 500,000 | purchase of one acre of land | 500,000 | Ongoing |
| Keteng Secondary (classroom) | 4-029-153-2630205-104-2017/18-009 | 500,000 | Construction of one classrooms, from slab to roofing | 500,000 | New |
| Kipkimba secondary school (Classroom) | 4-029-153-2630205-104-2017/18-010 | 500,000 | construction of one classrooms to walling | 500,000 | New |
| Kipkoror Secondary Classroom) | 4-029-153-2630205-104-2017/18-011 | 500,000 | construction of one classro oms to completion | 500,000 | New |
| Kisebwo Secondary (Classrooms) | 4-029-153-2630205-104-2017/18-012 | 1,000,000 | completiontion of two classroom from slab to completion | 1,000,000 | New |
| Koilot Day (Classroom) | 4-029-153-2630205-104-2017/18-013 | 500,000 | construction of one classroom from slab to completion | 500,000 | Ongoing |
| Kosoiywo Secondary School (classroom) | 4-029-153-2630205-104-2017/18-014 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | ongoing |
| Lelwak Boys ICT Hall | 4-029-153-2630205-104-2017/18-015 | 1,000,000 | Copletion of ICT ceiling and painting Center | 1,000,000 | Ongoing |
| Sirwa Secondary School (Classroom) | 4-029-153-2630205-104-2017/18-016 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting to completion | 1,000,000 | ongoing |
| Soiyet Secondary School(Classroom) | 4-029-153-2630205-104-2017/18-017 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | Ongoing |
| Taboiyat Secondary school(Classroom) | 4-029-153-2630205-104-2017/18-017 | 700,000 | Construction of one classroom; from slab to walling | 700,000 | Ongoing |
| Tereno Girls land | 4-029-153-2630205-104-2017/18-017 | 500,000 | Completion of one classroom; from slab to walling | 500,000 | Ongoing |
| Tigityo Secondary Bus | 4-029-153-2630205-104-2017/18-017 | 7,000,000 | 52 Seater bus | 7,000,000 | New |
|  |  |  |  | 29,400,000 |  |
| PRIMARY SCHOOLS |  |  |  |  |  |
| Chebilat Primary (Classrooms) | 4-029-153-2630204-104-2017/18-001 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | New |
| Chebinyiny Primary (Classroom) | 4-029-153-2630204-104-2017/18-002 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | New |
| Cheptingting Primary (Classroom) | 4-029-153-2630204-104-2017/18-003 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Great Highlands | 4-029-153-2630204-104-2017/18-004 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | ongoing |
| Kabikwen Primary School (Classroom) | 4-029-153-2630204-104-2017/18-005 | 1,000,000 | construction of one classroom; from slab to completion | 1,000,000 | ongoing |
| Mogobich Primary (Classroom) | 4-029-153-2630204-104-2017/18-006 | 500,000 | Completion of two classroom; from slab to walling | 500,000 | ongoing |
| Kapchumba Primary school (land) | 4-029-153-2630204-104-2017/18-007 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapnyemis Primary (Classroom) | 4-029-153-2630204-104-2017/18-008 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapsean Primary school (Classroom) | 4-029-153-2630204-104-2017/18-008 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Completion |
| Kaptuma Primary School(Classroom) | 4-029-153-2630204-104-2017/18-009 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Keben Primary (Classroom) | 4-029-153-2630204-104-2017/18-010 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Keteng Primary Classroom | 4-029-153-2630204-104-2017/18-011 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kimolonik Primary (Classroom) | 4-029-153-2630204-104-2017/18-012 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | ongoimg |
| Kipkorom Primary school (Classroom) | 4-029-153-2630204-104-2017/18-013 | 976,249 | Completion of two classroom; plaster and paint | 976,249 | new |
| kipsamoo Primary school(Classroom) | 4-029-153-2630204-104-2017/18-014 | 500,000 | construction of one to walling classroom | 500,000 | ongoing |
| Kitechgaa Primary (Classroom) | 4-029-153-2630204-104-2017/18-015 | 500,000 | construction of one classroom; from slab to completion | 500,000 | New |
| Koimur Primary | 4-029-153-2630204-104-2017/18-016 | 600,000 | Completion of two classroom to painting | 600,000 | Ongoing |
| Serengonik Primary (classrooms) | 4-029-153-2630204-104-2017/18-017 | 500,000 | Completion of two classroom; plaster and paint | 500,000 | New |
| Sile Primary (Classroom) | 4-029-153-2630204-104-2017/18-018 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | New |
| Simbi Primary(Land) | 4-029-153-2630204-104-2017/18-019 | 500,000 | Purchase of land 1 acre | 500,000 | New |
| Tereno Primary Classroom | 4-029-153-2630204-104-2017/18-019 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | New |
| Timobo Primary School (Classroom) | 4-029-153-2630204-104-2017/18-020 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | new |
|  |  | 12,576,249.31 |  | 12,576,249.31 |  |
|  |  | 86,810,345 |  | 86,810,345 | 86,810,344.82 |

There being no other business the meeting was adjourned with a word of prayer from Mary Mwaki.

Minutes Confirmed by:

……………………………………..		                              ……………………………………..

Chairman – Charles Kimutai	                                Secretary – Talam Tioni

907

2015                     National Government Constituencies Development Fund                                        No.30

THIRD SCHEDULE                                                    (s. 15)

CONSTITUENCY PROJECTS SUBMISSION FORM

Constituency No 183 Constituency Name NANDI HILLS Financial Year 2017/2018

| Serial | Name of Project | Amount Allocated |
| --- | --- | --- |
| 183/AP1 | Administration/Recurrent | 5,208,620.69 |
| 183/AP2 | Monitoring and Evaluation/Capacity Building | 2,604,310.30 |
| 183/2640100 | Bursary | 21,702,758.00 |
| 183/2630204 | Primary School Projects | 12,576,249.31 |
| 183/2630205 | Secondary School Projects | 29,400,000.00 |
| 183/2640509 | Sports Activities | 1,536,206.90 |
| 183/2640510 | Environmental Activities | 1,536,206.90 |
| 183/2640200 | Emergency Reserve | 4,568,965.52 |
| 183/2211310 | Strategic Plan | 3,000,000.00 |
| 183/2211311 | ICT HUB | 4,677,027.20 |
| Total |  | 86,810,344.82 |

Chairman NG- CDF Committee …………………… Signature………………….. Date………………

Fund Account Manager …………………………… Signature…………………….Date………………

907

2015               National Government Constituencies Development Fund                              No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number 183/AP1

Project Title 6% Administration/Recurrent

Sector Administration

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

The allocation is to cater for CDFC Allowance, staff salaries, vehicle expenses and other administrative

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs. 5,208,620.69 dated…………………

Amount allocated last financial year 4,558,410.62

Amount allocated this financial year 5,208,620.69

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Employees’ Salaries | 4-029-183-2110000-100-2017/18-001 | Payment of staff salaries and gratuity | 2,000,000.00 | Ongoing |
| Goods and Services | 4-029-183-2210000-100-2017/18-002 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, etc. | 1,085,420.69 | Ongoing |
| Office Laptops | 4-029-183-2210000-100-2017/18-002 | Purchase of office generator for emergency when there is power interruption | 400,000.00 | New |
| NSSF | 4-029-183-2120101-100-2017/18-003 | Payment of NSSF Deductions | 50,000.00 | Ongoing |
| NHIF | 4-029-183-2120201-100-2017/18-004 | Payment of NHIF Deductions | 50,000.00 | Ongoing |
| Committee Expenses | 4-029-183-2210802-100-2017/18-005 | Payment of Committee sitting allowances, transport, conferences | 1,623,200.00 | Ongoing |
| TOTAL |  |  | 5,208,620.69 |  |

Person completing form: Name ……………………….. Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number 183/AP2

Project Title 3% Monitoring & Evaluation/Capacity Building

Sector Monitoring & Evaluation

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

To cater for Monitoring and Evaluation of CDF projects and capacity building of CDFC and PMCs in the constituency

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs.2, 456,896.50 dated…………………

Amount allocated last financial year 2,604,310.30

Amount allocated this financial year 2,604,310.30

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Goods and Services | 4-029-183-2210000-111-2017/18-001 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence, | 404,154.30 | Ongoing |
| Office laptop | 4-029-183-2210000-111-2017/18-001 | Purchase of photocopier to replace the old one that has broken down | 200,000.00 | New |
| Committee Expenses | 4-029-183-2210802-111-2017/18-002 | Payment of Committee sitting allowances, transport, conferences | 780,000.00 | Ongoing |
| CDFC/PMC Capacity Building | 4-029-183-2210700-111-2017/18-003 | Undertake Training of the PMCs/CDFCs/Staff on CDF Related issues | 1,220,156.00 | Ongoing |
| TOTAL |  |  | 2,604,310.30 |  |

Person completing form: Name ……………………… Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number183/2211310

Project Title Strategic plan

Sector ICT

Status of projects (tick one) New…√…..……………. Extension……………….. On-going…

Rehabilitation ………………….

Brief statement on project status at time of submission

To develop a five year strategic plan for the constituency.

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs.  3,000,000.00 date……………..

Amount allocated last financial year NIL

Amount allocated this financial year 3,000,000.00 ……………….

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Constituency Strategic Plan | 4-029-183-2211310-108-2017/18-001 | To develop a five year strategic plan for the constituency | 3,000,000.00 | New |
| Total |  |  | 3,000,000.00 |  |

Person completing form: Name ………………………….. Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number183/2211311

Project Title ICT HUBs

Sector ICT

Status of projects (tick one) New……√…..…………. Extension……………….. On-going….

Rehabilitation ………………….

Brief statement on project status at time of submission

To improve on ICT innovations in the Constituency

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs. 4,677,027.20 date……………..

Amount allocated last financial year NIL

Amount allocated this financial year kshs.4, 677,027.20 ……………………..

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| ICT HUB | 4-029-183-2211311-108-2017/18-002 | Establish Constituency innovation hub in partnership with Ministry of ICT through Telkom Kenya. | 4,677,027.20 | New |
| Total |  |  | 4,677,027.20 |  |

Person completing form: Name ………………………….. Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number183/2640200

Project Title Emergency Reserve (5% of the fund)

Sector Emergency

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Unallocated amount meant for emergencies that may occur within the Constituency

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs.  4,568,965.52 date……………..

Amount allocated last financial year 4,094,827.59

Amount allocated this financial year 4,568,965.52 ……………….

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Emergency | 4-031-183-2640200-101-2017/18-001 | To cater for any unforeseen occurrences in the constituency during the financial year | 4568,965.52 | Ongoing |
| Total |  |  | 4,568,965.52 |  |

Person completing form: Name ………………………….. Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number 183/2640509

Project Title 2% Environment Activities

Sector Environment

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Purchase and planting of tree seedling for schools and waste tanks in the constituency

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs.  1,536,206.90 dated………………

Amount allocated last financial year 1,000,000.00

Amount allocated this financial year khs.  1,536,206.90

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Nandi hills constituency Environment | 4-029-183-2640509-110-2017/18-001 | Purchase and installation of five 10,000 litre water tanks | 1,536,206.90 | Ongoing |
| Total |  |  | 1,536,206.90 |  |

Person completing form: Name ……………………… Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number183/2640509

Project Title 2% Sports Activities

Sector Sports

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Purchase of uniform & balls for constituency teams

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 1,536,206.90   dated…………………

Amount allocated last financial year 1,556,897.00

Amount allocated this financial year      1,536,206.90

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Sports | 4-031-183-2640509-112-2017/18-001 | Organizing constituency sports tournament where sports kits will be awarded to winning teams. | 1,536,206.90 | New |
| Total |  |  | 1,536,206.90 |  |

Person completing form: Name ……………………… Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number183/2640100

Project Title Bursary

Sector Bursary

Status of projects (tick one) New………………. Extension……………….. On-going…√….. Rehabilitation ………………….

Brief statement on project status at time of submission

Towards Bursary for payment of fees for needy students

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 21,702,758.00dated…………………

Amount allocated last financial year 20,474,137.47

Amount allocated this financial year 21,702,758.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Bursary Secondary Schools | 4-029-183-2640101-103-2017/18-001 | Payment of bursary to needy student | 10,002,000.00 | Ongoing |
| Bursary Tertiary Schools | 4-029-183-2640101-103-2017/18-002 | Payment of bursary to needy student | 11,700,758.00 | Ongoing |
| TOTAL |  |  | 21,702,758.00 |  |

Person completing form: Name ……………………….. Position Fund Account Manager

Signature…………………… Date………………………

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number 183/2630205

Project Title Secondary School Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions of Secondary by improving the infrastructure

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs.17, 600,000.00 dated…………………

Amount allocated last financial year 18,280,000.00

Amount allocated this financial year 29,400,000

| Project Name | Project Code | Project Activity | Amount Allocated | Status |  |
| --- | --- | --- | --- | --- | --- |
| Ainapngetuny Secondary | 4-029-153-2630205-104-2017/18-001 | 2,000,000 | Completion of two classrooms (storeyed) slab and plastering | 2,000,000 | ongoing |
| Chepngetuny Secondary | 4-029-153-2630205-104-2017/18-002 | 700,000 | Purchase of one acre of land | 700,000 | Ongoing |
| Choimim Secondary school | 4-029-153-2630205-104-2017/18-003 | 1,000,000 | Purchase of one acre of land | 1,000,000 | New |
| Jean Marie Secondary School | 4-029-153-2630205-104-2017/18-004 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | ongoing |
| Kapkoros Secondary Bus | 4-029-153-2630205-104-2017/18-005 | 7,000,000 | Purchase of 52 seater school bus | 7,000,000 | New |
| kaplelmet secondary (classroom) | 4-029-153-2630205-104-2017/18-006 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | Ongoing |
| Kaptien Secondary (Classrooms) | 4-029-153-2630205-104-2017/18-007 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | ongoing |
| Keben secondary (Classroom) | 4-029-153-2630205-104-2017/18-008 | 500,000 | purchase of one acre of land | 500,000 | Ongoing |
| Keteng Secondary (classroom) | 4-029-153-2630205-104-2017/18-009 | 500,000 | Construction of one classrooms, from slab to roofing | 500,000 | New |
| Kipkimba secondary school (Classroom) | 4-029-153-2630205-104-2017/18-010 | 500,000 | construction of one classrooms to walling | 500,000 | New |
| Kipkoror Secondary Classroom) | 4-029-153-2630205-104-2017/18-011 | 500,000 | construction of one classro oms to completion | 500,000 | New |
| Kisebwo Secondary (Classrooms) | 4-029-153-2630205-104-2017/18-012 | 1,000,000 | completiontion of two classroom from slab to completion | 1,000,000 | New |
| Koilot Day (Classroom) | 4-029-153-2630205-104-2017/18-013 | 500,000 | construction of one classroom from slab to completion | 500,000 | Ongoing |
| Kosoiywo Secondary School (classroom) | 4-029-153-2630205-104-2017/18-014 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | ongoing |
| Lelwak Boys ICT Hall | 4-029-153-2630205-104-2017/18-015 | 1,000,000 | Copletion of ICT ceiling and painting Center | 1,000,000 | Ongoing |
| Sirwa Secondary School (Classroom) | 4-029-153-2630205-104-2017/18-016 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting to completion | 1,000,000 | ongoing |
| Soiyet Secondary School(Classroom) | 4-029-153-2630205-104-2017/18-017 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | Ongoing |
| Taboiyat Secondary school(Classroom) | 4-029-153-2630205-104-2017/18-017 | 700,000 | Construction of one classroom; from slab to walling | 700,000 | Ongoing |
| Tereno Girls land | 4-029-153-2630205-104-2017/18-017 | 500,000 | Completion of one classroom; from slab to walling | 500,000 | Ongoing |
| Tigityo Secondary Bus | 4-029-153-2630205-104-2017/18-017 | 7,000,000 | 52 Seater bus | 7,000,000 | New |
|  |  | Total |  | 29,400,000 |  |

Person completing form: Name ……………………………. Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 183 Constituency Name NANDI HILLS County NANDI

Project Number 183/2630204

Project Title Primary Education Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions in the primary schools institutions by improving the infrastructure

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 25,086,249.30 dated…………………

Amount allocated last financial year 20,060,000.00

Amount allocated this financial year 12,576,249.31

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Chebilat Primary (Classrooms) | 4-029-153-2630204-104-2017/18-001 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | New |
| Chebinyiny Primary (Classroom) | 4-029-153-2630204-104-2017/18-002 | Construction of one classroom; from slab to walling | 500,000 | New |
| Cheptingting Primary (Classroom) | 4-029-153-2630204-104-2017/18-003 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Great Highlands(land) | 4-029-153-2630204-104-2017/18-004 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kabikwen Primary School (Classroom) | 4-029-153-2630204-104-2017/18-005 | construction of one classroom; from slab to completion | 1,000,000 | Ongoing |
| Mogobich Primary (Classroom) | 4-029-153-2630204-104-2017/18-006 | Completion of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapchumba Primary school (land) | 4-029-153-2630204-104-2017/18-007 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapnyemis Primary (Classroom) | 4-029-153-2630204-104-2017/18-008 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapsean Primary school (Classroom) | 4-029-153-2630204-104-2017/18-008 | Construction of one classroom; from slab to walling | 500,000 | Completion |
| Kaptuma Primary School(Classroom) | 4-029-153-2630204-104-2017/18-009 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Keben Primary (Classroom) | 4-029-153-2630204-104-2017/18-010 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Keteng Primary Classroom | 4-029-153-2630204-104-2017/18-011 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kimolonik Primary (Classroom) | 4-029-153-2630204-104-2017/18-012 | Construction of one classroom; from slab to walling | 500,000 | Ongoimg |
| Kipkorom Primary school (Classroom) | 4-029-153-2630204-104-2017/18-013 | Completion of two classroom; plaster and paint | 976,249 | New |
| kipsamoo Primary school(Classroom) | 4-029-153-2630204-104-2017/18-014 | construction of two classroom | 500,000 | Ongoing |
| Kitechgaa Primary (Classroom) | 4-029-153-2630204-104-2017/18-015 | construction of one classroom; from slab to completion | 500,000 | New |
| Koimur Primary | 4-029-153-2630204-104-2017/18-016 | construction of one classroom to completion | 600,000 | Ongoing |
| Serengonik Primary (classrooms) | 4-029-153-2630204-104-2017/18-017 | Completion of two classroom; plaster and paint | 500,000 | New |
| Sile Primary (Classroom) | 4-029-153-2630204-104-2017/18-018 | Construction of one classroom; from slab to walling | 500,000 | New |
| Simbi Primary(Land) | 4-029-153-2630204-104-2017/18-019 | Purchase of land 1 acre | 500,000 | New |
| Tereno Primary Classroom | 4-029-153-2630204-104-2017/18-019 | Completion of one classroom; from slab to walling | 500,000 | New |
| Timobo Primary School (Classroom) | 4-029-153-2630204-104-2017/18-020 | Construction of one classroom; from slab to walling | 500,000 | New |
| Total |  |  | 12,576,249.31 |  |

Person completing form: Name ……………………………. Position Fund Account Manager

Signature…………………… Date………………………

NANDI HILLS

IEBC NUMBER 183

CONSTITUENCY DEVELOPMENT FUND

WARD REPORTS

2017/2018 FINANCIAL YEAR

SUBMITTED

ON JANUARY 2018

- Introduction or Background

1.1About CDF

The Constituencies Development Fund (CDF) was set up under the CDF Act, 2003 now repealed by the CDF Act, 2013.The CDF Act 2013 aligns the Fund with the Constitution of Kenya 2010 and the Public Finance Management Act 2012 that lay emphasis on citizen participation in public finance management and decision making, transparency and accountability together with equity in public resource utilization. The overall management of the Fund is the responsibility of the Constituencies Development Fund Board.

  - About Nandi hills

Nandi hills Constituency was created in 2013 by the independent Electoral and Boundaries Commission (IEBC). It was split from Tinderet Constituency.

Constituency Vision.

A leading Constituency in integrated planning and good governance for sustainable development.

Constituency Mission.

To create, nurture and sustain an enabling environment for quality and adequate services delivery, sustainable development and prosperity of all communities in Nandi hills Constituency.

Core values and principles underpinning Nandi hills Constituency.

- Partnership, integration, collaboration and networking

- Integrity – honest, ethical, reliable, objectivity, openness, trustworthy.

- Gender equity and equality

- Respect for the principle of human rights and human dignity

- Respect of law and order

- Transparency and accountability

- Team work.

AN OVERVIEW OF THE KEY DEVELOPMENT ACHIEVEMENTS.

Years of sustained development and targeting resources to needy areas has yield key development in the Constituency. These include enhanced access to potable water in schools, improvement school infrastructure, and continuous bursary support to bright and needy students has enabled many to achieve their lifelong dreams

  - Projects funding in the previous financial year

  - Sect oral analysis of complete and ongoing projects

Brief about projects funded and disbursement of funds

- Amount of money used for bursaries, number of beneficiaries and criteria used for 2016/2017 financial year

| Ward | No. of beneficiaries | Amount allocated | Remarks (mention criteria |
| --- | --- | --- | --- |
| Nandi hills Constituency | 1,530 | 20,474,137.47 | Forms distributed through chiefs, filled, signed by the Location Chiefs and assistant Chiefs. |

- Reports

- Ward meetings

2.1 	Kapchorwa WARD

2.1.01 The meeting was conducted at the Labuywa polytechnic.

2.1.02 The members present included the chiefs and assistant chiefs from the ward, the principals and head teachers from the ward, the NG-CDFC members, the representative from the office of the director of Education,  the members of the community , the ACC 1, and the area MP.

2.1.03 the area MP graced the occasion.

2.1.04 Comments:

- ACC

The ACC on behalf of the sub county commissioner recommended the NG- CDF office for the good work of ensuring development in the constituency. He assured members of security within the locations and called upon NG- CDF to support security matters within the constituency. He thanked NG-CDF for the efforts of construction of Chief’s offices and their assistants.

- CHIEF

The area chief welcomed all members at the meeting and thanked NG-CDF for choosing his place as the venue. He informed the public that NG-CDF had completed constructing the office for him. The area chief then introduced other chiefs and assistant chiefs who echoed that the NG-CDF should fully support their offices for continued functioning, they also thanked NG-CDF for good works they are doing.

- D.E.O

The representative from the office of the D.E.O, thanked CDF for the efforts in promoting Education in Nandi hills constituency; he said that CDF has really done a lot in terms of infrastructure and bursary to ensure that the children of Nandi hills enjoy learning in their various institutions. He further urged the team to continue with the same spirit and called upon parents to be in full support by ensuring children are in school at the right time.

2.1.05 Comments from the FAM

The FAM informed the meeting that NG-NG-CDF is in full support of development in the community. She explained the nature of projects that are liable for funding by CDF which included infrastructure, buildings, and non-consumable equipment’s. She called upon principals, head teachers and all other stake holders to remain cooperative so that we can achieve the targets of the government.

2.1.06 Comments by Chairman on bursary and environment

The chairman CDFC informed the meeting that in support of Education, NG-CDF allocates up to 25% of the total allocation towards bursary to support the needy and clever children in the constituency, and urged the parents, guardians to get the forms at chief’s offices and the CDF office which are given free without discrimination. He also reminded the parents and guardians to attach all the documents required to avoid cheque replacements which has become a big issue in the office because of wrong names, admission numbers, wrong institution etc.

He said that all orphans and needy cases are getting almost full sponsorship or 80 -90% sponsorship and therefore encourage all the orphans not give up in pursuing their education but instead approach the Chiefs office or NG-CDF office for assistance.

The chairman CDFC also informed the institutions that trees were planted from environmental kitty to nature them well and those that had not received they will receive them in this financial year, he added by saying that the waste tanks will be distributed in all the institutions especially those with boarding sections and river bank protection will also be done. He finished by thanking all the stakeholders who joined up the NG-CDF office during environmental days to the make the sites the way they are.

LESSOSS WARD

2.1.07 projects priorities identified in the ward

The ACC Mr.Kitayi on behalf of the sub county commissioner recommended the NG-CDF office for the good work of ensuring development in the constituency. He assured members of the security within the localities and called upon NG-CDF to support security matters within the constituency. He thanked NG-CDF for the efforts to purchase land for Himaki police Station and requested for more funding to help them construct an offices.

- CHIEF

The area chief welcomed all members at the meeting and thanked NG- CDF for choosing his Location for the venue. He informed the public that NG-CDF promised to construct an office for him and requested for more funding to enable him furnish office and dropping of power.

The area chief then introduced other chiefs and assistant chiefs who echoed that the NG-CDF has recognized them fully on bursary vetting and requested that the students who school at local should also be considered but not only those in National schools since some in national schools totally lack schools to enable them enroll in school as they wait funding from CDF.

- D.E.O

The representative from the office of the D.E.O, thanked NG-CDF for the efforts in promoting Education in Nandi hills constituency; he said that CDF has really done a lot in terms of infrastructure and bursary to ensure that the children of Nandi hills enjoy learning in their various institutions. He further urged the team continue with the same spirit and called upon parents to be in full support by ensuring children are in school at the right time.

2.1.05 Comments from the FAM

The FAM informed the meeting that NG-CDF is in full support of development in the community. She explained the nature of projects that are liable for funding by NG-CDF which included infrastructure, buildings, and non-consumable equipment’s. She called upon principals, head teachers and all other stake holders to remain cooperative so that we can achieve the targets of the government.

| LOCATION |  | EDUCATION FACILITY |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  | STATUS |  | QNT |  |  | KSHS |  | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Koilot |  | Land |  |  |  |  |  | Koilot Day Secondary School |  |  |  |  |  | Land purchase |  | Ongoing |  | 2 acres |  |  | 2Million |  | Requested |
|  |  | Library |  |  |  |  |  | Koilot Day Secondary School |  |  |  |  |  | Library completion |  | Ongoing |  |  |  |  |  |  |  |
|  |  | Dinning Hall |  |  |  |  |  | Koilot Day Secondary School |  |  |  |  |  | Dinning construction |  | New |  |  |  |  |  |  |  |
|  |  | Admin Block |  |  |  |  |  | Koilot Day Secondary School |  |  |  |  |  | Amin Block |  | New |  |  |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Koilot Primary School |  |  |  |  |  | 4 class rooms |  | New |  | n/a |  |  |  |  | Old buldings |
|  |  | Admin Block |  |  |  |  |  | Ndururo Primary |  |  |  |  |  | Admin block |  | New |  | n/a |  |  |  |  |  |
| Koilot |  | Class rooms |  |  |  |  |  | Cheplelachbei Sec School |  |  |  |  |  | 2 class rooms |  | Ongoing |  | n/a |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Cheplelachbei Sec School |  |  |  |  |  | 2 class rooms |  | New |  | n/a |  |  |  |  |  |
|  |  | Laboratory |  |  |  |  |  | Cheplelachbei Sec School |  |  |  |  |  | Lab completion |  | Ongoing |  | n/a |  |  |  |  |  |
|  |  | Toilets |  |  |  |  |  | Cheplelachbei Sec School |  |  |  |  |  | Toilets |  | New |  | n/a |  |  |  |  |  |
|  |  | Admin Block |  |  |  |  |  | Cheptuingeny Primary School |  |  |  |  |  | Admin block |  | New |  | n/a |  |  |  |  |  |
| Koilot |  | Land |  |  |  |  |  | Chepngetuny Primary School |  |  |  |  |  | Day Sec School |  | Ongoing |  | 1.5 acres |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Chepngetuny Primary School |  |  |  |  |  | 5 class rooms |  | Ongoing |  | n/a |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Chepngetuny Primary School |  |  |  |  |  | 3 class rooms |  | Renovation |  | n/a |  |  |  |  |  |
| Koilot |  | Class rooms |  |  |  |  |  | Ogirgir Primary School |  |  |  |  |  | 5 class rooms |  | Ongoing |  | n/a |  |  |  |  |  |
|  |  | ECD Centre |  |  |  |  |  | Lengut village |  |  |  |  |  | 2 ECD centre |  | New |  | n/a |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Lengut village |  |  |  |  |  | Classes construction |  | New |  | n/a |  |  |  |  |  |
| Koilot |  | Class rooms |  |  |  |  |  | Keben Primary School |  |  |  |  |  | 3 class rooms |  | New |  | n/a |  |  |  |  |  |
|  |  | Secondary school |  |  |  |  |  | Keben Primary School |  |  |  |  |  | Day Sec Sch |  | New |  | n/a |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Lessoss Hills Primary sch |  |  |  |  |  | 3 class rooms ceiling |  | Ongoing |  | n/a |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Lolgireng Primary sch |  |  |  |  |  | Classes construction |  | Ongoing |  | n/a |  |  |  |  |  |
|  |  | Land |  |  |  |  |  | Kapchumba Primary sch |  |  |  |  |  | Land purchase |  | New |  | 2 acres |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Kapchumba Primary sch |  |  |  |  |  | Classes construction |  | New |  |  |  |  |  |  |  |
|  |  | Secondary school |  |  |  |  |  | Kapchumba Primary sch |  |  |  |  |  | Day Sec Sch |  | New |  |  |  |  |  |  |  |
| LOCATION |  | SECURITY FACILITY |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  | STATUS |  | QNT |  |  | KSHS |  | REMARKS |
| Koilot |  | Chiefs Office |  |  |  |  |  | Koilot next to Dos office |  |  |  |  |  | Chiefs office |  | New |  |  |  |  |  |  |  |
|  |  | Electricity |  |  |  |  |  | DO's Office |  |  |  |  |  | Electricity connection |  | New |  |  |  |  |  |  |  |
|  |  | Housing |  |  |  |  |  | DO's AP officers |  |  |  |  |  | AP line construction |  | New |  |  |  |  |  |  |  |
|  |  | Housing |  |  |  |  |  | DO's House |  |  |  |  |  | DO House renovation |  | New |  |  |  |  |  |  |  |
| LOCATION |  | EDUCATION FACILITY |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  | STATUS |  | QNT |  |  | KSHS |  | REMARKS |
| Ollessos |  | Class rooms |  |  |  |  |  | Cheptingting Pri Sch |  |  |  |  |  | 2 class rooms |  | Ongoing |  |  |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Ollessos Primary Sch |  |  |  |  |  | 2 class rooms |  | Ongoing |  |  |  |  |  |  |  |
|  |  | Laboratory |  |  |  |  |  | Ollessos Day Sec Sch |  |  |  |  |  | Laboratory |  | Ongoing |  |  |  |  |  |  |  |
| Ollessos |  | Class rooms |  |  |  |  |  | Kapkorio Primary Sch |  |  |  |  |  | Classes contruction |  | New |  |  |  |  |  |  |  |
|  |  | Administration Block |  |  |  |  |  | Cheptingting Pri Sch |  |  |  |  |  | Admin construction |  | New |  |  |  |  |  |  |  |
| LOCATION |  | SECURITY FACILITY |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  | STATUS |  | QNT |  |  | KSHS |  | REMARKS |
| Ollessos |  | Social Hall |  |  |  |  |  | Mogoon Social Hall |  |  |  |  |  | Renovation |  | Ongoing |  |  |  |  |  |  |  |
|  |  | Office |  |  |  |  |  | Mogoon Location |  |  |  |  |  | Chiefs office |  | New |  |  |  |  |  |  |  |
|  |  | Housing |  |  |  |  |  | Chiefs AP officers |  |  |  |  |  | AP line |  | New |  |  |  |  |  |  |  |
| LOCATION |  | EDUCATION FACILITY |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  | STATUS |  | QNT |  |  | KSHS |  | REMARKS |
| Sochoi |  | Class rooms |  |  |  |  |  | Koimur Pri School |  |  |  |  |  | 2 class rooms |  | Ongoing |  |  |  |  | 2Million |  |  |
|  |  | Class rooms |  |  |  |  |  | Sochoi Pri School |  |  |  |  |  | 2 class rooms |  | Ongoing |  |  |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Kapnyimis Pri School |  |  |  |  |  | 2 class rooms |  | Ongoing |  |  |  |  | 0.8Millin |  |  |
|  |  | Class rooms |  |  |  |  |  | Lolduga Pri School |  |  |  |  |  | 2 class rooms |  | Ongoing |  |  |  |  | 1Million |  |  |
|  |  | Dinning Hall |  |  |  |  |  | Sochoi Boys Sec School |  |  |  |  |  | Dinning Hall Completion |  | Ongoing |  |  |  |  | 3Million |  |  |
|  |  | Laboratory |  |  |  |  |  | Sochoi Girls Secondary |  |  |  |  |  | Lab construction |  | New |  |  |  |  | 3Million |  |  |
|  |  | Fields |  |  |  |  |  | Sochoi Pri School |  |  |  |  |  | Field leveling |  | New |  |  |  |  |  |  |  |
|  |  | Land |  |  |  |  |  | Koimur Pri School |  |  |  |  |  | Land purchase |  | New |  | 2 acres |  |  |  |  |  |
|  |  | Class rooms |  |  |  |  |  | Sochoi Day Sec School |  |  |  |  |  | Classes construction |  | New |  |  |  |  |  |  |  |
| LOCATION |  | SECURITY FACILITY |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  | STATUS |  | QNT |  |  | KSHS |  | REMARKS |
| Sochoi |  | Chiefs Office |  |  |  |  |  | Sochoi Location |  |  |  |  |  | Office construction |  | New |  |  |  |  | 1Million |  |  |

| NG-CDF NANDI HILLS CONSTITUENCY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Tartar |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ndubusat Pri School |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 4 class rooms |  |  |
|  |  |  |  |  |  | Staff Quarters |  |  |  |  |  |  |  |  |  | Ndubusat Pri School |  |  |  |  |  | Houses for teachers |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | School Gate |  |  |  |  |  |  |  |  |  | Ndubusat Pri School |  |  |  |  |  | School Gate |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Signpost |  |  |  |  |  |  |  |  |  | Ndubusat Pri School |  |  |  |  |  | School signpost |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Hall |  |  |  |  |  |  |  |  |  | Ndubusat Pri School |  |  |  |  |  | Social Hall |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | St Elizabeth Sec School |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 4 class rooms |  |  |
|  |  |  |  |  |  | Staff Quarters |  |  |  |  |  |  |  |  |  | St Elizabeth Sec School |  |  |  |  |  | Houses completion |  |  |  |  | Ongoing |  | 2 staff houses |  |  |
|  |  |  |  |  |  | Dinning Hall |  |  |  |  |  |  |  |  |  | St Elizabeth Sec School |  |  |  |  |  | Dinning hall completion |  |  |  |  | Ongoing |  | 1 dinning hall |  |  |
|  |  |  |  |  |  | Transfomer |  |  |  |  |  |  |  |  |  | Kapkorio Village |  |  |  |  |  | Instaal Transformer |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Land |  |  |  |  |  |  |  |  |  | Tartar sublocation |  |  |  |  |  | Land purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Tartar sublocation |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Hall |  |  |  |  |  |  |  |  |  | Tartar sublocation |  |  |  |  |  | Social Hall |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Bridge |  |  |  |  |  |  |  |  |  | Chekunyuk Tartar |  |  |  |  |  | Bridge |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Transfomer |  |  |  |  |  |  |  |  |  | Simatwet Tartar |  |  |  |  |  | Instaal Transformer |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Electricity |  |  |  |  |  |  |  |  |  | Kababii |  |  |  |  |  | electricity extension |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | SECURITY FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Tartar |  |  |  |  |  | Chiefs Office |  |  |  |  |  |  |  |  |  | Tartar Location |  |  |  |  |  | Office construction |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Siret |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Chebinyiny |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 3 class rooms |  |  |
|  |  |  |  |  |  | Staff quarters |  |  |  |  |  |  |  |  |  | Chebinyiny |  |  |  |  |  | Houses for teachers |  |  |  |  | New |  | 4 staff houses |  |  |
|  |  |  |  |  |  | Field |  |  |  |  |  |  |  |  |  | Chebinyiny |  |  |  |  |  | Playing ground |  |  |  |  | New |  | Levelland scaping |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Cheptabach |  |  |  |  |  | Classes renovation |  |  |  |  | Ongoing |  | 4 class rooms |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Cheptabach |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Staff quarters |  |  |  |  |  |  |  |  |  | Cheptabach |  |  |  |  |  | Houses for teachers |  |  |  |  | New |  | 2 stff houses |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Cheptabach Sec School |  |  |  |  |  | Classes completion |  |  |  |  | Ongoing |  | 3 class rooms |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Cheptabach Sec School |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Staff quarters |  |  |  |  |  |  |  |  |  | Cheptabach Sec School |  |  |  |  |  | Houses for teachers |  |  |  |  | New |  | 2 stff houses |  |  |
|  |  |  |  |  |  | Admin block |  |  |  |  |  |  |  |  |  | Cheptabach Sec School |  |  |  |  |  | Administration block |  |  |  |  | New |  | 1 admin block |  |  |
|  |  |  |  |  |  | Bus 55 Seater |  |  |  |  |  |  |  |  |  | Cheptabach Sec School |  |  |  |  |  | School Bus purchase |  |  |  |  | New |  | 1 shool bus |  |  |
| LOCATION |  |  |  |  |  | SECURITY FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Siret |  |  |  |  |  | Chiefs Office |  |  |  |  |  |  |  |  |  | Siret Location |  |  |  |  |  | Office construction |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Taito |  |  |  |  |  | Admin block |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | Administration block |  |  |  |  | New |  | 1 admin block |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | Classes construction |  |  |  |  | Ongoing |  |  |  |  |
|  |  |  |  |  |  | Laboratory |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | Laboratory construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Bus |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | School Bus Purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Field |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | Leveling of the field |  |  |  |  | Ongoing |  |  |  |  |
|  |  |  |  |  |  | Land |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | Land purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Dinning Hall |  |  |  |  |  |  |  |  |  | Taboyat Mixed Day Sec |  |  |  |  |  | Dinning Hall & kitchen |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Domitory |  |  |  |  |  |  |  |  |  | Taito Secondary School |  |  |  |  |  | Construction of a dom |  |  |  |  | New |  | 140 STUDENTS |  |  |
|  |  |  |  |  |  | Claasses |  |  |  |  |  |  |  |  |  | Taito Secondary School |  |  |  |  |  | Construction of classes |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Ablution/Toilets |  |  |  |  |  |  |  |  |  | Taito Secondary School |  |  |  |  |  | Ablution construction |  |  |  |  | New |  | 2 bloc of ablut |  |  |
|  |  |  |  |  |  | Dinning Hall |  |  |  |  |  |  |  |  |  | Taito Secondary School |  |  |  |  |  | Dinning Hall construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Laboratory |  |  |  |  |  |  |  |  |  | Taito Secondary School |  |  |  |  |  | Laboratory Construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | School Van |  |  |  |  |  |  |  |  |  | Taito Secondary School |  |  |  |  |  | School Van purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Admin Block |  |  |  |  |  |  |  |  |  | Kapkoimur Primary School |  |  |  |  |  | Adminstration block |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class room |  |  |  |  |  |  |  |  |  | Kapkoimur Primary School |  |  |  |  |  | Class construction |  |  |  |  | New |  | 1 class room |  |  |
|  |  |  |  |  |  | Ablution block |  |  |  |  |  |  |  |  |  | Kapkoimur Primary School |  |  |  |  |  | ablution construction |  |  |  |  | New |  | 2 Ablution blocks |  |  |
|  |  |  |  |  |  | Field |  |  |  |  |  |  |  |  |  | Kapkoimur Primary School |  |  |  |  |  | Leveling the field |  |  |  |  | Ongoing |  |  |  |  |
|  |  |  |  |  |  | Staff quarters |  |  |  |  |  |  |  |  |  | Kapkoimur Primary School |  |  |  |  |  | Houses for teachers |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Taboyat Primary School |  |  |  |  |  | Cealing of class rooms |  |  |  |  | Ongoing |  | 12 class rooms |  |  |
|  |  |  |  |  |  | Latrines |  |  |  |  |  |  |  |  |  | Taboyat Primary School |  |  |  |  |  | Toilets Construction |  |  |  |  | New |  | 2 latrines |  |  |
|  |  |  |  |  |  | Staff quarters |  |  |  |  |  |  |  |  |  | Taboyat Primary School |  |  |  |  |  | Houses for teachers |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | SECURITY FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Taito |  |  |  |  |  | Chiefs Office |  |  |  |  |  |  |  |  |  | Taito chiefs office |  |  |  |  |  | Chiefs office |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Housing |  |  |  |  |  |  |  |  |  | Chiefs AP officers |  |  |  |  |  | AP line construction |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Chebarus |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Kaptuma Primary School |  |  |  |  |  | Claas rooms |  |  |  |  | Ongoing |  | 2 Class rooms |  | 1.6Million |
|  |  |  |  |  |  | Bridge |  |  |  |  |  |  |  |  |  | Kaptuma Village |  |  |  |  |  | Bridge |  |  |  |  | New |  |  |  |  |
| Siwo |  |  |  |  |  | Secondary School |  |  |  |  |  |  |  |  |  | Choimim |  |  |  |  |  | Girls' Secondary School |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Land Purchase |  |  |  |  |  |  |  |  |  | Choimim |  |  |  |  |  | Girls' Secondary School |  |  |  |  | Ongoing |  | 2 acres bt 8 bal |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Choimim Primary School |  |  |  |  |  | Class rooms completion |  |  |  |  | Ongoing |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Choimim Primary School |  |  |  |  |  | Renovation |  |  |  |  | Ongoing |  | 10 class rooms |  |  |
|  |  |  |  |  |  | Drainages |  |  |  |  |  |  |  |  |  | Choimim Primary School |  |  |  |  |  | Drainages |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Nukiat Primary School |  |  |  |  |  | Constr of class rooms |  |  |  |  | New |  | 5 class rooms |  |  |
|  |  |  |  |  |  | Latrines |  |  |  |  |  |  |  |  |  | Nukiat Primary School |  |  |  |  |  | Construction of latrines |  |  |  |  | New |  | 4 Latrines |  |  |
|  |  |  |  |  |  | Admin Block |  |  |  |  |  |  |  |  |  | Nukiat Primary School |  |  |  |  |  | Admin Construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Chebilat Primary School |  |  |  |  |  | Constr of class rooms |  |  |  |  | New |  | 6 class rooms |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Chebilat Primary School |  |  |  |  |  | Constr of class rooms |  |  |  |  | Ongoing |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Admin block |  |  |  |  |  |  |  |  |  | Chebilat Primary School |  |  |  |  |  | Admin Construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Land |  |  |  |  |  |  |  |  |  | Chebilat Primary School |  |  |  |  |  | Expansion of the School |  |  |  |  | Ongoing |  | 2 acres |  |  |
|  |  |  |  |  |  | Latrines |  |  |  |  |  |  |  |  |  | Chebilat Primary School |  |  |  |  |  | Latrines construction |  |  |  |  | New |  | 8 latrines |  |  |
|  |  |  |  |  |  | Dinning Hall |  |  |  |  |  |  |  |  |  | Siwo Secondary Shool |  |  |  |  |  | D/ Hall construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Admin Block |  |  |  |  |  |  |  |  |  | Siwo Secondary Shool |  |  |  |  |  | Admin Construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Latrines |  |  |  |  |  |  |  |  |  | Siwo Secondary Shool |  |  |  |  |  | Latrines construction |  |  |  |  | New |  | 4 Latrines |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Siwo Secondary Shool |  |  |  |  |  | Classes construction |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Classes & offices |  |  |  |  |  |  |  |  |  | Siwo Secondary Shool |  |  |  |  |  | Renovation |  |  |  |  | Ongoing |  | all class rooms |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Siwo Primary School |  |  |  |  |  | Classes renovations |  |  |  |  | Ongoing |  | All class rooms |  | Condemned |
|  |  |  |  |  |  | Latrines |  |  |  |  |  |  |  |  |  | Siwo Primary School |  |  |  |  |  | construction of latrines |  |  |  |  | New |  | Modern latrines |  |  |
|  |  |  |  |  |  | Admin Block |  |  |  |  |  |  |  |  |  | Siwo Primary School |  |  |  |  |  | Admin Construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Primary School |  |  |  |  |  |  |  |  |  | Chemagar Village |  |  |  |  |  | Land Purchase |  |  |  |  | New |  | 5 acres |  |  |
|  |  |  |  |  |  | Land Purchase |  |  |  |  |  |  |  |  |  | Chemagar Village |  |  |  |  |  | Social Hall |  |  |  |  | New |  |  |  |  |
| Chepkunyuk |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Nduroto Primary School |  |  |  |  |  | classes construction |  |  |  |  | Ongoing |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Latrines |  |  |  |  |  |  |  |  |  | Nduroto Primary School |  |  |  |  |  | Latrine construction |  |  |  |  | New |  | Modern |  |  |
|  |  |  |  |  |  | Library |  |  |  |  |  |  |  |  |  | Nduroto Primary School |  |  |  |  |  | Renovation |  |  |  |  | Ongoing |  |  |  |  |
|  |  |  |  |  |  | Secondary School |  |  |  |  |  |  |  |  |  | Nduroto Primary School |  |  |  |  |  | Secondary School |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Resource centre |  |  |  |  |  |  |  |  |  | Kipsergech sub location |  |  |  |  |  | Resource centre constr. |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Chepkunyuk Pri School |  |  |  |  |  | Class Rooms renovation |  |  |  |  | Ongoing |  | 8 class rooms |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Chepkunyuk Pri School |  |  |  |  |  | class construction |  |  |  |  | New |  | 3 class rooms |  |  |
|  |  |  |  |  |  | Toilets |  |  |  |  |  |  |  |  |  | Chepkunyuk Pri School |  |  |  |  |  | Toilets construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Bursaries |  |  |  |  |  |  |  |  |  | Chepkunyuk Location |  |  |  |  |  | Award priority |  |  |  |  | New |  | Orp,pwds Single |  |  |
| LOCATION |  |  |  |  |  | SECURITY FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
|  |  |  |  |  |  | Asst Chief office |  |  |  |  |  |  |  |  |  | Kipsegech |  |  |  |  |  | Asst Chiefs office |  |  |  |  | New |  |  |  |  |
| Chepkunyuk |  |  |  |  |  | Police station |  |  |  |  |  |  |  |  |  | Himaki |  |  |  |  |  | Police station |  |  |  |  | Ongoing |  |  |  |  |
|  |  |  |  |  |  | Office |  |  |  |  |  |  |  |  |  | Chepkunyuk location |  |  |  |  |  | Chiefs office |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
|  |  |  |  |  |  | Land |  |  |  |  |  |  |  |  |  | Kapchuria Sub location |  |  |  |  |  | Secondary School |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Kapchuria Pri School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Kapchuria Pri School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Drainages |  |  |  |  |  |  |  |  |  | Kapchuria Pri School |  |  |  |  |  | Drainages |  |  |  |  | New |  | 2 drainage lines |  |  |
|  |  |  |  |  |  | Drainages |  |  |  |  |  |  |  |  |  | Kapchuria Pri School |  |  |  |  |  | Drainages |  |  |  |  | New |  | 12 drainage lines |  |  |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Lelwak |  |  |  |  |  | Dinning Hall/kitchen |  |  |  |  |  |  |  |  |  | Lelwak Boys Secondary |  |  |  |  |  | Dinning Hall & kitchen |  |  |  |  | New |  |  |  | 8.8Million |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Tikityo Sec School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 Class rooms |  | 2Million |
|  |  |  |  |  |  | Toilets |  |  |  |  |  |  |  |  |  | Lelwak Primary School |  |  |  |  |  | Completion of Toilets |  |  |  |  | Ongoing |  |  |  | 0.6Million |
|  |  |  |  |  |  | Field |  |  |  |  |  |  |  |  |  | Lelwak Primary School |  |  |  |  |  | Leveling of the field |  |  |  |  | New |  |  |  | 0.8Million |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Tikityo Secondary School |  |  |  |  |  | Renovation |  |  |  |  | Ongoing |  |  |  | 1Million |
|  |  |  |  |  |  | Toilets |  |  |  |  |  |  |  |  |  | Tikityo Secondary School |  |  |  |  |  | Construction of Toilets |  |  |  |  | New |  |  |  | 0.8Million |
|  |  |  |  |  |  | Land |  |  |  |  |  |  |  |  |  | Simbi Primary |  |  |  |  |  | Constr of class rooms |  |  |  |  | New |  | 0.9 acres |  | 0.96Million |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Simbi Primary |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 Class rooms |  | 2Million |
| Kibabet |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Lengubei Primary School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Desks |  |  |  |  |  |  |  |  |  | Lengubei Primary School |  |  |  |  |  | Desks purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Toilets |  |  |  |  |  |  |  |  |  | Lengubei Primary School |  |  |  |  |  | Toilet construction |  |  |  |  | New |  | Modern toilets |  |  |
|  |  |  |  |  |  | Field |  |  |  |  |  |  |  |  |  | Lengubei Primary School |  |  |  |  |  | Field leveling |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Toilets |  |  |  |  |  |  |  |  |  | Kipkorom Primary |  |  |  |  |  | Toilet construction |  |  |  |  | New |  | Modern toilets |  |  |
|  |  |  |  |  |  | ICT Lab |  |  |  |  |  |  |  |  |  | Kipkorom Primary |  |  |  |  |  | Construction of ICT |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Desks |  |  |  |  |  |  |  |  |  | Kipkorom Primary |  |  |  |  |  | Desks purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Water |  |  |  |  |  |  |  |  |  | Kipkorom Primary |  |  |  |  |  | provide water |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Academy |  |  |  |  |  |  |  |  |  | SDA academy |  |  |  |  |  | School |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Kipkorom Sec School |  |  |  |  |  | Construction of classes |  |  |  |  | New |  | 4 class rooms |  |  |
|  |  |  |  |  |  | Laboratory |  |  |  |  |  |  |  |  |  | Kipkorom Sec School |  |  |  |  |  | Lab construction |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Water |  |  |  |  |  |  |  |  |  | Kipkorom Sec School |  |  |  |  |  | provide water |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Admin Block |  |  |  |  |  |  |  |  |  | Kipkorom Sec School |  |  |  |  |  | Admin block constr. |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Dining Hall |  |  |  |  |  |  |  |  |  | Kipkorom Sec School |  |  |  |  |  | Dining hall constr. |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | ICT Lab/Library |  |  |  |  |  |  |  |  |  | Kipkorom Sec School |  |  |  |  |  | ICT & Library constr |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | SECURITY FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Kibabet |  |  |  |  |  | Office |  |  |  |  |  |  |  |  |  | Kibabet Location |  |  |  |  |  | Chiefs Office |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Public Hall |  |  |  |  |  |  |  |  |  | Kibabet Location |  |  |  |  |  | Social Hall |  |  |  |  | New |  |  |  |  |
| LOCATION |  |  |  |  |  | EDUCATION FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Mogobich |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Kaputi Primary School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Ngame Primary School |  |  |  |  |  | Class rooms |  |  |  |  | Ongoing |  | 1 class room |  |  |
|  |  |  |  |  |  | Land |  |  |  |  |  |  |  |  |  | Ngame Primary School |  |  |  |  |  | Land purchase |  |  |  |  | New |  |  |  |  |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Sile Primary School |  |  |  |  |  | Class rooms |  |  |  |  | Ongoing |  | 1 class room |  |  |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Sile Primary School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 1 class room |  |  |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Kaputi mixed Sec School |  |  |  |  |  | Class rooms |  |  |  |  | Ongoing |  | 1 class room |  |  |
|  |  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Kaputi mixed Sec School |  |  |  |  |  | Class rooms |  |  |  |  | New |  | 2 class rooms |  |  |
|  |  |  |  |  |  | Laboratory |  |  |  |  |  |  |  |  |  | Kaputi mixed Sec School |  |  |  |  |  | Lab construction |  |  |  |  | New |  |  |  |  |
| Mogobich |  |  |  |  |  | Bursaries |  |  |  |  |  |  |  |  |  | Mogobich Location |  |  |  |  |  | Award from village level |  |  |  |  | New |  | 8 sec, 4 c, 4u |  |  |
| LOCATION |  |  |  |  |  | SECURITY FACILITY |  |  |  |  |  |  |  |  |  | SITE |  |  |  |  |  | ITEM PROPOSED |  |  |  |  | STATUS |  | QNT |  | KSHS |
| Mogobich |  |  |  |  |  | Office |  |  |  |  |  |  |  |  |  | Mogobich Location |  |  |  |  |  | Chiefs Office |  |  |  |  | New |  | Land available |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Kosoiywo |  |  |  |  | Laboratory construction |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | New |  |  |  | 2 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms Renovation |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  | 8 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms construction |  |  |  |  |  |  |  |  |  | New |  |  |  | 2 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Kosoiywo |  |  |  |  | Asst Chiefs office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Multipurpose Hall |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity provision |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Cheptililik |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | School Bus |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Lab construction |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity provision |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Cheptililik |  |  |  |  | Chiefs office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Chemomi |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | new |  |  |  | 2 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Laboratory |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Toilets construction |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Dining hall & Kitchen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | new |  |  |  | 2 acres |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | School Bus |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity provision |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Reliable water supply |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity provision |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | classes renovation |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Staff room constr |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Staff room constr |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity provision |  |  |  |  |  |  |  |  |  | new |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Nandi Hills |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Library |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | staff room |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Septic Tank |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Classes double alloc |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Septic Tank |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Leveling of the field |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  | 2 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Lab construction |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Toilets construction |  |  |  |  |  |  |  |  |  | New |  |  |  | 4 Toilets |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | New |  |  |  | 2 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Toilets construction |  |  |  |  |  |  |  |  |  | New |  |  |  | 4 Toilets |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land Purchase |  |  |  |  |  |  |  |  |  | New |  |  |  | Extension |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Bursary provision |  |  |  |  |  |  |  |  |  | New |  |  |  | Needy students |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Nandi Hills |  |  |  |  | Asst Chiefs office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Asst Chiefs office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity Provision |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Chebarus |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | New |  |  |  | 2 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Electricity |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Chebarus |  |  |  |  | Chiefs Office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Kaplelmet |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Modern Toilets |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Leveling of the field |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Bursary provision |  |  |  |  |  |  |  |  |  | New |  |  |  | Consider PWDs |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | School Bus |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class Rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class Rooms compl |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Admin block constr |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | New |  |  |  | 3 acres |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Leveling of the field |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Modern Toilets |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  | 3 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Admin block construction |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | New |  |  |  | 2 acres |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Leveling of the field |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Kaplelmet |  |  |  |  | Chiefs office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Kipsebwo |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | New |  |  |  | 1 Class room |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Class rooms |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  | 5 class rooms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Domitory construction |  |  |  |  |  |  |  |  |  | New |  |  |  | 2 Doms |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Land purchase |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | 30, 20, 20, thousands |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  |  |  | ITEM PROPOSED |  |  |  |  |  |  |  |  |  | STATUS |  |  |  | QNT |  |  |  |  | KSHS |  |  |  |  |  |  |  |
| Kipsebwo |  |  |  |  | Chiefs office |  |  |  |  |  |  |  |  |  | New |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| LOCATION |  |  | EDUCATION FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QNT |  |  | KSHS |  | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Class rooms |  |  | Sirwo Primari School |  |  |  |  | Class rooms |  |  |  | Ongoing |  |  | 5 class rooms |  |  |  |  |  |
|  |  |  | Staff Quarters |  |  | Sirwo Secondary School |  |  |  |  | Staff Houses |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Ablution Block |  |  | Sirwo Secondary School |  |  |  |  | Ablution block |  |  |  | New |  |  | 4 Blocks |  |  |  |  |  |
|  |  |  | Laboratory |  |  | Sirwo Secondary School |  |  |  |  | Lab Completion |  |  |  | Ongoing |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Timobo Primary School |  |  |  |  | Class rooms |  |  |  | New |  |  | class room |  |  |  |  |  |
|  |  |  | Staff Quarters |  |  | Timobo Primary School |  |  |  |  | Staff Houses |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Ablution Block |  |  | Timobo Primary School |  |  |  |  | Ablution block |  |  |  | New |  |  | 6 Blocks |  |  |  |  |  |
|  |  |  | ICT Centre |  |  | Timobo Primary School |  |  |  |  | ICT Centre |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Fence |  |  | Timobo Primary School |  |  |  |  | School fence |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATION |  |  | SECURITY FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QUANTITY |  |  | KSHS |  | REMARKS |
| Kapchorwa |  |  | Office |  |  | Chiefs Camp |  |  |  |  | Chiefs Office |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Latrine |  |  | Chiefs Camp |  |  |  |  | Latrine |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Housing |  |  | Chiefs Camp |  |  |  |  | AP Line |  |  |  | New |  |  |  |  |  |  |  |  |
| LOCATION |  |  | EDUCATION FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QUANTITY |  |  | KSHS |  | REMARKS |
| Kapchorwa |  |  | Class rooms |  |  | Serengonik Primary School |  |  |  |  | Class rooms |  |  |  | New |  |  | 6 class rooms |  |  |  |  |  |
|  |  |  | Latrines |  |  | Serengonik Primary School |  |  |  |  | Lab completion |  |  |  | New |  |  | 8 latrines |  |  |  |  |  |
|  |  |  | Admin Block |  |  | Serengonik Primary School |  |  |  |  | Staff room |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Mogobich Day Sec Sch |  |  |  |  | Class rooms |  |  |  | New |  |  | 2 Class rooms |  |  |  |  |  |
|  |  |  | Laboratory |  |  | Mogobich Day Sec Sch |  |  |  |  | Lab completion |  |  |  | Ongoing |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Mogobich Primary School |  |  |  |  | Classes renovation |  |  |  | Ongoing |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kipkorom Primary School |  |  |  |  | Class rooms |  |  |  | Ongoing |  |  | 2 Class rooms |  |  |  |  |  |
|  |  |  | Staff quarters |  |  | Kipkorom Primary School |  |  |  |  | Staff Houses |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | School |  |  | Kipkorom |  |  |  |  | Secondary School |  |  |  | New |  |  | 2 Class rooms |  |  |  |  | Land available |
| LOCATION |  |  | EDUCATION FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QUANTITY |  |  | KSHS |  | REMARKS |
| Kapkoros |  |  | Multipurpose Hall |  |  | Kapkoros Sec School |  |  |  |  | Social Hall |  |  |  | New |  |  | Modern |  |  |  |  |  |
|  |  |  | Laboratory |  |  | Kapkoros Sec School |  |  |  |  | Lab Completion |  |  |  | Ongoing |  |  |  |  |  |  |  |  |
|  |  |  | Admin Block |  |  | Kapkoros Sec School |  |  |  |  | Admin Block |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Bus |  |  | Kapkoros Sec School |  |  |  |  | School Bus |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Land |  |  | Kapkoros Sec School |  |  |  |  | Land purchase |  |  |  | New |  |  | Expansion |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Tereno Girls Sec School |  |  |  |  | Classes renovation |  |  |  | Ongoing |  |  | All Classes |  |  |  |  |  |
|  |  |  | School |  |  | Lengon |  |  |  |  | Secondary School |  |  |  | New |  |  | 2 classes |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Samutet Primary School |  |  |  |  | class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kapsokio Sec School |  |  |  |  | class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kitechgaa Sec School |  |  |  |  | class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kitechgaa Primary Sch |  |  |  |  | class rooms |  |  |  | New |  |  | 4 class rooms |  |  |  |  |  |
| LOCATION |  |  | SECURITY FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QUANTITY |  |  | KSHS |  | REMARKS |
| Kapkoros |  |  | Offices |  |  | Chiefs and Dos camp |  |  |  |  | Chifs and Dos Office |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Electricity |  |  | Chiefs and Dos camp |  |  |  |  | Electricity provision |  |  |  | New |  |  |  |  |  |  |  |  |
| LOCATION |  |  | EDUCATION FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QUANTITY |  |  | KSHS |  | REMARKS |
| Ainapngetuny |  |  | ICT Centre |  |  | Ainapngetuny Sec Sch |  |  |  |  | ICT Centre |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Library |  |  | Ainapngetuny Sec Sch |  |  |  |  | Library |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Ainapngetuny Sec Sch |  |  |  |  | Class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kimugul Sec School |  |  |  |  | Class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | School |  |  | Cherobon |  |  |  |  | Secondary sch |  |  |  | New |  |  |  |  |  |  |  | Land needed |
|  |  |  | School |  |  | Kisiga |  |  |  |  | Secondary sch |  |  |  | New |  |  |  |  |  |  |  | Land needed |
|  |  |  | Class rooms |  |  | Ainapngetuny Pri Sch |  |  |  |  | Class rooms |  |  |  | New |  |  | 7 class rooms |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Cherobon Pri School |  |  |  |  | Class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Great Highlands Prep |  |  |  |  | Class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Land |  |  | Great Highlands Prep |  |  |  |  | land purchase |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Land |  |  | Chemalal Pri School |  |  |  |  | land purchase |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kimugul Pri School |  |  |  |  | Class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Class rooms |  |  | Kisoga Pri School |  |  |  |  | Class rooms |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | School |  |  | Chepkoper |  |  |  |  | Primary School |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | School |  |  | Hill Star |  |  |  |  | Primary School |  |  |  | New |  |  |  |  |  |  |  |  |
| LOCATION |  |  | SECURITY FACILITY |  |  | SITE |  |  |  |  | ITEM PROPOSED |  |  |  | STATUS |  |  | QUANTITY |  |  | KSHS |  | REMARKS |
| Ainapngetuny |  |  | Office |  |  | Ainapngetuny |  |  |  |  | Chiefs office |  |  |  | New |  |  |  |  |  |  |  |  |
|  |  |  | Office |  |  | Toroton new Location |  |  |  |  | Chiefs office |  |  |  | New |  |  |  |  |  |  |  |  |

Nandi hills National Government Constituency Development Fund

Project Proposal 2017/2018 Financial Year

Code list

| CODE LIST |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Name | Project Number | Original Cost | Activity | Amount | Status |
| Employees’ Salaries | 4-029-153-2110000-100-2017/18-001 | 2,000,000 | Payment of staff salaries and gratuity | 2,000,000 | Ongoing |
| Goods and Services | 4-029-153-2210000-100-2017/18-002 | 1,085,420.69 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, etc. | 1,085,420.69 | Ongoing |
| Office Laptops | 4-029-153-2210000-100-2017/18-002 | 400,000.00 | Purchase of office laptops for Manager, CDFC Chairman and secretary. | 400,000.00 | New |
| NSSF | 4-029-153-2120101-100-2017/18-003 | 50,000.00 | Payment of NSSF Deductions | 50,000.00 | Ongoing |
| NHIF | 4-029-153-2120201-100-2017/18-0z04 | 50,000.00 | Payment of NHIF Deductions | 50,000.00 | Ongoing |
| Committee Expenses | 4-029-153-2210802-100-2017/18-005 | 1,623,200.00 | Payment of Committee sitting allowances, transport, conferences | 1,623,200.00 | Ongoing |
| ` Goods and Services | 4-029-153-2210000-111-2017/18-001 | 404,154.30 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence, | 404,154.30 | Ongoing |
| office photo computers for | 4-029-153-2210000-111-2017/18-001 | 200,000.00 | Purchase of staplers paper punch and photocopier to replace the old ones that has broken down | 200,000.00 | New |
| Committee Expenses | 4-029-153-2210802-111-2017/18-002 | 780,000.00 | Payment of Committee sitting allowances, transport, conferences | 780,000.00 | Ongoing |
| CDFC/PMC Capacity Building | 4-029-153-2210700-111-2017/18-003 | 1,220,156.00 | Undertake Training of the PMCs/CDFCs/Staff on CDF Related issues | 1,220,156.00 | Ongoing |
| Constituency Strategic Plan | 4-029-153-2211310-108-2017/18-001 | 3,000,000.00 | To develop a five year strategic plan and website for the constituency | 3,000,000.00 | New |
| ICT HUB | 4-029-153-2211310-108-2017/18-002 | 4,677,027.20 | Establish Constituency innovation hub in partnership with Ministry of ICT through Telcom Kenya in Siwo Secondary, Koilot Day Secondary, Kimugul Primary School and Jean Marie Seronei Secondary School. | 4,677,027.20 | New |
| Emergency | 4-029-153-2640200-101-2017/18-001 | 4,568,965.52 | To cater for any unforeseen occurrences in the constituency during the financial year | 4,568,965.52 | Ongoing |
| Nandi hills constituency Environment | 4-029-153-2640509-110-2017/18-001 | 1,536,206.90 | Purchase and installation of water tanks distributions in Chesirikan Primary, Taboiyat Secondary, Timobo and Tereno Primary schools. | 1,536,206.90 | Ongoing |
| Nandi hills constituency sports | 4-029-153-2640509-112-2017/18-001 | 1,536,206.90 | Organizing constituency sports tournament where sports kits will be awarded to winning teams. | 1,536,206.90 | Ongoing |
| Bursary Secondary Schools | 4-029-153-2640101-103-2017/18-001 | 10,002,000.00 | Payment of bursary to needy student | 10,002,000.0 | Ongoing |
| Bursary Tertiary Schools | 4-029-153-2640101-103-2017/18-002 | 11,700,758.00 | Payment of bursary to needy student | 11,700,758.0 | Ongoing |
| Ainapngetuny Secondary | 4-029-153-2630205-104-2017/18-001 | 2,000,000 | Completion of two classrooms (storeyed) slab and plastering | 2,000,000 | ongoing |
| Chepngetuny Secondary | 4-029-153-2630205-104-2017/18-002 | 700,000 | Purchase of one acre of land | 700,000 | Ongoing |
| Choimim Secondary school | 4-029-153-2630205-104-2017/18-003 | 1,000,000 | Purchase of one acre of land | 1,000,000 | New |
| Jean Marie Secondary School | 4-029-153-2630205-104-2017/18-004 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | ongoing |
| Kapkoros Secondary Bus | 4-029-153-2630205-104-2017/18-005 | 7,000,000 | Purchase of 52 seater school bus | 7,000,000 | New |
| kaplelmet secondary (classroom) | 4-029-153-2630205-104-2017/18-006 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | Ongoing |
| Kaptien Secondary (Classrooms) | 4-029-153-2630205-104-2017/18-007 | 1,000,000 | Construction of one classrooms; from slab to completion | 1,000,000 | ongoing |
| Keben secondary (Classroom) | 4-029-153-2630205-104-2017/18-008 | 500,000 | purchase of one acre of land | 500,000 | Ongoing |
| Keteng Secondary (classroom) | 4-029-153-2630205-104-2017/18-009 | 500,000 | Construction of one classrooms, from slab to roofing | 500,000 | New |
| Kipkimba secondary school (Classroom) | 4-029-153-2630205-104-2017/18-010 | 500,000 | construction of one classrooms to walling | 500,000 | New |
| Kipkoror Secondary Classroom) | 4-029-153-2630205-104-2017/18-011 | 500,000 | construction of one classro | 500,000 | New |
|  |  |  | oms to completion |  |  |
| Kisebwo Secondary (Classrooms) | 4-029-153-2630205-104-2017/18-012 | 1,000,000 | completiontion of two classroom from slab to completion | 1,000,000 | New |
| Koilot Day (Classroom) | 4-029-153-2630205-104-2017/18-013 | 500,000 | construction of one classroom from slab to completion | 500,000 | Ongoing |
| Kosoiywo Secondary School (classroom) | 4-029-153-2630205-104-2017/18-014 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | ongoing |
| Lelwak Boys ICT Hall | 4-029-153-2630205-104-2017/18-015 | 1,000,000 | Copletion of ICT ceiling and painting Center | 1,000,000 | Ongoing |
| Sirwa Secondary School (Classroom) | 4-029-153-2630205-104-2017/18-016 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting to completion | 1,000,000 | ongoing |
| Soiyet Secondary School(Classroom) | 4-029-153-2630205-104-2017/18-017 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | Ongoing |
| Taboiyat Secondary school(Classroom) | 4-029-153-2630205-104-2017/18-017 | 700,000 | Construction of one classroom; from slab to walling | 700,000 | Ongoing |
| Tereno Girls land | 4-029-153-2630205-104-2017/18-017 | 500,000 | Completion of one classroom; from slab to walling | 500,000 | Ongoing |
| Tigityo Secondary Bus | 4-029-153-2630205-104-2017/18-017 | 7,000,000 | 52 Seater bus | 7,000,000 | New |
| Chebilat Primary (Classrooms) | 4-029-153-2630204-104-2017/18-001 | 1,000,000 | Construction of one classrooms; plastering, shutters and painting | 1,000,000 | New |
| Chebinyiny Primary (Classroom) | 4-029-153-2630204-104-2017/18-002 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | New |
| Cheptingting Primary (Classroom) | 4-029-153-2630204-104-2017/18-003 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Great Highlands | 4-029-153-2630204-104-2017/18-004 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | ongoing |
| Kabikwen Primary School (Classroom) | 4-029-153-2630204-104-2017/18-005 | 1,000,000 | construction of one classroom; from slab to completion | 1,000,000 | ongoing |
| Mogobich Primary (Classroom) | 4-029-153-2630204-104-2017/18-006 | 500,000 | Completion of two classroom; from slab to walling | 500,000 | ongoing |
| Kapchumba Primary school (land) | 4-029-153-2630204-104-2017/18-007 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapnyemis Primary (Classroom) | 4-029-153-2630204-104-2017/18-008 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kapsean Primary school (Classroom) | 4-029-153-2630204-104-2017/18-008 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Completion |
| Kaptuma Primary School(Classroom) | 4-029-153-2630204-104-2017/18-009 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Keben Primary (Classroom) | 4-029-153-2630204-104-2017/18-010 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Keteng Primary Classroom | 4-029-153-2630204-104-2017/18-011 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | Ongoing |
| Kimolonik Primary (Classroom) | 4-029-153-2630204-104-2017/18-012 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | ongoimg |
| Kipkorom Primary school (Classroom) | 4-029-153-2630204-104-2017/18-013 | 976,249 | Completion of two classroom; plaster and paint | 976,249 | new |
| kipsamoo Primary school(Classroom) | 4-029-153-2630204-104-2017/18-014 | 500,000 | construction of one to walling classroom | 500,000 | ongoing |
| Kitechgaa Primary (Classroom) | 4-029-153-2630204-104-2017/18-015 | 500,000 | construction of one classroom; from slab to completion | 500,000 | New |
| Koimur Primary | 4-029-153-2630204-104-2017/18-016 | 600,000 | Completion of two classroom to painting | 600,000 | Ongoing |
| Serengonik Primary (classrooms) | 4-029-153-2630204-104-2017/18-017 | 500,000 | Completion of two classroom; plaster and paint | 500,000 | New |
| Sile Primary (Classroom) | 4-029-153-2630204-104-2017/18-018 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | New |
| Simbi Primary(Land) | 4-029-153-2630204-104-2017/18-019 | 500,000 | Purchase of land 1 acre | 500,000 | New |
| Tereno Primary Classroom | 4-029-153-2630204-104-2017/18-019 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | New |
| Timobo Primary School (Classroom) | 4-029-153-2630204-104-2017/18-020 | 500,000 | Construction of one classroom; from slab to walling | 500,000 | new |
|  |  | 86,810,344.51 |  | 86,810,344.5 |  |