MIN010/2019/2020

MINUTES OF ELDAMA RAVINE NATIONAL GOVERNMENT CONSTITUENCIES DEVELOPMENT FUND COMMITTEE MEETING HELD ON WEDNESDAY, 28TH OCTOBER 2020 STARTING 11.00AM AT THE NGCDF OFFICE ELDAMA RAVINE

Members Present

- Joseph Ayabei     	 	 	-	Chairman

- Anne Mwangi		-	Secretary

- Fredrick Koros		-	Member

- Nancy Koech		-	Member

- Elijah Kamau		-	Member

- Felix Kangogo		-	Member

- Veronica Kaptich		-	Member

- John Suge				-	Coopted Member

- Geoffrey Koech		-	Fund Account Manager

Absent with Apology

- Ali Omar				-	Deputy County Commissioner

In Attendance

- Kipchilowen Tallam	-          Clerk of Works

Agenda

- Preliminaries

- Reading and Confirmation of the Previous Minutes

- Matters Arising

- Reports October 2020

  - Project Funds Disbursement as at October 2020

  - Kabimoi Day Secondary School

  - Maji Mazuri RC Day Secondary School

  - St Patrick’s Day Secondary School

  - Eldama Ravine Library Progress

  - Uzalendo School CSR Projects Report

  - Monitoring Reports July-September 2020

  - Eldama Ravine Technical College Scholarships

- Performance Contract FY 2020/21

  - Contract Signed FY 2020/21

  - Annual Workplan and  Procurement Plan

- Project Proposals FY 2020/2021

  - NGCDFB Guidelines FY 2019/2020

  - Approved Projects FY 2019/2020-Kshs 137,454,724.14

- Emergency Projects FY 2019/2020

- Reallocation of Funds FY 2019/2020

- Constituency Tenders FY 2020/2021

- Training of NGCDFC and Staff FY 2020/2021

- Others Issues

  - Request for Change of Activity

  - Employment of a Driver

  - Bechmarking Visit by Soy Constituency

  - Establishment of KMTC Eldama Ravine

  - Environment, Sports and Social Security Programme FY 2020/2021

- Approval of Payments

- AOB

MIN1/28/10/2020: Preliminaries

The meeting was called to order by the Chairman at 11AM and an opening prayer was offered by Ann Mwangi before the meeting officially commenced.

The Chairman thanked members for arriving on time and equally added that the sitting arrangement had been organized taking cognizance of the MOH directive on social distancing at all times as a strategy to fight COVID-19 pandemic. He equally observed that there had been delay in holding the full NGCDFC meeting due to the effects of the Corona Virus pandemic in Kenya and globally as well. On that note he challenged members to implore their community members to continually sanitize, wear face masks, wash hands and follow all Government directives on fighting the pandemic.

On matters development, the Chairman reported that despite the shutdown and/or scaling down of operations as directed by MOH, various programmes were implemented including:-

- Meeting of the NGCDFC Executives to deliberate on various matters pertinent to the effective management of the fund.

- Selection process for the new NGCDF Committee between February and March 2020.

- Disbursement of funds to various earmarked projects in FY 2019/2020.

- Implementation of various approved projects in FY 2019/2020.

- Monitoring and evaluation of new and ongoing projects by the NGCDFC staff.

- Issuance of mobile lab benches and primary school science kits to various schools in Eldama Ravine Constituency on 7th August 2020 in partnership with the Schools Equipment Production Unit (SEPU) under the Ministry of Education.

- The Appraisal meeting of FAMs on 28th August 2020 at Nuru Palace Hotel Nakuru.

- Preparation and submission of Eldama Ravine financial statements as well as signing of the Performance contract FY 2020/2021 at Starbucks Hotel Eldoret between 8th and 10th September 2020.

- Training by NGCDFB for Fund Account Managers on management of meetings and minute writing between 28th and 30th September 2020 at Lysan Haven Park Hotel Machakos.

- The benchmarking visit by the Soy National Government Constituency Development Fund Committee on 22nd October 2020 to the Constituency.

Aware of the above, the Chairman reported that these programmes and many others had taken up much of the time and hence the delay on convening the NGCDFC meeting.

On that note the Chair asked members to peruse their respective files to enable them contribute effectively during the deliberations once various matters are raised.

MIN2/28/10/2020: Reading and Confirmation of the Previous Minutes

The Minutes of the National Government Constituency Development Fund Committee meeting of 15th November 2019 were read through by the Secretary. They were proposed for adoption by Elijah Kamau and seconded by Nancy Koech.

The minutes of the meeting of 15th November 2019 were therefore adopted as a true record of the previous deliberations of the Committee.

MIN3/28/10/2020: Matters Arising

  - On MIN4/15/11/2019:  Project Funds Disbursement FY 2018/2019

Members were notified that the funds that were available for disbursement to various projects as was tabled in the previous meeting had been released. These funds have now been utilized to implement various earmarked activities which were now complete whereas others were at various stages of completion.

The Committee after careful and considered deliberations tasked the Clerk of Works to follow up on the said projects to ensure value for money and quality workmanship.

ii) On MIN9/15/11/2019 (a): Monitoring and Evaluation Plan and Programme

It was reported that the planned monitoring and evaluation of new and ongoing projects by the entire committee had not been done due to the restrictive guidelines from the MOH on fighting COVID-19 as well as the closure of schools occasioned by the pandemic as well.

Members after consideration agreed that the same was necessary to comply with government directive on Corona Virus and further resolved that the same shall be carried out as soon as is reasonably possible.

The Committee therefore tasked the Clerk of Works to plan for the same and inform them accordingly.

- On MIN9/15/11/2019 (d): Strategic Plan FY 2018/2019-2020/23

The Chairman indicated that the Constituency Strategic Plan 2018/2019-2022/23 that had been finalized and received was yet to be officially launched due to the scale down of operations and closure of schools brought about by the COVID-19 pandemic.

After careful and considered deliberations, members unanimously agreed that the Strategic Plan should be officially launched as soon as is reasonably possible in consultation with the MP and other Constituency stakeholders. It was agreed that this would ensure that members of the public officially receive the document, embrace it and understand the content so as to make informed choices and input during the mid-term review which is planned for FY 2020/21.

The Fund Account Manager on his part reported that the NGCDF Board expects every Constituency to ensure adherence to its Strategic Plan during project identification, prioritization and implementation in the FY 2020/2021 as well as in subsequent fiscal years to ensure focused approached in NGCDF project management.

- On MIN9/15/11/2019 (e ): Conditionally Approved Projects FY 2017/2018, FY 2018/2019 and FY 2019/2020

The Fund Account Manager tabled a list of conditionally approved projects pertaining to the FY 2017/2018, FY 2018/2019 and FY 2019/2020 for review by members and further deliberations. He further reported that a team from the NGCDF Board team had earlier visited the Constituency to assess the various conditionally approved projects in the FY 2017/2018 and FY 2018/2019 before issuance of the full approval.

As relates the projects that were conditionally approved in the FY 2019/2020, the Fund Account Manager reported that the Board had requested for additional clarifications and documentations in support of the various projects and the same had been submitted as required.

After careful and considered deliberations, the Committee tasked the Fund Account Manager to follow up with the Board to ensure the said projects are cleared and full approval letters and AIEs are issued in addition to the needed funding for the respective years.

A progress report on the same shall be tabled in the next meeting.

MIN4/28/10/2020: Reports October 2020

- Project Funds Disbursement as at October 2020

The Fund Account Manager reported that the AIEs received relating to the FY 2020/2021 as of 28th October 2020 were as follows:-

| No | AIE No | Date | Amount | Remarks |
| --- | --- | --- | --- | --- |
|  | B047394 | 13/11/2019 | 4,000,000 | 1st AIE Received FY 2019/2020 |
|  | B041263 | 19/11/2019 | 20,000,000 | 2nd AIE Received FY 2019/2020 |
|  | B047683 | 18/12/2020 | 7,000,000 | 3rd AIE Received FY 2019/2020 |
|  | B047875 | 30/01/2020 | 9,000,000 | 4th AIE Received FY 2019/2020 |
|  | B049253 | 25/02/2020 | 19,000,000 | 5th AIE Received FY 2019/2020 |
|  | B104267 | 20/03/2020 | 9,000,000 | 6th AIE Received FY 2019/2020 |
|  | B104143 | 20/03/2020 | 1,000,000 | 7th AIE Received FY 2019/2020 |
|  | B104419 | 15/07/2020 | 22,000,000 | 8th AIE Received FY 2019/2020 |
|  | B104593 | 26/08/2020 | 28,000,000 | 9th AIE Received FY 2019/2020 |
| Total AIEs Received FY 2019/2020 (Kshs) |  |  | 119,000,000 |  |

He further informed the Committee that these funds received in the main NGCDF Account No 1310299403791 held at Equity Bank Eldama Ravine had been disbursed to various earmarked projects and the planned project activities were either ongoing or had been completed.

The Committee thanked the Executive and the staff for working hard even during the Covid period to ensure that the approved projects were implemented accordingly.

- Kabimoi Day Secondary School

The Committee was informed that Kabimoi Day Secondary School had been allocated Kshs 700,000 during the FY 2018/2019 towards construction of 1No classroom and Kshs 2,800,000 in FY 2019/2020 towards construction of a 4No storeyed standard classrooms upto roofing level. It was further reported that the above funds had been disbursed to the school to commence the planned activities and the project was now at plastering level.

The Clerk of Works reported that the above contract for the construction of 4No standard story classrooms had been awarded to Brightlink Holdings Limited of P.O Box 681 Eldama Ravine at a contract sum of Kshs 5,395,280 (Five Million, Three Hundred and Ninety Five Thousand, Two Hundred and Eighty Only).

The Committee after careful and considered deliberations resolved that close monitoring of the project should be done to ensure expeditious completion and quality workmanship and a report tabled in the next NGCDFC meeting.

A report on the project shall be tabled in the next NGCDFC meeting.

- Maji Mazuri RC Day Secondary School

The Fund Account Manager reported that Maji Mazuri RC Day Secondary School was allocated Kshs 2,000,000 during the FY 2019/2020 towards the construction of a 4No storeyed standard classrooms upto roofing level. He further indicated that the above funds had been disbursed to the school to commence the planned activities and the project was now at walling level despite the challenges related to approval by the National Environment Management Authority (NEMA) which had delayed project implementation.

The Clerk of Works reported that the above contract for the construction of 4No standard story classrooms had been awarded to Simugi Limited of P.O Box Eldama Ravine at a contract sum of Kshs 5,237,490 (Five Million, Two Hundred and Thirty Seven Thousand, Four Hundred and Ninety Only).

The Committee after careful and considered deliberations resolved that the is need for follow up with NEMA to get the full approval and licensing to allow for the project implementation to proceed smoothly. Members equally resolved that there was need for close monitoring of the project should be done to ensure expeditious completion and quality workmanship and a report tabled in the next NGCDFC meeting.

A report on the project shall be tabled in the next NGCDFC meeting.

- St Patrick’s Day Secondary School

As relates St Patricks Day Secondary School in Eldama Ravine Township, the Fund Account Manager reported that it had been allocated Kshs 4,000,000 in FY 2018/2019 to commence construction of 4No modern standard classrooms and Kshs 3,000,000 in FY 2019/2020 towards completion of the 4No storeyed classroom-Plastering, ceiling, painting, staircase, keying, verandah etc. (Kshs 1,055,700) and construction of a new 40 students science laboratory (Kshs 1,944,300) upto roofing level.

It was reported that the contract for the construction of 4No standard story classrooms was awarded to Dakikasons Limited of P.O Box Eldama Ravine at a contract sum of Kshs 5,055,700 and payments made by the Project Management Committee to the main contractor based on approved certificates by the Works Officer.

After careful and considered deliberations, the Committee noted that the project completion had delayed beyond the earlier anticipated completion period due to various factors include the closure of schools to combat the COVID-19 pandemic. In that regard, it was resolved that the main contractor be asked to complete the works within four weeks to enable for its commissioning in preparation for January 2021 when schools will be officially opened.

The Committee further observed that the quality of workmanship so far was good and resolved to undertake close monitoring and evaluation of the project to ensure adherence to such standards while guaranteeing value for money.

A report on the project shall be tabled in the next NGCDFC meeting.

- Eldama Ravine Library Progress

The Clerk of Works  reported that most works in Phase One and Two of the Eldama Ravine Library Project had been done except for the completion of fence, gate, sentry, parking cabro blocks, landscaping, fence electrical installations, internal toilets mechanical works amongst other minor finishing works.

It was further reported that other works include repair of cracks on gypsum, installation of hand dryers, toilet cisterns, door locks, sinks, data points, strong room doors, water heater switches, CCU covers, soap dish holders, urinal bowls, taps for kitchen and toilets, fillers for doors and gypsum, general cleaning of all floors and stairs, flash doors, water connection amongst other completion works.

The Committee deliberated and agreed that there was need to complete the pending works for the library to be stocked with more books and commissioned somewhere in November or December 2020 to enable the public enjoy the same.

Members further that follow up be made Waitrose Foundation (Now FarmAfrica) on the supply of computers, printers and kindles as earlier pledged to enable the ICT section be operational as well.

To enable the library and offices be stocked with locally published books, it was resolved that an allocation of Kshs 2,000,000 out of the funding for the FY 2020/2021 be set aside for purchase of the same since other books, periodicals, journals and reference materials had been donated by the Kenya National Library Service in addition to books awaited from the Canadian donor.

- Uzalendo School CSR Projects Report

As relates the ongoing NGCDF Board CSR projects at Uzalendo School, the Fund Account Manager reported as follows:-

      - Phase One:- Contract for the proposed Construction of Dining Hall and Kitchen) at Uzalendo School Eldama Ravine was awarded to M/s Ne Onstyle Contractors Limited of P.O Box 441 Eldama Ravine at a tender sum of Kshs 7,723,650. The proposed works included construction of kitchen and dining hall to completion. He indicated that there were no ongoing works on site and the remaining works yet to be done included fitting floor tiles, painting walls, doors, windows and ceiling, fitting of kitchen platforms and cold rooms shelves, ramp and stairs amongst other works. Variations

      - Phase Two:- The contract for this phase was awarded to  M/s Chesrob Enterprises Limited of P.O Box 166-20103 Eldama Ravine at a tender sum was Kshs 7,464,430. Works included construction of 1No Classroom, 90,000L septic tank, sockpit and furniture for the dining hall and kitchen. He indicated that 1No classroom and 90,000L septic tank alongside its sock pit were complete. The remaining works include completion of manholes and waste piping, supply of dining hall tables, chairs, kitchen cooking jikos, and other attendant equipment.

      - Phase Three:- The Contract for the proposed construction and equipping of 124 capacity girls dormitory at Uzalendo School in Eldama Ravine Constituency was awarded to M/S Abejean Company Limited of P.O Box 364-20103 Eldama Ravine at a contract sum of Kshs 7,502,540. The tendered works included construction of a 124 bed capacity girls’ dormitory to completion as well as equipping of the same with beds. It was reported that there was no work that was ongoing on site and the pending works yet to be done included electrical installations, mechanical works, painting internal walls, ceiling and external sections, doors and windows, completion of ramp and stairs, skirting and other finishing works.

After further deliberations and considerations, it was agreed that the Project Implementation Committee be asked to follow up for expeditious completion of the said works and further ensure close monitoring of the ongoing projects to ensure value for money and quality workmanship.

A report on the same shall be tabled in the next NGCDFC meeting.

- Monitoring Reports July-September 2020

The Clerk of Works reported that during the first quarter of FY 2020/2021 that ran from 1st July 2020 upto 30th September 2020 various projects had been implemented and the team had undertaken close monitoring of the same.

These projects includes the following:-Kokorwonin Primary School, Arama Secondary School, Mochongoi Primary School, Bakhita Secondary School, Kapsoit Primary School, Kabimoi Mixed Day Secondary School, Timboroa Chief’s Office, Benonin Secondary School, Kapcholoi Primary School, Maji Mazuri RC Girls Day Secondary School, Tamket Primary School, Cheraik Primary School, Cheptililik Primary School, Kipkoriony Primary School, Eldama Ravine Day and Boarding Primary School and Emkwen Primary School.

He further reported that some of the observations noted during the visit to these projects include the following:-

- Good progress made in implementation of the projects since funds were disbursed to the Project Management Committee.

- Good workmanship in implementation and completion of projects e.g Kabimoi Day Secondary, Emkwen Primary School and Cheraik Primary School

- Delayed completion in some projects with poor workmanship.

- Incomplete projects that require more funds to complete e.g. Arama Secondary School, Benonin Secondary School, Eldama Ravine Day and Boarding Primary School, Bakhita Secondary School, Cheptililik Secondary School.

- Poor record keeping and documentation by some PMCs for the project procurement and expenditures which are needed for audit purposes.

After careful and considered deliberations on the above observations during the projects monitoring and evaluation programmes, the Committee resolved to undertake the following:-

- Notify PMCs with poorly implemented projects of the same in writing and asked them to ensure the noted defects are corrected accordingly.

- Convene a meeting with respective PMCs that had not implemented their projects within the strict requirements for quality workmanship to ensure the same is addressed expeditiously.

- Undertake close monitoring and evaluation of all new and ongoing projects.

- Liaise with the technical officers for their input on all ongoing projects.

- Withhold further disbursements to respective PMCs until the issues noted are addressed and the said projects completed satisfactorily.

- Budget and train all PMCs during the FY 2020/2021 on various aspects of project management to reduce the noted challenges.

- Eldama Ravine Technical College Scholarships

The Chairman reminded the Committee that it had issued scholarships to needy students to pursue selected courses at the Eldama Ravine Technical and Vocational College in December 2020. The funding for the same was released as follows:-

| Payee Institution | Amount Allocated (Kshs) | Date | PV No | Cheque No | Amount |
| --- | --- | --- | --- | --- | --- |
| Eldama Ravine Technical and Vocational College | 2,400,000 | 23/12/2019 | 71 | 6134 | 2,400,000.00 |
| Eldama Ravine Technical and Vocational College | 3,000,000 | 17,03/2020 | 117 | 6283 | 3,000,000.00 |
| Total Disbursed to Institution as Scholarships in (Kshs) |  |  |  |  | 5,400,000 |

The Committee was further informed that the courses that had been funded include the following:-

- Hairdressing and beauty therapy.

- Electrical installations.

- Plumbing

- Driving and maintenance.

- Welding and fabrication.

After further deliberations, the Committee concurred that the three months Curriculum based Education and Training is expected to help those individuals who could not join regular courses to acquire and improve their skills for self-reliance, employability and to adapt to the changing technology.

In that regard, it was further resolved that a meeting shall be convened with the ETVC management in order to review progress of the programme and agree on the way forward as relates the same.

MIN5/28/10/2020: Performance Contract FY 2020/2021

  - Contract Signed FY 2020/2021

The Chairman informed members that during the FY 2020/2021, they had signed a performance contract with the NGCDF Board which shows the performance criteria category, unit of measurement, weight, status of the previous year’s performance and the target for FY 2020/2021. The exercise of signing the performance contract FY 2020/2021 was done between 8th and 10th September 2020 at Starbucks Hotel Eldoret.

After careful and considered deliberations, the Committee unanimously agreed to work as a team to ensure that the targets for the year 2020/2021 are achieved on even surpassed.

  - Annual Workplan, Procurement Plan and Training Plan FY 2020/2021

The Fund Account Manager also tabled the annual workplan, procurement plan as well as the training plan for Eldama Ravine Constituency relating to the FY 2020/2021 for review and adoption by the Committee.

After careful and considered deliberations, the Committee adopted the Annual Workplan, the Procurement Plan and the Training Plan for Eldama Ravine Constituency relating to the FY 2020/2021.

A report on its implementation shall be tabled in the next NGCDFC meeting.

MIN6/28/10/2020: Project Proposals FY 2020/2021

- NGCDFB Guidelines FY 2020/2021

The Fund Account Manager informed the Committee that the NGCDF Board had issued guidelines on the submission of Constituency Project Proposals for the 2020/2021 financial year vide its Circular dated 10th August 2020 and referenced NGCDF BOARD/CEO/BOARD CIRCULARS/VOL1I (024). The guidelines provided as follows:-

- Basis for Identification of Project Proposals

The Circular made reference to Section 27 of the NGCDF Act which provides that the Chairperson of the Constituency Committee shall within the first year of a new parliament and at least once every two years convene open forum public meetings in every ward in the Constituency to deliberate on development matters in the Ward and in the Constituency in line with Article 10 of the Constitution and Section 27 of the NGCDF Act.

The Constituency Project Proposals shall take into consideration the provisions of the National Development Plans and policies as outlined in the Vision 2030-Medium Plan III; the Big Four Agenda; the Constituency Strategic Plan and the International Commitments an conventions to which Kenya is a signatory.

- Eligible Projects under the Act

The guidelines issued stipulated that eligible projects are those in compliance with Section 24 of the Act which provides that these projects are those that are in respect of works and services falling within the function of National Government under the Constitution.

Equally, these projects must be community based in order to ensure the benefits are available to a widespread cross-section of the inhabitants of a particular area. Further these projects should be those that foster sustainable development, promote human dignity and protection of the marginalized as outlined in national values and principles of governance.

The Board therefore directed the Fund Account Managers in liaison with the NGCDF Committees to ensure that the project proposals submitted to the Board are in conformity with the Act to facilitate expeditious approval.

- Constituency Interventions in Response to COVID-19 Pandemic

Constituency Committees were reminded to make us of the guidelines dated 21st May 2020 and referenced NGCDFB/BOARD CIRCULARS/VOL.II/019 in consciously recommending appropriate project proposals that address the development challenges brought about by COVID-19 pandemic and are in conformity with NGCDF Act 2015 as amended in 2016, the Regulations 2016 and other pertinent laws.

The guidelines further reminds the NGCDFCs to advise all PMCs on the requirement to comply with “Access to Government Procurement Opportunities (AGPO) and local content guidelines with a view to maximizing backward and forward linkages for quick resumption of normalcy and restoration of the country to optimal growth path.

- Projects Proposals Co-funded with other Agencies

The communication further refers to Section 49 of the NG-CDF Act which provides that the Board may consider part funding of a project financed from sources other than the Fund so long as the other financiers or donors of that project have no objection and provided that the part funding for the project availed pursuant to this Act shall go to a defined unit or any part thereof or phase of the project in order to ensure that the particular portion defined in the allocation is completed with the funds allocated under this Act.

It further guides that NG-CDFCs are therefore expected to enter into a formal agreement with providers of counterpart funding, clearly indicating the phase to be financed by the each party.

- Completion of Ongoing Projects, Clearance of Outstanding Issues and pending Bills with regard to previous financial year’s Project Proposals

The Circular provided that in conformity with Article 201 (d) of the Constitution and Section 46 (2) of the NGCDF Act, Constituencies are required to focus on completion of ongoing projects before embarking on new ones. Equally, NGCDF Committees are required to submit detailed report on all ongoing projects including estimated cost of construction of an entire project or defined phase that can be put to productive use upon completion.

In the guidelines, Fund Account Managers were reminded to prioritize clearance of outstanding issues to facilitate clearance and release of funds meant for the pending project proposals. Disbursement of funds to Constituencies with respect to new project proposals will be conditional on clearance of outstanding issues.

- Adherence to Public Finance Management Act, Public Procurement and Asset Disposal Act and other Existing Laws

Fund Account Managers were further reminded of the Provisions of Section 53 (8) and (9) of the PPADA, 2015 which stipulates that “An accounting officer shall not commence any procurement proceeding until satisfied that sufficient funds to meet the obligations of the resulting contract are reflected in its approved budget estimates.”

Furthermore, the guidelines further indicated that there was need for Fund Account Managers to ensure that relevant Government departments are involved in project implementation, and that PMCs do not enter into contractual agreements for sums beyond the approved annual project allocation. In instances where the contract exceeds the budgetary allocation, the Fund Account Manager shall ensure that the project is tender for in appropriate phases.

Notwithstanding the above requirements, the NGCDF Committee shall ensure that initiated projects are implemented to completion with three (3) financial years to ensure that benefits promptly accrue to the intended beneficiaries.

- Labelling/Branding of Constituency Projects

As relates labeling and branding of Constituency projects, the guidelines provided that Constituency Committees are expected to ensure that the cost of labeling/branding for each projects is incorporated in the Bills of Quantities for each project.  In addition, the communication indicates that while labeling completed projects, NGCDFCs are required to adhere to the Board’s guidelines on labeling/Branding of projects.

- Adherence to Statutory Ceilings

The Circular also indicated that while preparing project proposals, NG-CDF Committees are expected to adhere to the statutory ceilings for the following  category of projects provided in the NGCDF Act:-

| No | Project Category | Statutory Ceiling |
| --- | --- | --- |
|  | Administration and Recurrent Costs of NGCDFCs | 6% |
|  | Emergency Reserve | 5% |
|  | Sports Activities | 2% |
|  | Environment Activities | 2% |
|  | Monitoring and Evaluation of Ongoing Projects and Capacity Building of various Operatives | 3% |
|  | Social Security Programmes, Education Bursary Schemes, Mocks Examinations and Continuous Assessment Tests | 35% |

- Implementation of Constituency Strategic Plans

The Communication further indicated that it was expected that the NGCDFC that had developed their Strategic Plans now implements the same by ensuring that the project proposals for FY 2020/20 financial year are generated with reference to the strategic plans.

It further noted that the strategic plan is an important tool for the NGCDF Committees forward planning as it also aligns the Constituency interventions with national and global development agenda including Kenya Vision 2030 and Medium Term III, the Government Big Four Agenda as well as the Sustainable Development Goals.

- Budgetary Provision for Employment of NGCDFC Staff

The Circular indicated that in line with Section 45 of the NGCDF Act, the Constituency Committee may engage such staff as may be necessary for the execution of its functions. Such staff shall be remunerated from the funds allocated for administration and recurrent expenses of the Constituency Committee.

In conformity with the above provision, NGCDF Committees are required to plan and make budgetary provisions for necessary number of employees based on a clear organization structure backed by a job description for each employee approved by the Committee.

It further stated that the NGCDF Committee shall make a separate budgetary provision for Monthly staff gratuity for employees on contract terms. In addition to the provision for monthly salaries and remunerative allowances.

- Assets of the Board in Custody of Constituency Committees

Constituency Committees were advised to ensure that the Board’s Property in custody of Constituency Committees bears the name and number of the Constituency as delineated by the IEBC. The original ownership documents shall be submitted to the Board for safe custody and disposal of such assets or equipment acquired should be done with the authority of the Board.

  - Construction of the NG-CDF Office

Section 25 (5) of the NG-CDF Act 2015 as amended in 2016 provides for the construction of the NGCDF Office as an eligible project under the Fund.  Accordingly, the Board advised all Constituencies that are yet to construct NG-CDF Offices to incorporate the project among their 2020/2021 financial year priorities.

The guidelines further stipulated that while submitting project proposals to the Board, the Fund Account Manager shall attach a detailed report on the implementation of the NGCDFC Offices.

  - Procurement of NGCDF Committee Motor Vehicles

It is policy of the Board that each NGCDF Committee procures and maintains on Four Wheeled Drive (4WD) motor vehicle suitable for rough road terrain, with a capacity of at least 4 passengers to ensure mobility for effective administration of the Fund, including regular monitoring of projects.

Further each NGCDFC is required to purchase a motorcycle of an engine capacity of at least 125cc to enhance mobility of the Clerk of Works for day to day tracking of progress of implementation of projects.

Constituencies without a serviceable motor vehicle or motor cycle are therefore advised to make necessary budgetary provisions in the 2020/2021 financial year project proposal.

- Declaration of Appropriation In Aid (AIA)

In compliance with Sec 12(9) and 36(6) of the NGCDF Act, the Board has incorporated revenues and Appropriation in Aid (AIA) by each Constituency in the allocation for 2020/2021 financial year. Fund Account Managers are reminded to collect and ensure that all accruals are declared to the Board for incorporation as part of next year’s Constituency fund.

While submitting project proposals, FAMs are reminded to ensure they include a clear project description of the project or phase of the project to be funded through AIA realized by the Constituency.

- Project Coding

Project proposals shall be submitted alongside project codes pursuant to section 33 of the NGCDF Act for approval by the Board. For this to be effectively done, FAMs are expected to keenly input project details specifically project name and activities by properly describing it in a SMART language.

- Authentication of NGCDFC Minutes

The communication further indicates that in preparing the NGCDFC minutes, the FAM shall work closely with the NGCDFC Secretary to ensure that the details of the project proposal are properly captured in minutes with each page numbered, duly signed by Chairman and Secretary and stamped by the Fund Account Manager.

- Timeline for Submission of Project Proposals

The timeline for submission of project proposals was not later than 30th September 2020.

After careful and considered deliberations, and aware of the above guidelines from the NGCDF Board as relates the preparation and submission of Constituency project proposals FY 2020/2021, the Committee agreed to comply with them accordingly in submission of the project proposal FY 2020/2021 to the NGCDF Board.

- Open Forum Public Meetings Report 2019/2020

The Committee further deliberated with reference to Chapter 12 of the Constitution on Public Finance and specifically Article 201(a) which provides that “there shall be openness and accountability, including public participation in financial matters.” Accordingly, members further referred to Article 10(2)(a) of the Constitution on national values which stipulates that “the national values and principles of governance include the rule of law, democracy and participation of the people.”

The Chairman further made reference to the National Government CDF Act, 2015, as amended in 2016 under Section 27(1) which further provides that “the Chairperson of the Constituency Committee shall, within the first year of the commencement of a new Parliament and at least once every two years thereafter, convene open forum public meetings in every Ward in the Constituency to deliberate on development matters in the Ward and in the Constituency.”

After careful and considered deliberations and aware of the above provisions of the law as relates public participation, the Committee concurred that the open forum public meetings held across the Constituency on  6th and 7th March 2019 were done in compliance with the provisions of the Constitution and the NGCDF Act 2015, as amended in 2016. The Committee concurred that the priorities from the forums will be considered in two financial years from FY 2019/2020 and FY 2020/2021.

Members observed that the public participation forums enabled the Committee to get vital feedback which is critical in Constituency projects prioritization and this report will also helped inform the development of the Constituency Strategic Plan 2018/2019-2022/23 that will be reviewed in FY 2020/2021.

- Approved Projects FY 2020/2021-Kshs 137,101,879.31

After careful and considered deliberations, and aware of the project priorities from various Wards as were captured during the open forum public meetings of 6th and 7th March 2019, the Committee approved the projects proposals for the FY2020/2021 totaling Kshs 137,101,879.31 as hereunder provided:-

| Sub Project Number (Project GFS Code) | Sub Project Title (Name of the Project) | Original Cost Estimates (Kshs) | Cumulative Allocation (Kshs) | Current Project Activity to be Done | Amount Allocated FY2020/2021 | Current Status |
| --- | --- | --- | --- | --- | --- | --- |
| Administration and Recurrent Expenditure |  |  |  |  |  |  |
| 4-030-162-2110000-100-2020/21-001 | Employees’ Salaries | 3,225,283.45 |  | Payment of staff salaries, wages and gratuity | 3,225,283.45 | New |
| 4-030-162-2110000-100-2020/21-002 | NSSF | 48,000.00 |  | Payment of NSSF statutory deductions | 48,000.00 | New |
| 4-030-162-2110000-100-2020/21-003 | NHIF | 74,000.00 |  | Payment of NHIF statutory deductions | 74,000.00 | New |
| 4-030-162-2210000-100-2020/21-004 | Goods and Services | 1,878,829.27 |  | Purchase of fuel, vehicle repairs and maintenance, printing, stationery, telephone, electricity, travel, subsistence and office tea | 1,878,829.27 | New |
| 4-030-162-2210802-100-2020/21-005 | Committee Expenses | 3,000,000.00 |  | Payment of NGCDF Committee members sitting allowances | 3,000,000.00 | New |
|  | Total (Kshs) | 8,226,112.72 | 54,257,115.90 |  | 8,226,112.72 |  |
| Emergency Fund |  |  |  |  |  |  |
| 4-030-162-2640200-101-2020/21-001 | 5% Emergency Fund | 7,192,206.90 |  | To cater for unforeseen occurrences in the Constituency | 7,192,206.90 | New |
|  | Total (Kshs) | 7,192,206.90 | 62,110,229.45 |  | 7,192,206.90 |  |
| Constituency Sports Activities |  |  |  |  |  |  |
| 4-030-162-2640509-112-2020/21-001 | Constituency Sports | 1,500,000.00 |  | Carry out a Constituency sports tournaments and the winning teams to be awarded with trophies, balls, and uniforms | 1,500,000.00 | New |
|  | Total (Kshs) | 1,500,000.00 | 11,319,544.58 | - | 1,500,000.00 |  |
| Training, Monitoring and Evaluation |  |  |  |  |  |  |
| 4-030-162-2210000-111-2020/21-001 | Goods and Services | 500,000.00 |  | Purchase of fuel, repairs and maintenance, printing, stationery, airtime and refreshments | 500,000.00 | New |
| 4-030-162-2210802-111-2020/21-002 | Committee Expenses | 2,397,663.92 |  | Payment of Committee allowances, transport and conferences costs | 2,397,663.92 | New |
| 4-030-162-2210700-111-2020/21-003 | NGCDFC/PMC Capacity Building | 1,213,641.72 |  | Undertake training of the PMCs, staff and NG-CDFCs on NG-CDF related issues | 1,213,641.72 | New |
|  | Total (Kshs) | 4,111,305.64 | 27,521,698.90 | - | 4,111,305.64 |  |
| Bursary, Mocks and CATs |  |  |  |  |  |  |
| 4-030-162-2640101-103-2020/21-001 | Bursary Secondary Schools | 10,500,000.00 |  | To assist bright but needy students from the Constituency in secondary schools through bursary support | 8,500,000.00 | New |
| 4-030-162-2640102-103-2020/21-002 | Bursary Tertiary Schools | 11,000,000.00 |  | To assist bright but needy students from the Constituency in colleges and universities through bursary support | 10,000,000.00 | New |
| 4-030-162-2640105-103-2020/21-004 | Bursary Special Schools | 1,325,469.83 |  | To assist students from the Constituency in special schools through bursary support | 1,442,254.05 | New |
| 4-030-162-2120201-103-2020/21-005 | Eldama Ravine NGCDF Social Security Programme | 1,950,000.00 |  | Towards provision of medical insurance cover for 325 vulnerable families within the Constituency. | 1,950,000.00 | Ongoing |
|  | Total (Kshs) | 24,775,469.83 | 205,809,693.64 |  | 21,892,254.05 |  |
| Constituency Environment Activities |  |  |  |  |  |  |
| 4-030-162-2640510-110-2020/21-001 | Bhakita Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-002 | Kipkoriony Mixed Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-003 | Equator Primary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-004 | Kiptuno Day Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-005 | Muserechi Day Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-006 | Tinet Day Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-007 | Tolmo Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-008 | Kapcholoi Secondary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-009 | Uhuru High School Kabiyet | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-010 | Cheraik Primary School | 100,000.00 |  | To cater for the supply of 10,000 litres tank and water harvesting installations | 100,000.00 | New |
| 4-030-162-2640510-110-2020/21-011 | Koibatek Primary School | 60,000.00 |  | To cater for the planting of 1000 tree seedlings towards environment conservation and protection in the Constituency | 60,000.00 | New |
| 4-030-162-2640510-110-2020/21-012 | Lebolos Secondary School | 60,000.00 |  | To cater for the planting of 1000 tree seedlings towards environment conservation and protection in the Constituency | 60,000.00 | New |
| 4-030-162-2640510-110-2020/21-013 | Kiplongon Primary School | 60,000.00 |  | To cater for the planting of 1000 tree seedlings towards environment conservation and protection in the Constituency | 60,000.00 | New |
| 4-030-162-2640510-110-2020/21-014 | Kibarassoi Primary School | 60,000.00 |  | To cater for the planting of 1000 tree seedlings towards environment conservation and protection in the Constituency | 60,000.00 | New |
| 4-030-162-2640510-110-2020/21-015 | Kamasaba Primary School | 60,000.00 |  | To cater for the planting of 1000 tree seedlings towards environment conservation and protection in the Constituency | 60,000.00 | New |
|  | Total (Kshs) | 1,300,000.00 | 7,718,798.58 |  | 1,300,000.00 |  |
| Primary Schools |  |  |  |  |  |  |
| 4-030-162-2630204-104-2020/21-020 | Kewangoi Primary School | 8,400,000.00 | 7,600,000.00 | Completion of 1No ablution bock-Plastering, plumbing works, tiles, ceiling, keying, painting | 800,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-043 | Kipkoriony Primary School | 2,300,000.00 | 1,500,000.00 | Completion of 5 roomed administration block-completion of plastering, windows glasses, ceiling works, painting, electrical, mechanical and other external works | 800,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-044 | Eldama Ravine Day and Boarding Primary School | 4,750,000.00 | 4,000,000.00 | Completion of 96 bed capacity boy's dormitory- completion of ablution block, fitting tiles, keying, painting and external works | 750,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-049 | Lalut Primary School | 2,000,000.00 | 1,500,000.00 | Completion of 4 roomed administration block, roofing, windows, door, plastering, ceiling | 500,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-073 | Poror Primary School | 1,400,000.00 | NIL | Construction of 1No standard classrooms to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-081 | Cheptililik Primary school | 2,450,000.00 | 2,100,000.00 | Completion of 4 roomed administration block-Completion of plastering works, door and windows glasses, ceiling, painting and external works (Kshs 250,000) and fencing of school land (Kshs 100,000) | 350,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-088 | Kabiyet Primary School | 2,200,000.00 | 1,700,000.00 | Completion of 5 roomed administration block-roofing, plastering, doors, windows, fascia board, painting | 500,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-099 | Naitili Primary School | 1,550,000.00 | 700,000.00 | Completion of 1No Classroom-Plastering, doors, window panes and glasses, floor screeding, keying, painting and other finishing works (Kshs 150,000) as well construction of 1No standard classroom to completion (Kshs 700,000) | 850,000.00 | Ongoing /New |
| 4-030-162-2630204-104-2020/21-100 | Tebeswet Primary School | 700,000.00 | NIL | Construction of a 1No standard classroom upto `completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-101 | Emkwen Primary School | 700,000.00 | NIL | Construction of 1No standard classrooms to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-103 | Kibarassoi primary school | 700,000.00 | NIL | Construction of a 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-104 | Lebolos Primary School | 500,000.00 | 250,000.00 | Refurbishment of 5No classrooms-Repairing floors, window glasses, painting and other works | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-105 | Chepness Primary School | 700,000.00 | NIL | Construction of a 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-108 | Simotwet Special School | 2,500,000.00 | 1,350,000.00 | Completion and equipping of a 50 bed special dormitory for the school-electrical installations, plumbing, ramp, painting, external works and beds | 1,150,000.00 | Ongoing |
| 4-030-162-2630204-104-2020/21-111 | Mochongoi Primary School | 700,000.00 | NIL | Construction of a 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-113 | Kaptim Primary School | 700,000.00 | NIL | Construction of a 1No Standard Classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-114 | St. Mary's Andama Primary School | 700,000.00 | NIL | Construction of 1No Standard Classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-115 | Kirobon Primary School | 1,400,000.00 | NIL | Construction of 2No standard classrooms to completion | 1,400,000.00 | New |
| 4-030-162-2630204-104-2020/21-119 | Koibatek Primary School | 700,000.00 | NIL | Construction of a 1No Standard Classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-120 | Kapsoit Primary School | 950,000.00 | NIL | Construction of a 1No Standard Classroom to completion (Kshs 700,000) and completion of 1No classroom (Kshs 250,000) | 950,000.00 | New |
| 4-030-162-2630204-104-2020/21-121 | Tambarass Primary School | 900,000.00 | NIL | Completion of 1No NGCDF funded Classroom-Plastering, window glasses, cementing floor, keying, verandah and painting (Kshs 200,000) and construction of a 1No Standard Classroom to completion (Kshs 700,000) | 900,000.00 | New |
| 4-030-162-2630204-104-2020/21-122 | Nakurtakwei Primary School | 1,050,000.00 | NIL | Construction of 5 roomed Administration block upto roofing level | 1,050,000.00 | New |
| 4-030-162-2630204-104-2020/21-123 | Kiplombe Primary School | 1,400,000.00 | NIL | Construction of 2No standard classrooms to completion | 1,400,000.00 | New |
| 4-030-162-2630204-104-2020/21-124 | Kanjulul Primary School | 700,000.00 | NIL | Construction of 1No standard classrooms to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-125 | Sogonin Primary School | 1,050,000.00 | NIL | Construction of 5 roomed Administration block upto roofing level | 1,050,000.00 | New |
| 4-030-162-2630204-104-2020/21-126 | Maji Mazuri Forest Primary School | 500,000.00 | NIL | Construction of 10 door toilets to completion | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-127 | Kamngoech primary school | 1,080,000.00 | NIL | Construction of a 1No standard classroom to completion (Kshs 700,000) and construction of 6 -door toilets (Kshs 380,000) | 1,080,000.00 | New |
| 4-030-162-2630204-104-2020/21-128 | Tinet Primary school | 500,000.00 | NIL | Renovations of 5No classrooms-floor, window glasses, doors, roof and painting | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-129 | Sinende Primary School | 700,000.00 | NIL | Construction of a 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-130 | Kamelilo Primary School | 1,000,000.00 | NIL | Construction of a 1No standard classroom to completion (Kshs 700,000) and refurbishment of 3No classrooms-Floor, roof, window glasses, painting, verandah (Kshs 300,000) | 1,000,000.00 | New |
| 4-030-162-2630204-104-2020/21-131 | Equator Primary School | 1,000,000.00 | NIL | Construction of a 1No standard classroom to completion (Kshs 700,000) and refurbishment of 3No classrooms-Floor, roof, window glasses, doors and painting (300,000) | 1,000,000.00 | New |
| 4-030-162-2630204-104-2020/21-132 | Kaprorwa Primary School | 500,000.00 | NIL | Renovation of 5No classrooms-Floor, window glasses, doors, roof and painting | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-133 | Kibias primary school | 500,000.00 | NIL | Renovation of 5No classrooms-Plastering walls, floor, window glasses, painting, roof, verandah and external keying | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-134 | Metipso primary school | 860,000.00 | NIL | Construction of 1No Standard classroom to completion (Kshs 700,000) and completion of modern NGCDF funded toilet-Plumbing, fittings and painting (Kshs 160,000) | 860,000.00 | New/ Ongoing |
| 4-030-162-2630204-104-2020/21-135 | Igure primary school | 400,000.00 | NIL | Completion of 2No standard classrooms-Plastering, windows, doors, verandah, keying and painting | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-136 | Ngarie primary school | 1,400,000.00 | NIL | Construction of 2No standard classrooms to completion | 1,400,000.00 | New |
| 4-030-162-2630204-104-2020/21-137 | Kiplongon primary school | 700,000.00 | NIL | Construction of 1No classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-138 | Sinonin Primary school | 500,000.00 | NIL | Renovation of 5No Classrooms-Plastering, roof repair, window glasses, verandah and external works | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-139 | Kipkaber Primary School | 850,000.00 | NIL | Construction of 20 teacher capacity staffroom upto roofing level | 850,000.00 | New |
| 4-030-162-2630204-104-2020/21-140 | Tolmo Primary School | 380,000.00 | NIL | Construction of 6 door staff toilets to completion | 380,000.00 | New |
| 4-030-162-2630204-104-2020/21-141 | Mumberes Primary School | 1,080,000.00 | NIL | Construction of 6-door toilet to completion (Kshs 380,000) and purchase of 2 acres land for the construction of the school at Kaptembwo area (Kshs 700,000) | 1,080,000.00 | New |
| 4-030-162-2630204-104-2020/21-142 | Mwachon Primary School | 1,050,000.00 | NIL | construction of 1No Standard classroom (Kshs 700,000) and 6-door toilets to completion | 1,080,000.00 | New |
| 4-030-162-2630204-104-2020/21-143 | Tugumoi Primary School | 480,000.00 | NIL | Construction of 8 door girls toilet to completion | 480,000.00 | New |
| 4-030-162-2630204-104-2020/21-116 | Bikwen Primary School | 480,000.00 | NIL | Construction of 8-door boys toilet to completion | 480,000.00 | New |
| 4-030-162-2630204-104-2020/21-144 | Moringwo Primary School | 500,000.00 | NIL | Refurbishment of 5No classrooms-Repairing floors, window glasses, painting, verandah, keying | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-145 | Torokwonin Primary School | 380,000.00 | NIL | Construction of 6 door boys toilets to completion | 380,000.00 | New |
| 4-030-162-2630204-104-2020/21-146 | Arama Primary School | 400,000.00 | NIL | Refurbishment of 4No classrooms-Repairing floors, window glasses, painting, verandah, keying | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-147 | Benonin Primary School | 500,000.00 | NIL | Refurbishment of 5No classrooms-Repairing floors, window glasses, painting, verandah, keying | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-148 | Boito Primary School | 380,000.00 | NIL | Construction of 6 door boys toilets to completion | 380,000.00 | New |
| 4-030-162-2630204-104-2020/21-149 | Kabimoi Primary School | 500,000.00 | NIL | Refurbishment of 5No classrooms-Repairing floors, window glasses, painting, verandah, keying | 500,000.00 | New |
| 4-030-162-2630204-104-2020/21-150 | Kamura Primary School | 400,000.00 | NIL | Refurbishment of 4No classrooms-Repairing floors, window glasses, painting, verandah, keying | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-151 | Kipkuyang Primary School | 400,000.00 | NIL | Refurbishment of 4No classrooms-Repairing floors, window glasses, painting, verandah, keying | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-152 | Mandina Primary School | 300,000.00 | NIL | Renovations of 3No classrooms-Cementing floors, plastering cracked walls, window glasses and painting | 300,000.00 | New |
| 4-030-162-2630204-104-2020/21-153 | Muserechi Primary School | 650,000.00 | NIL | Refurbishment of 4No classrooms funded by PTA-Repairing floors, window glasses, painting, verandah, keying (Kshs 400,000) and completion of 2No classrooms at Chemelil area (Kshs 250,000) | 650,000.00 | New/Ongoing |
| 4-030-162-2630204-104-2020/21-154 | Nerkwo Primary School | 400,000.00 | NIL | Renovations of 4No classrooms-Cementing floor, wall repair, window glasses, roof, verandah and painting | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-155 | Nyakio Primary School | 300,000.00 | NIL | Equipping of the administration block with office swivel chairs, ordinary chairs, office tables, file cabinets and ICT equipment | 300,000.00 | New |
| 4-030-162-2630204-104-2020/21-156 | Orinie Primary School | 700,000.00 | NIL | Construction of 1No Standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-157 | Sagat Primary School | 380,000.00 | NIL | Construction of 6 door toilets to completion | 380,000.00 | New |
| 4-030-162-2630204-104-2020/21-158 | Sigoro Primary School | 400,000.00 | NIL | Renovation of 4No classrooms- plastering walls, cementing floors, repair of roof, window glasses and painting | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-159 | Simotwet Primary School | 400,000.00 | NIL | Renovation of 4No classrooms- plastering walls, cementing floors, repair of roof, window glasses and painting | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-160 | Tarigo Primary School | 400,000.00 | NIL | Renovation of 4No classrooms- plastering walls, cementing floors, repair of roof, window glasses and painting | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-161 | St Patricks Shimoni Primary School | 1,080,000.00 | NIL | Refurbishment of 7No classrooms-Repairing floors, window glasses, painting, verandah, keying (Kshs 700,000) and construction of toilet at Bondeni area (Kshs 380,000) | 1,080,000.00 | New |
| 4-030-162-2630204-104-2020/21-162 | Solian Primary School | 400,000.00 | NIL | Renovation of 4No classrooms- plastering walls, cementing floors, repair of roof, window glasses and painting | 400,000.00 | New |
| 4-030-162-2630204-104-2020/21-163 | Soibei Primary School | 700,000.00 | NIL | Construction of 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630204-104-2020/21-164 | Kokwomoi Primary School | 300,000.00 | NIL | Completion of 1No NGCDF funded classroom at Kapyemit area-Roofing, plastering, cementing floors, wall finish, window panes and glasses, keying and external completion works | 300,000.00 | New |
| 4-030-162-2630204-104-2020/21-165 | St Joseph Makutano Primary School | 700,000.00 | NIL | Construction of 1No standard classroom to completion | 700,000.00 | New |
|  | Total (Kshs) | 65,670,000.00 | 20,700,000.00 | - | 44,510,000.00 |  |
| Secondary Schools |  |  |  |  |  |  |
| 4-030-162-2630205-104-2020/21-016 | Benonin Secondary School | 6,500,000.00 | 5,700,000.00 | Completion of one storeyed 14 roomed administration block- Floor tiles, plastering ground floor walls, windows panes and glasses, painting and external pavement | 800,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-066 | Bakhita Secondary School | 4,200,000.00 | 3,200,000.00 | Completion of 300 student capacity dining hall and kitchen-Window glasses, terrazzo, electrical and mechanical works, painting, external pavement | 900,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-067 | Sinonin Day Secondary school | 4,350,000.00 | 3,850,000.00 | Completion of the twin lab-Floor tiles, plumbing, wiring and painting | 500,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-070 | Mary Keitany Shoe4 Africa Secondary School | 4,350,000.00 | 1,200,000.00 | Construction of a 40 student capacity laboratory to completion but without equipping | 2,050,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-071 | Sabatia Secondary School | 500,000.00 | 3,000,000.00 | Equipping of a 300 student capacity dining hall with tables, chairs and modern kitchen energy efficient cooking pots | 500,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-073 | Maji Mazuri RC Girls Day Secondary School | 5,200,000.00 | 2,000,000.00 | Construction of 4No modern standard classrooms for the story building to completion | 3,200,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-074 | Kabimoi Mixed Day Secondary School | 5,200,000.00 | 3,500,000.00 | Construction of 4No standard classrooms for the story building to completion | 1,700,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-075 | Arama Secondary School | 5,700,000.00 | 4,300,000.00 | Completion of 120 bed boys dormitory-Upper floor walling, plastering, floor tiles, wiring, plumbing, painting, keying and fascia boards | 1,400,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-076 | Kamura Day Secondary School | 3,250,000.00 | 2,250,000.00 | Completion of 40 students laboratory-laboratory worktops, plumbing works, gas chamber fitting, electrical installations and minor completion works | 1,000,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-077 | Kipkoriony Day Secondary School | 5,200,000.00 | 700,000.00 | Construction of 4 standard storeyed classroom upto roofing level | 3,000,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-083 | St.Patricks Day Secondary School | 4,944,300.00 | 1,944,300.00 | Completion of a new science laboratory-Plastering walls, floor tiles, work tops, plumbing, electrical installations, gas chamber, ceiling, painting and external keying and construction of 8 door toilet to completion | 2,900,000.00 | Ongoing |
| 4-030-162-2630205-104-2020/21-084 | Solian Day Secondary School | 700,000.00 | NIL | Construction of 1No standard classroom | 700,000.00 | New |
| 4-030-162-2630205-104-2020/21-085 | Tiripkatoi Day Secondary School | 700,000.00 | NIL | Construction of 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2640510-110-2020/21-086 | Lelgel Day Secondary School | 700,000.00 | NIL | Construction of a 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630205-104-2020/21-087 | Kiptuno Day Secondary School | 700,000.00 | NIL | Construction of 1No standard classroom to completion | 700,000.00 | New |
| 4-030-162-2630205-104-2020/21-088 | Tinet Secondary School | 1,050,000.00 | NIL | Construction of 5 roomed Administration block upto roofing level | 1,050,000.00 | New |
| 4-030-162-2630205-104-2020/21-089 | Uhuru kabiyet Secondary School | 2,500,000.00 | NIL | Construction of 5 roomed twin staff houses upto roofing level | 1,100,000.00 | New |
| 4-030-162-2630205-104-2020/21-090 | Kiplombe Secondary School | 6,900,000.00 | NIL | First installment for the purchase of a new 51 seater school the balance (Kshs 3,900,000) of which shall be paid through reallocation of funds in process | 3,000,000.00 | New |
| 4-030-162-2630205-104-2020/21-09 | St Marys Boito Secondary School | 1,200,000.00 | NIL | Construction of 40 student capacity library upto roofing level | 1,200,000.00 | New |
| Total (Kshs) |  | 63,844,300.00 | 30,144,300.00 |  | 27,100,000.00 |  |
| Tertiary Institutions |  |  |  |  |  |  |
| 4-030-162-2630206-104-2020/21-005 | Eldama Ravine Technical and Vocational College | 1,000,000.00 | NIL | Purchase of a saloon vehicle for the driving school approved by National Industrial Training Authority (NITA) s per request letter herein submitted | 1,000,000.00 | New |
| 4-030-162-2630206-104-2020/21-006 | Kenya Medical Training College Eldama Ravine | 3,000,000.00 | NIL | Construction of the 3 roomed tuition block for the college to completion | 3,000,000.00 | New |
|  | Total (Kshs) | 4,000,000.00 | - | - | 4,000,000.00 |  |
| Security |  |  |  |  |  |  |
| 4-030-162-2640507-113-2019/20-007 | Lembus Central Chief's Office | 2,080,000.00 | 1,700,000.00 | Completion of 1No 4 roomed Chief's office-Construction of external 6 door toilets | 380,000.00 | Ongoing |
| 4-030-162-2640507-113-2019/20-008 | Timboroa Chief's Office | 2,080,000.00 | 1,700,000.00 | Completion of 1No 4 roomed Chief's office-Construction of external 6 door toilets | 380,000.00 | Ongoing |
| 4-030-162-2640507-113-2020/21-012 | Torongo Police Post | 2,100,000.00 | 800,000.00 | Completion of 1No 4 roomed police post offices-Plastering walls, cementing floors, doors and windows, painting, keying | 1,100,000.00 | Ongoing |
| 4-030-162-2640507-113-2020/21-014 | Kiplombe Chief's Office | 2,080,000.00 | NIL | Construction of 1No 4 roomed Chief’s office upto roofing level. | 800,000.00 | New |
| 4-030-162-2640507-113-2020/21-015 | Saos Chiefs Office | 2,080,000.00 | NIL | Construction of 1No 4 roomed Chief’s office upto roofing level | 800,000.00 | New |
| 4-030-162-2640507-113-2020/21-017 | Nyorki Kabulkulet Security Road | 350,000.00 | NIL | Opening up of the security road connecting Nyorki to Kabulkulet approximately 0.9KM-Grading, drainage and culverts | 350,000.00 | New |
|  | Total (Kshs) | 10,770,000.00 | 4,200,000.00 | - | 3,810,000.00 |  |
| Schools Equipment |  |  |  |  |  |  |
| 4-030-162-2640507-113-2020/21-017 | Schools Equipment Production Unit | 2,340,000.00 | 975,000.00 | Purchase of Secondary Schools Mobile laboratory benches for 12 No Secondary Schools in Eldama Ravine Constituency, Kshs 2,200,000 (Kipkuyang Day, Sinonin Day, Kamura Day, Tugumoi Koibatek Day, Muserechi Day, Solian Mixed Day, Benonin Day, Uhuru Kabiyet Secondary, Bhakita Day, Moi Highlands Secondary, Tolmo Secondary and Simotwet Day Secondary) @ Kshs 195,000 each | 2,340,000.00 | New |
| 4-030-162-2640507-113-2020/21-018 | Schools Lockers and Chairs | 1,925,000.00 | NIL | Purchase of 400 lockers and chairs for distribution to various schools to enhance social distancing and fight against Covid-19 pandemic | 1,925,000.00 | New |
|  | Total (Kshs) | 4,265,000.00 | - | - | 4,265,000.00 |  |
| Constituency Strategic Plan |  |  |  |  |  |  |
| 4-030-162-2211310-108-2019/20-001 | Constituency Strategic Plan | 1,195,000.00 | NIL | To cater for the mid- term review of the Eldama Ravine Strategic Plan FY 2018/2019-2022/2023 as indicated in the performance contract FY 2020/2021 | 1,195,000.00 | New |
|  | Total (Kshs) | 1,195,000.00 | - |  | 1,195,000.00 |  |
| NGCDF Office |  |  |  |  |  |  |
| 4-030-162-3110202-113-2019/20-001 | National Government Constituencies Development Fund Office | 87,083,688.61 | 67,083,688.61 | Completion of the Eldama Ravine Library and Offices Project-Masonry fence, cabro blocks for parking, landscaping, gate and sentry, mechanical and electrical works, external lighting, smoke detectors and other finishing works (Kshs 6,000,000) and purchase of locally published books (Kshs 2,000,000) | 8,000,000.00 | Ongoing |
|  | Total (Kshs) | 8,000,000.00 | 67,083,688.61 | - | 8,000,000.00 |  |
| Grand Total Approved for Disbursed to Projects in FY 2020/2021 |  |  |  |  | 137,101,879.31 |  |
| Grand Total Allocated to Constituency in FY 2020/2021 |  |  |  |  | 137,101,879.31 |  |

After careful and considered deliberations, members approved that the above list of priority projects shall be submitted to the NGCDF Board for consideration and approval.

The requisite schedules shall therefore be prepared and forwarded accordingly.

MIN7/28/10/2020: Emergency Projects FY 2019/2020

The Fund Account Manager reported that during the FY2019/2020, the emergency allocation was Kshs 7,198,241.31 which was available to cater for various emergency interventions that were to arise during the Financial Year 2019/2020 in the Constituency that are allowable in the NGCDF Act 2015, as amended in 2016.

Accordingly, the Committee also deliberated and noted that there were various emergency requests that had been received from various projects which required support during the FY 2019/2020 when COVID-19 protocol measures were in force and hence the full NGCDFC meeting could not be convened to deliberate on the same.  Aware of the above, the Chairman NGCDF reported that the Executive Committee had met and approved to support the various key emergency interventions as hereunder provided:-

| No | Project Name | Location | Amount (Kshs) | Activity |
| --- | --- | --- | --- | --- |
|  | Kiplongon Primary School | Mumberes | 550,000 | Construction of 8-door toilet after collapse of another one |
|  | Lelgel Primary School | Mumberes | 550,000 | Construction of 8-door toilet after collapse of another one |
|  | Eldama Ravine Police Station | Ravine | 600,000 | Roofing and repair of the leaking water tank to avert health hazards identified by water office and avoid impending closure by public health office |
|  | Kipkoriony Day Secondary School | Perkerra | 200,000 | Completion of 6 door toilet to improve health and sanitation in the school |
|  | Mavazi Textiles and Branding Limited | N/A | 392,000 | Purchase and distribution of 5,600 reusable face masks for distribution to the community in fight against the COVID-19 pandemic |
|  | Uhuru Kabiyet Secondary School | Kabiyet | 250,000 | Construction of 4-door toilets after the collapse of another in the school |
|  | Schools Lockers and Chairs | Various | 1,375,000 | Purchase of lockers and chairs for distribution to various day secondary schools to enhance social distancing after 100% transition policy |
|  | Mary Keitany Shoe4 Africa Secondary School | Kiplombe | 200,000 | Completion of the school kitchen and installation of 10,000L water tank to enhance health and sanitation and fight against COVID-19 pandemic |
|  | Kenya Prisons Services Eldama Ravine | Ravine | 450,000 | Construction of a 6-door toilet and connection of water at the entrance of Prisons to improve health and sanitation and fight against COVID-19 pandemic in the prison |
|  | Kabimoi Day Secondary School | Kabimoi | 450,000 | Construction of 6-door toilet to improve health and sanitation in the institution and fight against COVID-19 pandemic in the institution |
|  | Moi Highlands Secondary School | Mumberes | 400,000 | Construction of 6-door toilet to improve health and sanitation in the institution and fight against COVID-19 pandemic in the institution |
|  | St Patricks Shimoni Primary School | Ravine | 350,000 | Renovation of dilapidated classrooms floor, window glasses and roof |
|  | Kanjulul Primary School | Kiplombe | 300,000 | Construction of 4-door toilet to improve health and sanitation in the institution and fight against COVID-19 pandemic in the institution |
|  | Equator Primary School | Mumberes | 328,241.31 | Completion of 6-door toilet to improve health and sanitation in the institution and fight against COVID-19 pandemic in the institution |
|  | Critical Infrastructure Protection Unit Eldama Koibatek | Ravine | 203,000 | Renovation of leaking roof, cracked floor and walls and supply of furniture to improve the working environment for the security unit in Koibatek |
|  | Cheraik Primary School | Saos/Kibias | 400,000 | Construction of 6-door toilet to improve health and sanitation in the institution and fight against COVID-19 pandemic in the institution |
|  | Mwachon Primary School | Torongo | 200,000 | Construction of 4-door toilet to improve health and sanitation in the institution and fight against COVID-19 pandemic in the institution |
| Total Amount Approved for Disbursement (Kshs) |  |  | 7,198,241.31 |  |

After consideration, the Committee resolved that follow up shall be made with all PMCs that had received emergency funding to ensure expeditious implementation of their projects as well as to ensure value for money. The Committee further resolved that there was need for urgent branding of the NGCDF funded emergency as well as other projects to ensure identity and avoid duplication by other players who may support similar initiatives.

MIN8/28/10/2020: Reallocation of Funds FY 2019/2020

The Committee deliberated and noted that during the FY 2019/2020, they had allocated funding totaling Kshs 34,363,681.02 for bursary, mocks and CATs which was meant to support needy students in secondary, colleges and universities as well as those in special schools through bursary funding. In addition, members were informed that out of the total allocation, Kshs had been disbursed to various needy cases in secondary, colleges and universities and thus there was a balance of Kshs that was available for disbursement to other needy cases.

The breakdown of the allocation to the bursary, mocks and CATs vote is as hereunder tabulated:-

| Project GFS Code | Name of Project | Project Activity | Amount Allocated (Kshs) | Current Status |
| --- | --- | --- | --- | --- |
| 4-030-162-2640101-103-2019/20-001 | Bursary Secondary Schools | To assist bright but needy students from the Constituency in secondary schools through bursary support | 11,127,263.78 | New |
| 4-030-162-2640102-103-2019/20-002 | Bursary Tertiary Schools | To assist bright but needy students from the Constituency in colleges and universities through bursary support | 19,000,000.00 | New |
| 4-030-162-2640105-103-2019/20-004 | Bursary Special Schools | To assist students from the Constituency in special schools through bursary support | 2,286,417.24 | New |
| 4-030-162-2120201-103-2019/20-005 | Social Security Programme | Towards provision of medical insurance cover for 325 vulnerable families including Orphans and Vulnerable Children (OVCs), poor older persons, Persons with Disabilities (PWDs) and destitute families in partnership with NHIF as shall be identified within the Constituency. | 1,950,000.00 | New |
|  | Total Allocation to Bursary, Mocks and CATS FY 2019/2020 (Kshs) |  | 34,363,681.02 |  |

Noting the above, Members deliberated and observed the part of the funding had not been released in support of various needy students as the government had closed schools countrywide due to the effects of Covid-19 pandemic. In that regard and after careful and considered deliberations, the Committee noted that there were various projects that required urgent support and hence the funds available in the vote should be earmarked for reallocations.

After further deliberations and aware of the various needs in the Constituency, the Committee approved to reallocate the funds as hereunder provided:-

| Project Title | Amount Allocated (Kshs) | Amount Disbursed (Kshs) | Balance (Kshs) | Unspent to Be Reallocated (Kshs) | Reallocated To | Amount (Kshs) | Specific Activity |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bursary Secondary Schools | 11,127,263.78 | 7,037,263.78 | 4,090,000 | 4,090,000 | Sigoro Secondary School | 4,090,000 | Purchase of a 51 new seater bus for the school cofounding with the school Board (Kshs 2,700,000) |
| Bursary Tertiary Institutions | 19,000,000.00 | 11,510,000 | 7,490,000 | 7,490,000 | Kamelilo Secondary School | 4,290,000 | Second Installment for the purchase of a 51 new seater bus for the school. First allocation FY 2019/2020 was Kshs 2,500,000 |
|  |  |  |  |  | Mandina (Proposed) Day Secondary School | 2,500,000 | Purchase of 5 acres of land for the construction of the school |
|  |  |  |  |  | Mwachon Primary School | 700,000 | Construction of 1 No standard classroom to completion |
| Grand Total Proposed for Reallocation During the FY 2019/2020 (Kshs) |  |  |  |  |  | 11,580,000 |  |

After further consideration, the Committee approved that the relevant reallocation schedules shall be forwarded to the NGCDF Board accordingly.

MIN9/28/10/2020: Constituency Tenders FY 2019/2020

The Clerk of Works reported that the tenders were processed by the procurement office and awarded to various contractors during the FY 2019/2020 are as follows:-

| No | Tender Name | Tender No | Contract Sum (Kshs) | Proposed Activity | Awarded To | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | Proposed electrical installation at Eldama Ravine library and offices project | ERC/NGCDF/002/2018-2019 | 2,305,554 | Electrical installation works, lightning arrester, trunking and all fittings | M/S Femsa Company Limited of P.O Box 759-20103 Eldama Ravine | Complete |
|  | Proposed construction of 4No classrooms at Kabimoi Day Secondary School | ERC/NGCDF/007/2018-2019 | 5,395,280 | Construction of 4No new standard classrooms | M/S Brightlink Company Ltd of P.O Box 681 Kabarnet | Ongoing (60%) |
|  | Proposed completion of 1No science laboratory at Sinonin Secondary School | ERC/NGCDF/020/2018-2019 | 2,410,380 | Completion of 1No science laboratory at | M/S Chesrob Company Limited of P.O Box 165-20103 Eldama Ravine | Complete |
|  | Proposed renovations of Eldama Ravine police station | ERC/NGCDF/001/2019-2020 | 597,980 | Renovation of police station | M/S Ardent Logistic Limited of P.O Box 727-20100 Nakuru | Complete |
|  | Proposed renovation 100M3 masonry tank at Eldama Ravine Police Station | ERC/NGCDF/002/2019-2020 | 538,936 | Renovation 100M3 masonry tank | M/S Ardent Logistic Limited of P.O 727-20100 Nakuru | Complete |
|  | Proposed completion of 4No classrooms and 1NO 40 students science laboratory | ERC/NGCDF/002/2019-2020 | 2,000,000 | Completion of 4No classrooms and 1NO 40 students science laboratory | M/S Dusech Limited of P.O Box 785-20103 Eldama Ravine | Complete |
|  | Proposed construction of 1No 4 roomed chief’s office Timboroa Location | ERC/NGCDF/005/2019-2020 | 1,728,905 | Construction of 1No 4 roomed chief’s office | M/S Terolto Company Ltd of P.O Box 437-20103 Eldama Ravine | Ongoing (60%) |
|  | Proposed construction of 1No 4 roomed chief’s office Lembus Central Location | ERC/NGCDF/006/2019-2020 | 1,700,000 | Construction of 1No 4 roomed chief’s office | M/S Eldarav Agencies of P.O Box 811-20103 Eldama Ravine | Ongoing (40%) |
|  | Proposed completion of 1No 96 bed dormitory at Kewangoi Primary School | ERC/NGCDF/008/2019-20 | 1,900,000 | Completion of 1No 96 bed dormitory | M/S Veneers Ltd of P.O Box 43-20103 Eldama Ravine | Ongoing (90% Complete) |
|  | Proposed construction of 4No story classrooms block at Majimazuri RC Girls Day Secondary School | ERC/NGCDF/016/2019-20 | 5,237,490 | construction of 4No story classrooms block | M/S Simugi Essential Ltd of P.O Box 843-20103 Eldama Ravine | Ongoing (30% Complete) |

Noting the above, the Committee resolved that there was need for close monitoring of ongoing projects to ensure value for money and quality workmanship. The Committee further tasked the Clerk of Works to table a report of all the completed projects for review and approval as required.

MIN10/28/10/2020: Training of NGCDFC and Staff FY 2020/2021

The Committee deliberated and noted that there was need for training of the PMCs to benefit from the funds awaited in FY 2020/2021 to ensure that they are fully aware of the provisions of the NGCDF Act and other guiding laws on management of the fund at the Constituency level.

The Fund Account Manager indicated that it was critical to commence with the training of NGCDFC and staff before training PMC to ensure members and staff are acquainted with the relevant laws and information requisite for building the capacity of all PMCs.

After careful consideration, the Committee tasked the Fund Account Manager to prepare a programme and budget for the same tentatively for January 2021 and inform all the Committee members accordingly. In addition, it was they tasked the Clerk of Works and the Fund Account Manager to identify the facilitators and the venue as well as planning gets underway.

Min11/28/10/2020: Others Issues

- Request for Change of Activity

The Fund Account Manager informed the Committee that there we requests for change of activity as follows:

| No | Project Name | Approved Activity | Amount Allocated (Kshs) | New Proposed Project Activity | Reason for Change of Activity | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | Kipkoriony Day Secondary School | Construction of 1No standard classroom to completion | 700,000 | Construction of 4No story classrooms foundation | The size of the school land is small necessitating a construction of a story building | Recommended and the NGCDF Board shall be notified for approval |
|  | Kiplombe Secondary School | Drilling of borehole and installation of fittings to pump water to the elevated storage tank for distribution | 1,300,000 | Construction of 8-door girls toilets (Kshs 600,000), completion of laboratory (Kshs 500,000) and renovation of Principal’s house (Kshs200,000) | The drilling of the borehole at the school has been done by Central Rift Water Service Board | Recommended and the NGCDF Board shall be notified for approval |
|  | Constituency Electrification Programme | To cater for the maximization of transformers and installation of security lighting masts at Bondeni and Shauri settlements of Eldama Ravine Constituency under matching facility with the Rural Electrification Authority | 1,500,000 | To cater for the installation of security lights at Bondeni and Shauri settlements of Eldama Ravine Constituency under competitive tendering by NGCDFC | The comparative cost of the security lights is cheaper in relation to the REREC matching facility | Recommended and the NGCDF Board shall be notified for approval |
| Total Amount Approved for Change of Activity (Kshs) |  |  | 3,500,000 |  |  |  |

- Staff Issues (Employment of a Driver, Renewal of Contracts)

- Employment of a Driver

The Fund Account Manager reported that following the resolution of the Committee in the previous meeting, the Executive Committee had met had invited applications from qualified, experienced, dynamic and highly motivated candidates to fill the position of a driver. Equally, he further indicated that the Executive Committee had met to vet, shortlist, interview and select a suitable candidate to fill the position of driver to be engaged by the NGCDF Committee.

He further indicated that the recruitment and selection was guided by established criteria which included having a minimum of Grade D (plain) in Kenya Certificate of Secondary Education (KCSE) from a recognised institution, holding a valid driving license for the relevant class as per NTSA requirements, having passed the suitability test for drivers conducted by the relevant Ministry/Department or trainer, possessing the relevant NTSA badge and at least five (5) years of driving experience. In addition, the Committee was informed that the selection of the suitable candidate was also guided by gender and Ward representation/Distribution of the NGCDF staff.

The Fund Account Manager drew the attention of members to the Circular date 24th June 2013 and referenced CDF BOARD/CIRCULARS/VOLII/166 which provided guidelines on recruitment of NGCDFC staff and provided as follows:-

- The management of human resource at the NGCDFC level shall be in line with the Constitution of Kenya 2010, the Employment Act 2007, the NGCDF Act and all laws governing labor.

- Recruitment of NGCDFC staff shall be competitive to afford all candidates equal opportunity.

- NGCDFC staff shall be employed on contract period for a three year period, which may be renewable subject to performance.

- The candidates must meet the minimum qualifications and experience outlined by the Board.

- The Fund Account Manager shall maintain a file for each NGCDFC employee during and after the period of employment.

- The remuneration of the NGCDFC staff shall be benchmarked to the prevailing Civil Service salary scale.

- Other remunerative allowances payable to the NGCDFC employees shall be pegged to the applicable government guidelines for each cadre.

After careful and considered deliberations and having tabled the full list of 31 initial applicants for the post as well as the list of 6 shortlisted applicants, the Committee approved the name of the driver tabled by the Executive Committee and his details are as follows:-

| No | Full Names | ID No | Driver License No | Location | Sub Location |
| --- | --- | --- | --- | --- | --- |
| 1. | James K. Kipsengwer | 22818625 | ZYDO67 | Seguton | Seguton |

The Fund Account Manager further reported that the new driver will be issued with an appointment letter and contract with a probation period of 6 months effective 1st December 2020. Equally, he indicated that his details shall be forwarded to the NGCDF Board for approval and issuance of authorization letter to drive the GK vehicle as stipulated in the Board’s guidelines and directives on use of official government vehicles.

As relates his duties, the Committee approved the same as hereunder provided:-

- Drive the official vehicle of the NG-CDFC under authority of the Fund Account Manager or any authorized person.

- Carrying out routine checks on the vehicles cooling system, oil, electrical and brakes systems, tyre pressure etc.

- Detecting and reports any malfunctioning of vehicle systems.

- Maintaining work tickets for vehicle on and off the road.

- Ensuring safety of the vehicle and its accessories.

- Ensuring safety of the passengers and other items at all times.

- Maintaining cleanliness of the vehicle.

- Performing any other duty as may be assigned by the Fund Account Manager

After further deliberations as relates his remuneration and guided by the NGCDF Board Circular referenced CDF BOARD/CIRCULARS/VOLI.I/166 and dated 24th June 2013 the Committee approved as follows:-

- THAT the recruited and selected staff is James Kipchirchir Kipsengwer of ID No 22818625 who was the overall best evaluated.

- THAT the designation of the recruited staff shall by NGCDFC Driver.

- THAT the 6 months’ probation period begins on 1st December 2020 and ends on 31st May 2021 when the staff performance shall be reviewed before confirmation.

- THAT the salary for the candidate shall be Kshs 16,692 effective 1st December 2020.

- THAT the salary payments to the new staff shall be subject to all the applicable statutory deductions.

- THAT the NGCDFC Executive Committee shall sign a formal contract with the staff to effectively seal the engagement.

- THAT the contractual terms for the new staff shall be entered into upon the expiry of the probationary period.

The Committee further resolved that all others terms and conditions of service shall be clearly stipulated in the contract to be entered into between the NGCDFC and the newly engaged driver.

ii) Renewal of Staff Contracts

The Fund Account Manager reported that the contracts of the staff employed by the NGCDFC to assist in its office and field operations had expired and ought to be renewed based on satisfactory performance. He reported that the staff had been engaged on contractual basis for 36 months from 1st October 2017 up to 30st September 2020. A report on the performance appraisal for each member of staff was tabled for deliberation by the Committee before the issue of contract renewal could be discussed further.

After careful and considered deliberations on the performance report, the Committee approved to renew the contract for the below-mentioned staff for another period of 36 months effective 1st October 2020 upto 30th September 2023. The details of the said staff are as hereunder provided:-

| No | Name | I.D Number | Designation | Salary (Kshs) | Salary Account Number |
| --- | --- | --- | --- | --- | --- |
|  | Kipchilowen Tallam | 3446693 | Clerk of Works | 30,000 | 5040769301 |
|  | Stephen Bundotich | 13547830 | ICT Officer | 25,000 | 5040001501 |
|  | Dickson Chelimo | 22636541 | Clerical Assistant | 21,034 | 5040769201 |
|  | Evans Keter | 22313016 | Accounts Clerk | 24,662 | 5040759101 |
|  | Peter Kiptanui | 22405744 | Accounts Clerk | 24,662 | 5040769001 |
|  | Samuel K. Boronjo | 4013300 | Security Officer | 15,000 | 5040976701 |
| Total Salary Per Month (Kshs) |  |  |  | 140,358 |  |

The Committee further resolved that each staff shall be expected to sign a new contract with the NGCDFC stipulating the terms and conditions of service for the period entered into.

iii) Support Staff

The NGCDF Committee was also informed that the contract for the support staff Fatma Bilali engaged with the NGCDFC for 3 days weekly and paid wages for the works done on a monthly basis at a rate of Kshs 500 per day had expired and also ought to be renewed. After consideration, and in view of the impressive performance by the support staff, the Committee approved to renew her contract under the following terms:-

| No | Name | I.D Number | Designation | Wages | Salary Account Number |
| --- | --- | --- | --- | --- | --- |
| 1 | Fatima Bilali | 22636541 | Office Cleaner | 1000/Day | 1310199523272 |

The Committee unanimously agreed that the respective support staff shall also sign a contract extending her term accordingly.

- Benchmarking Visits (Soy Constituency, Eldama Ravine NGCDFC)

The Chairman reported that the visit by the Soy Constituency Development Fund to benchmark in Eldama Ravine on 22nd October 2020 was successful. He noted that the visiting NGCDFC had visited various projects across the Constituency to learn on best practices as well as share their experiences on how they implement their projects back home. He further thanked the Committee members who had availed themselves to accompany the team during the visit.

The Committee on their part observed that there had been various visits by other NGCDFCs to the Constituency equally adding that this was a sign of confidence in the work of the NGCDFC and the Constituency leadership.

After careful and considered deliberations, the Committee also unanimously agreed that there was need for them to benchmark with other Constituencies as well in order to learn from best practices in other jurisdictions as well for implementation once back. In that regard, the Committee tasked the Fund Account Manager to prepare a budget and programme for the visit which should be held in December 2020. Members further proposed that the visit should be to select Constituencies in Bomet and Narok Counties between on dates to be agreed between 10th December 2020 and 22nd December 2020.

- Establishment of KMTC Eldama Ravine

The Committee discussed on the plans earlier commenced, in consultation with the Member of Parliament and other stakeholders, relating the establishment of the medical training college in Eldama Ravine Constituency. The Fund Account Manager reported that he had written formally to the Eldama Ravine Sub County Hospital as well as Baringo County Government seeking clarifications on the availability of land and the size earmarked for the establishment of the medical college in Eldama Ravine Township.

Similarly, the Fund Account Manager reported that he had written to the National KMTC Board seeking approval for the commencement of the said medical college in Eldama Ravine in consultation with the Member of National Assembly and their written response was being awaited.

After careful and considered deliberations, the Committee resolved as follows:-

- THAT the allocation of Kshs 3M towards construction of the first tuition block in FY 2020/2021 shall be forwarded to the NGCDF Board for approval and the balance of funding shall be allocated in FY 2021/2022.

- THAT follow up shall be made with Baringo County Government as relates allocating land and funding towards the planned medical college.

- THAT follow up shall be made with the National KMTC Board for the requisite approval to establish a medical college in consultation with the Member of National Assembly.

- THAT a stakeholders meeting shall be convened as soon as is reasonably possible to deliberate on the project and other incidental matters thereto.

- THAT the support of other community stakeholders shall be sought towards cofounding the project to ensure expeditious completion and opening of the same foe entry students.

- Audit by NGCDFB

The Fund Account Manager informed the Committee that there was a planned audit by the NGCDF Board team between 9th November 2020 and 20th November 2020 and the was to be conducted on a risk based approach as opposed to the value for money or process approach.

A report on the same shall be tabled for deliberations by the Committee once received.

- Constituency Sports (Eldama Ravine Half Marathon, Tournament)

The Committee was informed that during the FY 2018/2019, the allocation to the sports kitty was Kshs 1,090,409 whereas during the FY 2019/2020, the allocation was Kshs 2,399,094.48 which was meant for carrying out a Constituency football tournament and the winning teams/schools to be awarded with trophies, balls, games kits as well as supporting athletics and volleyball with training kits.

The Chairman reported that there were various proposals received for funding support during the FY 2019/2020 that required consideration. He indicated that these requests include the support for the 7th Annual Ravine Half Marathon to be held on 28th November 2020 as well as the planned tournaments for football as well as the volleyball clubs in the Constituency.

The Committee deliberated and agreed that it was critical to ensure the funding support is distributed to the various sporting clubs covering athletics, football and volleyball to ensure equity in support of the clubs at the Constituency level.

After careful and considered deliberations, and an extensive review of the various teams that had submitted their requests, members approved to disburse the funds as hereunder tabulated:-

| No | Team | Location | Amount (Kshs) | Specific Activity |
| --- | --- | --- | --- | --- |
|  | E/Ravine Half Marathon | Constituencywide | 500,000 | Purchase of sports kits and T-shirts to raise funds in support needy students at Uzalendo School in Eldama Ravine |
|  | Football Kenya Federation Koibatek Sub Branch | Constituencywide | 600,000 | Purchase of uniform, boots, balls and other sports kits |
|  | Kenya Volleyball Federation Koibatek Sub Branch | Constituencywide | 230,500 | Purchase of uniform, boots, balls and other sports kits |
| Total Approved for Disbursement from Sports Kitty (Kshs) |  |  | 1,330,500 |  |

The respective officials for the clubs shall be asked to provide the required documentation to enable release of funds for the planned activities accordingly.

- Constituency Environment (Tree Planting, Tree Nursery, Tanks)

The Committee further deliberated on the Environment kitty funding for the FY 2018/2019 and FY 2019/2020 and noted that the allocation was Kshs 1,090,409 and Kshs 1,300,000 respectively. After careful and considered deliberations, the Committee resolved as follows:-

- THAT planting of 6000 tree seedlings each getting 1,000 seedlings shall be done in the following six schools (Metipso Primary School, Uzalendo School, Tebeswet Primary School, Mochongoi Primary School and Torongo Primary School) as per the workplan to ensure environmental conservation and protection.

- THAT there will be issuance of 10,000 litre tanks to 10 schools alongside water harvesting installations to provide sufficient water and help in the fight against Covid-19 pandemic in the Constituency.

- THAT Kshs 300,000 shall be disbursed to Koibatek Conservancy Association which is a youth group for the construction of gabions, opening up of drainages and terracing upto Lebolos Secondary School to avoid soil erosion and ensure environmental protection.

- THAT environmental protection and conservation sensitization shall be done across the Constituency during the sensitization forums in line with the environment action plan for the FY 2020/2021.

- Constituency Electrification Programme

As relates the Constituency Electrification Programme which had been allocated Kshs 1,500,000 towards maximization of transformers and installation of security lighting masts at Bondeni and Shauri settlements of Eldama Ravine, the Committee resolved that there be a change of activity to cater for the installation of security lights at Bondeni and Shauri settlements of Eldama Ravine Constituency under competitive tendering that shall be done.

On that note the Committee resolved that the NGCDF Board shall be notified of the change of activity and the tendering for the installation of security lights shall be done by the NGCDFC accordingly.

- Social Security Programme

The Fund Account Manager reported that during the FY 2019/2020, Kshs 1,950,000 had been allocated under Bursary, Mocks and CATs towards provision of medical insurance cover for 325 vulnerable families including Orphans and Vulnerable Children (OVCs), poor older persons, Persons with Disabilities (PWDs) and destitute families in partnership with NHIF as shall be identified within the Constituency.

Aware of the above, the Committee resolved to collect the requisite forms from NHIF office Eldama Ravine and to task the Bursary Sub Committee to develop guidelines and criteria for vetting and identification of beneficiaries across the Constituency.

On that note, it was also resolved that there was need for collaboration with the Social Services Office which manages the Cash Transfer for the vulnerable as well as well as other relevant departments to avoid duplication.

A report on the same shall be table in the next meeting.

- Covid-19 Interventions and Compliance Measures

The Fund Account Manager reported that in compliance with the government directive on the adoption of measures to ensure continuity of government business and fight the COVID-19 pandemic, they had done the following:-

- Opened a register at the NGCDF office to record details of all customers that visit for various services to ensure effective tracking as and when needed.

- Installation of hand washing tank with sufficient liquid soap and hand sanitizers to enhance the fight against the pandemic.

- Purchase of a thermal gun to check temperatures of all customer that visit the NGCDF Office.

- Purchase and distribution of lockers and chairs to various schools to assist in enhancing social distancing in classrooms and check the spread of the pandemic.

- Allocated funding during the FY 2019/2020 and FY 2020/2021 towards construction of various critical infrastructures to fight against the pandemic.

- Purchased and distributed a total of 5,600 reusable masks approved by the Kenya Bureau of Standards to help the Community fight the spread of the pandemic.

- Issuance of 10,000 litre tanks to 10 schools alongside water harvesting installations to provide sufficient water and help in the fight against Covid-19 pandemic in the Constituency.

- Adhered to all other protocols issued by the Ministry of Health and other relevant government agencies.

- Gazettement of NGCDFC

As relates the gazettement of the NGCDF Committee by the NGCDF Board, the Fund Account Manager reported that the same had delayed but was being finalized after parliament approved the list of the submitted Committee members for gazettement.

A report on the same shall be tabled in the next meeting.

MIN12/28/10/2020: Approval of Payments

The Clerk of Works further reported that there were outstanding payments in favor of various parties who had supplied goods and services to the NGCDF Office. After careful deliberations on the matter, the Committee approved the following outstanding payments:-

- Payment of Kshs 127,390 in favor of Bunste Computer Agencies of P.O Box 755 Eldama Ravine for the supply of photocopy reams, airtime, files, toners and assorted office stationery up to November 2020.

- Payment of Kshs 32,560 in favor of Jonah Tuwei for the supply of assorted newspapers upto November 2020.

- Payment of Kshs 20,000 in favor of Kenya Power for the supply of electricity.

MIN13/28/10/2020: AOB

- The benchmarking tour of the NGCDFC to be planned as soon as possible and members informed accordingly.

- NGCDFC and staff to participate in E/Ravine Half marathon slated for 28th November 2020.

- Various members appreciated the support of the office during the bereavement.

- NGCDFC requested for sanitizers to be issued.

Adjournment

There being no any other business, the meeting ended .2.14PM with a prayer from Veronicah Kaptich.

These minutes are hereby confirmed as a true record of the previous deliberations

Prepared by:-

NGCDFC Secretary …………………………Sign ………………… Date ……………

Minutes Confirmed by:-

NGCDFC Chairman ………………………...Sign …………………… Date …………