| NG-CDF | National Government Constituencies Development Fund Naivasha Constituency P.O Box 1918 NAIVASHA Tel: ……………………………………………… ¦ Cell: ………………………… Email: cdfnaivasha@cdf.go.ke ¦ Website: ……………………… |
| --- | --- |

MINUTES OF NAIVASHA NG-CDFC MEETING HELD ON 22TH SEPTEMBER 2020 AT 10.00 AM IN THE BOARDROOM

PRESENT

- MR. PETER NGUGI                -      FAM

- MR. ALEX MBUGUA            -      CHAIRMAN

- MR. PATRICK KIARA           -      SECRETARY

- MS. IMMACULATE K.          -      ACC

- MR. FRANCIS KAMAU        -      MEMBER

- MR. RICHARD CHEGE         -      MEMBER

- MS. RECHO KABURA          -      MEMBER

- MS. JUDITH GESARE           -      MEMBER

- MR. AMOS SHAYO               -      MEMBER

- MS. MARGARET MATHE    -      MEMBER

IN ATTENDANCE

- MR. BONIFACE KAMAU –   NG - CDF LIAISON OFFICER

- MR. CHARLES WAIREGI –   CONSTITUENCY MANAGER

AGENDA

- Preliminaries

- Confirmation of the previous minutes

- Matters arising

- M&E reports

- 20/21 project proposals

- Training

- Bonding meetings

- Adjournment

MIN NVS NG-CDFC: 2020/09/22 – 01: PRELIMINARIES.

The meeting was called to order at 10:08 am with a word of prayer by Mr. Amos Shayo. Members were welcomed to the meeting.

MIN NVS NG-CDFC: 2020/09/22– 02: CONFIRMATION OF THE PREVIOUS MINUTES.

The minutes of the previous meeting were read and confirmed as a true record of the day’s proceedings. They were proposed by Mr. Francis Kamau and seconded by Mr. Amos.

MIN NVS NG-CDFC: 2020/09/22 – 03: MATTERS ARISING.

- MIN NVS NG-CDF 2020/07/28 – 04: MARYLAND POLICE POST.

It was reported that the PMC had agreed to use the remaining funds in the account to offset the debt, and the same be paid through the bank. It was agreed that the same should be communicated in the next meeting.

MIN NVS NG-CDFC: 2020/09/22 – 04: M/E REPORTS.

|  | PROJECT NAME | PROJECT STATUS |
| --- | --- | --- |
|  | Maiela Primary School | 85% - It was reported that the project had stalled due to management transition. It was agreed that the project be re-engineered |
|  | Nyamathi Primary School | Initial Stage |
|  | Mirera Primary School | Initial Stage |
|  | Kabati Primary School | 98% Complete |
|  | Kinamba Primary School | 95% Complete |
|  | Maai- Mahiu Chief’s Office | 90% Complete |
|  | Karima Mixed Secondary School | 95% Complete |
|  | Gathima Primary School | 80% Complete |
|  | Longonot Primary School Toilets | 80% Complete |
|  | Kiambogo Secondary School | Complete |
|  | Mitamaiyu Primary School | 60% Complete |
|  | Kayole Chief’s Office | 90% Complete |
|  | Naivasha Police Cells Station | On-going |

MIN NVS NG-CDFC: 2020/09/22 – 05:  20/21 PROJECT PROPOSALS.

A prioritized list of project was tabled for discussion and adoption. The list was approved for execution. The list below indicated the project and activities.

| NAIVASHA NGCDF PROJECT PROPOSALS FOR F/Y 2020/2021 DRAFT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | ALLOCATION | 137,190,813.15 |  |
| Name of Project | Original Cost Estimate | Cummulative Allocation | Project Activity | Amount Allocated | Current Status |
|  |  |  | Administration/Recurrent(6%) |  |  |
| Employees Salaries | 2,460,000 |  | Payment of staff salaries and gratuity | 2,460,000 | On-going |
| Goods and Services | 1,549,920.30 |  | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea. | 1,447,920.30 | On-going |
| NSSF | 90,000 |  | Payment of NSSF Deductions | 90,000 | On-going |
| Committee Expenses | 3,700,000 |  | Payment of Committee sitting allowances, transport, conferences | 3,700,000 | On-going |
| 168/AP2 | 0.00 | 0.00 | Monitoring and Evaluation/Capacity Building | 0.00 | On-going |
| Goods and Services | 599,960.20 |  | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence. | 599,960.20 | On-going |
| Committee Expenses | 1,300,000 |  | Payment of Committee sitting allowances, transport, conferences | 1,300,000 | On-going |
| NG-CDFC/PMC Capacity Building | 2,000,000.00 |  | Undertake Training of the PMCs/NG-CDFCs on NGCDF Related issues | 2,000,000.00 | On-going |
| BursarySecondary Schools) | 18,000,000.00 |  | Payment of Bursary to Secondary school | 18,000,000.00 | New |
| Bursary(Tertiary Institutions) | 12,000,000.00 |  | Payment of Bursary to Tertiary Institution | 11,200,000.00 | New |
| NHIF | 2,400,000.00 |  | Payment of Social Security (NHIF) 400 benaficieries | 2,400,000.00 | New |
| Constituency Sports | 2,599,973.40 |  | To carry out sports tournament, support constituency clubs and purchase of sports equipment and kits for various clubs | 2,599,973.40 | New |
| 168/2640510 | 0.00 | 0.00 | Environmental activities | 0.00 | New |
| Narasha secondary school | 400,000 |  | Construction of 4 door pit latrines for staff, to completion | 400,000 | New |
| Narasha Primary school | 1,788,752.35 |  | Renovation; Plastering, floor and roof repairs of 3 classrooms to completion | 1,788,752.35 | New |
| Sisioni Police Post | 300,000.00 |  | Top up for plastering and painting to completion | 300,000.00 | New |
| Emergency | 7,192,206.90 |  | Emergency (5%)To cater for any unforeseen occurrences in the constituency during the financial year | 7,192,206.90 | New |
| Electricity Connection | 5,000,000 |  | Electricity Project(The Matching Fund)(Letter from REA and beneficiaries) | 5,000,000.00 | New |
|  | Primary Schools |  |  | 0 |  |
| Nys Primary school | 7,600,000 |  | Purchase of 3 acres of land (kshs. 7,500,000) processing of title(kshs 100,000) (To Submit land valuation from government valuer) | 7,600,000 | New |
| Central Primary School | 3,300,000 |  | Construction of 2 classrooms with a slab to completion | 3,300,000 | New |
| Gk prison primary School | 4,400,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion | 4,400,000 | New |
| Kinungi primary School | 3,660,000 |  | Construction of 3 classrooms(kshs 3,300,000) and purchase of 90 desks(ksh 360,000) to completion | 3,660,000 | New |
| Munyu Primary School | 5,600,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion, roofing of 4 classrooms to completion. | 5,600,000 | New |
| Old Kijabe Primary School | 4,400,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion, | 4,400,000 | New |
| Karima Primary School | 4,400,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion, | 4,400,000 | New |
| Namcha Primary School | 1,200,000 |  | Construction of 12 door pit latrines with a urinal to completion | 1,200,000 | New |
| Milimani Primary School | 6,900,000 |  | Construction of 1 storey block of 4 classrooms(kshs 6,100,000) and purchase of 200 desks(ksh 800,000) to completion | 6,900,000 | New |
| Lakeview Primary School | 3,850,000 |  | renovation of 7 classrooms: plastering , painting, flooring and roofing to completion, | 3,850,066.16 | New |
| Ngondi Primary School | 1,200,000 |  | Construction of 12 door pit latrines with a urinal to completion | 1,200,000 | New |
| Shermoi Primary School | 4,400,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion, | 4,400,000 | New |
| Mwiciringiri Primary School | 4,400,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion, | 4,400,000 | New |
| Nyamathi Primary School | 4,400,000 |  | renovation 8 classrooms: plastering , painting, flooring and roofing to completion, | 4,400,000 | New |
| Ng'ati Primary School | 2,200,000 |  | renovation 4 classrooms: plastering , painting, flooring and roofing to completion, | 2,200,000 | New |
|  | Secondary School Projects |  |  | 0 |  |
| Ngondi Secondary School | 2,600,000 |  | Construction of 2 classrooms(ksh 2,200,000) and purchase of 80 lockers and chairs(ksh 400,000) to completion | 2,600,000 | New |
| Kihara Secondary School | 3,200,000 |  | Construction of 2 classrooms(kshs 2,200,000) and purchase of 200 lockers and chairs(kshs 1,000,000) to completion | 3,200,000 | New |
| Nyojoro secondary School | 2,600,000 |  | Construction of 2 classrooms(kshs 2,200,000), and purchase of 80 lockers and chairs(kshs 400,000) to completion | 2,600,000 | New |
| Ndoroto Secondary School | 1,500,000 |  | construction of one classroom(kshs 1,100,000) and 4 door toilet(kshs 400,000) complete | 1,500,000 | New |
|  | Security Projects |  |  | 0 |  |