- REPUBLIC OF KENYA

- KILGORIS CONSTITUENCY

| Kilgoris NG-CDF Building |  | P.O Box 361-40700 |
| --- | --- | --- |
|  |  | Kilgoris. |
| OFF Kisii - Kilgoris Road, |  | Cell: 0722 405 245 |
| E mail: muange5@yahoo.com |  |  |

MINUTES OF CDF COMMITTEE MEETING HELD ON 16THNOVEMBER, 2018 AT THE KILGORIS CONSTITUENCY BOARDROOM AT 12.30 PM

MEMBERS PRESENT

- Shadrack Kasy Seiyio			                 Chairperson

- Ruth Naiduya Saisi   Member		                Secretary

- Isaac Lemayian Musunkui                                       Member

- Bancy Cherono Korir                                              Member

- David Karuiki Wainaina                                          Member

- Samwel Naikada                                                      Member

- Mary Ampany                                                          Member

- John Megorokini. Kirentuan	              	   Member

- Hassan 	Nuru Muhammed	                      	   DCC

- Gedion Konchella	   	                                      Member of Parliament

- Benson Aseka                                                        District Accountant

AGENDA

- Confirmation Of Previous Meeting Minutes

- CDF Projects Proposal For Financial Year 2018/2019 Revision

- A.O.B

PRELIMINARIES

The meeting started with prayers led by Mr. Samwel Naikada. The chair welcomed the members to the meeting and asked them to be ready to deliberate on the meeting’s agenda.

MIN 01/11/2018. CONFIRMATION OF PREVIOUS MEETING MINUTES:

The secretary read through the minutes of the previous meeting. The minutes were proposed to be the true copy of the deliberations held by Isaac Musunkui and seconded by David Kariuki.

MIN 02/11/2018: CDF PROJECTS PROPOSAL BUDGET FOR FINANCIAL YEAR 2018/2019

The Chairman briefed members that the NG-CDF Board had send a circular for allocation and forwarding of the project proposals for the financial year 2018/2019 with each constituency set to receive ksh. 109,040,8725.52 including standard emergency of ksh. 5,738,993.45.The deadline for submission of the project proposal  set by the NG-CDF Board was 30th November, 2018.  The board required priority to be given to the ongoing projects in compliance to the list of the ongoing projects that had already been submitted to the board.

After lengthy deliberations the NG - CDF committee agreed on the following projects to be funded in the Financial Year 2018 –2019 in all the six wards in the Constituency. Priority was given to the ongoing projects. Because of the shortage of funds any other ongoing project that has not been factored will be be funded in financial year 2019/2020.

| Project name | Project code | proposed activities | Original Cost (Kshs.) | Cumulated allocation (ksh) | Allocation (Ksh) | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Employees’ Salaries-6% | 4-033-177-2110000-100-2018/2019-001 | Payment of staff salaries, PAYE and gratuity | 2,000,000.00 | 2,000,000.00 | 2,000,000.00 | Ongoing |
| Goods and Services-6% | 4-033-177-2210000-100-2018/2019-002 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea. | 1,582,452.00 | 1,582,452.00 | 1,582,452.00 | Ongoing |
| NSSF | 4-033-177-2120500-100-2018/2019-003 | Payment of NSSF Deductions | 80,000.00 | 80,000.00 | 80,000.00 | Ongoing |
| NHIF | 4-033-177-2120200-100-2018/2019-004 | Payment of NHIF Deductions | 80,000.00 | 80,000.00 | 80,000.00 | Ongoing |
| Committee Allowances -6% | 4-033-177-2210802-100-2018/2019-006 | Payment of Committee allowances | 2,800,000.00 | 2,800,000.00 | 2,800,000.00 | Ongoing |
|  |  |  |  | Total | 6,542,452.00 |  |
| Bursary secondary schools | 4-033-177-2640101-103-2018/2019-001 | To cater for needy/&bright students in secondary Schools | 14,760,577.52 | 14,760,577.52 | 15,260,218.88 | Ongoing |
| Bursary tertiary institutions | 4-033-177-2640101-103-2018/2019-002 | To cater for needy/&bright students in, tertiary institutions & universities | 8,000,000.00 | 8,000,000.00 | 8,000,000.00 | Ongoing |
| Social security programme-NHIF | 4-033-177-2120201-103-2018/19-003 | Payment for NHIF targeting OVC, poor older persons, PWD's, poor widows & widowers & destitute families | 4,000,000.00 | 4,000,000.00 | 4,000,000.00 | Ongoing |
|  |  |  |  | Total | 27,260,218.88 |  |
| Emergency | 4-018-177-2640200-101-2018/2019-001 | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | 5,738,993.45 | 5,738,993.45 | Ongoing |
| Goods and Services 3% | 4-033-177-2210000-111-2018/2019-001 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence. | 771,226.00 | 771,226.00 | 771,226.00 | Ongoing |
| Committee Expenses 3% | 4-033-177-2210802-111-2018/2019-002 | Payment of Committee sitting allowances, transport, conferences | 1,900,000.00 | 1,900,000.00 | 1,900,000.00 | Ongoing |
| NG CDFC/PMC Capacity Building 3% | 4-033-177-2210700-111-2018/2019-003 | Undertake Training of the PMCs/NG CDFCs on NG CDF Related issues | 600,000.00 | 600,000.00 | 600,000.00 | Ongoing |
|  |  |  |  | Total | 3,271,226.00 |  |
| Kilgoris NG-CDF Office | 4-033-177-3110104-108-2018/2019-001 | Purchase of NG-CDF office furniture & Equipment, i.e one desktop Computer and two laptops with at least icore 5, 4GB,HD 500GB,monitor 18.5' at ksh. 100,000 each ,Conference chairs at ksh.7,000 | 3,000,000.00 | 2,000,000.00 | 1,000,000.00 | Ongoing |
| Ilookwaya primary school | 4-033-177-2630204-103-2018/19-001 | completion of two classrooms, external & internal finishes, fixing windows & doors , flooring & painting | 1,900,000.00 | 1,000,000.00 | 900,000.00 | Ongoing |
| Poroko friends special School for the mentally handicapped | 4-033-177-2630204-103-2018/19-002 | purchase & supply of 33 double decker beds and Macintosh | 500,000.00 | 500,000.00 | 500,000.00 | Ongoing |
| Ilkarian primary school | 4-033-177-2630204-103-2018/19-003 | Dormitory completion, wiring, septic , water reticulation | 4,000,000.00 | 3,000,000.00 | 1,000,000.00 | Ongoing |
| Osupukiai primary school | 4-033-177-2630204-103-2018/19-004 | Completion of a classroom, internal & external finishes, door window panes, flooring , keying & fascial board | 900,000.00 | 150,000.00 | 750,000.00 | Ongoing |
| Manyatta primary School | 4-033-177-2630204-103-2018/19-005 | Completion of two classrooms | 1,600,000.00 | 1,500,000.00 | 100,000.00 | Ongoing |
| Shartuka primary school | 4-033-177-2630204-103-2018/19-006 | Completion of two classrooms, Roofing done. Funds for gambles, roofing, windows/panes, metal doors, plastering , external & internal finishes, painting & branding | 2,000,000.00 | 1,200,000.00 | 800,000.00 | Ongoing |
| Sosio primary school | 4-033-177-2630204-103-2018/19-007 | Renovation of four classrooms | 3,000,000.00 | 1,500,000.00 | 1,500,000.00 | Ongoing |
| Kaptembwo primary School | 4-033-177-2630204-103-2018/19-008 | Completion of one classroom i.e internal & external finishes i.e plastering, flooring , painting & labelling | 1,295,010.00 | 1,000,000.00 | 295,010.00 | Ongoing |
| Mashangwa primary school | 4-033-177-2630204-103-2018/19-009 | Completion of one classroom i.e external &internal finishes, plastering , painting , flooring & labelling | 1,240,000.00 | 1,000,000.00 | 240,000.00 | Ongoing |
| Karda primary school | 4-033-177-2630204-103-2018/19-010 | Completion of one classroom, internal & external finishes plastering & painting | 1,121,000.00 | 1,000,000.00 | 121,000.00 | Ongoing |
| Mapashi primary school | 4-033-177-2630204-103-2018/19-011 | Construction of one classroom to completion | 1,100,000.00 | - | 1,100,000.00 | New |
| Njipship primary school | 4-033-177-2630204-103-2018/19-012 | Completion of two classrooms, at lintel. Funds for gambles, roofing, windows/panes, metal doors, plastering , external & internal finishes, painting & branding | 2,000,000.00 | 900,000.00 | 1,100,000.00 | Ongoing |
| Iltolish primary school | 4-033-177-2630204-103-2018/19-013 | Construction of two staff houses to completion | 2,000,000.00 | 2,000,000.00 | 2,000,000.00 | New |
| Supply and delivery of 220 double decker beds for 11 primary boarding schools | 4-033-177-2630204-103-2018/19-014 | Supply & delivery of 220 double decker beds for 11 primary schools each @ksh.15,000 i.e Enoosaen, Ilpashire,Mashangwa,Lolgorian,, Romosha,Narallong,Angata,Oldoinyo Orok,Sitoka,Saparingo & Olorukoti primary schools | 3,300,000.00 | 3,300,000.00 | 3,300,000.00 | Ongoing |
| Iloolkwaya primary school access road | 4-033-177-2630204-103-2018/19-015 | Heavy grading & gravelling of road i.e bush clearing 4000sq. M*5.75/-,culvert installation 8m*25,000,heavy grading 800sq.M*13.5/-, Gravelling with watering & compaction 900 cubic .M*2,2250, contingencies & publicity sign board ksh. 200,000 | 2,556,000.00 | 2,556,000.00 | 2,556,000.00 | New |
| Tumpelian primary school access road | 4-033-177-2630204-103-2018/19-016 | Heavy grading & gravelling of road i.e bush clearing 3200sq. M*5.75/-,culvert installation 16m*25,000,heavy grading 6,400sq.M*13.5/-, Gravelling with watering & compaction 800cubic .M*2,2250, contingencies & publicity sign board ksh. 200,000 | 2,504,800.00 | 2,504,800.00 | 2,504,800.00 | New |
|  |  |  |  |  | 18,766,810.00 |  |
| Kerenkani secondary School | 4-033-177-2630205-104-2018/19-001 | completion of a dormitory ,Walling, roofing , external & internal finishes | 6,400,000.00 | 700,000.00 | 5,700,000.00 | Ongoing |
| Oloorukoti secondary School | 4-033-177-2630205-104-2018/19-002 | Completion of a dormitory, External & internal finishes, fixing of windows, doors & window panes & ablution block | 5,400,000.00 | 2,000,000.00 | 3,400,000.00 | Ongoing |
| Nkararo secondary School | 4-033-177-2630205-104-2018/19-003 | Completion of a dormitory, external & internal finishes, plastering , flooring , painting & branding | 4,500,000.00 | 4,000,000.00 | 500,000.00 | Ongoing |
| Sikawa secondary School | 4-033-177-2630205-104-2018/19-004 | Completion of a laboratory i.e plastering, flooring, painting, doors, windows and general finishing, Plumbing, gas works & work tops | 4,000,000.00 | 1,600,000.00 | 2,400,000.00 | Ongoing |
| Kilgoris Girls secondary School | 4-033-177-2630205-104-2018/19-005 | completion of a dining hall block | 4,500,000.00 | 2,500,000.00 | 2,000,000.00 | Ongoing |
| Kilgoris Girls secondary School | 4-033-177-2630205-104-2018/19-005 | completion of & renovation of dormitory block | 4,500,000.00 | 3,000,000.00 | 1,500,000.00 | Ongoing |
| Enoosaen secondary school | 4-033-177-2630205-104-2018/19-007 | Completion of a dining hall , External & internal finishes i.e Ceiling & painting | 7,500,000.00 | 6,496,194.00 | 1,000,000.00 | Ongoing |
| Shartuka Girls secondary School | 4-033-177-2630205-104-2018/19-008 | Completion of principal house | 2,000,000.00 | 1,500,000.00 | 500,000.00 | Ongoing |
| Shartuka Girls secondary School | 4-033-177-2630205-104-2018/19-008 | Completion of a twin dormitory & i.e roofing, internal & external finishes i.e windows, doors, window panes, plastering , flooring , painting , branding | 8,500,000.00 | 3,500,000.00 | 5,000,000.00 | Ongoing |
| Ntulele Girls secondary School | 4-033-177-2630205-104-2018/19-009 | Construction of one classroom & two pit latrines 2 door & 3 door | 1,500,000.00 | - | 1,500,000.00 | Ongoing |
| Kondamet secondary School | 4-033-177-2630205-104-2018/19-010 | Completion of a laboratory Gas & plumbing works, ceiling and painting, | 3,600,000.00 | 1,600,000.00 | 2,000,000.00 | Ongoing |
| Mutenkuar secondary School | 4-033-177-2630205-104-2018/19-011 | completion of a multi storey administration block, ceiling, fitting of window grills , doors, plastering , flooring, external & finishes, flooring , painting & branding | 10,200,000.00 | 5,000,000.00 | 5,200,000.00 | Ongoing |
| Mutenkuar secondary School | 4-033-177-2630205-104-2018/19-011 | Completion of a dormitory | 7,500,000.00 | 6,628,889.90 | 1,000,000.00 | Ongoing |
| Sitoka secondary School | 4-033-177-2630205-104-2018/19-012 | completion of two classrooms | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | Ongoing |
| Donyo Onkopit secondary school | 4-033-177-2630205-104-2018/19-013 | Completion of two classrooms, fixing windows, doors, window panes , plastering , flooring, external & internal finishes & painting & branding | 1,900,000.00 | 600,000.00 | 1,300,000.00 | Ongoing |
|  |  |  |  |  | 34,000,000.00 |  |
| Angata Barrikoi Chiefs Office | 4-033-177-2640507-113-2018/19-001 | Completion of chief's office, external & internal finishes, fixing window panes , Flooring & painting | 1,200,000.00 | 800,000.00 | 400,000.00 | Ongoing |
| Oldoinyo Orok Chiefs Office | 4-033-177-2640507-113-2018/19-002 | Completion of chief office, external & internal finishes, fixing window panes & painting | 1,000,000.00 | 800,000.00 | 200,000.00 | Ongoing |
| Esoit GSU houses | 4-033-177-2640507-113-2018/19-003 | Construction of GSU houses four (4) additional GSU houses ,pit latrine block, wiring, water tank & water gutters (phase II) | 10,000,000.00 | 4,000,000.00 | 6,000,000.00 | Ongoing |
| Enoosaen Police station | 4-033-177-2640507-113-2018/19-004 | Completion of police station, offices i.e plastering and painting, external & internal finishes, painting & branding. (phase 1) | 5,300,000.00 | 1,500,000.00 | 3,800,000.00 | Ongoing |
|  |  |  |  |  | 10,400,000.00 |  |
| Sports Activities | 4-033-177-2640508-112-2018/19-001 | Carry out Constituency Sports tournament and the winning teams/School to be awarded with trophies, balls, and games kits | 2,080,810.00 | 2,080,810.00 | 2,061,175.19 | Ongoing |
|  |  |  |  | Total | 109,040,875.52 |  |

The committee members requested the Fund Account Manager to expedite the necessary documentation for project proposal for approval by NG-CDF Board. The committee also requested the Area MP to follow up with the board for speedy approval of the proposal.

MIN: CDFC 03/ 11/2018	ADJOURNMENT

There being no other business, the meeting ended at 1.370 pm with a word of prayer from Samwel Naikada.

Minutes Taken by:

CDFC Secretary: Ruth Saisi                                      Sign_______________________

Confirmed by:

CDFC Chairman: Shadrack Seiyio                              Sign_______________________