National Government Constituencies Development Fund

Sabatia Constituency

P. O. Box 260-50311, Wodanga

Cell: 0722- 870733/ 0722-358998

Email: cdfsabatia@cdf.go.ke/Website: www.cdfsabatia.go.ke

NG-CDF

MINUTES OF NG-CDF SABATIA N- CDFC MEETING HELD ON 23rd NOVEMBER 2018 AT THE NG- CDFC BOARDROOM STARTING 9.00AM.

MEMBERS PRESENT

NAME			 DESIGNATION

- Mr.Tonui Isaiah  			DCC Sabatia

- Mr. Tom M. Gimonge			FAM Sabatia

- Mr.Paul Gimode		 	NGCDFC Chairman

- Mrs.Margret Masaya 			NGCDFC Member

- Mr. Ephraim Galo			 NGCDFC Member

- Ms Mary Goretti Mmoji		NGCDFC Member

- Mr.Humpreys Museywa		NGCDFC Member

- M/s Nancy Kanguha 			NGCDFC Member

- Mr.Oliver Mudora			NGCDFC Member

- Mrs. Nancy Injairu Kisala		NGCDFC Member

INATTENDANCE

- Hon. Alfred Agoi 		 	MP Sabatia Constituency

AGENDA

- Opening Prayer and preliminaries

- Brief from the Member Of Parliament

- Brief from the fund account manager

- Proposal for the financial year 2018/2019

- A.O.B

MIN. 1/NOV/2018 - OPENING PRAYER AND PRELIMINARIES.

The meeting started at 9.00.am with a word of prayer from Mrs. Margaret Masaya.

The chairman welcomed all the members present and thanked the area Member of Parliament for his attendance.

MIN. 2/NOV/2018 - BRIEF FROM THE MEMBER OF PARLIAMENT

The area Member of Parliament thanked the fund manager and his committee members for organizing ward forums on gathering of opinions on project identification.

He emphasized members to prioritize the completion of the ongoing projects.

He also enlightened on the need of improving security in the constituency by installation of high mast security lights, construction and rehabilitation of AP lines and Assistant Chiefs Offices.

MIN. 3/NOV/2018 – BRIEF FROM THE FUND ACCOUNT MANAGER

The fund account manager reminded members on the CDF Act on identification of projects. He notified them that the Board had issued a circular for proposals for the financial year 2018/2019 which was totaling to Kshs. 109,040,875.52. He read to them the projects that are eligible and not eligible to be proposed for funding.

The fund manager told members that it was difficult to monitor the NGCDF funded projects He further told them that the spirit of the NGCDF board was to complete the ongoing projects. He welcomed members for an open discussion and come up with the priority projects for the financial year 2018/2019.

MIN. 4/NOV/2018 – PROJECT PROPOSAL 2018/2019 FINANCIAL YEAR

The ongoing projects from the previous financial years were thirteen. The committee approved the funding of ten ongoing projects for this financial year. On the remaining two tabulated below, committee committed itself to undertake and complete the projects in the financial year 2019/2020.

| Financial Year | Project name | Approved Activities | Pending Activities | Estimated Cost (Kshs) | Allocation/ Approved Amount (Ksh) | Amount Disbursed (Kshs) | Balance to complete (Kshs) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2014/2015 | Munoywa Secondary School | Storey building to host administration offices and 5No. classrooms | Walling, laying slab, roofing, plastering, flooring and painting | 15,000,000 | 2,000,000 | 2,000,000 | 13,000,000 |
| 2015/2016 | Bugina Secondary School | Construction of Dining hall | Roofing, plastering, fitting doors and windows, ceiling, and painting | 12,500,000 | 4,500,000 | 4,500,000 | 8,000,000 |

Members were informed that Kigama Secondary had raised Ksh. 3.8 million towards the purchase of 52-seater school bus and had requested the office to top the difference of Ksh. 2.5 million towards the same. The committee approved the amount to be included in this financial year’s budget.

Members went through the ward reports and the Project Implementation Status, and came with the following as the Proposal for the financial year 2018/2019.

| Name of Project |  | Activity | Amount (Ksh) | Status |
| --- | --- | --- | --- | --- |
| ADMINISTRATION/ RECURRENT |  |  |  |  |
| Employees’ Salaries |  | Payment of staff salaries and gratuity | 2,352,895.59 | Ongoing |
| Goods and Services |  | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 1,331,401.85 | Ongoing |
| NSSF |  | Payment of NSSF Deductions | 219,103.09 | Ongoing |
| NHIF |  | Payment of NHIF Deductions | 263,600.00 | Ongoing |
| Committee Expenses |  | Payment of committee sitting allowances, transport, conferences | 2,263,655.27 | Ongoing |
|  |  |  | 6,430,655.80 |  |
| MONITORING & EVALUATION/ CAPACITY BUILDING |  |  |  |  |
| Goods and Services |  | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 542,821.99 | Ongoing |
| Committee Expenses |  | Payment of Committee sitting allowances, transport, conferences | 1,100,000.00 | Ongoing |
| CDFC/PMC Capacity Building |  | Undertake Training of the PMCs/ NGCDFCs on NG CDF Related issues | 1,028,404.28 | Ongoing |
|  |  |  | 2,671,226.27 |  |
| EMERGENCY |  |  |  |  |
| EMERGENCY |  | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | Ongoing |
|  |  |  | 5,738,993.45 |  |
| SPORTS & CULTURE |  |  |  |  |
| Sports and Cultural activities |  | Carry out constituency sports tournaments and cultural activities | 1,200,000.00 | Ongoing |
|  |  |  | 1,200,000.00 |  |
| MOTOR VEHICLE |  |  |  |  |
| MOTOR VEHICLE |  | Final payment for the purchase of office use motor vehicle | 7,000,000.00 | Ongoing |
|  |  |  | 7,000,000.00 |  |
| STRATEGIC PLAN |  |  |  |  |
| STRATEGIC PLAN |  | Printing and launching of strategic plan for the constituency | 800,000.00 | Ongoing |
|  |  |  | 800,000.00 |  |
| CDF OFFICE |  |  |  |  |
| Sabatia CDF Office |  | Construction of 4-door Modern latrine by laying foundation, walling, roofing, plastering, plumbing, tiling and painting to completion | 1,000,000.00 | New |
| Sabatia CDF Office |  | Purchase of 6 conference tables @ Ksh. 15,000, 40 conference chairs @ Ksh. 2,000, 15-executive office chairs @ Ksh. 7,950, 45 Visitors chairs 3500 and 4 steel filing cabinet @ Ksh. 12,450 | 500,000.00 | Ongoing |
|  |  |  | 1,500,000.00 |  |
| BURSARY |  |  |  |  |
| Bursary Secondary Schools |  | Cater for bursary for needy and bright students in secondary schools | 9,000,000.00 | Ongoing |
| Bursary Tertiary Schools |  | Cater for bursary for needy and bright students in tertiary schools | 10,000,000.00 | Ongoing |
| Bursary Special Schools |  | Cater for bursary for needy and bright students in tertiary schools | 1,000,000.00 | Ongoing |
|  |  |  | 20,000,000.00 |  |
| TRANSFERS TO PRIMARY SCHOOLS |  |  |  |  |
| Evojo Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Halombove Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Wanondi Primary School |  | Reroof, plaster, floor and paint 2No. Classrooms | 500,000.00 | Ongoing |
| Wagevi Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Mambai Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Lososi Primary School |  | Reroof, plaster, floor and paint 2No. Classrooms | 500,000.00 | Ongoing |
| Gahumbwa Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Nabwani Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Davanga Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Isitsi Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Lyaduywa Primary School |  | Reroof, plaster, floor and paint 2No. Classrooms | 500,000.00 | Ongoing |
| Ondeyo Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Endeli Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 500,000.00 | Ongoing |
| Chamasilihi Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Kibaala Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| BO Yusuf Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Homunoywa Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Budaywa Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| KilagiruPrimary School |  | Reroof, plaster, floor and paint 2No. Classrooms | 500,000.00 | Ongoing |
| Wandega Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Kivuye Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Hakerongo Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Selelwa Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Hombala Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Madegwa Special School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Vihindi Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Kigama Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Vohovole Primary School |  | Reroof, plaster, floor and paint 3No. Classrooms | 600,000.00 | Ongoing |
| Igunga Primary School |  | Reroof, plaster, floor and paint 4No. Classrooms | 700,000.00 | Ongoing |
|  |  |  | 17,200,000.00 |  |
| TRANSFERS TO SECONDARY SCHOOLS |  |  |  |  |
| Moi Girls High School - Vokoli | Completion of 3rd floor by walling, roofing and painting |  | 14,000,000.00 | Ongoing |
| Moi Girls High School - Vokoli | Purchase of 5 acres of land for school expansion |  | 6,800,000.00 | Ongoing |
| Evojo PAG Secondary School | Completion of 1No. Classrooms by roofing, plastering, flooring and painting |  | 700,000.00 | Ongoing |
| Jemovo Secondary School | Ongoing construction of an Administration block by laying of first floor slab |  | 1,500,000.00 | Ongoing |
| Gahumbwa Secondary School | Ongoing construction of a dormitory by second floor walling and roofing |  | 1,500,000.00 | Ongoing |
| Gaigedi Secondary School | Laying of foundation and walling of 1No. Classroom |  | 800,000.00 | Ongoing |
| Mukingi Secondary School | Ongoing construction of an administration block by walling and roofing |  | 1,500,000.00 | Ongoing |
| Ellongo Secondary School | Wiring of 7No. Classrooms and Administration block |  | 600,000.00 | Ongoing |
| Chamakanga Secondary School | Final installment for the purchase of a school bus |  | 1,000,000.00 | Ongoing |
| Busali Union Secondary School | Completion of laboratory by plastering, painting and piping. |  | 1,500,000.00 | Ongoing |
| Ikobero Secondary School | Completion of 2No. Classrooms by roofing, plastering and painting |  | 1,500,000.00 | Ongoing |
| Wangulu Secondary School | Ongoing construction of an administration block by walling and roofing of first floor |  | 1,500,000.00 | Ongoing |
| Chandumba Secondary School | Final installment for the purchase of school bus |  | 600,000.00 | Ongoing |
| Digula Secondary School | Completion of 1No. Classrooms by roofing, plastering, fitting steel doors and windows, flooring and painting |  | 600,000.00 | Ongoing |
| Kigama Secondary School | Installment for purchase for 52 seater school bus |  | 2,500,000.00 | Ongoing |
| Kisangula Secondary School | Ongoing construction of library by walling, roofing, plastering, painting and, fitting doors and windows |  | 1,500,000.00 | Ongoing |
| Kivagala Secondary School | Renovation of Administration block by reroofing, plastering, flooring and painting |  | 1,000,000.00 | Ongoing |
| Kegondi Secondary School | Laying of foundation, walling and roofing of a science laboratory |  | 1,000,000.00 | Ongoing |
|  |  |  | 40,100,000.00 | Ongoing |
| ENVIRONMENT |  |  |  | Ongoing |
| Mudete Primary School | Planting of 5,000 indigenous trees @Ksh. 10 at the school compound |  | 50,000.00 | Ongoing |
| Kivagala Primary School | Planting of 5,000 indigenous trees @Ksh. 10 at the school compound |  | 50,000.00 | Ongoing |
| Sabatia Primary School | Planting of 5,000 indigenous trees @Ksh. 10 at the school compound |  | 50,000.00 | Ongoing |
| Kilagiru Primary School | Planting of 5,000 indigenous trees @Ksh. 10 at the school compound |  | 50,000.00 | Ongoing |
|  |  |  | 200,000.00 |  |
| SECURITY |  |  |  |  |
| Maganyi AP Line | Start construction of an Administration Police line by laying of foundation and walling |  | 800,000.00 | New |
| Bugina AP Line | Ongoing construction of an Administration Police line by painting and fitting of steel doors |  | 500,000.00 | Ongoing |
| Kichutu AP Line | Start construction of an Administration Police line by laying of foundation and walling |  | 800,000.00 | New |
| Nadanya AP Line | Start construction of an Administration Police line by laying of foundation and walling |  | 800,000.00 | New |
| Chavakali Market High mast security lights | Installation of High mast security lights at Chavakali Market |  | 1,500,000.00 | New |
| Kivagala Ass. Chief's office | Start construction of Assistant - chief office by laying foundation and walling at Kivagala Sub-Location |  | 500,000.00 | New |
| Evojo Ass. Chief's office | Start construction of Assistant - chief office by laying foundation and walling at Evojo Sub-Location |  | 500,000.00 | New |
| Lusengeli Ass. Chief's office | Start construction of Assistant - chief office by laying foundation and walling at Lusengeli Sub-Location |  | 500,000.00 | New |
| Solongo Ass. Chief's office | Start construction of Assistant - chief office by laying foundation and walling at Solongo Sub-Location |  | 500,000.00 | New |
|  |  |  | 6,400,000.00 |  |

MIN. 5/NOV/2018 – A.O.B

- Members requested the Fund Manager to organize a trip or a seminar for them before their term expires.

There being no any other business the meeting ended at 4.50pm with a word of prayer from Mrs. Margret Masaya.

Full Names of NG-CDFC Chairman……………………………………………………

Signature………………………………………………………………………………….

Date……………………………………………………………………………………….

Full Names of NG-CDFC Secretary………………………………………………………

Signature……………………………………………………………………………………

Date…………………………………………………………………………………………