| NG-CDF | National Government Constituencies Development Fund Hamisi Constituency P.O Box 262-50309 Kaimosi Off Kapsabet –Eldoret Road ¦ Cell: 254722959351 Email: cdfhamisi@ngcdf.go.ke ¦ Website: www.ngcdf.go.ke |
| --- | --- |

______________________________________________________________________________________________

MINUTES OF HAMISI NG-CDF COMMITTEE MEETING HELD ON

29TH OCTOBER, 2019

MEMBERS PRESENT

- Mr. Silverius M. Wakoli	-	Fund Account Manager

- Mr. Stephen Ganira		-	NGCDFC Chairman

- Mrs. Lilian Langat		-	Deputy County Commissioner

- Miss Mujesia Laura		-	NGCDFC Secretary

- Mr. Serete Robert		-	NGCDFC Member

- Mrs. Eddah Lujesi		-	NGCDFC Member

- Miss Mary Jemaiyo		-	NGCDFC Member

- Mr. Bulimo Japheth		-	NGCDFC Member

ABSENT WITHOUT APOLOGY

- Mr. Kamidi Nathan		-	NGCDFC Co-opted Member

AGENDA

- Project Proposals FY 2019/2020

- Hamsi NGCDF Vehicle

- A.O.B

MIN. 01/29/10/2019: PRELIMINARIES

The chairman called the meeting to order at 8:30a.m. with a word of prayer from Mary Jemaiyo. He welcomed all members present to the meeting.

MIN. O2/29/10/2019: READING AND CONFIRMATION OF THE PREVIOUS MEETING MINUTES

The secretary Miss Laura Mujesia read through the precious meeting minutes dated 16th October, 2019. The minutes were proposed by Mrs. Lujesi Eddah seconded by Mr. Bulimo Japheth.

MIN. 03/29/10/2019: MATTERS ARISING FROM THE PREVIOUS MEETING MINUTES

The fund manager told members that the public works engineer and the clerk of works have ascertained the status of all the ongoing projects.

MIN. O4/29/10/2019: PROJECT PROPOSALS FINANCIAL 2019-2020

The fund manager informed members that the Board had released a ceiling of Kshs.                                                                    137,367,724.14 for the financial year 2019-2020. Members agreed that there was poor state of sanitation in schools in Hamisi Constituency due to heavy rains and poor soils. The committee agreed to improve all the toilets to exhaustible ones hence more schools should be covered in the current financial year.

The members agreed to prioritize on ongoing projects so that they be complete. On new projects, members agreed to go through the ward reports and the strategic plan, and come up with the priority ones that have bigger impact to the community.

All the projects that had been committed in the last financial year, NGCDFC unanimously agreed to include in the current year to complete the works. The projects are:-

- Bumuyange Secondary School

- Kinu Secondary School

- Nyang’ori Primary School

- Simbi Primary School

- Tigoi Primary School

- Dr. Gimose Jeviriri Secondary School

- Jebrongo Primary School

- Musiri Primary School

- Tambua DOs Office

- Hamisi Sub-County Headquarters

- Gidimo Primary School

- Hamisi Primary School

- Boyani Primary School

- Friends Primary School Kaimosi

- Luther Primary School

- Kaptik Secondary School

During the Monitoring and Evaluation exercise, members noted that projects like Malinda Secondary School, Chebunaywa Primary School and Kitagwa Secondary School have not been included in this financial year proposal because they have completed by BOM/PA. The projects are complete and in use thus no more funding.

Members also agreed that our NG-CDF office that constructed in the year 2008, was in a bad shape and requested the fund manager to include funds in the current year for rehabilitation.

After lengthily discussion, members proposed the projects for the financial year 2019-2020 as tabulated below:-

|  | Name of Project | Original Cost Estimate | Cumulative Allocation | Activity | Amount (Ksh) | Status |
| --- | --- | --- | --- | --- | --- | --- |
|  | ADMINISTRATION / RECURRENT |  |  |  |  |  |
|  | Employees’ Salaries | 3,242,063.00 | - | Payment of staff salaries and gratuity | 3,242,063.00 | Ongoing |
|  | Goods and Services | 3,426,480.00 | - | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, tea | 3,426,480.00 | Ongoing |
|  | NSSF | 241,920.00 | - | Payment of NG_CDF Staff NSSF | 241,920.00 | Ongoing |
|  | NHIF | 263,600.00 | - | Payment of NG_CDF Staff NHIF | 263,600.00 | Ongoing |
|  | Committee Expenses | 1,068,000.00 | - | Payment of committee sitting allowances, transport, conferences | 1,068,000.00 | Ongoing |
|  |  |  |  |  | 8,242,063.00 |  |
|  | MONITORING & EVALUATION / CAPACITY BUILDING |  |  |  |  |  |
|  | Goods and Services | 1,600,000.00 | - | Printing, stationery, airtime, travel and subsistence | 1,600,000.00 | Ongoing |
|  | Committee Expenses | 1,000,000.00 | - | Payment of committee sitting allowances, transport, conferences | 1,000,000.00 | Ongoing |
|  | NGCDFC/PMC Capacity Building | 1,521,031.72 | - | Undertake training of the PMCs/ NGCDFCs on NGCDF Related issues | 1,521,031.72 | Ongoing |
|  |  |  |  |  | 4,121,031.72 |  |
|  | EMERGENCY |  |  |  |  |  |
|  | Emergency | 7,198,241.38 | - | To cater for unforeseen emergency occurrences in the constituency during the financial year | 7,198,241.38 | Ongoing |
|  |  |  |  |  | 7,198,241.38 |  |
|  | SPORTS |  |  |  |  |  |
|  | Sports | 2,706,388.04 | - | Carry out constituency Hamisi Constituency football @ Ksh. 2,006,388.04 and Marathon @ Ksh. 700,000 for youth and women by purchasing football and marathon uniforms, balls, nets, boots, trophies and printing award certificates | 2,706,388.04 | Ongoing |
|  |  |  |  |  | 2,706,388.04 |  |
|  | NG-CDF OFFICE |  |  |  |  |  |
|  | Hamisi NG-CDF office | 1,900,000.00 | - | Renovation of NGCDF office housing Fund Manager’s office, Chairman’s office, Boardroom, clerk of works office, accounts office, Secretary’s office, Store, IT office and a reception constructed in 2008 by painting, tiling, fitting of doors and windows to completion | 800,000.00 | New |
|  |  |  |  |  | 800,000.00 |  |
|  | BURSARY |  |  |  |  |  |
|  | Bursary Secondary Schools | 10,000,000.00 | - | Cater for bursary for needy and bright students in secondary schools | 10,000,000.00 | Ongoing |
|  | Bursary Tertiary Schools | 7,000,000.00 | - | Cater for bursary for needy and bright students in tertiary institutions | 7,000,000.00 | Ongoing |
|  | Bursary Special Schools | 1,480,000.00 | - | Cater for bursary for needy and bright students in Special schools, and institutions | 1,480,000.00 | Ongoing |
|  | Social Security | 720,000.00 | - | Cater for remittance of NHIF to the 120 elderly people within the Constituency @ Ksh. 6,000 per year | 720,000.00 | New |
|  |  |  |  |  | 19,200,000.00 |  |
|  | EDUCATION |  |  |  |  |  |
|  | Transfers to Primary Schools |  |  |  |  |  |
| 1 | Banja Muslim Primary School | 800,000.00 | 400,000.00 | Complete construction of 10-door exhaustible pit latrine by roofing, plastering, flooring and painting to completion. | 400,000.00 | Ongoing |
| 2 | Boyani Primary School | 1,300,000.00 | 500,000.00 | Complete renovation of 3No. Classrooms by flooring, fitting doors and windows, wiring, painting and labelling to completion | 800,000.00 | Ongoing |
| 3 | Bulukhombe Primary School | 800,000.00 | 300,000.00 | Complete construction of 10-door exhaustible pit latrine by roofing, plastering, flooring, painting and labelling to completion | 500,000.00 | Ongoing |
| 4 | Bumuyange Primary School | 1,100,000.00 | 600,000.00 | Complete construction of 10-door exhaustible pit latrine and urinal by plastering, flooring, fitting doors, piping, painting and labelling to completion | 500,000.00 | Ongoing |
| 5 | Butiti Primary School | 800,000.00 | 500,000.00 | Complete construction of 10-door exhaustible pit latrine by piping, plastering, flooring and painting to completion | 300,000.00 | Ongoing |
| 6 | Chepsaga Primary School | 800,000.00 | 400,000.00 | Complete construction of 10-door exhaustible pit latrine by roofing, flooring, painting and labelling to completion | 400,000.00 | Ongoing |
| 7 | Cheptembu Primary School | 2,300,000.00 | 1,800,000.00 | Complete construction of 2No. Classroom by plastering, flooring, fit steel windows and door, painting and labelling to completion | 500,000.00 | Ongoing |
| 8 | Egemeni Primary School | 14,000,000.00 | 1,500,000.00 | Ongoing construction of two-floor storey building housing 8No. Classrooms by laying slab on the 1st floor, walling, fitting doors and windows, plastering and painting to completion | 4,000,000.00 | Ongoing |
| 9 | Erusui Girls Primary School | 850,000.00 | - | Construction of 10-door exhaustible pit latrine to completion | 850,000.00 | New |
| 10 | Friends Primary School Givogi | 2,400,000.00 | 1,000,000.00 | Ongoing completion of 2No. Classrooms by roofing, plastering, painting and labelling to completion | 1,000,000.00 | Ongoing |
| 11 | Friends Primary School Kaimosi | 800,000.00 | 500,000.00 | Ongoing Construction of 10No-door pit latrine by plastering, painting and labelling to completion | 300,000.00 | Ongoing |
| 12 | Gamalenga Primary School | 800,000.00 | - | Construction of 10No-door pit latrine by laying foundation, slabbing, walling and roofing to completion | 800,000.00 | New |
| 13 | Gambaragai Primary School | 950,000.00 | 600,000.00 | Final instalment for purchase of 1 acre of land for school expansion | 350,000.00 | Ongoing |
| 14 | Gidagadi Primary School | 2,000,000.00 | - | Construction of 2No. Classrooms by laying foundation, walling, plastering, fit doors and windows, and roofing, painting, facia board and labelling to completion | 2,000,000.00 | New |
| 15 | Gidimo Primary School | 4,000,000.00 | 2,800,000.00 | Ongoing construction of 4No. Classrooms by plastering , fitting doors and windows, flooring and painting to completion | 1,200,000.00 | Ongoing |
| 16 | Gimarakwa Primary School | 800,000.00 | 500,000.00 | Complete construction of 10-door exhaustible pit latrine by piping, flooring, painting and labelling to completion | 300,000.00 | Ongoing |
| 17 | Gimarian Primary School | 600,000.00 | - | Ongoing construction of 6No-door pit latrine by walling, roofing and fitting doors to completion | 600,000.00 | New |
| 18 | Gimengwa Primary School | 1,600,000.00 | - | Construction of 2No-10door exhaustible pit latrines for boys and girls to completion | 1,600,000.00 | New |
| 19 | Gimomoi Primary School | 1,000,000.00 | 300,000.00 | Ongoing completion of 1No. Classroom by roofing, plastering and painting to completion | 700,000.00 | Ongoing |
| 20 | Friends Special Primary School - Givavei | 800,000.00 | 500,000.00 | Complete construction of 10-door exhaustible pit latrine by piping, plastering, flooring, painting and labelling to completion | 300,000.00 | Ongoing |
| 21 | Givole Primary School | 800,000.00 | - | Construction of 10No-door pit latrine by laying foundation, slabbing, walling, roofing and fitting doors to completion | 700,000.00 | New |
| 22 | Givudemesi Primary School | 800,000.00 | 600,000.00 | Ongoing completion of 10No-door pit latrine by plastering and painting | 200,000.00 | Ongoing |
| 23 | Hamisi Primary School | 2,000,000.00 | 1,800,000.00 | Complete construction of 2No. Classrooms by painting and labelling to completion | 200,000.00 | Ongoing |
| 24 | Givogi Primary School | 1,500,000.00 | 500,000.00 | Ongoing construction of boys dormitory housing 60 students by walling and roofing to completion | 1,000,000.00 | Ongoing |
| 25 | Itiengere Primary School | 800,000.00 | 600,000.00 | Complete construction of 10-door exhaustible pit latrine by flooring, painting and labelling to completion | 200,000.00 | Ongoing |
| 26 | Itovo Primary School | 2,000,000.00 | - | Construction of 2No. Classrooms by laying foundation, walling, plastering, flooring and painting to completion | 2,000,000.00 | New |
| 27 | Ivumbu Primary School | 1,200,000.00 | 600,000.00 | Renovation of 3No. Classrooms by plastering, flooring, painting and labelling to completion | 600,000.00 | Ongoing |
| 28 | Jeblabuk Primary School | 800,000.00 | - | Renovation of 2No. Classrooms by raising lintel, reroofing, plastering, flooring and painting to completion | 800,000.00 | New |
| 29 | Jebrongo Primary School | 14,000,000.00 | 1,500,000.00 | Ongoing construction of one floor storey building housing 8No. Classrooms by laying slab on the 1st floor, walling and plastering to completion | 4,000,000.00 | Ongoing |
| 30 | Jeptorol Primary School | 850,000.00 | - | Construction of 10-door exhaustible pit to completion | 850,000.00 | New |
| 31 | Jidereri Primary School | 300,000.00 | - | Rehabilitation of 1No. Classrooms by reroofing, plastering, flooring and painting to completion | 300,000.00 | New |
| 32 | Jimarani Primary school | 1,000,000.00 | - | Construction of 1No. Classroom by laying foundation, walling, roofing, plastering, fitting doors and windows, painting, facia board and labelling | 1,000,000.00 | New |
| 33 | Jinjini Primary School | 2,000,000.00 | 1,000,000.00 | Ongoing construction of 2No. Classrooms by roofing, fitting doors and windows and flooring, plastering, wiring, facia board, and painting to completion | 1,000,000.00 | Ongoing |
| 34 | Kamuluguywa Primary School | 800,000.00 | 600,000.00 | Complete construction of 10-door exhaustible pit latrine by flooring, painting and labelling to completion | 200,000.00 | Ongoing |
| 35 | Kapchemgung Primary School | 800,000.00 | - | Rehabilitation of 2No. Classrooms by reinforcing lintel, reroofing, plastering, flooring, painting and labelling to completion | 800,000.00 | New |
| 36 | Kapchorwa Primary School | 3,000,000.00 | 1,100,000.00 | Ongoing construction of 3No. Classroom to by roofing, flooring, fitting doors and windows , plastering wiring, facia board and painting to completion | 1,900,000.00 | Ongoing |
| 37 | Kapsegeli Primary School | 1,000,000.00 | - | Construction of 1No. Classroom by walling, roofing, plastering, fitting doors and windows to completion | 1,000,000.00 | New |
| 38 | Kapsogoro Primary School | 1,000,000.00 | - | Construction of 1No. Classroom by laying foundation, walling, plastering, roofing, fitting doors and windows awaiting painting, facia board and labelling to completion | 1,000,000.00 | New |
| 39 | Kapsoi Primary School | 800,000.00 | - | Construction of 10-door exhaustible pit latrine to completion | 800,000.00 | New |
| 40 | Kapsotik Primary School | 1,700,000.00 | - | Rehabilitation of 5No. Classrooms by reroofing, plastering, flooring, painting and labelling to completion | 1,700,000.00 | New |
| 41 | Kaptis Primary School | 1,000,000.00 | - | Rehabilitation of 3No. Classrooms by reroofing, plastering, flooring, painting and labelling to completion | 1,000,000.00 | New |
| 42 | Kinu Primary School | 800,000.00 | 400,000.00 | Complete construction of 10-door exhaustible pit latrine by fitting facial board, doors, flooring, painting and labelling to completion | 400,000.00 | Ongoing |
| 43 | Kisasi Primary School | 850,000.00 | 400,000.00 | Complete construction of 10-door exhaustible pit latrine by fitting facial board, doors, flooring, painting and labelling to completion | 450,000.00 | Ongoing |
| 44 | Kitagwa Primary School | 800,000.00 | - | Construction of 10-door exhaustible pit latrine to completion | 800,000.00 | New |
| 45 | Kitambazi Primary School | 800,000.00 | 600,000.00 | Complete construction of 10-door exhaustible pit latrine by fitting facial board, painting and labelling to completion | 200,000.00 | Ongoing |
| 46 | Logere Primary School | 800,000.00 | - | Construction of 10No-door pit latrine by laying foundation, slabbing, walling, roofing and fitting doors to completion | 800,000.00 | New |
| 47 | Luther Primary School | 1,000,000.00 | - | Construction of 1No. Classrooms by laying foundation, plastering, walling, roofing, wiring and fitting doors and windows , painting, facia board and labelling to completion | 1,000,000.00 | New |
| 48 | Madeya Primary School | 800,000.00 | - | Construction of 10-door exhaustible pit latrine to completion | 800,000.00 | New |
| 49 | Makuchi Primary School | 2,000,000.00 | 1,000,000.00 | Ongoing renovation of 5No. Classrooms by reinforcing lintel, re-roofing, flooring and plastering awaiting painting, facia board and labelling to completion | 1,000,000.00 | Ongoing |
| 50 | Malinda Primary School | 600,000.00 | 300,000.00 | Complete construction of 6-door exhaustible pit latrine by fitting doors, flooring and painting to completion | 300,000.00 | Ongoing |
| 51 | Mudindi Primary School | 2,000,000.00 | - | Construction of 2No. Classrooms by laying foundation, walling, roofing, plastering, flooring and fitting doors and windows to completion | 2,000,000.00 | New |
| 52 | Mungavo Primary School | 800,000.00 | 500,000.00 | Complete construction of 10-door exhaustible pit latrine by fitting doors and facia board, flooring, painting and labelling to completion | 300,000.00 | Ongoing |
| 53 | Munzatsi Primary School | 800,000.00 | 300,000.00 | Complete construction of 10-door exhaustible pit latrine by roofing, plastering, flooring, painting and labelling to completion | 500,000.00 | Ongoing |
| 54 | Musawa Primary School | 800,000.00 | 500,000.00 | Complete construction of 10-door exhaustible pit latrine by fitting doors and facia board, flooring, painting and labelling to completion | 300,000.00 | Ongoing |
| 55 | Museywa Primary School | 2,490,000.00 | 1,200,000.00 | Renovation of 6No. Classrooms by reroofing, flooring, plastering and painting to completion | 1,200,000.00 | Ongoing |
| 56 | Musiri Primary School | 1,560,000.00 | 500,000.00 | Renovation of 5No. Classrooms by reroofing, flooring, plastering and painting to completion | 800,000.00 | Ongoing |
| 57 | Mutave Primary School | 2,000,000.00 | 500,000.00 | Construction of 2No. Classrooms by laying foundation, walling, roofing, fitting doors and windows, plastering and flooring, painting, facia board and labelling | 1,500,000.00 | New |
| 58 | Mutiva Primary School | 600,000.00 | - | Renovation of 2No. Classrooms by reroofing, flooring, plastering and painting to completion | 600,000.00 | New |
| 59 | Ivola Primary School | 800,000.00 | - | Complete renovation of 2No. Classrooms by reinforcing lintel, reroofing, flooring, plastering and painting to completion | 800,000.00 | New |
| 60 | Mwanzo ADC Primary School | 4,500,000.00 | 2,500,000.00 | Complete construction of 4No. Classrooms by roofing, plastering, flooring, fitting doors and windows, painting and labelling to completion | 2,000,000.00 | Ongoing |
| 61 | Mwembe Primary School | 1,500,000.00 | - | Complete renovation of 4No. Classrooms by reroofing, flooring, plastering and painting to completion | 1,500,000.00 | New |
| 62 | Nyang'ori Primary School | 800,000.000 | - | Complete rehabilitation of 2No. Classrooms by reinforcing lintel, reroofing, flooring, plastering and painting to completion | 800,000.00 | New |
| 63 | Saosi Primary School | 1,400,000.00 | - | Complete renovation of 4No. Classrooms by reroofing, flooring, plastering and painting to completion | 1,400,000.00 | New |
| 64 | Saride Primary School | 800,000.00 | 400,000.00 | Ongoing construction of 10-door pit latrine Plaster, floor, paint and labelling to completion | 400,000.00 | Ongoing |
| 65 | Shikomoli Primary School | 800,000.00 | 300,000.00 | Complete construction of 10-door exhaustible pit latrine by roofing, plastering, flooring, painting and labelling to completion | 500,000.00 | Ongoing |
| 66 | Siekuti Primary School | 500,000.00 | - | Renovation of 2No. Classrooms by fitting doors and windows, facia board, plastering, flooring, painting and labelling to completion. | 500,000.00 | New |
| 67 | Simbi Primary School | 3,600,000.00 | 2,500,000.00 | Complete renovation of 10No. Classrooms by reroofing, flooring and plastering | 500,000.00 | Ongoing |
| 68 | Tigoi Primary School | 2,600,000.00 | 1,800,000.00 | Ongoing construction of Administration block housing, Head teacher’s office, Deputy Head teacher’s office, Senior teacher’s office, store, boardroom and staffroom by roofing, plastering, flooring, fitting doors and windows to completion | 800,000.00 | Ongoing |
| 69 | Ikonza ADC Primary School | 500,000.00 | - | Complete construction of 6-door exhaustible pit latrine by roofing, plastering, flooring, painting and labelling to completion | 500,000.00 | New |
|  |  |  |  |  | 61,300,000.00 |  |
|  | Transfers to Secondary Schools |  |  |  |  |  |
| 70 | Bumuyange Secondary School | 4,000,000.00 | 2,900,000.00 | Complete construction of 4No. Classrooms by plastering, flooring, fitting doors and windows awaiting painting, facia board and labelling to completion. | 1,100,000.00 | Ongoing |
| 71 | Chebunaywa Secondary School | 2,400,000.00 | 1,400,000.00 | Complete construction of 2No. Classrooms by roofing, plastering, wiring and flooring | 700,000.00 | Ongoing |
| 72 | Chepsaga Secondary School | 1,200,000.00 | 500,000.00 | Ongoing construction of 1No. Classroom by roofing, plastering, flooring and roofing to completion | 700,000.00 | Ongoing |
| 73 | St. John’s Cheptech Secondary School | 2,200,000.00 | 1,500,000.00 | Ongoing construction of 2No. Classrooms by roofing, plastering, flooring, wiring, painting and labelling to completion | 700,000.00 | Ongoing |
| 74 | Dr. Gimose Secondary School Jeviriri | 33,000,000.00 | 24,800,000.00 | Ongoing construction of storey building housing 8No. Classrooms on the 1st floor and administration block on the ground floor housing Principal’s office, Deputy Principal’s office, Director of Studies Office, Accounts Office, Boardroom, staffroom, reception, and store by fitting doors and windows and plastering | 4,000,000.00 | Ongoing |
| 75 | Dr. Maurice Dangana Sec. School | 14,000,000.00 | 2,000,000.00 | Ongoing construction of two-floor storey building housing 4No. Classrooms on the 2nd floor and administration block on the ground floor accommodating Principal’s office, Deputy Principal’s office, Accounts office, store, Director of Studies Office, boardroom and staffroom by slabbing 1st floor, walling and roofing to completion | 4,000,000.00 | Ongoing |
| 76 | Gamoi Secondary School | 1,700,000.00 | - | Construction of science laboratory accommodating 70 students by laying foundation, walling to lintel level | 1,000,000.00 | New |
| 77 | Gidagadi Secondary School | 1,000,000.00 | - | Construction of 1No. Classroom by laying foundation, walling, flooring, and roofing to completion | 1,000,000.00 | New |
| 78 | Gimarian Secondary School | 1,600,000.00 | 1,000,000.00 | Complete construction of 2No- 10door exhaustible pit latrine by plastering, flooring, fitting doors and windows, painting and labelling to completion | 600,000.00 | Ongoing |
| 79 | Gimengwa Secondary School | 1,000,000.00 | - | Construction of 1No. Classrooms by laying foundation, walling, plastering, roofing, fitting doors and windows, flooring, painting, facia board and labelling to completion | 1,000,000.00 | New |
| 80 | George Khaniri Secondary Jepkoyai | 1,000,000.00 | - | Renovation of 3No. classrooms by re-roofing, plastering, fitting doors and windows, flooring and painting to completion | 700,000.00 | New |
| 81 | Kapsotik Secondary School | 7,400,000.00 | - | Construction of dining hall housing 300 students by laying foundation, walling to lintel level | 2,000,000.00 | New |
| 82 | Kaptik Secondary School | 4,500,000.00 | - | Construction of twin science laboratory housing 120 students by laying foundation, walling to lintel level | 1,500,000.00 | New |
| 83 | Kinu Secondary School | 6,000,000.00 | 4,000,000.00 | Ongoing Construction of 5No. Classrooms by roofing, plastering, fitting doors and windows, painting, and labelling to completion | 2,000,000.00 | Ongoing |
| 84 | Kitwagwa Secondary School | 3,000,000.00 | 1,000,000.00 | Ongoing construction of 3No. Classroom by walling, roofing, plastering, flooring, fitting steel windows and doors awaiting painting, facia board and labelling | 1,600,000.00 | Ongoing |
| 85 | Muhaya Secondary School | 3,000,000.00 | - | Purchase of 3acres of land for school expansion | 3,000,000.00 | New |
| 86 | Muhudu Secondary School | 2,400,000.00 | 1,500,000.00 | Ongoing completion of 2No. Classrooms by roofing, plastering, flooring and painting to completion | 800,000.00 | Ongoing |
| 87 | Munzatsi Secondary School | 1,800,000.00 | - | Construction of boys dormitory housing 150 students by roofing, plastering, and fitting steel doors and windows awaiting painting, wiring, ceiling and labelling | 1,000,000.00 | New |
| 88 | Musiri Secondary School | 2,400,000.00 | 1,000,000.00 | Ongoing construction of 2No. classrooms by walling, roofing, fitting doors and windows, and flooring awaiting plastering, wiring, painting, ceiling, and labelling | 700,000.00 | Ongoing |
| 89 | Muyere Secondary School | 1,000,000.00 | - | Start construction of 1No. Classroom by laying foundation, walling, roofing, fitting doors and windows, plastering and flooring, painting, facia board and labelling to completion | 1,000,000.00 | New |
|  |  |  |  |  | 29,100,000.00 |  |
|  | Transfer to Security Projects |  |  |  |  |  |
| 90 | Deputy County Commissioner - Hamisi | 2,000,000.00 | 1,500,000.00 | Ongoing renovation of Hamisi Sub-county Headquarter by tiling, grilling windows and doors, and painting to completion | 500,000.00 | Ongoing |
| 91 | Shaviringa Assistant County Commissioner’s Office | 410,000.00 | - | Renovation of 3-roomed Assistant County Commissioner’s office by plastering, flooring and painting to completion | 400,000.00 | New |
| 93 | Gambogi Police Station | 6,800,000.00 | - | Start construction of police station housing Officer Commanding Station, Deputy Officer Commanding Station, Sub-county Criminal Investigation Officer, armoury, reception, 2No. Cells by laying foundation and walling to lintel level | 1,500,000.00 | New |
| 94 | Muhudu Chiefs Office | 1,100,000.00 | - | Construction of 3roomed chiefs office by laying foundation, walling and roofing to completion | 600,000.00 | New |
|  |  |  |  |  | 3,000,000.00 |  |
|  | Electricity Projects |  |  |  |  |  |
| 95 | Karandini Area | 400,000.00 | - | Payment to Kenya Rural Electricity Authority for installation of Transformer and power line in Karandini area | 400,000.00 | New |
|  |  |  |  |  | 400,000.00 |  |
|  | Environment |  |  |  |  |  |
| 96 | Kimarani Primary School | 600,000.00 | - | Construction of exhaustible 8-door pit latrine to completion | 600,000.00 | New |
| 97 | Givole Secondary school | 600,000.00 | - | Construction of 8-door exhaustible pit latrine to completion | 600,000.00 | New |
| 98 | Jinjini Primary School | 100,000.00 | - | Purchase a 5000litre water tank and fit on a concrete water base for water harvesting | 100,000.00 | New |
|  |  |  |  |  | 1,300,000.00 |  |
|  | GRAND TOTAL |  |  |  | 137,367,724.14 |  |

The members requested the fund account manager to hasten the same to the board for approval.

The chairman thanked all the members for considering all the ongoing projects that had been committed in the financial year 2018-2019.

MIN. 05/29/10/2019: HAMISI NG-CDF VEHICLE

The members requested the fund manager to follow up with the funds meant for purchase of office vehicle. They complained of inconveniences to staff and members on NGCDF operations.

MIN. 06/29/10/2019: ADJOURNEMNT

There being no other item to be discussed the meeting was adjourned at 05:11p.m. with a word of prayer from Miss Lujesi Jemaiyo Mary.