| NG-CDF BOARD | National Government CONSTITUENCIES DEVELOPMENT Fund |
| --- | --- |
|  | Sirisia constituency P.O BOX 55-028, Sirisia |
|  | Email: cdfsirisia@ngcdf.go.ke ¦ Website: www.ngcdf.go.ke |

NG-CDFC MEETING OF 2/12/2024 HELD AT THE CONSTITUENCY BOARD ROOM

Members present

- David Watwati                                  Chairperson

- Edwick Wanjala             		 Secretary

- Beryl Achieng			            FAM

- Emily Masolo                      		 Member

- Nancy Masakari     	 		 Member

- Linet Gidosi			            Member

- Mourice Wanda                                Member

- AF Muhammed			 DCC

- Allan Kiboi		                       Member

Agenda

- Preamble

- Confirmation of previous minutes

- Matters Arising

- Summary of on-going projects

- JSS Classrooms

- Climate Change Mitigation

- Construction of 2No. classrooms at Kamunyong’ole Primary School.

- A.I.A

- Summary of Ward Reports

- Project Proposal FY 24/25

- AOB

MIN 1. SIR/NGCDF/2/12/2024-PREAMBLE

The chair called the meeting to order after word of prayer, said by Mourice Wanda at 9:16 AM. The chairman thanked members for their commitment to attend the meeting despite being festive season.

MIN 2. SIR/NGCDF/2/12/2024-CONFIRMATION OF PREVIOUS MINUTES

The minutes of the previous meeting were proposed and confirmed by Allan Kiboi–as being the true matters discussed, then adopted by the whole committee.

MIN 3. SIR/NGCDF/2/12/2024-MATTERS ARISING

Members wanted to know if the advertisement of the NGCDFCs was effected as agreed on the previous meeting. The Fund Account Manager confirmed that the same had been done and that the Advert will run for a maximum of 14 days.

Being no matter arising, the meeting proceeded to the main agenda.

MIN 4. SIR/NGCDF/2/12/2024- SUMMARY OF ONGOING PROJECTS

The fund account manager read a list of all the ongoing projects which were submitted to NG-CDF Board during the submission of 2024/2025 financial year ongoing report. The manager explained to the committee the need to consider the ongoing projects in their 2024/2025 financial year proposal. The committee resolved that all the ongoing projects be considered for funding to completion in the FY 2024/2025 after an in-depth deliberation except for Karibuni Girls Secondary School where the committee committed that the funding would be in three phases. So that the FY 2024/2025, Ksh, 15,000,000.00 to be allocated. While the remaining bit of Ksh. 5,989,330.00 to the project completion to be allocated in the FY 2025/2026. The decision on Karibuni Girls was a result of the project being enormous. Besides, there is need to balance the funding across the constituency to avoid under developing particular wards.

MIN 5.SIR/NGCDF/2/12/2024- JSS CLASSROOMS.

The Fund Account Manager then reminded members that there was directive by NG-CDF Board to implement JSS classrooms as per MOE guidelines and welcomed members to deliberate on the above issue. After thorough deliberations, members argued that in FY 2023/24 all the JSS classrooms, both funded by MOE and NG-CDF board were all implemented as agreed, and additionally, MOE again funded JSS classrooms in the Constituency around November 2024. The Committee agreed on funding two institutions (Chwele Boys Primary School and Chebukutumi Primary School) construction of two classrooms in each for this financial year. The members agreed to fund the other JSS classrooms in FY 2025/26.

MIN 6.SIR/NGCDF/2/12/2024-CLIMATE CHANGE MITIGATION.

The Fund Account Manager then welcomed the Chairman to discuss Climate Change Mitigation as one of the activities funded by NG-CDF.

The chairman thanked the fund account manager and invited members to deliberate on climate change mitigation.

Members discussed in depth and agreed that since in the FY 2023/2024 they planted trees in 29 schools within the constituency and additionally did grassroot sensitization and seedling production in the constituency, there was no urgent need to plant more trees and that, the funds should be directed to construction of classrooms, they however agreed to do climate Change mitigation in FY 2025/2026.

MIN 7.SIR/NGCDF/2/12/2024-CONSTRUCTION OF 2NO.CLASSROOMS AT KAMUNYONGO’LE PRIMARY SCHOOL

The chairman then invited Allan Kiboi who comes from Kamunyong’ole.  Allan thanked Chairman and went ahead to explain about Kamunyong’ole primary school.

He informed members that the terrain in that area was very bad, and it would not be possible to construct 2No classrooms at the cost of Ksh 2,400,000.

Members agreed with his concern and an additional Ksh 100,000 was added, they then approved an estimated cost of Kshs 2,500,000 for construction of 2No classrooms at Kamunyong’ole primary school.

MIN 8.SIR/NGCDF/2/12/2024- A.I.A 2,056,726.48.

The fund Account Manager then informed members that the declared A.I.A from PMC account balances was 2,056,726.48 and that there was need to allocate it for FY 2024/2025.

After in-depth discussions by members, they agreed that the amount to renovate 2No. classrooms at Toloso Secondary School as the school was in a bad shape and had requested for renovations.

They all agreed that Toloso Secondary School to get a total of 5No. classrooms renovated, Two classrooms from A.I.A and Three classrooms from FY 2024/25 funding.

MIN 9. SIR/NGCDF/2/12/2024- SUMMARY OF WARD REPORT

The ward report was presented to the plenary of which there was an in-depth review of the prioritized projects. The list of projects presented during public participation were discussed per ward as follows;

Malakisi/South Kulisiru Ward

| Project Proposed | Sector | Activities |
| --- | --- | --- |
| Ndakaru Primary School | Education | Construction of classrooms |
| Kasiamo Chief’s office | Security | Construction of Chief’s office |
| Namang’ofulo primary school | Education | Construction of classrooms |
| Kasiamo Primary school | Education | Construction of classrooms |
| Maeni primary school | Education | Construction of classrooms |
| Ndakaru secondary school | Education | Construction of pit Latrines |
| Yabeko Primary school | Education | Construction of pit latrines |
| Sibanga Primary School | Education | Construction of Administration block cum classrooms |
| Sirisia Township Primary School | Education | Construction of JSS classrooms |
| Namunyu Primary School | Education | Construction of classrooms |
| Sirisia MAL Primary School | Education | Construction of classrooms |
| Muanda Primary School | Education | Construction of Pit Latrines |
| Geof Brown Primary School | Education | Purchase of Land |
| Lukaala Primary School | Education | Construction of Administration block |
| Youth/Citizens | Education | a) Construction of ICT Hub. b) Request for a school in Tembwa |
| Chongoi Girls Secondary School | Education | - Construction of a library - Construction of classrooms - Construction of twin Laboratory - Purchase of Land - Construction of administration Block |
| Chebukutumi ACK Primary School | Education | Construction of classrooms |
| Matunda Primary School | Education | Construction of classrooms |
| Ngaalasia Primary School | Education | Construction of classrooms |
| Kibeu primary school | Education | Construction of classrooms |
| Lukaala Secondary School | Education | Construction of classrooms |
| Namwesi primary school | Education | Construction of classrooms |

Namwela Ward

| Project Proposed | Sector | Activities |
| --- | --- | --- |
| Chwele Boys Primary School. | Education | Construction of classrooms |
| Kikai Boys Secondary school | Education | Construction of a library |
| Toloso Secondary School | Education | Construction of classrooms |
| Sengeteti Primary School | Education | Construction of classrooms |
| Kapkanai primary School | Education | Construction of classrooms |
| Binyenya Secondary school | Education | Construction of Dormitory |
| Binyenya Primary School | Education | Construction of Administration Block |
| Maliki Primary school | Education | Construction of classrooms |
| Wanjoya primary school | Education | Constructing of classrooms |
| Butunde primary school | Education | Construction of Administration Block Purchase of Land |
| Sibumba Primary school | Education | Construction of staff houses Purchase of Land |
| Masaba Primary School | Education | Construction of pit latrines |
| Youth/Citizens | Education | - Land for police post - ICT Hub. |

Lwandanyi Ward

| Project Proposed | Sector | Activities |
| --- | --- | --- |
| Tulienge Secondary School | Education | a) Construction of admin block b) Purchase of Land |
| Kabkara Secondary School | Education | Construction of a multipurpose Hall. |
| Tororo Primary school | Education | Construction of classrooms. |
| Kapsitet Primary School | Education | Purchase of Land |
| Khabukhoya Primary School | Education | Construction of Classrooms |
| Wamono Primary school | Education | Construction of Administration Block |
| Machakha Primary School | Education | Construction of classrooms |
| Kakaala Primary School | Education | Construction of classrooms |
| Youth/Citizens | Security | - Construction of Wamono Chief’s office - Construction of Chief’s office at Tamulega - Regional police training College - ICT Hub |
| Kaprot Primary School | Education | Construction of classrooms |
| Mayekwe Primary | Education | Construction of classrooms |
| Namundi Primary school | Education | Construction of classrooms |
| Lwakhakha primary school | Education | Construction of classrooms |
| Namawanga Primary school | Education | Construction of classrooms |
| Chebukhuyi Primary school | Education | Construction of pit Latrines |
| Chebukhuyi Secondary school | Education | Construction of classrooms |
| Butonge Primary school | Education | Construction of Classrooms |
| Kamunongole Primary school | Education | Construction of Classrooms |
| Mufungu Primary School | Education | Construction of Classrooms |
| Malakisi Muslim Secondary school | Education | Construction of classrooms |
| Lurare Primary school | Education | Construction of classrooms |
| Nambuya primary school | Education | Construction of classrooms |
| Natumbayi primary school | Education | Construction of classrooms |
| Korosiadeti Primary School | Education | Purchase of Land |
| Tororo Primary School | Education | Purchase of Land |
| Matunda Primary school | Education | Construction of classrooms |
| Tembelela primary school | Education | Construction of classrooms |
| Stabicha primary school | Education | Construction of classrooms |
| Namwesi Primary school | Education | Construction of Administration Block |
| Moses Wetangula Lurare Primary school | Education | Construction of Classrooms |
| Butonge ACK | Education | Construction of Administration block |

MIN 10. SIR/NGCDF/2/12/2024- PROJECT PROPOSAL FOR FINANCIAL YEAR 2024/2025.

The Fund account manager notified the members that the Constituency’s 2024/2025 financial year allocation was Kshs.161,497,759

She called upon members to go through the ward report and prioritize the projects.  After detailed deliberation, the committee approved the following projects for funding in the FY 2024/2025;

PROJECT PROPOSAL FINANCIAL YEAR 2024/2025

| S/No. | Project Number | Project Name | Project Activity | ESTIMATED COST TO COMPLETION | CUMULATIVE ALLOCATION PREVIOUS FYs | AMOUNT ALLOCATED CURRENT FY | CURRENT STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ADMINSTRATION AND RECCURENT EXPENDITURE |  |  |  |  |  |  |
| 1 | 4-039-217-2110000-100-2024-2025-1 | Contractual employees | Payment of 9 no. NG-CDFC staff Basic salaries. | 3,118,104 | - | 3,118,104 | New |
| 2 | 4-039-217-2110000-100-2024-2025-2 | Casual labour and internship | payment of basic wages for 1 casual and 1 intern | 480,000 |  | 480,000.00 | New |
| 3 | 4-039-217-2110000-100-2024-2025-3 | House allowance | Payment of 9 no. NG-CDFC house allowance | 324,000 |  | 324,000 | New |
| 4 | 4-039-217-2110000-100-2024-2025-4 | Transport allowance | Payment of 9no NG-CDFC transport allowance | 324,000 |  | 324,000 |  |
| 5 | 4-0039-217-2120101-100-2024-2025-4 | NSSF | Employer contribution to NSSF f0r 9 NGCDF STAFF | 225,960 | - | 225,960 | New |
| 6 | 4-039-217-2710102-100-2024-2025-5 | Gratuity-contractual employees | Payment of gratuity to 9 no. NGCDFC staff. | 966,600 | - | 966,600 | New |
| 7 | 4-0039-217-2110301-100-2024-2025-6 | Housing Levy | Employer contribution to Housing Levy for the 9 NG-CDFC staff | 56,472 |  | 56,472 | New |
| 8 | 4-039-217-2210302-100-2024-2025-7 | Accommodation - Domestic Travel | Payment of accommodation on domestic travel | 200,000 |  | 200,000 | New |
| 9 | 4-039-217-2210502-100-2024-2025-8 | Publishing and printing services | Payment of publishing and printing services | 50,000 |  | 50,000 | New |
| 10 | 4-039-217-2210504-100-2024-2025-9 | Advertising, Awareness and Publicity Campaigns | Payment of Advertising, Awareness and Publicity Campaigns | 70,000 | - | 70,000 | New |
| 11 | 4-039-217-2211301-100-2024-2025-10 | Bank service commission and charges | Payment of Bank service commission and charges | 70,000 | - | 70,000 | New |
| 12 | 4-039-217-2210801-100-2024-2025-11 | Catering Services (receptions), Accommodation, Gifts, Food and Drinks | Payment of catering Services (receptions), Accommodation, Gifts, Food and Drinks | 150,000 | - | 150,000 | New |
| 13 | 4-039-217-2210203-100-2024-2025-12 | Courier and Postal Services | Payment of Courier and Postal Services | 30,000 | - | 30,000 | New |
| 14 | 4-039-217-2210303-100-2024-2025-13 | Daily Subsistence Allowance | Payment of Daily Subsistence Allowance | 250,000 | - | 250,000 | New |
| 15 | 4-039-217-2210101-100-2024-2025-14 | Electricity | Payment of Electricity charges | 38,290 | - | 38,290 | New |
| 16 | 4-039-217-2211101-100-2024-2025-15 | General Office Supplies (papers, pencils, forms, small office equipment etc) | Purchase of General Office Supplies (fuel, papers, pencils, forms, small office equipment) | 368,439 | - | 368,439 | New |
| 17 | 4-039-217-2220101-100-2024-2025-16 | Maintenance Expenses - Motor Vehicles | Payment of Maintenance Expenses - NGCDFC Motor Vehicles, motorcycles and other transport equipment | 500,000 | - | 500,000 | New |
| 18 | 4-039-217-2210811-100-2024-2025-17 | NGCDFC allowance | Payment of NGCDFC allowance charges | 1,248,000 | - | 1,248,000 | New |
| 19 | 4-039-217-2210802-100-2024-2025-18 | Other committee expenses | Payment of Other committee expenses | 500,000 | - | 500,000 | New |
| 20 | 4-039-217-2210302-100-2024-2025-19 | Motor Vehicle Insurance | Payment of Motor Vehicle Insurance GKB 540S | 200,000 | - | 200,000 | New |
| 21 | 4-039-217-2210302-100-2024-2025-20 | Refined Fuels and Lubricants for Transport | Refined Fuels and Lubricants for Transport | 450,000 |  | 450,000 | New |
| 22 | 4-039-217-2210102-100-2024-2025-22 | Water & sewerage charges | Payment of Water & sewerage charges | 70,000 | - | 70,000 | New |
|  | TOTAL |  |  | 9,689,865 |  | 9,689,865 |  |
|  | MONITORING, EVALUATION AND CAPACITY BUILDING |  |  |  |  |  |  |
| 23 | 4-039-217-2210301-111-2024-2025-1 | Travel costs | Payment of Travel Allowance of NGCDFC, National Government officers and PMC (NGCDFC & STAFF Training) | 180,000 | - | 180,000 | New |
| 24 | 4-039-217-2210302-111-2024-2025-2 | Accommodation - Domestic Travel | Payment of accommodation on domestic travel | 550,000 | - | 550,000 | New |
| 25 | 4-039-217-2210302-111-2024-2025-3 | Daily Subsistence Allowance | Payment of travel Allowance of NGCDFC, National Government officers and PMC (NGCDFC & STAFF Training) | 650,000 |  | 650,000 |  |
| 26 | 4-039-217-2210710-111-2024-2025-3 | Catering Services (receptions), Accommodation, Gifts, Food and Drinks | Payment of catering Services (receptions), Accommodation, Gifts, Food and Drinks | 571,309 | - | 571,309 | New |
| 27 | 4-039-217-2210710-111-2024-2025-4 | Hire of Training Facilities and Equipment | Hire of Training Facilities and Equipment (NGCDFC, STAFF &PMC Training) | 200,000 | - | 200,000 | New |
| 28 | 4-039-217-2210710-111-2024-2025-6 | NGCDFC allowance | Payment of NGCDFC allowance | 1,200,000 | - | 1,200,000 | New |
| 29 | 4-039-217-2210710-111-2024-2025-7 | Refined Fuels and Lubricants for Transport | Purchase of Refined Fuels and Lubricants for Transport of GK vehicles | 550,000 | - | 550,000 | New |
| 30 | 4-039-217-2210710-111-2024-2025-8 | Remuneration of Instructors and Contract Based Training Services | Payment of Instructors and Contract Based Training Services (NG-CDFC, STAFF &PMC Training) | 200,000 | - | 200,000 | New |
| 31 | 4-039-217-2210710-111-2024-2025-9 | Telephone, Telex, Facsimile and Mobile Phone Service | Payment of Telephone expenses | 98,817 | - | 98,817 | New |
| 32 | 4-039-217-2210710-111-2024-2025-10 | Travel Allowance on training | Payment of Travel Allowance of NGCDFC, National Government officers and PMC (NGCDFC, STAFF &PMC Training) | 180,000 | - | 180,000 | New |
| 33 | 4-039-217-2211101-111-2024-2025-11 | General Office Supplies (Papers, Pencils, Forms, Small Office Equipment etc.) | payment of General Office Supplies (Papers, Pencils, Forms, Small Office Equipment etc.) | 320,000 |  | 320,000 | New |
| 34 | 4-039-217-2210502-111-2024-2025-12 | Publishing and printing services | Payment of publishing and printing services | 100,000 |  | 100,000 | New |
| 35 | 4-039-217-2210703-111-2024-2025-13 | Production and printing of Training materials | Payment of production and printing of Training materials | 44,806 |  | 44,806 | New |
|  | TOTAL |  |  | 4,844,932 |  | 4,844,932 |  |
|  | BURSARY |  |  |  |  |  |  |
| 36 | 4-039-217-2640101-103-2024/2025-1 | Bursary Secondary Schools | Payment of bursary to needy students in secondary schools | 38,000,000 | - | 38,000,000 | New |
| 37 | 4-039-217-2640102-103-2024/2025-2 | Bursary Tertiary Institutions | Payment of bursary to needy students in tertiary institutions | 23,000,000 | - | 23,000,000 | New |
| 38 | 4-039-217-2640105-103-2024-2025-3 | Bursary Special Institutions | Payment of bursary to needy students in special Institutions | 3,599,103 | - | 3,599,103 | New |
|  | TOTAL |  |  | 64,599,103 |  | 64,599,103 |  |
|  | EMERGENCY RESERVE |  |  |  |  |  |  |
| 39 | 4-039-217-2640200-101-2024-2025-1 | Emergency Reserve | To cater for any unforeseen occurrences in the constituency during the financial year |  | - | 8,499,879 | New |
|  | TOTAL |  |  |  |  | 8,499,879 |  |
|  | PRIMARY SCHOOL PROJECTS |  |  |  |  |  |  |
| 40 | 4-039-217-2630209-104-2024-2025-1 | Kamunyong’ole Primary School | Construction to completion of 2No. classrooms. | 2,500,000 |  | 2,500,000 |  |
| 41 | 4-039-217-2630209-104-2024-2025-2 | Mufungu Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
| 42 | 4-039-217-2630209-104-2024-2025-3 | Machakha Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
| 43 | 4-039-217-2630209-104-2024-2025-4 | Namundi Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
| 44 | 4-039-217-2630209-104-2024-2025-5 | Lwakhakha Primary school | Construction to completion of 3No. classrooms | 3,600,000 |  | 3,600,000 |  |
| 45 | 4-039-217-2630209-104-2024-2025-6 | Chebukutumi Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
| 46 | 4-039-217-2630209-104-2024-2025-7 | Matunda ACK Primary School | Construction to completion of 2No. classrooms. | 2,400,000 |  | 2,400,000 |  |
| 47 | 4-039-217-2630209-104-2024-2025-8 | Lurare Primary School | Construction to completion of 2No. classrooms. | 2,400,000 |  | 2,400,000 |  |
| 48 | 4-039-217-2630209-104-2024-2025-9 | Kasiamo Primary School | Construction to completion of 2No. classrooms. | 2,400,000 |  | 2,400,000 |  |
| 49 | 4-039-217-2630209-104-2024-2025-10 | Chwele Boys Primary School | Construction to completion of 2No. classrooms. | 2,400,000 |  | 2,400,000 |  |
| 50 | 4-039-217-2630209-104-2024-2025-11 | Nambuya ACK Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
| 51 | 4-039-217-2630209-104-2024-2025-12 | Kibeu Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
| 52 | 4-039-217-2630209-104-2024-2025-13 | Namangofulo Primary School | Construction to completion of 2No. classrooms | 2,400,000 |  | 2,400,000 |  |
|  | TOTAL |  |  | 32,500,000 |  | 32,500,000 |  |
|  | SECONDARY SCHOOL PROJECTS |  |  |  |  |  |  |
| 53 | 4-0037-204-2630210-104-2024-2025-1 | Chwele Girls Secondary School The project was initiated in 23-24FY with an allocation of 30M. The NG-CDFC submitted certified technical drawings and a BoQ amounting to 39.5M of the project. The documents were reviewed by the Boards technical team and they satisfied technical requirements. This allocation will be adequate for project completion. | Additional funds for the completion of construction of a 1500 students capacity dining hall comprising of a dining area and kitchen: roofing, flooring, fixing of windows and doors, electrical and mechanical works, plastering, and painting. | 39,500,000 |  | 9,500,000 |  |
| 54 | 4-0037-204-2630210-104-2024-2025-2 | Karibuni Girls Secondary School The project was initiated in 23-24FY with an allocation of 30M. The NG-CDFC submitted certified technical drawings and a BoQ amounting to Kshs.28.9M of the project. The documents were reviewed by the Boards technical team and they satisfied technical requirements. The NG-CDFC has committed to allocate the balance of Kshs.5.9M in 25-26FY for project completion. | Additional funds for completion of construction of the tuition cum administration block comprising of 3 offices and 8 classrooms up to roofing level: laying of the suspended slab, erection of columns, walling, roofing and fixing of windows and doors. | 28,989,330 | 8,000,0000 | 15,000,000 |  |
| 55 | 4-0037-204-2630210-104-2024-2025-3 | Malakisi Muslim Secondary School | Construction to completion of 3No. classrooms | 3,600,000 |  | 3,600,000 |  |
| 56 | 4-0037-204-2630210-104-2024-2025-4 | Toloso Secondary School NG-CDFC to submit certified cost estimates. | Renovation to completion of 3No classrooms: Roofing, flooring, installation of doors and windows, installation of a ramp, electrical works, painting, branding and labelling. | 4,063,977 |  | 4,063,977 |  |
|  | TOTAL |  |  | 76,153,307 |  | 32,163,977 |  |
|  | OTHERS |  |  |  |  |  |  |
| 57 | 4-39-217-2211310-108-2023/24-001 | Sirisia Digital HUB | Construction to completion of the Standard model Digital hub | 9,200,003 |  | 9,200,003 |  |
|  | TOTAL |  |  | 9,200,003 |  | 9,200,003 |  |
|  | GRAND TOTAL |  |  | 196,987,210 |  | 161,497,759 |  |

MIN 11. SIR/NGCDF/2/12/2024- ADJOURNMENT.

Being no any other business, the meeting was adjourned at 16:45hrs

ANNEX 1

ADMINISTRATION, GOODS AND SERVICES

|  | EXPENDITURE ITEMS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | Description | Scale | Number | Rate | Total Amount pm | Total Amount pa |
|  | Contractual Employees |  |  |  |  |  |
|  | Accounts Assistant | CSG 10 | 1 | 44,040 | 44,040 | 528,480 |
|  | Security officer | CSG 10 | 1 | 23,182 | 23,182 | 278,184 |
|  | Clerical officer | CSG 11 | 1 | 37,732 | 37,732 | 452,784 |
|  | Records Management Assistant | CSG 12 | 1 | 44,040 | 44,040 | 528,480 |
|  | Clerk of works | CSG 12 | 1 | 30,100 | 30,100 | 361,200 |
|  | Driver | CSG 12 | 1 | 24,182 | 24,182 | 290,184 |
|  | Office Assistant | CSG 13 | 1 | 23,182 | 23,182 | 278,184 |
|  | Tea girl | CSG 13 | 1 | 16,692 | 16,692 | 200,304 |
|  | Receptionist | CSG 13 | 1 | 16,692 | 16,692 | 200,304 |
| Sub Total |  |  | 9 |  | 259,842 | 3,118,104 |
|  | Casual Labour and Internship |  |  |  |  |  |
|  | Office assistant |  | 2 | 20 | 40 | 480,000 |
| Sub Total |  |  | - |  |  | 480,000 |
|  | House Allowance |  |  |  |  |  |
|  | Accounts Assistant | CSG 10 | 1 | 3,000 | 3,000 | 36,000 |
|  | Security officer | CSG 10 | 1 | 3,000 | 3,000 | 36,000 |
|  | Clerical officer | CSG 12 | 1 | 3,000 | 3,000 | 36,000 |
|  | Records Management Assistant | CSG 12 | 1 | 3,000 | 3,000 | 36,000 |
|  | Clerk of works | CSG 12 | 1 | 3,000 | 3,000 | 36,000 |
|  | Driver | CSG 12 | 1 | 3,000 | 3,000 | 36,000 |
|  | Tea girl | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
|  | receptionist | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
|  | Office Assistant | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
| Sub Total |  |  | 9 |  | 27,000 | 324,000 |
|  | Transport Allowance |  |  |  |  |  |
|  | Accounts Assistant | CSG 10 | 1 | 3,000 | 3,000 | 36,000 |
|  | Security officer | CSG 10 | 1 | 3,000 | 3,000 | 36,000 |
|  | Clerical officer | CSG 12 | 1 | 3,000 | 3,000 | 36,000 |
|  | Records Management Assistant | CSG 12 | 1 | 3,000 | 3,000 | 36,000 |
|  | Clerk of works | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
|  | Driver | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
|  | Tea girl | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
|  | receptionist | CSG 13 | 1 | 3,000 | 3,000 | 36,000 |
|  | Office Assistant | CSG 14 | 1 | 3,000 | 3,000 | 36,000 |
| Sub Total |  |  | 9 |  | 27,000 | 324,000 |
|  | Gratuity-Contractual Employees |  |  |  |  |  |
|  | Accounts Assistant | CSG 11 | 1 | 44,040 | 13,652 | 163,824 |
|  | Security officer | CSG 11 | 1 | 23,182 | 7,186 | 86,232 |
|  | Clerical officer | CSG 12 | 1 | 37,732 | 11,697 | 140,364 |
|  | Records Management Assistant | CSG 12 | 1 | 44,040 | 13,652 | 163,824 |
|  | Clerk of works | CSG 13 | 1 | 30,100 | 9,331 | 111,972 |
|  | Driver | CSG 13 | 1 | 24,182 | 7,496 | 89,952 |
|  | Tea girl | CSG 13 | 1 | 16,692 | 5,175 | 62,100 |
|  | Receptionist | CSG 13 | 1 | 16,692 | 5,175 | 62,100 |
|  | Office Assistant | CSG 14 | 1 | 23,182 | 7,186 | 86,232 |
| Sub Total |  |  | 9 |  | 80,550 | 966,600 |
|  | Employer Contribution to NSSF |  |  |  |  |  |
|  | Accounts Assistant | CSG 11 | 1 | 3,002 | 3,002 | 36,024 |
|  | Security officer | CSG 11 | 1 | 1,751 | 1,751 | 21,012 |
|  | Clerical officer | CSG 12 | 1 | 2,623 | 2,623 | 31,476 |
|  | Records Management Assistant | CSG 12 | 1 | 3,002 | 3,002 | 36,024 |
|  | Clerk of works | CSG 13 | 1 | 2,166 | 2,166 | 25,992 |
|  | Driver | CSG 13 | 1 | 1,811 | 1,811 | 21,732 |
|  | Tea girl | CSG 13 | 1 | 1,362 | 1,362 | 16,344 |
|  | Receptionist | CSG 13 | 1 | 1,362 | 1,362 | 16,344 |
|  | Office Assistant | CSG 14 | 1 | 1,751 | 1,751 | 21,012 |
| Sub Total |  |  | 9 |  | 18,830 | 225,960 |
|  | Employer Contribution to Housing levy |  |  |  |  |  |
|  | Accounts Assistant | CSG 11 | 1 |  | 751 | 9,012 |
|  | Security officer | CSG 11 | 1 |  | 438 | 5,256 |
|  | Clerical officer | CSG 12 | 1 |  | 653 | 7,836 |
|  | Records Management Assistant | CSG 12 | 1 |  | 751 | 9,012 |
|  | Clerk of works | CSG 13 | 1 |  | 542 | 6,504 |
|  | Driver | CSG 13 | 1 |  | 453 | 5,436 |
|  | Tea girl | CSG 13 | 1 |  | 340 | 4,080 |
|  | Receptionist | CSG 13 | 1 |  | 340 | 4,080 |
|  | Office Assistant | CSG 15 | 1 |  | 438 | 5,256 |
| Sub Total |  |  | 9 |  | 4,706 | 56,472 |
|  | USE OF GOODS AND SERVICES |  |  |  |  |  |
|  | Utilities, Supplies and Services |  |  |  |  |  |
| 2210101 | Electricity |  |  |  |  | 38,290 |
| 2210102 | Water & Sewerage Charges |  |  |  |  | 70,000 |
| 2210103 | Gas Expenses |  |  |  |  |  |
| 2210104 | Office Rent |  |  |  |  | - |
|  | Communication, Supplies and Services |  |  |  |  |  |
| 2210201 | Telephone, Telex, Facsimile and Mobile Phone Service |  |  |  |  |  |
| 2210202 | Internet Connections |  |  |  |  | - |
| 2210203 | Courier and Postal Services |  |  |  |  | 30,000 |
|  | Domestic Travel and Subsistence & Other Transport Costs |  |  |  |  |  |
| 2210301 | Travel Costs (Airlines, Bus, Railway, Mileage Allowances, etc.) | Persons | xxx |  |  |  |
| 2210302 | Accommodation - Domestic Travel | Persons | 10 | 4tavels | 5000 | 200,000 |
| 2210303 | Daily Subsistence Allowance | Persons | 10 | 5 travels | 5,000 | 250,000 |
|  | Printing, Advertising and Information Supplies & Services |  |  |  |  |  |
| 2210502 | Publishing and Printing Services |  |  |  |  | 50,000 |
| 2210503 | Subscriptions to Newspapers, Magazines and Periodicals |  |  |  |  |  |
| 2210504 | Advertising, Awareness and Publicity Campaigns |  |  |  |  | 70,000 |
| 2210604 | Hire of Transport |  |  |  |  |  |
|  | Hospitality Supplies and Services |  |  |  |  |  |
| 2210801 | Catering Services (Receptions), Accommodation, Gifts, Food and Drinks |  |  |  |  | 150,000 |
| Sub Total |  |  |  |  |  | 858,290 |
|  | Committee Expenses |  |  |  |  |  |
| 2210802 | Other Committee Expenses | Members | 9 | 10 functions | 5,000 | 450,000 |
|  |  | Chair | 1 | 10 | 5,000 | 50,000 |
| 2210811 | NGCDFC Allowance | Members | 9 | 24sittings | 5,000 | 1,080,000 |
|  |  | Chair | 1 | 7,000 | 14,000 | 168,000 |
| Sub Total |  |  |  |  |  | 1,748,000 |
|  | Insurance Costs |  |  |  |  |  |
| 2211308 | Legal Dues/fees, Arbitration and Compensation Payments |  |  |  |  |  |
|  | Specialised Materials and Services |  |  |  |  |  |
| 2211016 | Purchase of Uniforms and Clothing - Staff |  |  |  |  |  |
|  | Office and General Supplies and Services |  |  |  |  |  |
| 2211101 | General Office Supplies (Papers, Pencils, Forms, Small Office Equipment etc.) |  |  |  |  | 368,440 |
| 2211102 | Supplies and Accessories for Computers and Printers |  |  |  |  |  |
| 2211103 | Insurance |  |  |  |  | 200,000 |
|  | Fuel, Oil & Lubricants |  |  |  |  |  |
| 2211201 | Refined Fuels and Lubricants for Transport |  |  |  |  | 450,000 |
|  | Refined Fuels and Lubricants - Other |  |  |  |  |  |
|  | Other Fuels (wood, charcoal, cooking gas etc.) |  |  |  |  |  |
|  | Other Operating Expenses |  |  |  |  |  |
| 2211301 | Bank Service Commission and Charges |  |  |  |  | 70,000 |
| 2211305 | Contracted Guards and Cleaning Services |  |  |  |  |  |
| 2211310 | Contracted Professional Services - e.g. Strategic Plan |  |  |  |  |  |
| 2211311 | ICT Hubs |  |  |  |  |  |
|  | Routine Maintenance - Vehicles and Other Transport Equipment |  |  |  |  |  |
| 2220101 | Maintenance Expenses - Motor Vehicles |  |  |  |  | 500,000 |
|  | Routine Maintenance - Other Assets |  |  |  |  |  |
| 2220202 | Maintenance of Office Furniture and Equipment |  |  |  |  |  |
| 2220205 | Buildings Insurance |  |  |  |  |  |
| Sub Total |  |  |  |  |  | 1,588,440 |
| TOTAL |  |  |  |  |  | 9,689,866 |