WEBUYE WEST NG-CDFC MEETING HELD ON 31ST AUGUST 2017 AT THE CDF BOARDROOM AT 10:00 AM.

NG-CDFC MEETING 2

PRELIMINARIES

1. Prayer

2. Introduction

3. Apologies

3. Adoption of Agenda

4. Communication from Chair

AGENDA

1. Reading and confirmation of previous minutes

2. Matters arising

3. Project proposals 2017/2018

5. Payments

6. A.O.B

MEMBERS PRESENT

1. PETER AMUTALLAH                             		CHAIRMAN

2. CALEB MUSEE SIMIYU                        		 SECRETARY

3. GEORGE SHIBANDA                			FAM

4. ESTHER SIMIYU 			           		MEMBER

5. MARY BUTASI					MEMBER

6. ELIUD WEPUKHULU                            		MEMBER

7. EMMANUEL BARASA				MEMBER

8. KIZITO KISIANG’ANI           		 	MEMBER

9. ROBERT .K. KORIR	                  		ACC

IN ATTENDANCE

- ANDREW NGEIYWA                     		 COM

- JACKSON SHIKUTWA			PWD

- EZEKIEL MUGITA				DA

NG-CDFC WBY.W/MIN-01/31/8/17 PRELIMINARIES

1. Prayer

The meeting was called to order at 9:57am with a word of prayer from Mary Butasi. The chairman welcomed members to the meeting and thanked them for the good work. He asked the C.O.M to pass the committees congratulation message to the Area MP Hon. Daniel Wanyama for winning the elections and also wished every member well. The members unanimously adopted the agenda of the day.

NG-CDFC WBY.W/MIN-02/31/8/17 READING AND CONFIRMATION OF PREVIOUS MINUTES

The minutes of the previous meeting held on …………………were read by the secretary. They were proposed by Kizito Kisiang’ani and seconded by Mary Butasi as a true record of the deliberations. The members unanimously confirmed the minutes as true record.

ACCs REMARKS

- The ACC appreciated every member for attending the meeting.

- He commended on the value of construction in the region and asked the Public Works to look on the values again.

- The contractors should be put on task to work as per the work given to them to get value for money.

NG-CDFC WBY.W/MIN-03/31/8/17 MATTERS ARISING

- Correction on member’s present name Amtallah misspelled as Amatallah.

- The FAM said the work plan for the FY 2017/2018 to be tabled in the next meeting.

- The oversight committee to be put in place.

- The FAM clarified on the Audit queries and said that the response had been given back to the auditor.

- The issue of youths and sports it was to be handled with great concern.

NG-CDFC WBY.W/MIN-04/31/8/17 PROJECT PROGRESS REPORT

On project progress report; is as the attached report from the Public Works. The members discussed and were not happy with some contractors.

NG-CDFC WBY.W/MIN-05/31/8/17: PROJECT PROSALS 2017/2018

The FAM explained that allocation and statutory allocations for financial year 17/18 as bellow

- The constituency was allocated 101,416,090.

- Statutory allocation

- Bursary 			25%	Kshs 25,354,022

- Emergency 			5%	Ksh 5,337,689

- Administration & M&E	9%      Ksh  8,930,000

- Constituency innovation hubs no                  Ksh 4,677,028

Totals for Statutory and Conditional             Ksh 44,298,739

Members discussed proposal from the 4 wards : Sitikho, Misikhu , Matulo and Bokoli and prioritized the following projects after considering issues of priority, ongoing projects to be given first consideration regional balancing .

Having gone through the proposal for the f/y 2017/2018 it was approved by Eliud Wepukhulu and seconded by Esther Simiyu.

- Education projects                                        Ksh 49,852,911

- Environments                                                Ksh     500,000

- Sports                                                            Ksh     378,741

- Security                                                         Ksh   4,385,700

Totals for Sectors                                          Ksh 55,117,352

The complete list of projects approved by the committee is as below:

| NO | Project Name | ward | Original Cost | Cumulative allocation | Project activity | Balance to complete | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Ndurusia Primary School | Bokoli | 4,000,000 | - | Construction of 3 classrooms | 1,200,000 | New |
| 2 | St Anthony school for the deaf | Matulo | 6,500,000 | 3,400,000 | Completion of Admn block plastering, Floor screed fittings and finishes | 4,000,000 | Ongoing |
| 3 | Webuye Muslim Pry sch | Matulo | 16,863,905 | 9,520,000 | Completion of 1 storey block of 6 classrooms walling, roofing and finishes | 7,343,905 | Ongoing |
| 4 | Chengoli Primary School | Misikhu | 4,000,000 | - | Construction of 3 classrooms | 3,600,000 | New |
| 5 | Lukhuna Pry sch | Misikhu | 3,599,606 | 2,300,000 | Completion of 3 classrooms Plasterworks, floor screed, painting and finishes | 1,299,606 | Ongoing |
| 6 | Manani pry school | Misikhu | 4,000,000 | - | Construction of 3 classrooms | 3,600,000 | New |
| 7 | Mang'ana Pry sch | sitikho | 3,599,606 | 2,300,000 | Construction of 3 classrooms | 3,600,000 | New |
| 8 | Bituyu Pry sch | Sitikho | 3,539,653 | 2,400,000 | Completion of 3 classrooms Plasterworks, floor screed, painting and finishes | 1,139,653 | Ongoing |
| 9 | Kuywa pry sch | sitikho | 3,646,495 | 3,150,000 | Completion of 3 classrooms Plasterworks, floor screed, painting and finishes | 250,000 | Ongoing |
| 10 | Webuye SA Pry School | Matulo | 7,000,000 | - | Purchase of 51 Seater School Bus | 6,500,000 | New |
| 11 | Bunjosi Pry School | Misikhu | 4,000,000 | - | Construction of 3 classrooms | 3,600,000 | New |
| 12 | Makhonge Primary School | Misikhu | 500,000 | - | Fabrication of 100 Lockable School Desks With Chairs | 500,000 | New |
| 13 | Bituyu Pry sch | Sitikho | 500,000 | - | Fabrication of 100 Lockable School Desks With Chairs | 500,000 | New |
| 15 | Misikhu Friends pry sch | Misikhu | 1,800,000 | 1,400,000 | Completion of 2 classrooms Plasterworks, floor screed, painting and finishes | 300,000 | New |
| 16 | Sirende Sec School | Misikhu | 6,400,000 | 4,525,000 | Final payment of School bus | 1,875,000 | Ongoing |
| 17 | Brendah girls Misikhu secondary sch | Misikhu | 6,929,000 | 6,279,665 | Completion of a dormitory plasterworks, floor screed, painting and finishes. | 649,335 | Ongoing |
| 19 | Misikhu Friends Boys High sch | Misikhu | 8,812,885 | 5,850,000 | Completion of a dormitory plasterworks, floor screed, painting and finishes. | 2,962,885 | Ongoing |
|  | Sitikho secondary sch | Sitikho | 7,670,865 | 7,220,000 | Completion of a dormitory plasterworks, floor screed, painting and finishes. | 450,865 | Ongoing |
| 20 | Ngwelo Sec School | Sitikho | 7,650,384 | 6,500,000 | Completion of a dining hall roofing plasterworks, floor screed, painting and finishes. | 2,481,662 | Ongoing |
| 21 | Chebosi SA Sec School | Bokoli | 2,000,000 | 0 | Construction of 250M Capacity Septic Tank | 1,000,000 | New |
| 23 | Sitikho Sec School | Sitikho | 2,000,000 | 0 | Construction of 250 Capacity Septic Tank | 1,500,000 | New |
| 24 | Misikhu Friends Boys High sch | Misikhu | 2,000,000 | 0 | Construction of 250 Capacity Septic Tank | 1,500,000 | New |
| 25 | Bokoli chiefs office | Bokoli | 5,500,000 | 300,000 | Completion of chiefs office roofing plastering, Floor screed fittings and finishes | 2,500,000 | Ongoing |
| 27 | Township chiefs office | Matulo | 3,906,305 | 3,120,605 | Completion of chiefs office plastering, Floor screed fittings and finishes | 785,700 | Ongoing |
| 28 | Bukholi Police post | Sitikho | 1,600,000 | 0 | Drilling of borehole and installation of solar powered Water Pump | 1,100,000 | New |
| 29 | Secondary Bursaries | Constituency | 10,000,000 | 0 | To cater for education bursary for needy and deserving secondary school students in the constituency | 10,354,022 | New |
| 31 | Tertiary Bursaries | Constituency | 15,000,000 | 0 | To cater for education bursary for needy and deserving tertiary school students in the constituency | 15,000,000 | New |
| 32 | Employee salaries office admin | Constituency | 4,200,000 | 0 | Payment of NGCDF staff salaries and gratuity | 4,065,600 | New |
| 33 | Goods and services office admin | Constituency | 1,560,033 | 0 | Advertisements, publications, and public awareness, office utility bills, stationery and motor vehicle operating costs | 1,029,200 | New |
| 34 | NSSF office admin | Constituency | 80,000 | 0 | Payment of NSSF deductions | 85,200 | New |
| 36 | Committee expenses office admin | Constituency | 1,200,000 | 0 | Payment of NGCDF sitting allowances, transport and conferences | 1,000,000 | New |
| 38 | Emergency | Constituency | 5,337,689 | 0 | Unallocated amount to be available for emergencies that may occur within the constituency | 5,337,689 | New |
| 39 | Monitoring and evaluation CDFC/PMC capacity building | Constituency | 1,750,000 | 0 | Monitoring & evaluation goods and services committee expenses CDFC/PMC capacity building | 1,750,000 | New |
| 40 | Committee expenses | Constituency | 500,000 | 0 | Payment committee sitting allowances, transport and conferences | 500,000 | New |
| 41 | Goods and services | Constituency | 500,000 | 0 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence | 500,000 | New |
| 41 | Development of 5 yr constituency strategic plan | Constituency | 3,500,000 | 0 | Development of 5 year strategic plan for the constituency | 2,000,000 | New |
| 42 | Brendah girls Misikhu secondary sch | Misikhu | 1,169,257 | 0 | Setting up of Constituency innovation hub | 1,169,257 | New |
| 43 | NGCDF office Matisi | Bokoli | 1,169,257 | 0 | Setting up of Constituency innovation hub | 1,169,257 | New |
| 44 | Bokoli Boys Sec sch | Bokoli | 1,169,257 | 0 | Setting up of Constituency innovation hub | 1,169,257 | New |
| 45 | Kuywa sec sch | sitikho | 1,169,257 | 0 | Setting up of Constituency innovation hub | 1,169,257 | New |
| 46 | `Environment | Constituency | 2,000,000 | 0 | Establishment of green zones at Chebosi Girls and Manani pry sch School | 500,000 | New |
| 47 | Sports | Constituency | 2,000,000 | 0 | Purchase of Equipments for winning teams in soccer tournaments Misikhu Location Team, Sirende Location Team, Miendo Location Team, Bokoli Location Team, Sitikho Location Team and Webuye Location Team | 378,741 | New |
|  | TOTAL |  |  |  |  | 101,416,091 |  |

NG-CDFC WBY.W/MIN-06/31/8/17: PAYMENTS

- NGCDFC meeting allowances Kshs. 67,000

- Central farmers garage for service  Ksh   45,274.80

- Purchase of water accessories         Ksh 110,000.00

- Evaluation committee allowances Ksh     18,000.00

- Installation of Public notice board at NG-CDF office Ksh 50,000

- Supply of fuel Ksh 100,000 for NG-CDF to suez energy

There being no other business, the meeting ended at 13:00 hrs with a word of prayer from Caleb Simiyu.

NG-CDFC CHAIRMAN …………………………………    DATE……………………………

NG- CDFC SECRETARY ……………………………      DATE………………………………

MINUTES SIGNED AT THE NEXT MEETING

NG-CDFC CHAIRMAN ……………………………………   DATE……………………………

NG- CDFC SECRETARY …………………………………      DATE…………………………