MINUTES OF BUTULA NG CDFC MEETING HELD ON 22ND NOVEMBER, 2018 AT BUTULA NG CDF BOARDROOM.

Members Present

Name						Designation

- Allan Odipo					Chairperson

- Coleta Ayomba Ong’ong’o			Secretary

- Moses Ochowa Warinda			Member

- Phoebe Lucy Bwibo				Member

- Isah Atinda Kukuya				Member

- Ann Anyango					Member

- Winston Murungi				Deputy County Commissioner

- Winston Lihanda				Fund Account Manager

Agenda

- Preliminaries

- Reading & confirmation of previous minutes

- Matters arising

- Approval of Project Proposals - 2018/2019 - F/Y

- A.O.B

MIN 1 BTL NGCDFC/22/11/2018: PRELIMINARIES.

The Chairperson called the meeting to order at 1000hrs with an opening prayer led by Isah Atinda Kukuya. The Chairperson welcomed members present and thanking each one of them for taking time to attend the meeting.

MIN 2 BTL NGCDFC/22/11/2018: CONFIRMATION OF PREVIOUS MINUTES.

The Secretary took the committee through the minutes of previous meeting which were proposed by Ann Anyango and seconded by Phoebe Lucy Bwibo and was later adopted as a true record of the previous proceedings.

MIN 3 BTL NGCDFC/22/11/2018: MATTERS ARISING.

- On MIN 4, it was noted that the project proposals were forwarded to the NG CDF Board.

MIN 4 BTL NGCDFC/22/11/2018: APPROVAL OF PROJECT PROPOSALS - 2018/2019 F/Y

The FAM tabled the NG CDF Board Circular Ref. NG-CDF BOARD/CIRCULAR /Vol. II (008) dated 30th October, 2018 that outlined requirements for preparation and submission of project proposals for board approval.

It was noted that Butula Constituency had been allocated Kes. 109,040,875.52 in 2018/19

financial year.

The secretary further tabled the ward report that was adopted by the committee.

After discussions it was unanimously agreed upon that the following project proposals be forwarded to the NG CDF Board for consideration of approval and further funding.

| S/NO | SECTOR | AMOUNT |  | PROJECT NAME | PROJECT ACTIVITY | AMOUNT ALLOCATED | CURRENT STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ADMINISTRATION & RECURRENT | 6,542,453 | 1 | Employees Salaries | Payment of NG CDFC staff salaries and gratuity. | 2,542,453 | Ongoing |
|  |  |  | 2 | Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel & subsistence and office tea. | 2,800,000 | Ongoing |
|  |  |  | 3 | N.S.S.F | Payment of N.S.S.F deductions. | 150,000 | Ongoing |
|  |  |  | 4 | N.H.I.F | Payment of N.H.I.F deductions. | 50,000 | Ongoing |
|  |  |  | 5 | Committee Expenses | Payment of committee sitting allowances, transport, conferences | 1,000,000 | Ongoing |
| 2 | MONITORING, EVALUATION & CAPACITY BUILDING | 3,271,227 | 1 | Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, airtime, travel and subsistence. | 1,271,227 | Ongoing |
|  |  |  | 2 | Committee Expenses | Payment of committee sitting allowances, transport, conferences etc | 1,000,000 | Ongoing |
|  |  |  | 3 | NG CDFC/PMC Capacity Building | Undertake training of the PMCs/NG CDFCs on NG CDF related issues. | 1,000,000 | Ongoing |
| 3 | EDUCATION BURSARY | 21,000,000 | 1 | Bursary Secondary School | Provision of bursary awards to needy students in secondary education institutions. | 11,000,000 | Ongoing |
|  |  |  | 2 | Bursary Tertiary Institutions | Provision of bursary awards to needy students in tertiary institutions. | 10,000,000 | Ongoing |
| 4 | PRIMARY SCHOOL PROJECTS | 16,200,000 | 1 | Sirandala Primary School | Construction of (4) classrooms to completion. | 4,000,000 | New |
|  |  |  | 2 | Bukhakhala Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 3 | Busibi Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 4 | St. Augustine Butunyi Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 5 | Khunyangu Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes - Kes.700,000. Installation of 24 - metre high mast, 10 km radius coverage lightening arrestor - Kes. 2,600,000 | 3,300,000 | New |
|  |  |  | 6 | Ekanjala Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 7 | Butula Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 8 | Musibiriri Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 9 | Siribo Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 10 | Mungabwa Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 11 | Bwaliro Primary School | Renovation of (3) classrooms - repair of floor, repair of wall, fittings & finishes | 700,000 | New |
|  |  |  | 12 | Bulwani Primary School | Installation of 24 - metre high mast, 10 km radius coverage lightening arrestor - Kes. 2,600,000 | 2,600,000 | New |
| 5 | SECONDARY SCHOOL PROJECTS | 13,000,000 | 1 | Buduma Girls Secondary School | Acquisition of land for expansion - 2 acres. | 2,000,000 | New |
|  |  |  | 2 | Kingandole Secondary School | Purchase of School Bus - 51 Seater | 3,000,000 | Ongoing |
|  |  |  | 3 | Sibembe Secondary School | Construction of (1) classroom to completion | 1,000,000 | New |
|  |  |  | 4 | Simuli Secondary School | Construction of (1) classroom to completion | 1,000,000 | New |
|  |  |  | 6 | Bumala AC Secondary School | Construction of Tuition Block - walling, roofing, finishes & fittings. | 2,000,000 | Ongoing |
|  |  |  | 7 | Buhuyi Secondary School | Renovation of dormitory - Replacement of roof, repair of floor, repair of wall, fittings & finishes. | 2,000,000 | New |
|  |  |  | 8 | Bulwani Secondary School | Construction of (2) classrooms completion | 2,000,000 | New |
| 5 | TERTIARY INSTITUTION PROJECTS | 17,000,000 | 1 | Butula Technical and Vocational Education Training | Construction of (1) workshop, (3) lecture rooms & (1) office to completion - Kes. 10,000,000 & Acquisition of land - 10 acres @ Kes. 4,500,000 | 14,500,000 | New |
|  |  |  | 2 | Benga Technical Training Institute | Construction of Multi-Storey Students’ Hostel to cater for a capacity of 100 students | 2,500,000 | Ongoing |
| 6 | SECURITY PROJECTS | 10,226,568 | 1 | Burinda Chief Camp | Construction of a Storey Administration Block - sub structure, walling & roofing | 4,000,000 | Ongoing |
|  |  |  | 2 | Bukhalalire Chief Camp | Construction of an Administration Block - walling & roofing | 2,000,000 | Ongoing |
|  |  |  | 3 | Bumala Police Station | Construction of Administration Block to completion | 4,226,568.07 | New |
| 7 | SPORTS ACTIVITIES | 2,180,817 | 1 | Sports Activities | Organizing of tournaments & Purchase of sports kits i.e. balls, uniforms for Marachi East, Marachi West, Marachi Central, Kingandole, Marachi North, Elugulu teams in the Constituency @ 363,469.50. | 2,180,817 | Ongoing |
| 8 | ENVIRONMENTAL ACTIVITIES | 2,180,817 | 1 | Environmental Activities | Purchase and planting of tree seedlings in Burinda Primary School, Bukhakhala Primary School, Musibiriri Primary School, St. Augustine Butunyi Primary School, Musibiriri Primary School, Ekanjala Primary School, Butula Primary School, Siribo Primary School, Mungabwa Primary School, Bwaliro Primary School, Bulwani Primary School, Butunyi Mixed School @ Kes. 181,734.75 | 2,180,817 | Ongoing |
| 9 | EMERGENCY | 5,738,993.45 | 1 | Emergency | Supporting of urgent, unforeseen need for expenditure. | 5,738,993.45 | Ongoing |
| 10 | NG CDF VEHICLE | 1,500,000 | 1 | NG CDF Vehicle | Purchase of NG CDF Vehicle (4x4) | 1,500,000 | Ongoing |
| 11 | GEOGRAPHICAL INFORMATION SYSTEM | 10,000,000 | 1 | Geographical Information System | Establishment of a Geographical Information System for the constituency | 10,000,000 | New |
|  | TOTAL |  |  |  |  | 109,040,875.52 |  |

MIN 5 BTL NGCDFC/22/11/2018: A.O.B

There being no other business the meeting was adjourned at 1600 hrs with a word of closing prayer from Isah Atinda Kukuya.

Minutes confirmed by:

Chairperson: Allan Odipo			Date: ………………	Sign: ………………….…

Secretary: Coleta Ayomba Ong’ong’o		Date: ………………	Sign: …………………….