RANGWE

IEBC NUMBER 248

CONSTITUENCY DEVELOPMENT FUND

PROJECT PROPOSAL

2018/2019 FINANCIAL YEAR

SUBMITTED

30 DECEMBER 2018

TABLE OF CONTENTS

| SN | TITLE | PAGE |
| --- | --- | --- |
|  | MINUTES | 3 |
|  | THIRD SCHEDULE | 9 |
|  | FOURTH SCHEDULE | 10 |
|  | ISUZU BUSES |  |

NG-CDF RANGWE CONSTITUENCY DEVELOPMENT FUND

P.O.BOX  63 RANGWE

REF: NG CDF RANGWE/ MIN/OCT 2018

MINUTES OF RANGWE CDF HELD  AT THE CDF OFFICE RANGWE

MEMBERS PRESENT

- Mercy Okombo – Chairperson

- .Carolyne Atieno - Secretary

- Jackline Mwombo - Member

- .Jared Otieno Alosi - Member

- Sammy Ochieng Ogola - Member

- Jasmine Musembi – Assistant County Commissioner

- .Joseph Ager Oyugi - Member

- Charles M.Omosa - FAM

APPOLOGY

- Eric Odhiambo Mwa - Member

AGENDA

- Preliminaries

- Reading and confirmation of the previous minutes

- Matters  arising

- project proposals fy 2018/2019

- Adjournment

RANGWE CDF MIN 1/30/11/2018 PRELIMINARIES

The Chairperson brought the meeting to order at 10.30 am with a word of prayer being offered by Jackline Muombo. She then welcomed the members and thanked them for responding to the meeting in short notice. She told the members that the meeting will be brief since agendas for discussion were few.

RANGWE CDF MIN 2/30/11/2018: READING  AND CONFIRMATION OF THE PREVIOUS MINUTES

The secretary was called to read the previous minutes which were proposed by Alosi Jared  and seconded by Jasmine Musembi  as the true minutes for adoption.

RANGWE CDF MIN 3/10/11/2018: MATTERS ARISING.

There was no matter arising.

RANGWE CDF MIN 4/10/11/2018: PROJECT PROPOSALS FINANCIAL YEAR 2018/2019.

The Fund account manager told the members that  time for presenting the project proposal financial year 2018/2019 has up to 30/11/2019.  Therefore the committee was tasked to speed up the  process giving prioty to on going projects. The chairperson took the members through the ward proposals as received from the various four wards of Rangwe Sub County. The proposals were critically analysed by the members and the projects were selected as per the ward priorities. The following is the list of projects as attached in the first and second schedules.

| No. | Project Name | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| 1 | Employees’ Salaries | Payment of staff salaries and gratuity | 3,000,000 | Ongoing |
| 2 | Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, airtime, | 1,500,000 | Ongoing |
| 3 | NSSF | Payment of NSSF Deductions | 80,000 | Ongoing |
| 4 | NHIF | Payment of NHIF Deductions | 95,000 | Ongoing |
| 5 | Purchase of computers | Purchase of photocopiers, staplers, printing papers, tonners and cartridges | 250,000 | Ongoing |
| 6 | Purchase of furniture | Purchase of desks and tables | 250,000 | Ongoing |
| 7 | Committee expenses | Payment of Committee sitting allowances, transport, conferences | 1,367,452.53 | Ongoing |
| 8 | Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 1,300,000 | Ongoing |
| 9 | CDFC/PMC Capacity Building | Undertake Training of the PMCs/CDFCs on CDF Related issues | 571,226.27 | Ongoing |
| 10 | Committee Expenses | Payment of Committee sitting allowances, transport, conferences | 1,400,000 | Ongoing |
| 11 | Emergency | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | New |
| 12 | Constituency Sports Tournament | Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits | 2,180,817.51 | Ongoing |
| 13 | Environmental Activities | To carry out tree planting in the below mentioned schools Each at kshs.100,000 (Kotora Primary, Nyaundho Primary, Gul Kagembe Primary, Nyabola Primary, Onganga Primary, Omoche Secondary, Omoche Primary, God Marera Secondary, Nyakwadha Primary, Rabuor Ponge Primary, Nyajanja Primary, Atili Primary, Got Kabok Primary, Kuoyo Kochia Primary, God Bondo Secondary, Marienga Secondary, Manga Primary, Onyege Primary, Bondo Secondary, Nyadiere Primary and Ongeti Primary) 80,817.40 allocated for Achego Primary School | 2,180,817.51 | Ongoing |
| 14 | Bursary Secondary Schools | Payment of bursary to needy student | 14,000,000 | Ongoing |
| 15 | Bursary Tertiary Schools | Payment of bursary to needy student | 13,260,218.88 | Ongoing |
| 16 | Omoche primary school | Renovation of 3No. Classrooms at kshs.1,500,000 (uprooting of the roof timber and replacement of the ordinary iron sheets with box profile iron sheets, plastering, fitting and electrical installation) Construction of 5 door girls toilet and 5 door boys toilet at kshs.500,000 each. | 2,500,000 | Ongoing |
| 17 | Odienya Primary School | Construction of an administration block | 1,000,000 | New |
| 18 | Nyachar Primary School | Construction of two model classrooms. | 1,500,000 | Ongoing |
| 19 | Aoch Muga Primary School | Construction of an administration block | 1,500,000 | Ongoing |
| 20 | Rabuor Kaura Primary School | Completion of the ongoing administration block (Plastering, Fitting, Electrification, flooring and painting) | 1,500,000 | Ongoing |
| 21 | Ondiche Primary School | Completion of 6 classrooms in a storey building (Plastering, Fitting, Flooring and Ceilling) | 1,000,000 | Ongoing |
| 22 | Gul Kagembe Primary School | Construction of One model classroom. | 1,000,000 | Ongoing |
| 23 | Aora Chak Koga Primary School Road | Opening of 3km access road to Koga Primary School | 1,500,000 | New |
| 24 | Store Pamba Ongoro Primary School Road | Opening of 4km access road to Ongoro Primary School | 1,600,000 | New |
| 25 | Onyege Primary School | Completion of Two Classrooms | 1,000,000 | Ongoing |
| 26 | Nyandema Primary School (Ndiru Sports Ground) | Construction of podium (kshs.1,200,000) Toilet (kshs.300,000)Goal Posts of football and netball (kshs100,000) and Fencing (kshs.400,000) | 2,000,000 | New |
| 27 | Wikoteng Secondary School | Completion of the laboratory (plastering, fittings, painting and electrification) | 1,000,000 | Ongoing |
| 28 | Sinogo Secondary School | Construction of Two model classrooms. | 2,000,000 | New |
| 29 | Omoche Secondary School | Ongoing Already paid kshs.5,000,000 to KCI fy 2017/2018 for supply of 33 seater school bus and a balance of kshs.500,000 to be paid fy2018/19 | 500,000 | Ongoing |
| 29 | Nyawita Secondary School | Ongoing Already paid kshs.5,000,000 to KCI fy 2017/2018 for supply of 33 seater school bus and a balance of kshs.500,000 to be paid fy2018/19 | 500,000 | ongoing |
| 30 | Rangwe Girls Secondary School | Purchase of 33 seater bus | 5,500,000 | New |
| 31 | Rabango Mixed Secondary School | Purchase of 33 seater bus | 5,500,000 | New |
| 32 | Koyoo Mixed Secondary School | Construction of a dormitory | 1,000,000 | New |
| 33 | Nyakwadha Mixed Secondary School | Construction of 4 door toilets | 500,000 | New |
| 34 | Orero Secondary School | Construction of a laboratory | 1,000,000 | Ongoing |
| 35 | Asumbi TTC | Construction of a dormitory | 2,000,000 | New |
| 36 | Rangwe Sub County Administration and Educational center | Construction of the administration and Educational center | 25,000,000 | New |
| 37 | Rangwe AP Line | Renovation of AP Toilets | 266,349.37 | Ongoing |
| 38 | Strategic plan | Ongoing Development of NG-CDF Strategic Plan for 2017-2022 | 1,000,000 | Ongoing |
|  | SUB-TOTAL |  | 109,040,875.52 |  |

Rangwe cdf min 5/07/25/2018 Adjournment

There no being any other business for discussion, the meeting was adjourned at 2.00 pm with closing prayer from Jared Alosi. The members were then allowed to leave at their pleasure.

Prepared by Cdfc secretary …… Caroline Otieno……………..date ……………………… sign……………………………….

Certified by:  Cdfc Chairman…….Mercy Okombo.

Date……………………..…sign……………………………….

907

2015                      National Government Constituencies Development Fund                                     No.  30

THIRD SCHEDULE (ss.25(6,(11) and 29 (1)

CONSTITUENCY PROJECTS SUBMISSION FORM

Constituency No 248 Constituency Name RANGWE. Financial Year 2018/2019

| Serial | Name of Project | Amount Allocated |
| --- | --- | --- |
| 248/AP1 | Administration/Recurrent 6% | 6,542,452.53 |
| 248/AP2 | Monitoring and Evaluation/Capacity Building 3% | 3,271,226.27 |
| 248/2630205 | Bursary/ Social Programmes 25% | 27,260,218.88 |
| 248/2630204 | Primary School Projects | 16,100,000 |
| 248/2630205 | Secondary School Projects | 17,500,000 |
| 248/2630206 | Tertiary School Projects | 2,000,000 |
| 248/ 2640509 | Sports Activities 2% | 2,180,817.51 |
| 248/ 2640510 | Environment 2% | 2,180,817.51 |
| 248/2640200 | Emergency Reserve 5% | 5,738,993.45 |
| 248-2640507 | Security | 25,266,349.37 |
| 248-2211310 | Strategic Plan | 1,000,000 |
| Total |  | 109,040,875.52 |

Chairman CDF Committee …………………………. Signature………………….. Date………………

Fund Account Manager …………………………… Signature…………………….Date………………

907

2015              National Government Constituencies Development Fund                              No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE  County HOMA BAY

Project Number 248/AP1

Project Title 6% Administration/Recurrent

Sector Administration

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

The allocation is to cater for CDFC Allowance, staff salaries, vehicle expenses and other administrative

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 6,542,452.53   dated…………………

Amount allocated last financial year kshs 4,281,033.62

Amount allocated this financial year kshs 6,542,452.53

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Employees Salaries | 4-043-248-2110000-100-2018/19-001 | Payment of staff salaries and gratuity | 3,000,000 | Ongoing |
| Goods and Services | 4-043-248-2110000-100-2018/19-002 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea. | 1,500,000 | Ongoing |
| Purchase of Computers | 4-043-248-2110000-100-2018/19-003 | Purchase of photocopiers, staplers. | 250,000 | Ongoing |
| Purchase of Furniture/equipment | 4-043-248-2110000-100-2018/19-004 | Purchase of CDF desks and tables. | 250,000 | Ongoing |
| NSSF | 4-043-248-2120101-100-2018/19-005 | Payment of NSSF Deductions | 80,000 | Ongoing |
| NHIF | 4-043-248-2120201-100-2018/19-006 | Payment of NHIF Deductions | 95,000 | Ongoing |
| Committee Expenses | 4-043-248- 2210802 -100-2018/19-007 | Payment of Committee sitting allowances, transport, conferences | 1,367,452.53 | Ongoing |
| TOTAL |  |  | 6,542,452.53 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015                   National Government Constituencies Development Fund                       No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/AP2

Project Title 3% Monitoring & Evaluation/Capacity Building

Sector Monitoring & Evaluation

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To cater for Monitoring and Evaluation of CDF projects and capacity building of CDFC and PMCs in the constituency

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs3, 271,226.27 dated…………………

Amount allocated last financial year Kshs 2,604,310.32

Amount allocated this financial year Kshs3,271,226.27

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Goods and Services | 4-043-248-2210000-111-2018/2019-001 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence, e.t.c | 1,300,000 | Ongoing |
| Committee Expenses | 4-043-248-2210802-111-2018/2019-002 | Payment of Committee sitting allowances, transport, conferences | 1,400,000 | Ongoing |
| CDFC/PMC Capacity Building | 4-043-248-2210700-111-2018/2019-003 | Undertake Training of the PMCs/CDFCs on CDF Related issues | 571,226.27 | Ongoing |
| TOTAL |  |  | 3,271,226.27 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015              National Government Constituencies Development Fund            No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/2640200

Project Title Emergency (5% of the fund)

Sector Emergency

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Unallocated amount meant for emergencies that may occur within the Constituency

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 5,738,993.45 dated…………………

Amount allocated last financial year 5,137,931.32

Amount allocated this financial year kshs 5,738,993.45

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Emergency | 4-043-248-2640200-101-2018/2019-001 | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | Ongoing |
| Total |  |  | 5,738,993.45 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015               National Government Constituencies Development Fund                No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/ 2640509

Project Title Sports Activities

Sector Sports

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,180,817.51  dated…………………

Amount allocated last financial year 900,000

Amount allocated this financial year 2,180,817.51

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Constituency Sports Tournament | 4-043-248- 2640509 -112-2018/2019-001 | Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits | 2,180,817.51 | Ongoing |
| Total |  |  | 2,180,817.51 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015                   National Government Constituencies Development Fund                     No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/2630205

Project Title Bursary/Social Programmes

Sector Bursary  25%

Status of projects (tick one) New………………. Extension……………….. On-going…√….. Rehabilitation ………………….

Brief statement on project status at time of submission

Payment of bursaries to needy students in various institutions.

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs. 27,260,218.88 dated…………………

Amount allocated last financial year 25,778,448.04

Amount allocated this financial year Kshs 27,260,218.88

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Bursary Secondary Schools | 4-043-248-2630205-103-2018/2019-001 | Payment of bursary to n3eedy student | 14,000,000 | Ongoing |
| Bursary Tertiary Schools | 4-043-248-2630205-103-2018/2019-003 | Payment of bursary to needy student | 13,260,218.88 | Ongoing |
| TOTAL |  |  | 27,260,218.88 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015                  National Government Constituencies Development Fund                     No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/ 2630204

Project Title Primary Education Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhance better learning conditions in the primary schools institutions by improving the infrastructural facilities

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs. 16,100,000    dated…………………

Amount allocated last financial year kshs 17,400,000.00

Amount allocated this financial year kshs 16,100,000

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Omoche primary School | 4-043-248-2630204-110-2018/2019-001 | Renovation of 3No. Classrooms at kshs.1,500,000 (uprooting of the roof timber and replacement of the ordinary iron sheets with box profile iron sheets, plastering, fitting and electrical installation) Construction of 5 door girls toilet and 5 door boys toilet at kshs.500,000 each. | 2,500,000 | Ongoing |
| Odienya Primary School | 4-043-248- 2630204-110-2018/2019-002 | Construction of an administration block | 1,000,000 | New |
| Nyachar Primary School | 4-043-248- 2630204-110-2018/2019-003 | Construction of two model classrooms. | 1,500,000 | Ongoing |
| Aoch Muga Primary School | 4-043-248- 2630204-110-2018/2019-004 | Construction of an administration block | 1,500,000 | Ongoing |
| Rabuor Kaura Primary School | 4-043-248- 2630204-110-2018/2019-005 | Completion of the ongoing administration block (Plastering, Fitting, Electrification, flooring and painting) | 1,500,000 | Ongoing |
| Ondiche Primary School | 4-043-248- 2630204-110-2018/2019-006 | Completion of 6 classrooms in a storey building(Plastering,Fitting,Flooring and Ceilling) | 1,000,000 | Ongoing |
| Gul Kagembe Primary School | 4-043-248- 2630204-110-2018/2019-007 | Construction of One model classroom. | 1,000,000 | Ongoing |
| Aora Chak Koga Primary School Road | 4-043-248- 2630204-110-2018/2019-008 | Opening of 3km access road to Koga Primary School | 1,500,000 | New |
| Store Pamba Ongoro Primary School Road | 4-043-248- 2630204-110-2018/2019-009 | Opening of 3km access road to Ongoro Primary School | 1,600,000 | New |
| Onyege Primary School | 4-043-248- 2630204-110-2018/2019-010 | Completion of Two classrooms | 1,000,000 | Ongoing |
| Nyandema Primary School (Ndiru Sports Ground) | 4-043-248- 2630204-110-2018/2019-011 | Construction of podium (kshs.1,200,000) Toilet (kshs.300,000)Goal Posts of football and netball (kshs100,000) and Fencing (kshs.400,000) | 2,000,000 | New |
| Total |  |  | 16,100,000 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015                National Government Constituencies Development Fund                       No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/ 2630205

Project Title Secondary School Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhance better learning conditions of secondary institutions by improving the infrastructural facilities.

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs. 17,500,000 dated…………………

Amount allocated last financial year 14,000,000.00

Amount allocated this financial year 17,500,000

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Wikoteng Secondary School | 4-043-248- 2630205-110-2018/19-001 | Completion of the laboratory (plastering, fittings, painting and electrification) | 1,000,000 | Ongoing |
| Sinogo Mixed Secondary School | 4-043-248- 2630205-110-2018/19-002 | Construction of Two model classrooms | 2,000,000 | New |
| Omoche Mixed Secondary | 4-043-248- 2630205-108-2018/2019-003 | Ongoing Already paid kshs.5,000,000 to KCI fy 2017/2018 for supply of 33 seater school bus and a balance of kshs.500,000 to be paid in fy2018/19 | 500,000 | Ongoing |
| Nyawita Mixed Secondary | 4-043-248- 2630205-108-2018/2019-004 | Ongoing Already paid kshs.5,000,000 to KCI fy 2017/2018 for supply of 33 seater school bus and a balance of kshs.500,000 to be paid in fy2018/19 | 500,000 | Ongoing |
| Rangwe Girls Secondary | 4-043-248- 2630205-110-2018/19-005 | Purchase of a 33 seater school bus | 5,500,000 | New |
| Rabango Mixed Secondary | 4-043-248- 2630205-110-2018/19-006 | Purchase of a 33 seater school bus | 5,500,000 | New |
| Koyoo Mixed Secondary School | 4-043-248- 2630205-110-2018/19-007 | Construction of a dormitory | 1,000,000 | New |
| Nyakwadha | 4-043-248- 2630205-110-2018/19-008 | Construction of 4 door toilets | 500,000 | New |
| Orero Secondary School | 4-043-248- 2630205-110-2018/19-009 | Construction of a laboratory | 1,000,000 | Ongoing |
| Total |  |  | 17,500,000 |  |

Person completing form: Name Charles M. Omosa        Position Fund Account Manager

Signature…………………… Date………………………

907

2015                National Government Constituencies Development Fund                       No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/ 2640206

Project Title Tertiary School Projects

Sector Education

Status of projects (tick one) New…….…. Extension……….. On-going…√…..Rehabilitation …….

Brief statement on project status at time of submission

To enhance better learning conditions of tertiary institutions by improving the infrastructural facilities.

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,000,000 dated…………………

Amount allocated last financial year 0

Amount allocated this financial year 2,000,000

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Asumbi TTC | 4-043-248- 2640206-110-2018/19-001 | Construction of a dormitory | 2,000,000 | New |

Person completing form: Name Charles M. Omosa        Position Fund Account Manager

Signature…………………… Date………………………

907

2015            National Government Constituencies Development Fund                       No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/ 2640510

Project Title Environment (2% of the fund)

Sector Environment

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………

Brief statement on project status at time of submission

To carry out  tree planting across the schools in the constituency.

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,180,817.51 dated…………………

Amount allocated last financial year 1,200,000

Amount allocated this financial year kshs 2,180,817.51

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Environment | 4-043-248- 2640510 -101-2018/2019-001 | To carry out tree planting in the below mentioned schools Each at kshs.100,000 (Kotora Primary, Nyaundho Primary, Gul Kagembe Primary, Nyabola Primary, Onganga Primary, Omoche Secondary, Omoche Primary, God Marera Secondary, Nyakwadha Primary, Rabuor Ponge Primary, Nyajanja Primary, Atili Primary, Got Kabok Primary, Kuoyo Kochia Primary, God Bondo Secondary, Marienga Secondary, Manga Primary, Onyege Primary, Bondo Secondary, Nyadiere Primary and Ongeti Primary) 80,817.40 allocated for Achego Primary School | 2,180,817.51 | Ongoing |
| Total |  |  | 2,180,817.51 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………

907

2015                    National Government Constituencies Development Fund                 No. 30

FOURTH SCHEDULE (s. 30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/2650507

Project Title Security

Sector Security

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To construct a model administration and educational center

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 25,266,349.37     dated…………………

Amount allocated last financial year 5,500,000

Amount allocated this financial year kshs 25,266,349.37

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Administration and Educational Center | 4-043-248-2650507-101-2018/2019-001 | Construction of the administration and Educational center | 25,000,000 | New |
| Rangwe AP Line | 4-043-248-2650507-101-2018/2019-002 | Renovation of AP Toilets | 266,349.37 | Ongoing |
| Total |  |  | 25,266,349.37 |  |

Person completing form: Name Charles M. Omosa          Position Fund Account Manager

Signature…………………… Date………………………

907

2015                  National Government Constituencies Development Fund                      No. 30

FOURTH SCHEDULE (s.30)

PROJECT DESCRIPTION FORM

Constituency No: 248 Constituency Name RANGWE County HOMA BAY

Project Number 248/2211310

Project Title Strategic Plan

Sector Strategic

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Development of NG-CDF Strategic Plan for 2019-2022

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 3,500,000 dated…………………

Amount allocated last financial year 2,500,000

Amount allocated this financial year kshs 1,000,000

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Strategic Plan | 4-043-248-2211310-108-2018/2019-001 | Development of NG-CDF Strategic Plan for 2019-2022 | 1,000,000 | Ongoing |
| Total |  |  | 1,000,000 |  |

Person completing form: Name Charles M Omosa Position Fund Account Manager

Signature…………………… Date………………………