|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No.** | **Constituency name**  | **Allocation (Kshs.)** | **Compliance to NG-CDF Act and other guidelines**  | **Board’s Resolution** |
|  | **Maara** | 145,132,603 |  | ***The entire proposal to pend approval subject to NG-CDFC allocating entire balances to the following projects initiated in 2019/20 Financial Year***  |
| Gituntu Day Secondary School, Kshs.1,000,000 - Construction of an administration block comprising of five rooms and staffroom; Shutter slab | NG-CDFC to allocate the entire balance of Kshs.4.2 millionNG-CDFC to submit contract documents and certified BoQsManagement to carry out verification visit to ascertain the scope of the outstanding works.The Project was initiated in 2019/20 with an allocation of Kshs.1 million. In 2021/22 the project was allocated Kshs.1.5 million for completion with estimated cost being indicated as Kshs.2.5 millionThe estimated cost has now been revised to Kshs.6,756,701 but the contract sum has been indicated as Kshs.*5,542,633*The FAM indicated that additional allocation of Kshs,1,000,000 will complete the project. |
| Maara Police Division, Kshs.4,500,000 - Completion of Officer Commanding Police Division and Directorate of Criminal Investigation offices comprising of 5 rooms (phase two);substructure, superstructure, roofing, plastering, electrification and painting | Management to carry out verification visitNG-CDFC to submit contract documents/certified BoQs/designs.The project was initiated in 2018/19 with an allocation of Kshs.2,000,000 for construction of an office block from foundation ***to completion*** and was indicated as newIn 2020/21, the police division was allocated Kshs.2,000,000 for construction of a six roomed office block **to completion** and was indicated as newThe project has now been allocated additional Kshs.4,500,000 and the estimated cost has been indicated as Kshs.8,500,000 |
| Maara NG-CDF Office, Kshs.15,000,000 - Construction to completion of 12 roomed and boardroom NG-CDFC office(inclusive of kitchen, four roomed ablution block reserving two for people with disability, accounts office, registry, procurement office, mp’s office, secretary to mp’s office, constituency manager office, NGCDF chair office, NGCDF secretary office computer lab and NGCDF office) | **Pending approval**NG-CDFC to submit certified BoQs and designs for the proposed office |
| Mwimbi Social Hall, Kshs.5,000,000 - Construction to completion of a 300 persons capacity social hall | ***Declined***Projects fall under the functions of the County Government |
| Muthambi Social Hall, Kshs.5,000,000 - Construction to completion of a 300 persons capacity social hall |