MEETING NO.27

MINUTES OF EMUHAYA NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND COMMITTEE HELD ON 7TH OCTOBER, 2020 AT THE NG-CDFC OFFICE’S BOARDROOM.

PRESENT

1.  MR. CHARLES OMUCHILO                        -            NG-CDFC CHAIRMAN

2.  MR. GIDEON  OYALO                               -            SECRETARY

3.  BENJAMIN  OPANDE                                -            MEMBER

4  .MRS. ROSELINE AKISO OCHONYA             -            MEMBER

5.  MR. JOEL AKAKI ATIELI                           -            MEMBER

6.  MS.FRIDAH AYOTI                                  -             MEMBER

7.  MRS. MIRIAM  EKAMBI                            -             MEMBER

8.  MR. KELVIN ONGAYA                               -            MEMBER

9.  MR. CHUCK  MASUA                                -            DCC

10. PAUL CHARLES MOGENDI                       -            FAM.

IN ATENDANCE.

1. MR.REARDON  MUSUTA                                  -         OVERSIGHT

2. MR.PAUL  MUKUNA                                         -         OVERSIGHT

3. MR.AYUB EBOLE                                            -          CLERK OF WORKS

ABSENT WITH APOLO

- OKATA  KABALA                                   -            OVERSIGHT

The meeting was called to order by the chairman at 9:30 am, with a word of prayer from Mrs. Miriam Ekambi.

- CONFIRMATION OF THE QUORUM

Members noted that the meeting was quorate to transact the business of the committee.

- ADOPTION OF THE AGENDA.

The agenda for the meeting was adopted as follows.

- Opening prayer.

- Attendance.

- Adoption of the Agenda.

- Reading and confirmation of previous minutes

- Approval of the budget for 2020-2021 FY.

- Benchmarking

- Closing prayer.

Agenda 4 was referred to next meeting on the request of the FAM. This was to allow or have more time to discuss Agenda no.5 exhaustively. Members agreed anonymously to discuss the budget and benchmarking.

MIN. 113: EMU/NG-CDFC/MIN.113/ APPROVAL OF THE BUDGET FOR 2020-2021 FY.

The FAM took the NGCDFC through the numerous projects they had proposed for consideration during 2020/2021 F/Y.

Key Consideration that the FAM highlighted to the NGCDFC was observing guidelines laid down by the NGCDFB through NGCDFB Circular dated 10/07/2020, Referenced; NG-CDFB/CEO/BOAD CIRCULARs VOL II (024) while preparing the Budget Proposal.

While discussing, the NGCDFC proposed that the FAM to first take them through the following;

- Total budget funding

- Total Emergency Funds

- Ongoing Projects and their implication in terms of finances,

- Statutory Expenditure Ceiling as per the NGCDFB ACT and its implications in terms of finances.

- List of new projects that the NGCDFC had discussed.

The informed the NGCDFC that as per the Circular mentioned above, 2020/2021 F/Y TOTAL Allocation to Emuhaya Constituency will be kshs.137, 088,879.31 and Emergency funds will be Kshs.7, 192,206.90

He also provided to NGCDFC the list of ongoing projects. Refer to ANNEX 1 for the same; He adequately took them through the NGCDFB Circular more so where Statutory Expenditure Ceilings were provided.

After extensive deliberations, the NGCDFC came up with the Budget Proposal of F/Y 2020/2021 as listed below;

| EMUHAYA NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PROJECT PROPOSAL FOR 2020/2021 FINANCIAL YEAR |  |  |  |  |  |  |  |
| CODE LIST |  |  |  |  |  |  |  |
| FINANCIAL YEAR 1ST JULY, 2020 TO 30TH JUNE, 2021 |  |  |  |  |  |  |  |
| NO. | PROJECT NAME | PROJECT NUMBER | ORIGINAL COST | CUMMULATIVE ALLOCATION | PROJECT ACTIVITY | AMOUNT ALLOCATED | CURRENT STATUS |
|  | ADMINISTRATION/RECURRENT |  |  |  |  |  |  |
| 1 | Employees’ Salaries | 4-038-215-2110000-100-2020/21-001 | 3,278,274.00 | 3,278,274.00 | Payment of staff salaries @ Kshs. 2,502,840.00 and gratuity @ Kshs. 775,434.00 | 3,278,274.00 | Ongoing |
| 2 | Goods & Services | 4-038-215-2110000-100-2020/21-002 | 2,980,000.00 | 2,980,000.00 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 2,980,000.00 | Ongoing |
| 3 | National Social Security Fund | 4-038-215-2120101-100-2020/21-003 | 255,715.20 | 255,715.20 | Payment of NSSF deductions | 255,715.20 | Ongoing |
| 4 | National Hospital Insurance Fund | 4-038-215-2120201-100-2020/21-004 | 85,200.00 | 85,200.00 | Payment of NHIF deductions | 85,200.00 | Ongoing |
| 5 | Committee Expenses | 4-038-215-2210802-100-2020/21-005 | 1,626,144.56 | 1,626,143.56 | Payment of NG-CDFC allowances, Conferences and other NGCDFC functions that require facilitation. | 1,626,143.56 | Ongoing |
|  |  |  |  |  |  | 8,225,332.76 |  |
|  | MONITORING & EVALUATION/ CAPACITY BUILDING |  |  |  |  |  |  |
| 6 | Goods and Services | 4-038-215-2210000-111-2020/21-001 | 1,200,000.00 | 1,200,000.00 | Purchase of fuel, repairs and maintenance, printing, stationery, airtime, travel and subsistence | 1,200,000.00 | Ongoing |
| 7 | Committee Expenses | 4-038-215-2210802-111-2020/21-002 | 1,286,181.00 | 1,286,181.00 | Payment of Committee allowances, transport, conferences | 1,277,665.66 | Ongoing |
| 8 | NG-CDFC/PMC Capacity Building | 4-038-215-2210700-111-2020/21-003 | 1,635,000.72 | 1,635,000.72 | Undertake training of the PMCs/NG-CDFCs on NG-CDF related issues | 1,635,000.72 | Ongoing |
|  |  |  |  |  |  | 4,112,666.38 |  |
|  | BURSARY/SOCIAL SECURITY |  |  |  |  |  |  |
| 9 | Bursary for Secondary Schools | 4-038-215-2640101-103-2020/21/001 | 20,000,000.00 | 22,000,000.00 | Payment of bursary to needy students in secondary schools | 20,000,000.00 | Ongoing |
| 10 | Bursary for Tertiary Institutions | 4-038-215-2640102-103-2020/21/002 | 13,000,000.00 | 13,000,000.00 | Payment of bursary to needy students in Tertiary Institutions | 13,000,000.00 | Ongoing |
| 11 | Bursary special school | 4-038-215-2640105-103-2020/21/003 | 2,000,000.00 | 2,000,000.00 | Payment of bursary to needy students in special schools | 2,000,000.00 | On-going |
|  |  |  |  |  |  | 35,000,000.00 |  |
|  | PRIMARY SCHOOLS PROJECTS |  |  |  |  |  |  |
| 12 | Esalwa Primary School | 4-038-215-2630204-104-2020/21-001 | 1,000,000.00 | - | Renovations of 4 No. Classrooms; re-roofing, re-flooring, wall repairs, glazing & re-painting to completion. | 1,000,000.00 | New |
| 13 | Musirili Primary School | 4-038-215-2630204-104-2020/21-002 | 1,500,000.00 | - | Construction of 2 No. classrooms to completion | 1,500,000.00 | New |
| 14 | Esibila Primary School | 4-038-215-2630204-104-2020/21-003 | 750,000.00 | - | Construction of 1 no. classroom to completion | 750,000.00 | New |
| 15 | Emurembe Primary school | 4-038-215-2630204-104-2020/21-004 | 1,500,000.00 | - | Construction of 2 no. classrooms to completion | 1,500,000.00 | New |
| 16 | Emwatsi Primary School | 4-038-215-2630204-104-2020/21-005 | 500,000.00 | - | Fencing of the compound & Installation of the gate approximate size 0.36 Ha; Angle bars, chain-link barbed wire & Installation of steel gate to completion | 500,000.00 | New |
| 17 | Ebusiloli Primary school | 4-038-215-2630204-104-2020/21-006 | 1,500,000.00 | - | Construction of 2 no. classrooms to completion | 1,500,000.00 |  |
| 18 | Mwiyala Primary School | 4-038-215-2630204-104-2020/21-007 | 900,000.00 | - | Purchase of Land approximately 0.36 Ha. Submit land valuation report and specify whether the cost of title deed processing is included | 900,000.00 | New |
| 19 | Mungoye Primary School | 4-038-215-2630204-104-2020/21-008 | 1,500,000.00 | - | Construction of 2 no. classrooms to completion | 1,500,000.00 | New |
| 20 | Ebunangwe Primary School | 4-038-215-2630204-104-2020/21-009 | 1,500,000.00 | - | Construction of 2 No. classrooms to completion | 1,500,000.00 | New |
| 21 | Kilingili Primary School | 4-038-215-2630204-104-2020/21-010 | 1,000,000.00 | - | Renovations of 4 no. classrooms; re-flooring, wall repairs, glazing & re-painting to completion | 1,000,000.00 | New |
| 22 | Ebumbuya Primary School | 4-038-215-2630204-104-2020/21-011 | 800,000.00 | - | Purchase of land approximately 0.4 Ha. Submit land valuation report and specify whether the cost of title deed processing is included | 800,000.00 | New |
| 23 | Emusutswi Primary school | 4-038-215-2630204-104-2020/21-012 | 1,400,000.00 | - | Renovation of 4 No. classrooms; Re-casting of ring beam, re-roofing, fitting of shutters, glazing, wall repairs, re-flooring & painting to completion | 1,400,000.00 | New |
| 24 | Mukhombe Primary school | 4-038-215-2630204-104-2020/21-013 | 1,500,000.00 | - | Construction of 2 No classrooms up to completion | 1,500,000.00 | New |
| 25 | Mwituha Primary School | 4-038-215-2630204-104-2020/21-014 | 750,000.00 | - | Construction of 1 classroom to completion | 750,000.00 | New |
| 26 | Emanyinya Primary School | 4-038-215-2630204-104-2020/21-015 | 1,500,000.00 | - | Renovations of 6 No. classrooms-re-roofing, re-flooring, wall repairs, glazing & re-painting to completion | 1,500,000.00 | New |
| 27 | Mundichiri Primary School | 4-038-215-2630204-104-2020/21-016 | 1,500,000.00 | - | Construction of 2 no. classrooms to completion | 1,500,000.00 | New |
| 28 | Emmukunzi Primary School | 4-038-215-2630204-104-2020/21-017 | 750,000.00 | - | Construction of 1 No. classroom to completion | 750,000.00 | New |
| 29 | Ebuyalu Special school | 4-038-215-2630204-104-2020/21-018 | 750,000.00 | - | Construction of 1No. classroom to completion | 750,000.00 | New |
| 30 | Essaba Primary School | 4-038-215-2630204-104-2020/21-019 | 750,000.00 | - | Construction of 1 No. classroom to completion | 750,000.00 | New |
| 31 | Mwitukho Primary School | 4-038-215-2630204-104-2020/21-020 | 1,500,000.00 | - | Construction of 2 No. classrooms to completion | 1,500,000.00 | New |
| 32 | Essunza Primary School | 4-038-215-2630204-104-2020/21-021 | 1,000,000.00 | - | Renovations of 4 no. classrooms; re-flooring, wall repairs, glazing & re-painting to completion | 1,000,000.00 | New |
| 33 | Emusire Primary School | 4-038-215-2630204-104-2020/21-022 | 1,000,000.00 | - | Renovations of 4 no. classrooms; re-flooring, wall repairs, glazing & re-painting to completion | 1,000,000.00 | New |
| 34 | Emuhondo Primary School | 4-038-215-2630204-104-2020/21-023 | 700,000.00 | - | Renovation of 2 No. classrooms; Re-casting of ring beam, re-roofing, fitting of shutters, glazing, wall repairs, re-flooring & painting to completion | 700,000.00 | New |
| 35 | Ikumu Primary School | 4-038-215-2630204-104-2020/21-024 | 1,500,000.00 | - | Construction of 2 No. classrooms to completion | 1,500,000.00 | New |
| 36 | Mumboko Primary School | 4-038-215-2630204-104-2020/21-025 | 750,000.00 | - | Construction of 1 No. classroom to completion | 750,000.00 | New |
| 37 | Esirulo Primary School | 4-038-215-2630204-104-2020/21-026 | 1,500,000.00 | - | Renovations to completion of 6 No. classrooms-re-flooring, wall repairs, glazing & re-painting to completion | 1,500,000.00 | New |
| 38 | Eluhobe primary school | 4-038-215-2630204-104-2020/21-027 | 1,000,000.00 | - | Renovations of 4 No. Classrooms; re-roofing, re-flooring, wall repairs, glazing & re-painting to completion | 1,000,000.00 | New |
| 39 | Ilungu Primary school | 4-038-215-2630204-104-2020/21-028 | 1,000,000.00 |  | Renovations of 4 No. classrooms-re-roofing, re-flooring, wall repairs, glazing & re- painting to completion | 1,000,000.00 | New |
| 40 | Eluyeka Primary school | 4-038-215-2630204-104-2020/21-029 | 800,000.00 | - | Purchase of Land approximately 0. 4 Ha Submit land valuation report and specify whether the cost of title deed processing is included | 800,000.00 | New |
| 41 | Ebulondi primary school | 4-038-215-2630204-104-2020/21-030 | 1,000,000.00 | - | Renovations of 4 No. classrooms-re-roofing, re-flooring, glazing & re- painting to completion | 1,000,000.00 | New |
| 42 | Ebukobelo primary school | 4-038-215-2630204-104-2020/21-031 | 750,000.00 | - | Construction of 1 No. classroom to completion | 750,000.00 | New |
| 43 | Ikalikha Primary school | 4-038-215-2630204-104-2020/21-032 | 750,000.00 | - | Construction of 1 No. classroom to completion | 750,000.00 | New |
| 44 | Esibuye Primary school | 4-038-215-2630204-104-2020/21-033 | 500,000.00 | - | Renovation of 2 No. Classrooms;re-roofing, re-flooring, re wall repairs, glazing & re-painting to completion | 500,000.00 | New |
|  |  |  |  |  |  | 35,100,000.00 |  |
|  | SECONDARY SCHOOLS PROJECTS |  |  |  |  |  |  |
| 45 | Esibila Secondary School | 4-038-215-2630204-104-2020/21-001 | 7,544,000.00 | - | Co-fund; Purchase of 51 seater School Bus Confirm that the school has adequate funds to make a one-off purchase | 3,000,000.00 | New |
| 46 | Bunyore Boys' secondary school | 4-038-215-2630204-104-2020/21-002 | 1,500,000.00 | - | Construction of 2 classrooms up to completion | 1,500,000.00 | New |
| 47 | Mwituha secondary school | 4-038-215-2630204-104-2020/21-003 | 5,000,000.00 | 3,000,000.00 | Construction of Dining Hall & kitchen; Fitting of shutters, plaster & external render, flooring, glazing, wiring &re-painting | 2,000,000.00 | 0n-going |
| 48 | Ebukhaya secondary school | 4-038-215-2630204-104-2020/21-004 | 4,500,000.00 | 1,000,000.00 | Construction of Dining Hall & Kitchen; erection of dining hall to wall plate | 1,500,000.00 | New |
| 49 | Ebunangwe High School | 4-038-215-2630204-104-2020/21-005 | 3,000,000.00 | 1,000,000.00 | Completion; Construction of Laboratory; Fitting of shutters, plaster & external render, flooring, glazing, wiring & painting | 2,000,000.00 | New |
|  |  |  |  |  |  | 10,000,000.00 |  |
|  | TERTIARY INSTITUTIONS PROJECTS |  |  |  |  |  |  |
| 50 | Bunyore Teachers Training College | 4-038-215-2630206-104-2020/21-001 | 14,771,295.00 | 5,000,000.00 | Construction of 2 No. blocks of dormitories; Erection of 2nd dormitory to completion | 9,771,295.00 | Ongoing |
| 51 | Ebunangwe technical teachers training Institute | 4-038-215-2630206-104-2020/21-002 | 4,000,000.00 |  | Fencing of the compound & Installation of the gate approximate size 9.04 Ha; Concrete posts, chain link & barbed wire. NG-CDFC to submit approval letter from the MOE for the establishment of the institution . | 4,000,000.00 | New |
|  |  |  |  |  |  | 13,771,295.00 |  |
|  | SECURITY PROJECTS |  |  |  |  |  |  |
| 52 | Emuhaya Administration Centre | 4-038-215-2640507-109-2020/21-001 | 49,666,629.60 | 41,117,543.11 | Completion; Construction of the sub-county offices storey-Casting 3rd floor slab, roofing, walling & fitting of shutters at the 3rd floor, plaster/external render, flooring, painting, wiring at both 2nd floor & 3rd floor & fitting of ceiling board the 3rd floor | 8,549,086.49 | Ongoing |
| 52 | Emuhaya Sub-county Police service | 4-038-215-2640507-109-2020/21-002 | 10,000,000.00 | 1,500,000.00 | Construction of Administration office(to contain 6 no. offices & cells; Activities to done includes- Walling, roofing, fitting of shutters, glazing, plaster/external render, flooring & painting Remaining works includes; fitting of ceiling board & electrification | 4,000,000.00 | Ongoing |
| 54 | Emurembe Administration police/Assistant chief's | 4-038-215-2640507-109-2020/21-003 | 1,200,000.00 | - | Construction of Administration office for police; Activities to done includes; substructure, walling, roofing, fitting of shutters, plaster/external render, flooring glazing & painting Remaining works; fitting of ceiling Board & electrification. To contain 2 no. offices & 2 no. cells | 800,000.00 | New |
| 55 | Rural Electrification and Renewable Energy Corporation | 4-038-215-2640507-109-2020/21-004 | 3,238,535.99 | - | Rural electrification under Matching Funds in IKALIKHA Area, Central Bunyore Ward. Activities to be done include; Establishment of 1 x 50 Kva. 11/0.433 KV transformers, construction of approximately 1.2 KM of KV three phase line and associated 0.5 KM 3 phase and 3.56 KM Single phase lines and connect approximately 55 No. household customers in single phase and 1 No. customer in 3 phase at Ikalikha area Submit letter from REREC | 3,238,562.99 | New |
| 56 | Emuhaya Magistrate court | 4-038-215-2640507-109-2020/21-005 | 10,000,000.00 | 1,800,000.00 | Construction of Court; walling & roofing | 4,000,000.00 | Ongoing |
|  |  |  |  |  |  | 20,587,649.48 |  |
|  | SPORTS |  |  |  |  |  |  |
| 57 | Constituency Sports Tournament | 4-038-215-2640509-112-2020/21-001 | 2,659,728.79 | 2,659,728.79 | To carry out a constituency sports tournament where the winning teams will be awarded with balls, uniforms and trophies where facilitation of the tournament @ Kshs.1,759,728.79 and Purchase of balls, uniforms, trophies and equipments @ Kshs.900,000.00 | 2,659,728.79 | Ongoing |
|  |  |  |  |  |  | 2,659,728.79 |  |
|  | ENVIRONMENTAL PROJECTS |  |  |  |  |  |  |
| 58 | Esirulo Secondary school | 4--038-113-2210502-110-2020/21-001 | 80,000.00 | - | Planting of trees;800 stems | 80,000.00 | New |
| 59 | Mumboko primary school | 4--038-113-2210502-110-2020/21-002 | 100,000.00 | - | Planting of trees;1000 stems | 100,000.00 | New |
| 60 | Eluyeka Primary school | 4--038-113-2210502-110-2020/21-003 | 80,000.00 | - | Planting of trees;800 stems | 80,000.00 | New |
| 61 | Bunyore teachers training college | 4--038-113-2210502-110-2020/21-004 | 100,000.00 | - | Planting of trees;1000 stems | 100,000.00 | New |
| 62 | Essunza Secondary school | 4--038-113-2210502-110-2020/21-005 | 80,000.00 | - | Planting of trees;800 stems | 80,000.00 | New |
|  |  |  |  |  |  | 440,000.00 |  |
| 63 | EMERGENCY | 4-038-215-2640200-101-2020/21-001 | 7,192,206.90 | 7,192,206.90 | To cater for any unforeseen occurrences in the Constituency during the financial year | 7,192,206.90 | Ongoing |
|  |  |  |  |  |  | 137,088,879.31. |  |

MIN. 114: EMU/NG-CDFC/MIN.114/ BENCHMARKING.

After numerous deliberations, members agreed to visit Kwale and also approved an expenditure of, Kshs. 480,000.00towards benchmarking exercise. Refer to annex

II  for a copy of budget. FAM was authorized to seek permission with any of the constituencies in Kwale that may accept them visiting. Expected date for the visit was fixed to be the end of the month of October, 2020 or early following month of November 2020.

CHAIRMAN ……………………… ……………….. SIGN……………DATE……………

SECRETARY ……………………………………….. SIGN……………DATE……………