MEETING NO. 19

MINUTES OF EMUHAYA NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND COMMITTEE HELD ON 24TH  OCTOBER, 2019 AT THE NG-CDFC OFFICE’S BOARDROOM

PRESENT                                                                        DESIGNATION

1.MR. CHARLES OMUCHILO                              NG-CDFC CHAIRMAN

2.MR. GIDEON OYALO                                       SECRETARY

3.BENJAMIN OPANDE                                        MEMBER

4.MRS. ROSELINE AKISO OCHONYA              MEMBER

5.MR. JOEL AKAKI ATIELI                                 MEMBER

6.MS. FRIDAH AYOTI                                          MEMBER

7.MRS. MIRIAM EKAMBI                                    MEMBER

8.PAUL CHARLES MOGENDI                             FAM

9. JACK MASUA                                                     DCC

INATENDANCE.

1.MR. REARDON MUSUTA                                            OVERSIGHT

2.MR. AYUB EBOLE                                                       CLERK OF WORKS

3.MR. HELLAM AINEAH                                                CLERICAL OFFICER

ABSENT WITH APOLOGY:

The meeting was called to order by the chairman at 11.40 AM. With a word of prayer from Mrs. Roselyne Akiso

CONFIRMATION OF THE QUORUM

Members noted that the meeting was quorate to transact the business of the committee.

ADOPTION OF THE AGENDA.

The agenda for the meeting was adopted as follows.

- Opening prayer

- Attendance

- Adoption of the Agenda.

- Reading and confirmation of previous minutes.

- Matters arising.

- Reports from sub-committees

- Disposal of office vehicles ie GKA 459 S.

- Finance statement on expenditure.

- NG-CDF staff salary review and Leave allowance.

- State of projects 2018-2019.

- Budget proposal for 2019-2020 FY.

- Date for benchmarking.

- Closing prayer.

A member noted the weight and urgency of agenda no. 11 on Budget proposal and suggested that it be given enough time to handle it. The committee agreed and resolved to handle it and postpone the other agenda on a separate day.  A part from minute no. 11 member agreed to discuss sports which was also of urgency. Member agreed to discuss the two agendas and pushed forward the rest to the next meeting. Proposal of the agenda was done by Mr. Joel Akaki   and seconded by Ms Fridah Ayoti.

MIN. 74 : EMU/NG-CDFC/MIN. 74/OCTOBER/2019;

READING AND CONFIRMATION OF PREVIOUS MINUTES.

Minutes of the previous meeting were perused through by the secretary and members confirmed it to be a true record of the meeting. Proposal was done by Mrs. Roseline Akiso and seconded by Ms. Frida Ayoti.

MIN. 75 : EMU/NG-CDFC/MIN. 75/OCTOBER/2019;

MATTERS  ARISING FROM THE MINUTES.

Emergency allocation.

It was noted that Ebukhaya secondary school had not been considered as earlier agreed in the previous meeting. The committee resolved that the case be addressed immediately to assist the school which is facing that big challenge of ablution facility.

MIN. 76 : EMU/NG-CDFC/MIN. 76/OCTOBER/2019;

BUDGET PROPOSAL FOR 2019/2020 F/Y.

It was noted that Emuhaya NG-CDFC through a circular from the board with ref: NG-CDFB/CEO/BOARDCIRCULARS vol ii (014), had been allocated a total of Kshs. 137,371,724.14 for 2018/2019 financial year. This amount is Inclusive of Kshs.  7,198,241.38 reserved for emergency. In view of that, the committee, having held wards stakeholders’ meetings on 8th, 9th and 11th October 2019, prioritized projects for funding and came up with the following budget for 2019/2020 financial year for onward submission to the NG-CDF Board for consideration for funding.

The meeting also took into account that on-going projects to be given priority over new projects.

| NO. | PROJECT NAME | PROJECT NUMBER | ORIGINAL COST | CUMMULATIVE ALLOCATION | PROJECT ACTIVITY | AMOUNT ALLOCATED | CURRENT STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ADMINISTRATION/ RECURRENT |  |  |  |  |  |  |
| 1 | Employees’ Salaries | 4-038-215-2110000-100-2019/20-001 | 3,577,448.25 | 3,577,448.25 | Payment of staff salaries and gratuity | 3,577,448.25 | Ongoing |
| 2 | Goods & Services | 4-038-215-2110000-100-2019/20-002 | 2,980,000.00 | 2,980,000.00 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 2,980,000.00 | Ongoing |
| 3 | National Social Security Fund | 4-038-215-2120101-100-2019/20-003 | 255,715.20 | 255,715.20 | Payment of NSSF deductions | 255,715.20 | Ongoing |
| 4 | National Hospital Insurance Fund | 4-038-215-2120201-100-2019/20-004 | 85,200.00 | 85,200.00 | Payment of NHIF deductions | 85,200.00 | Ongoing |
| 5 | Committee Expenses | 4-038-215-2210802-100-2019/20-005 | 1,343,940.00 | 1,344,000.00 | Payment of NG-CDFC allowances, Conferences and only other NGCDFC functions that require facilitation. | 1,343,940.00 | Ongoing |
|  |  |  | 8,242,303.45 |  |  | 8,242,303.45 |  |
|  | MONITORING & EVALUATION/ CAPACITY BUILDING |  |  |  |  |  |  |
| 6 | Goods and Services | 4-038-215-2210000-111-2019/20-001 | 1,200,000.00 | 1,200,000.00 | Printing, stationery, airtime, travel and subsistence | 1,200,000.00 | Ongoing |
| 7 | Committee Expenses | 4-038-215-2210802-111-2019/20-002 | 1,286,181.00 | 1,286,181.00 | Payment of Committee allowances, transport, conferences | 1,286,181.00 | Ongoing |
| 8 | NG-CDFC/PMC Capacity Building | 4-038-215-2210700-111-2019/20-003 | 1,635,000.72 | 1,635,000.72 | Undertake training of the PMCs/NG-CDFCs on NG-CDF related issues | 1,635,000.72 | Ongoing |
|  |  |  |  |  |  | 4,121,181.72 |  |
|  | BURSARY/SOCIAL SECURITY |  |  |  |  |  |  |
| 9 | Bursary for Secondary Schools | 4-038-215-2640101-103-2019/20/001 | 20,000,000.00 | 20,000,000.00 | Payment of bursary to needy students | 20,000,000.00 | Ongoing |
| 10 | Bursary for Tertiary Institutions | 4-038-215-2640102-103-2019/20/002 | 14,000,000.00 | 14,000,000.00 | Payment of bursary to needy students | 14,000,000.00 | Ongoing |
| 11 | Bursary special school | 4-038-215-2640105-103-2019/20/003 | 2,000,000.00 10,000,000.00 | 2,000,000.00 3,200,000.00 | Payment of bursary to needy students | 2,000,000.00 | On-going |
|  |  |  |  |  |  | 36,000,000.00 |  |
|  | PRIMARY SCHOOLS PROJECTS |  |  |  |  |  |  |
| 12 | Itumbu Primary School | 4-038-215-2630204-104-2019/20-001 | 1,200,000.00 | - | Renovation of 4 No. Classrooms -Re-flooring, wall repairs & re-painting to completion | 1,200,000.00 | New |
| 13 | Musirili Primary School | 4-038-215-2630204-104-2019/20-002 | 800,000.00 | - | Purchase of Land approximately 0.4 Ha | 800,000.00 | New |
| 14 | Esibakala Primary School | 4-038-215-2630204-104-2019/20-003 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 15 | Ebusiloli Primary School | 4-038-215-2630204-104-2019/20-004 | 600,000.00 | - | Construction of 1No. Classroom up to completion | 600,000.00 | New |
| 16 | Emurembe Primary School | 4-038-215-2630204-104-2019/20-005 | 1,200,000.00 | - | Construction of 2 No classroom up to completion | 1,200,000.00 | New |
| 17 | Kilingili Primary School | 4-038-215-2630204-104-2019/20-006 | 1,000,000.00 | - | Renovations of 3 No. classrooms; re-flooring & painting to completion. | 1,000,000.00 | New |
| 18 | Ilungu Primary School | 4-038-215-2630204-104-2019/20-007 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 19 | Emusutswi Primary school | 4-038-215-2630204-104-2019/20-008 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 20 | Mwituha Primary School | 4-038-215-2630204-104-2019/20-009 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 21 | Assebu Primary School | 4-038-215-2630204-104-2019/20-010 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 22 | Mundichiri Primary School | 4-038-215-2630204-104-2019/20-011 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 23 | Emmukunzi Primary School | 4-038-215-2630204-104-2019/20-012 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 24 | Elununi Primary School | 4-038-215-2630204-104-2019/20-013 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 25 | Msiakhupa Primary School | 4-038-215-2630204-104-2019/20-014 | 1,500,000.00 | - | Construction of 2 No. classrooms up to completion | 1,500,000.00 | New |
| 26 | Ebukhuliti Primary School | 4-038-215-2630204-104-2019/20-015 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 27 | Essaba Primary School | 4-038-215-2630204-104-2019/20-016 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 28 | Mukhungu Primary School | 4-038-215-2630204-104-2019/20-017 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 29 | Ebututi Primary School | 4-038-215-2630204-104-2019/20-018 | 700,000.00 | - | Construction of 1 classroom up to completion | 700,000.00 | New |
| 30 | Emusire Primary School | 4-038-215-2630204-104-2019/20-019 | 1,500,000.00 | - | Construction of Administration block, containing 4 no. offices. Works; Substructure, walling, roofing, plaster/external render, flooring & painting. Remaining works; Ceiling and electrification. | 800,000.00 | New |
| 31 | Esinaka Primary School | 4-038-215-2630204-104-2019/20-020 | 2,200,000.00 | - | Construction of 2 No. classrooms up to completion NOTE: Area is waterlogged hence foundation needs more reinforcement. INDICATE IT IN THE MINUTES FOR ALL THE SCHOOLS WITH A HIGHER COST OFF CONSTRUCTION THAN THE REST | 2,200,000.00 | New |
| 32 | Mungoye Primary School | 4-038-215-2630204-104-2019/20-021 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 33 | Mumboko Primary School | 4-038-215-2630204-104-2019/20-022 | 1,600,000.00 | - | Construction of 2 No. classrooms up to completion | 1,600,000.00 | New |
| 34 | Emwatsi Primary School | 4-038-215-2630204-104-2019/20-023 | 1,500,000.00 | - | Construction of Administration block, containing 4 no. offices. Works; Substructure, walling, roofing, plaster/external render, flooring & painting. Remaining works; Ceiling and electrification. | 800,000.00 | New |
| 35 | Eluhobe primary school | 4-038-215-2630204-104-2019/20-024 | 1,500,000.00 | - | Construction of Administration block; containing 4 no. offices. Works; Substructure, walling, roofing, plaster/external render, flooring & painting. Remaining works; Ceiling and electrification. | 800,000.00 | New |
| 36 | Ebulondi primary school | 4-038-215-2630204-104-2019/20-025 | 1,500,000.00 | - | Construction of Administration block; containing 4 no. offices. Works; Substructure, walling, roofing, plaster/external render, flooring & painting. Remaining works; Ceiling and electrification. | 800,000.00 | New |
| 37 | Ebukobelo primary school | 4-038-215-2630204-104-2019/20-026 | 600,000.00 | - | Construction of 1 No. classrooms up to completion | 600,000.00 | New |
| 38 | Emmabwi primary school | 4-038-215-2630204-104-2019/20-027 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 39 | Ebukanga Primary school | 4-038-215-2630204-104-2019/20-028 | 1,500,000.00 | - | Construction of Administration block; containing 4 no. offices. Works; Substructure, walling, roofing, plaster/external render, flooring & painting to completion. Remaining works; Ceiling and electrification. | 800,000.00 | New |
| 40 | Ikalikha Primary school | 4-038-215-2630204-104-2019/20-029 | 1,345,000.00 | 1,000,000.00 | Completion purchase of approximately 0.48 Ha. | 345,000.00 | Ongoing |
| 41 | Ikalikha Primary school | 4-038-215-2630204-104-2019/20-030 | 1,500,000.00 | - | Construction of 2 No. classrooms up to completion. NOTE: Terrain is uneven hence requires more cut and fill to attain suitable level for foundation. | 1,500,000.00 | New |
| 42 | Esibuye Primary school | 4-038-215-2630204-104-2019/20-031 | 1,500,000.00 | - | Construction of Administration block; containing 4 no. offices. Works; Substructure, walling, roofing, plaster/external render, flooring & painting to completion. Remaining works; Ceiling and electrification. | 800,000.00 | New |
| 43 | Salvation Army Emuhondo Special school for the Deaf | 4-038-215-2630204-104-2019/20-032 | 800,000.00 | - | Purchase of land approximately 0.36 Ha. | 800,000.00 | New |
| 44 | Ebuyalu Primary school | 4-038-215-2630204-104-2019/20-033 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 45 | Ebucheli Primary school | 4-038-215-2630204-104-2019/20-034 | 600,000.00 | - | Purchase of land approximately 0.30 Ha. | 600,000.00 | New |
| 46 | Mwitukho Primary school | 4-038-215-2630204-104-2019/20-035 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 47 | Ematsuli Primary school | 4-038-215-2630204-104-2019/20-036 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 48 | Mukhombe Primary school | 4-038-215-2630204-104-2019/20-037 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
|  |  |  |  |  |  | 34,445,000.00 |  |
|  | SECONDARY SCHOOLS PROJECTS |  |  |  |  |  |  |
| 49 | Esibila Secondary School | 4-038-215-2630205-104-2019/20-001 | 11,000,000.00 | 1,000,000.00 | Co-fund; Construction of storey building, containing 2 no. Laboratories each to accommodate 40 students when complete and 2 No. classrooms. Works include; Roofing. Remaining works general finishes to be financed between NGCFC and BOM in the next Financial year. | 1,000,000.00 | Ongoing |
| 50 | Esibila Boys's secondary school | 4-038-215-2630205-104-2019/20-002 | 1,600,000.00 | - | Construction of 2 No. classrooms up to completion | 1,600,000.00 | New |
| 51 | Emmabwi secondary school | 4-038-215-2630205-104-2019/20-003 | 700,000.00 | - | Purchase of land approximately 0.4 Ha. | 700,000.00 | New |
| 52 | Mungoye Secondary School | 4-038-215-2630205-104-2019/20-004 | 1,000,000.00 | - | Purchase of Land approximately 0.5 Ha. | 1,000,000.00 | New |
| 53 | Ebusiloli Secondary School | 4-038-215-2630205-104-2019/20-005 | 9,000,000.00 | 6,400,000.00 | Construction of Dining Hall/kitchen-storey; Plaster/external render to completion. Remaining Works 1st phase-ground floor include; flooring, glazing, painting & electrification and 2nd phase; Includes the Entire 1st floor carrying 3 no. classrooms and offices. Can hold 500 students when complete. | 600,000.00 | Ongoing |
| 54 | Essunza Secondary School | 4-038-215-2630205-104-2019/20-006 | 500,000.00 | - | Fencing of the compound approximate 1.1 Ha; Angle bars, barbed wire & Installation of steel gate | 500,000.00 | New |
| 55 | Esirulo secondary school | 4-038-215-2630205-104-2019/20-007 | 2,500,000.00 | - | Construction of Laboratory; substructure, walling, roofing, fitting of shutters, plaster/external render Remaining works; glazing, flooring, fitting of ceiling board, electrification, fitting of work tops & painting | 1,000,000.00 | New |
| 56 | Emanyinya secondary school | 4-038-215-2630205-104-2019/20-008 | 7,544,000.00 | - | Co-fund; Purchase of 51-seater School Bus-Isuzu. Refer to Schools proposal attached committing that this is a co- funded project and NGCDFC part is to provide kshs. 3M only. Balance to be provided by the institution. - Forward evidentiary proof that BoM have the balance of the funds - NGCDFC will fund the bus up to the principal amount WITHOUT PROVISION FOR HIRE PURCHASE | 3,000,000.00 | New |
| 57 | Bunyore Boys' secondary school | 4-038-215-2630205-104-2019/20-009 | 750,000.00 | - | Construction of 1 classroom up to completion | 750,000.00 | New |
| 58 | Mwituha secondary school | 4-038-215-2630205-104-2019/20-010 | 5,000,000.00 | 2,000,000.00 | Construction of Dining Hall/kitchen; Walling up to wall plate NOTE: project is being done on phases. Already 1st phase(kitchen) is complete and on use. 2nd phase is Dining Hall- To be done as specified above. Remaining works; roofing, fitting of shutters and general finishes. Dining Hall expected to hold 500 students when complete. - Indicate capacity - Allocate adequate funds to enable construction of project to usable level | 1,000,000.00 | 0n-going |
| 59 | Ikumu Secondary school | 4-038-215-2630205-104-2019/20-011 | 1,000,000.00 | - | Purchase of Land approximately 0.5 Ha. | 1,000,000.00 | New |
| 60 | Ebuyalu secondary school | 4-038-215-2630205-104-2019/20-012 | 1,200,000.00 | - | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 61 | Esikhuyu Secondary school | 4-038-215-2630205-104-2019/20-013 | 800,000.00 | - | Purchase of Land approximately 0.44 Ha. | 800,000.00 | New |
| 62 | Ebukhaya secondary school | 4-038-215-2630205-104-2019/20-014 | 4,500,000.00 | - | Construction of Dining Hall/Kitchen; erection from foundation to completions NOTE: To be done on phases. 1st phase to do kitchen to completion and 2nd to do Hall (to be factored in the next financial year). | 1,000,000.00 | New |
| 63 | Emmukunzi Secondary School | 4-038-215-2630205-104-2019/20-015 | 600,000.00 | - | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 64 | Ebusiratsi secondary school | 4-038-215-2630205-104-2019/20-016 | 5,000,000.00 | 1,000,000.00 | Construction of a dormitory; Finishes at ground floor -Fitting of shutters, glazing plaster/external render, wiring, flooring & painting to completion. NOTE: we committed to provide a balance 4million to complete our part on co-funding. Works remaining to be done by amount are as specified above. The dormitory (which is a storey building) when complete will hosts 432 beds. | 4,000,000.00 | Ongoing |
| 65 | Ematsuli secondary school | 4-038-215-2630205-104-2019/20-017 | 600,000.00 | - | Renovation of 2 No. Classrooms; Re-roofing, reflooring, wall repairs, fitting of shutters, glazing & painting to completion. | 600,000.00 | New |
| 66 | Ebunangwe High School | 4-038-215-2630205-104-2019/20-018 | 3,000,000.00 | - | Construction of 1 no. Laboratory; Substructure to roof. Remaining works; fitting of shutters and general finishes. It will take 40 students at a time. | 1,000,000.00 | New |
|  |  |  |  |  |  | 21,350,000.00 |  |
|  | TERTIARY INSTITUTIONS PROJECTS |  |  |  |  |  |  |
| 67 | Bunyore Teachers Training College | 4-038-215-2630206-104-2019/20-001 | 8,000,000.00 | - | Construction of 2 No. blocks of dormitories. Will accommodate approximately 150 beds each. NOTE: will be done on phases. 1st phase to fund 1 no. dormitory to completion and lay foundation (sub-structure) for second dormitory. 2nd phase expected to fund the remaining dormitory to completion. | 6,000,000.00 | New |
| 68 | Ebunangwe technical teachers training Institute | 4-038-215-2630206-104-2019/20-002 | 4,017,543.11 |  | Fencing of the compound approximate 9.04 Ha.; Concrete posts, chain link & barbed wire | 4,017,543.11 | New |
|  |  |  |  |  |  | 10,017,543.11 |  |
|  | SECURITY PROJECTS |  |  |  |  |  |  |
| 69 | Emuhaya Administration Centre | 4-038-215-2640507-109-2019/20-001 | 49,666,629.60 | 36,000,000.00 | Construction of sub-county offices -storey; Walling, fitting of shutters, plaster at the 2nd floor. NOTE: Project will contain three floors when complete. Project is expected to accommodate Sub county departmental Offices. Ground floor and 1st floor contains 15 offices and 2 no. board rooms of approximately a capacity of 50 people. 2nd floor and 3rd floor will not be sub divided. Officers wishing to be accommodated in 2nd & 3rd floor will be allocated space. | 1,000,000.00 | Ongoing |
| 70 | Ipali AP Camp/Assistant chief office | 4-038-215-2640507-109-2019/20-002 | 1,000,000.00 | - | Construction of 3 No. units staff houses to completion | 1,000,000.00 | New |
| 71 | Ipali AP Camp/Assistant chief office | 4-038-215-2640507-109-2019/20-003 | 150,000.00 | - | Construction of 2 No. Doors Pit Latrine to completion | 150,000.00 | New |
| 72 | Essaba AP Camp | 4-038-215-2640507-109-2019/20-004 | 2,000,000.00 | - | Construction of Administration office for police; substructure walling, roofing, plaster/external render. Remaining works; fitting of ceiling Board & electrification. To contain 4 no. offices. | 800,000.00 | New |
| 73 | Ematsuli AP Camp/Assistant chief office | 4-038-215-2640507-109-2019/20-005 | 600,000.00 | - | Construction of Administration office for assistant chief; substructure, walling, roofing, plaster/external render, flooring and painting to completion. To contain 2 no. offices and reception. Indicate no of units for the office Indicate level of completion | 600,000.00 | New |
| 74 | Emuhaya Sub-county Police Offices. | 4-038-215-2640507-109-2019/20-006 | 6,000,000.00 | - | Construction of Administration office; To be done in phases. 1st phase; Works; substructure & walling. 2nd phase: Works; Roofing, shutters, glazing, electrification and general finishes to completion. To contain 6 no. offices & 2 no cells. | 1,500,000.00 | New |
| 75 | Emurembe Administration police/Assistant chief's | 4-038-215-2640507-109-2019/20-007 | 600,000.00 | - | Purchase of Land approximately 0.2 Ha. | 600,000.00 | New |
| 76 | Emuhaya magistrate court | 4-038-215-2640507-109-2019/20-008 | 5,000,000.00 | - | Construction of the court chamber; substructure to roof. Remaining Works. Fitting shutters and general finishes. | 1,800,000.00 | New |
| 77 | Emakakha Police Post | 4-038-215-2640507-109-2019/20-009 | 1,500,000.00 | - | Construction of an Administration block; Contains 10 no. offices Works; Plaster/external render, flooring, & painting. Remaining works; fitting of ceiling board and electrification. | 1,000,000.00 | Ongoing |
| 78 | Duka moja Police Patrol Base | 4-038-215-2640507-109-2019/20-010 | 800,000.00 | - | Purchase of Land approximately 0.4 Ha. | 800,000.00 | New |
| 79 | Ebukhaya AP Camp | 4-038-215-2640507-109-2019/20-011 | 600,000.00 | - | Construction of 1 No. unit staff house; substructure, walling, roofing, plaster/external render, flooring, fixing of electrical conduits and painting. Remaining Works; ceiling board and wiring. | 400,000.00 | New |
| 80 | Rural Electrification and Renewable Energy Corporation | 4-038-215-2640507-109-2019/20-012 | 6,261,292.76 | - | Establishment of 1 x 50 Kva. 11/0.433 KV transformers, construction of approximately 1.2 KM of KV three phase line and associated 0.5 KM 3 phase and 3.56 KM Single phase lines and connect approximately 55 No. household customers in single phase and 1 No. customer in 3 phase | 3,130,646.38 |  |
|  |  |  |  |  |  | 12,780,646.38 |  |
|  | SPORTS |  |  |  |  |  |  |
| 81 | Constituency Sports Tournament | 4-038-215-2640509-112-2019/20-001 | 2,666,808.10 | 2,666,808.10 | Carry out Constituency Sports tournament and the wining team to be awarded with trophies, balls and playing kits | 2,666,808.10 | Ongoing |
|  |  |  |  |  |  | 2,666,808.10 |  |
|  | ENVIRONMENTAL PROJECTS |  |  |  |  |  |  |
| 82 | Ebusiekwe Hills | 4--038-113-2210502-110-2019/20-001 | 250,000.00 | - | Planting of trees; 3125 stems. NOTE: Office to seek guidance from relevant department. Forward letter of ownership and sustainability for the project | 250,000.00 | New |
| 83 | Esalwa Natural spring/Stream | 4--038-113-2210502-110-2019/20-002 | 100,000.00 | - | Planting of 1000 stems of bamboo along the stream/rehabilitation of the spring Indicate no of bamboo tree seedlings | 100,000.00 | New |
| 84 | Essaba natural spring/stream | 4--038-113-2210502-110-2019/20-003 | 100,000.00 | - | Planting of 1000 stems of bamboo along the stream/rehabilitation of the spring Indicate no of bamboo tree seedlings | 100,000.00 | New |
| 85 | Ekaita natural spring/stream | 4--038-113-2210502-110-2019/20-004 | 100,000.00 | - | Planting of 1000 stems of bamboo along the stream/rehabilitation of the spring Indicate no of bamboo tree seedlings | 100,000.00 | New |
|  |  |  |  |  |  | 550,000.00 |  |
| 86 | EMERGENCY |  |  |  |  |  |  |
|  |  | 4-038-215-2640200-101-2019/20-001 |  |  | To cater for any unforeseen occurrences in the Constituency during the financial year | 7,198,241.38 | Ongoing |
|  |  |  |  |  |  | 137,371,724.14 |  |

The committee approved the above budget as the one for the Financial Year 2019/2020 and instructed the Fund Account Manager to expedite and send/forward it to the NG-CDF Board. A part from approving the Budget Proposal members also requested for clarification on the differences of the cost of construction per classroom. Bringing out this question, it was noted that, “the average cost of construction of a classroom was kshs. 600,000 (labour based), while projects like; Esibila Boys Sec. School, Ikalikha Primary School, Ebututi primary school,Msiakhupa Primary School, Esinaka Primary School, Mumboko primary school & Bunyore Boys Sec. School, the cost of construction of a classroom was high. Why?”. The FAM & Chair reminded members that the difference was as a result of topography or Terrain and soil status. Refer to the table below for more details;

| NO: | NAME OF INSTITUTION | REASON | CONCLUSION |
| --- | --- | --- | --- |
| 1. | ESIBILA SEC. SCHOOL | Terrain is full granitic rocks | Requires more funds for levelling. |
| 2. | IKALIKHA PRIMARY SCHOOL | Terrain is uneven, several heaps & falls, numerous tree stumps | Requires more funds or levelling. |
| 3. | MSIAKHUPA PRIMARY SCHOOL | Terrain is uneven, its gradient slopes downstream | Requires more funds for levelling. |
| 4. | ESINAKA PRIMARY SCHOOL | The soil status is water logged & mushy | Requires more funds for the reinforcement of the foundation. |
| 5. | MUMBOKO PRIMARY SCHOOL | Soil status is water logged, | Requires more funds for the reinforcement of the foundation. |
| 6. | BUNYORE BOYS SEC. SCHOOL | Terrain is uneven/rugged involves cut & fill to achieve required level for erection of the classroom | Requires more funds for leveling. |
| 7. | EBUTUTI PRIMARY SCHOOL | The ground is rocky | Requires more funds for levelling. |

7.MIN. 77: EMU/NG-CDFC/MIN. 77/OCTOBER/2019;

SPORTS:

The Fund Manager briefed the committee on sports as below:

NGCDFC Emuhaya starts running from September to 23rd or 24th December.

This time round we are late and the official launch date was done on 20/10/2019 at Ebukanga Primary School.

He informed the committee that the budget for running the whole tournament and the fixture (timetable) have been completed by the Sports Committee.

The total budget arrived at by the sports Sub Committee was Kshs. 2,713,680.00 and as per their fixture the balls will run from 20 /10/2019 to the finals on 24/10/2019. A part from football we will also have athletics.

Members deliberated on the budget and the fixture. One member noted that, we needed to focus next time on installation of goal posts since goal posts on most of the field were wearing out.

Also included in the budget was the acquisition/purchase of equipment’s to be used during the sport tournament. Key items highlighted were balls and first aid kits.  The FAM explained that as the fixture they are 43 men teams and 24 ladies’ teams. Therefore, we need 80 balls, 67 balls will be given to the teams. Each team will receive one ball each. Thirteen (13) balls will be held in the office. During finals, out of the 13 balls, the winning team and the first runners will receive two balls each. The remaining nine (9) balls will be at the office to be used on games and any other emergencies.

So far, the following funds have been spent in facilitating the tournament (that’s as per 27th/10/20190

| S/NO | ACTIVITY | AMOUNT |
| --- | --- | --- |
| 1. | Facilitation meeting club officials | 102,000.00 |
| 2. | Launch on 20th oct.2019. | 219,600.00 |
| 3. | Facilitation of match officials on 26th & 27th Oct.2019 | 239,000.00 |
| 4. | Facilitation of match officials on 2nd,3rd & 5th Oct.2019 | 113,000.00 |
| 5. | Purchase of 80 no. balls (Adidas) – 80x3300.00 | 264,000.00 |
| 6. | Purchase of 12 no. first aid kits. – 12x4000.00 | 48,000.00 |
| TOTAL |  | 985,600.00 |

The committee approved the expenditure of kshs. 985,600.00 as illustrated in the table above and advised that the budget be relooked to conform with the 2% provided in sports as per the Act.

8.MIN. 78: EMU/NG-CDFC/MIN. 77/OCTOBER/2019; CLOSURE;

There being no other business, the chairman thanked all members for their contribution and the         meeting ended with a word of prayer from Ms. Miriam Ekambi.

CHAIRMAN ………………………………………………………………

SECRETARY ………………………………………………………………..