MEETING NO. 19

MINUTES OF EMUHAYA NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND COMMITTEE HELD ON 24TH  OCTOBER, 2019 AT THE NG-CDFC OFFICE’S BOARDROOM

PRESENT                                                                        DESIGNATION

1.MR. CHARLES OMUCHILO                              NG-CDFC CHAIRMAN

2.MR. GIDEON OYALO                                       SECRETARY

3.BENJAMIN OPANDE                                        MEMBER

4.MRS. ROSELINE AKISO OCHONYA              MEMBER

5.MR. JOEL AKAKI ATIELI                                 MEMBER

6.MS. FRIDAH AYOTI                                          MEMBER

7.MRS. MIRIAM EKAMBI                                    MEMBER

8.PAUL CHARLES MOGENDI                             FAM

9. JACK MASUA                                                     DCC

INATENDANCE.

1.MR. REARDON MUSUTA                                            OVERSIGHT

2.MR. AYUB EBOLE                                                       CLERK OF WORKS

3.MR. HELLAM AINEAH                                                CLERICAL OFFICER

ABSENT WITH APOLOGY:

The meeting was called to order by the chairman at 11.40 AM. With a word of prayer from Mrs. Roselyne Akiso

CONFIRMATION OF THE QUORUM

Members noted that the meeting was quorate to transact the business of the committee.

ADOPTION OF THE AGENDA.

The agenda for the meeting was adopted as follows.

- Opening prayer

- Attendance

- Adoption of the Agenda.

- Reading and confirmation of previous minutes.

- Matters arising.

- Reports from sub-committees

- Disposal of office vehicles ie GKA 459 S.

- Finance statement on expenditure.

- NG-CDF staff salary review and Leave allowance.

- State of projects 2018-2019.

- Budget proposal for 2019-2020 FY.

- Date for benchmarking.

- Closing prayer.

A member noted the weight and urgency of agenda no. 11 on Budget proposal and suggested that it be given enough time to handle it. The committee agreed and resolved to handle it and postpone the other agenda on a separate day.  A part from minute no. 11 member agreed to discuss sports which was also of urgency. Member agreed to discuss the two agendas and pushed forward the rest to the next meeting. Proposal of the agenda was done by Mr. Joel Akaki   and seconded by Ms Fridah Ayoti.

MIN. 74 : EMU/NG-CDFC/MIN. 74/OCTOBER/2019;

READING AND CONFIRMATION OF PREVIOUS MINUTES.

Minutes of the previous meeting were perused through by the secretary and members confirmed it to be a true record of the meeting. Proposal was done by Mrs. Roseline Akiso and seconded by Ms. Frida Ayoti.

MIN. 75 : EMU/NG-CDFC/MIN. 75/OCTOBER/2019;

MATTERS  ARISING FROM THE MINUTES.

Emergency allocation.

It was noted that Ebukhaya secondary school had not been considered as earlier agreed in the previous meeting. The committee resolved that the case be addressed immediately to assist the school which is facing that big challenge of ablution facility.

MIN. 76 : EMU/NG-CDFC/MIN. 76/OCTOBER/2019;

BUDGET PROPOSAL FOR 2019/2020 F/Y.

It was noted that Emuhaya NG-CDFC through a circular from the board with ref: NG-CDFB/CEO/BOARDCIRCULARS vol ii (014), had been allocated a total of Kshs. 137,371,724.14 for 2018/2019 financial year. This amount is Inclusive of Kshs.  7,198,241.38 reserved for emergency. In view of that, the committee, having held wards stakeholders’ meetings on 8th, 9th and 11th October 2019, prioritized projects for funding and came up with the following budget for 2019/2020 financial year for onward submission to the NG-CDF Board for consideration for funding.

The meeting also took into account that on-going projects to be given priority over new projects.

| NO. | PROJECT NAME | PROJECT ACTIVITY | AMOUNT ALLOCATED | CURRENT STATUS |
| --- | --- | --- | --- | --- |
|  | ADMINISTRATION/ RECURRENT |  |  |  |
| 1 | Employees Salaries | Payment of staff salaries and gratuity | 3,577,448.25 | Ongoing |
| 2 | Goods & Services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 2,980,000.00 | Ongoing |
| 3 | National Social Security Fund | Payment of NSSF deductions | 255,715.20 | Ongoing |
| 4 | National Hospital Insurance Fund | Payment of NHIF deductions | 85,200.00 | Ongoing |
| 5 | Committee Expenses | Payment of NG-CDFC allowance | 1,344,000.00 | Ongoing |
|  |  |  | 8,242,363.45 |  |
|  | MONITORING & EVALUATION/ CAPACITY BUILDING |  |  |  |
| 6 | Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, airtime, travel and subsistence | 1,200,000.00 | Ongoing |
| 7 | Committee Expenses | Payment of Committee allowances, transport, conferences | 1,286,181.00 | Ongoing |
| 8 | NG-CDFC/PMC Capacity Building | Undertake training of the PMCs/NG-CDFCs on NG-CDF related issues | 1,635,000.72 | Ongoing |
|  |  |  | 4,121,181.72 |  |
|  | BURSARY/SOCIAL SECURITY |  |  |  |
| 9 | Bursary for Secondary Schools | Payment of bursary to needy students | 20,000,000.00 | Ongoing |
| 10 | Bursary for Tertiary Institutions | Payment of bursary to needy students | 14,000,000.00 | Ongoing |
| 11 | Bursary special school | Payment of bursary to needy students | 2,000,000.00 | On-going |
|  |  |  | 36,000,000.00 |  |
|  | PRIMARY SCHOOLS PROJECTS |  |  |  |
| 12 | Itumbu Primary School | Renovation of 4 No. Classrooms -Re-flooring, wall repairs & re-painting | 1,200,000.00 | New |
| 13 | Musirili Primary School | Purchase of Land approximately 0.4 Ha | 800,000.00 | New |
| 14 | Esibakala Primary School | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 15 | Ebusiloli Primary School | Construction of 1No. Classroom up to completion | 600,000.00 | New |
| 16 | Emurembe Primary School | Construction of 2 No classroom up to completion | 1,200,000.00 | New |
| 17 | Kilingili Primary School | Renovations of 3 No. classrooms-reflooring & painting | 1,000,000.00 | New |
| 18 | Ilungu Primary School | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 19 | Emusutswi Primary school | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 20 | Mwituha Primary School | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 21 | Assebu Primary School | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 22 | Mundichiri Primary School | Construction of 2 No. classroom up to completion | 600,000.00 | New |
| 23 | Emmukunzi Primary School | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 24 | Elununi Primary School | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 25 | Msiakhupa Primary School | Construction of 2 No. classrooms up to completion | 1,500,000.00 | New |
| 26 | Ebukhuliti Primary School | Construction of 2 No.classrooms up to completion | 1,200,000.00 | New |
| 27 | Essaba Primary School | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 28 | Mukhungu Primary School | Construction of 2 No.classrooms up to completion | 1,200,000.00 | New |
| 29 | Ebututi Primary School | Construction of 1 classroom up to completion | 700,000.00 | New |
| 30 | Emusire Primary School | Construction of Administration block;Substructure,walling,roofing,plaster/external render,flooring,painting | 800,000.00 | New |
| 31 | Esinaka Primary School | Construction of 2 No. classrooms up to completion | 2,200,000.00 | New |
| 32 | Mungoye Primary School | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 33 | Mumboko Primary School | Construction of 2 No. classrooms up to completion | 1,600,000.00 | New |
| 34 | Emwatsi Primary School | Construction of Administration block;Substructure,walling,roofing,plaster/external render,flooring,painting | 800,000.00 | New |
| 35 | Eluhobe primary school | Construction of Administration block;Substructure,walling,roofing,plaster/external render,flooring,painting | 800,000.00 | New |
| 36 | Ebulondi primary school | Construction of Administration block;Substructure,walling,roofing,plaster/external render,flooring,painting | 800,000.00 | New |
| 37 | Ebukobelo primary school | Construction of 1 No. classrooms up to completion | 600,000.00 | New |
| 38 | Emmabwi primary school | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 39 | Ebukanga Primary school | Construction of Administration block;Substructure,walling,roofing,plaster/external render,flooring,painting | 800,000.00 | New |
| 40 | Ikalikha Primary school | Completion purchase of approximately 0.48 Ha. | 345,000.00 | Ongoing |
| 41 | Ikalikha Primary school | Construction of 2 No. classrooms up to completion | 1,500,000.00 | New |
| 42 | Esibuye Primary school | Construction of Administration block;Substructure,walling,roofing,plaster/external render,flooring,painting | 800,000.00 | New |
| 43 | Salvation Army Emuhondo Special school for the Deaf | Purchase of land approximately 0.36 Ha. | 800,000.00 | New |
| 44 | Ebuyalu Primary school | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 45 | Ebucheli Primary school | Purchase of land approximately 0.30 Ha. | 600,000.00 | New |
| 46 | Mwitukho Primary school | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 47 | Ematsuli Primary school | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 48 | Mukhombe Primary school | Construction of 1 No. classroom up to completion | 600,000.00 | New |
|  |  |  | 34,445,000.00 |  |
|  | SECONDARY SCHOOLS PROJECTS |  |  |  |
| 49 | Esibila Secondary School | Co-fund; Construction of Laboratory and 2 No. classrooms; storey-roofing | 1,000,000.00 | Ongoing |
| 50 | Esibila Boys's secondary school | Construction of 2 No. classrooms up to completion | 1,600,000.00 | New |
| 51 | Emmabwi secondary school | Purchase of land approximately 0.4 Ha. | 700,000.00 | New |
| 52 | Mungoye Secondary School | Purchase of Land approximately 0.5 Ha. | 1,000,000.00 | New |
| 53 | Ebusiloli Secondary School | Construction of Dining Hall/kitchen-storey; Plaster/external render | 600,000.00 | Ongoing |
| 54 | Essunza Secondary School | Fencing of the compound approximate 1.1 Ha; Angle bars , barbed wire & Installation of steel gate | 500,000.00 | New |
| 55 | Esirulo secondary school | Construction of Laboratory; substructure, walling, roofing, fitting of shutters, plaster/external render | 1,000,000.00 | New |
| 56 | Emanyinya secondary school | Co-fund; Purchase of 51 seater School Bus-Isuzu | 3,000,000.00 | New |
| 57 | Bunyore Boys' secondary school | Construction of 1 classroom up to completion | 750,000.00 | New |
| 58 | Mwituha secondary school | Construction of Dining Hall/kitchen; Walling up to wall plate | 1,000,000.00 | 0n-going |
| 59 | Ikumu Secondary school | Purchase of Land approximately 0.5 Ha. | 1,000,000.00 | New |
| 60 | Ebuyalu secondary school | Construction of 2 No. classrooms up to completion | 1,200,000.00 | New |
| 61 | Esikhuyu Secondary school | Purchase of Land approximately 0.44 Ha. | 800,000.00 | New |
| 62 | Ebukhaya secondary school | Construction of Dining Hall/Kitchen; Substructure-Excavation of foundation trench to casting of the floor slab. | 1,000,000.00 | New |
| 63 | Emmukunzi Secondary School | Construction of 1 No. classroom up to completion | 600,000.00 | New |
| 64 | Ebusiratsi secondary school | Construction of dormitory; Finishes at ground floor -Fitting of shutters, plaster/external render, wiring, flooring & painting. | 4,000,000.00 | Ongoing |
| 65 | Ematsuli secondary school | Renovation of 2 No. Classrooms; re-roofing, reflooring, wall repairs, fitting of shutters, glazing & painting | 600,000.00 | New |
| 66 | Ebunangwe High School | Construction of Laboratory ;Substructure to roof | 1,000,000.00 | New |
|  |  |  | 21,350,000.00 |  |
|  | TERTIARY INSTITUTIONS PROJECTS |  |  |  |
| 67 | Bunyore Teachers Training College | Construction of 2 No. blocks of dormitories | 6,000,000.00 | New |
| 68 | Ebunangwe technical teachers training Institute | Fencing of the compound approximate 9.04 Ha.;Concrete posts, chain link & barbed wire | 4,017,483.11 | New |
|  |  |  | 10,017,483.11 |  |
|  | SECURITY PROJECTS |  |  |  |
| 69 | Emuhaya Administration Centre | Construction of the sub-county offices storey; Walling, fitting of shutters, plaster at 2nd floor. | 1,000,000.00 | Ongoing |
| 70 | Ipali AP Camp/Assistant chief office | Construction of 3 No. units staff houses to completion | 1,000,000.00 | New |
| 71 | Ipali AP Camp/Assistant chief office | Construction of 2 No. Doors Pit Latrine to completion | 150,000.00 | New |
| 72 | Essaba AP Camp | Construction of Administration office for police;substructure walling,roofing,plaster/external render. | 800,000.00 | New |
| 73 | Ematsuli AP Camp/Assistant chief office | Construction of Administration office for assistant chief;substructure,walling, roofing,plaster/external render, flooring and painting | 600,000.00 | New |
| 74 | Emuhaya Sub-county Police services | Construction of Administration office; substructure & walling | 1,500,000.00 | New |
| 75 | Emurembe Administration police/Assistant chief's | Purchase of Land approximately 0.2 Ha. | 600,000.00 | New |
| 76 | Emuhaya magistrate court | Construction of the court chamber; substructure to roof | 1,800,000.00 | New |
| 77 | Emakakha Police Post | Construction of Administration block; Plaster/external render, flooring, & painting | 1,000,000.00 | Ongoing |
| 78 | Duka moja Police Patrol Base | Purchase of Land approximately 0.4 Ha. | 800,000.00 | New |
| 79 | Ebukhaya AP Camp | Construction of 1 No. units staff houses;substructure,walling, roofing, plaster/external render, flooring, fixing of electrical conduits and painting. | 400,000.00 | New |
| 80 | Rural Electrification and Renewable Energy Corporation | Establishment of 1 x 50 Kva. 11/0.433 KV transformers, construction of approximately 1.2 KM of KV three phase line and associated 0.5 KM 3 phase and 3.56 KM Single phase lines and connect approximately 55 No. household customers in single phase and 1 No. customer in 3 phase | 3,130,646.38 |  |
|  |  |  | 12,780,646.38 |  |
|  | SPORTS |  |  |  |
| 81 | Constituency Sports Tournament | Carry out Constituency Sports tournament and the wining team to be awarded with trophies, balls and playing kits | 2,666,808.10 | Ongoing |
|  |  |  | 2,666,808.10 |  |
|  | ENVIRONMENTAL PROJECTS |  |  |  |
| 82 | Anyole metrological community radio station-Ebusiekwe Hills | Planting of trees; 3125 stems | 250,000.00 | New |
| 83 | Esalwa Natural spring/Stream | Planting of Bamboo along the stream/rehabilitation of the spring | 100,000.00 | New |
| 84 | Essaba natural spring/stream | Planting of Bamboo along the stream/rehabilitation of the spring | 100,000.00 | New |
| 85 | Ekaita natural spring/stream | Planting of Bamboo along the stream/rehabilitation of the spring | 100,000.00 | New |
|  |  |  | 550,000.00 |  |
| 86 | EMERGENCY | To cater for any unforeseen occurrences in the Constituency during the financial year | 7,198,241.38 | Ongoing |
|  |  |  | 137,371,724.14 |  |

The committee approved the above budget as the one for the Financial Year 2019/2020 and instructed the Fund Account Manager to expedite and send/forward it to the NG-CDF Board.

7.MIN. 77: EMU/NG-CDFC/MIN. 77/OCTOBER/2019;

SPORTS:

The Fund Manager briefed the committee on sports as below:

NGCDFC Emuhaya starts running from September to 23rd or 24th December.

This time round we are late and the official launch date was done on 20/10/2019 at Ebukanga Primary School.

He informed the committee that the budget for running the whole tournament and the fixture (timetable) have been completed by the Sports Committee.

The total budget arrived at by the sports Sub Committee was Kshs. 2,713,680.00 and as per their fixture the balls will run from 20 /10/2019 to the finals on 24/10/2019. A part from football we will also have athletics.

Members deliberated on the budget and the fixture. One member noted that, we needed to focus next time on installation of goal posts since goal posts on most of the field were wearing out.

Also included in the budget was the acquisition/purchase of equipment’s to be used during the sport tournament. Key items highlighted were balls and first aid kits.  The FAM explained that as the fixture they are 43 men teams and 24 ladies’ teams. Therefore, we need 80 balls, 67 balls will be given to the teams. Each team will receive one ball each. Thirteen (13) balls will be held in the office. During finals, out of the 13 balls, the winning team and the first runners will receive two balls each. The remaining nine (9) balls will be at the office to be used on games and any other emergencies.

So far, the following funds have been spent in facilitating the tournament (that’s as per 27th/10/20190

| S/NO | ACTIVITY | AMOUNT |
| --- | --- | --- |
| 1. | Facilitation meeting club officials | 102,000.00 |
| 2. | Launch on 20th oct.2019. | 219,600.00 |
| 3. | Facilitation of match officials on 26th & 27th Oct.2019 | 239,000.00 |
| 4. | Facilitation of match officials on 2nd,3rd & 5th Oct.2019 | 113,000.00 |
| 5. | Purchase of 80 no. balls (Adidas) – 80x3300.00 | 264,000.00 |
| 6. | Purchase of 12 no. first aid kits. – 12x4000.00 | 48,000.00 |
| TOTAL |  | 985,600.00 |

The committee approved the expenditure of kshs. 985,600.00 as illustrated in the table above and advised that the budget be relooked to conform with the 2% provided in sports as per the Act.

8.MIN. 78: EMU/NG-CDFC/MIN. 77/OCTOBER/2019; CLOSURE;

There being no other business, the chairman thanked all members for their contribution and the         meeting ended with a word of prayer from Ms. Miriam Ekambi.

CHAIRMAN ………………………………………………………………

SECRETARY ………………………………………………………………..