ELDAS

IEBC NUMBER 037

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND

PROJECT PROPOSAL

2018/2019 FINANCIAL YEAR

SUBMITTED

NOVEMBER 2018

| NG-CDF ELDAS | National Government Constituencies Development Fund Eldas Constituency P.O Box 491-70200. WAJIR Cell: +254 722930356 Email: cdfeldas@ngcdf.go.ke ¦ Website: www.ngcdf.go.ke |
| --- | --- |

ELDAS  NG- CDFC MEETING HELD ON 12TH NOVEMBER 2018  AT  ELDAS NG-CDF OFFICE

MEMBERS PRESENT:

Present

- Mohamud Abdi Ibrahim– chairman

- Irshad Mohamed  –FAM

- Asha Bishar Jelle – Secretary

- Adow Shahu Dakat – member

- Bishara Gaiya Ahmed – member

- Vincent Loctari Lomachar - DCC– member

- Ibrahim Khalif Abdullahi –member

- Mohamed Gabow Kulow – member

- Shamsa Abdi Ahmed –  member

AGENDA

- Preliminaries

- Confirmation Of Previous Minutes

- NG-CDF Projects Proposal For Financial Year 2018/2019

- A.O.B

MIN 01/12/11/2018 INTRODUCTION

The meeting was called into order at 9.00 am. The chairperson introduced the agendas. Thereafter he requested Mr. Ibrahim to open the sitting with a word of prayer.

MIN 02/12/11/2018 CONFIRMATION OF PREVIOUS MEETING MINUTES:

The meeting was started with a word of prayer from Ibrahim Khalif Abdullahi and the Chairman welcomed all members and thanked them for being punctual, he urged members to contribute to the meeting agendas. The secretary read through the minutes of the previous meeting. The minutes were confirmed to be the true copy of the deliberations by Shamsa Abdi Ahmed who was seconded by Mohamed Gabow Kulow. There were no matters arising.

MIN 03/12/11/2018 NG-CDF PROJECTS PROPOSAL  FOR FINANCIAL YEAR 2018/2019

The Chairman introduced that the core business of the day was to discuss and approve the project proposal for the Financial Year 2018/2019. He informed the sitting that the role of the members using the needs from the four wards in the constituency was to select projects amongst those requested by different institutions and also approve reasonable costs and estimates. The members also scrutinized the needs assessment reports that were carried out in the last financial year. After agreeing on these roles, the members came up with bench marks that will guide them in approving the projects. These included; -

- Equality – this is to ensure that every ward should benefit from the kitty. The members must ensure that within the ward itself equality must be ensured. All the locations, sub locations, villages, settlements must equally be funded.

- Priority – the need of the people must be primary in selecting the projects. During the needs assessment exercise projects were arranged in the order of their priority.

- Legality – the project financed must be within the scope of NGCDF legal frame work. It should not be a project of personal gain, political activities or religious affiliations. Any projects with such issues would not be approved.

- Cost – in approving the projects the members also should consider reasonability and value for money.

The Fund Manager thereafter drew members attention to NG-CDF board circular referenced; NG-CDFB /CIRCULARs Vol.11 (008) dated 30th October, 2018, Submission of Project proposals for the 2018/2019 financial year which the committee discussed at length. He also informed the members of the NG-CDF Act in relation to projects identification and that the available money for the Financial Year 2018/2019 was Kshs 109,040,875.52.

The Chair informed the sitting that they would use the Ward Reports that had been prepared after their just concluded needs assessment exercise.

After lengthy deliberations the NG-CDF committee agreed on the following projects to be funded in the Financial Year 2017 – 2018 in all the four wards in the Constituency:

| PROJECT NAME | PROJECT ACTIVITY | AMOUNT ALLOCATED | STATUS |
| --- | --- | --- | --- |
| ADMINISTRATION & RECURRENT |  |  |  |
| Employees Salaries | Payment of staff salaries and gratuity | 3,217,800.00 | Ongoing |
| Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 1,264,437.93 | Ongoing |
| NSSF | Payment of NSSF Deductions | 81,600.00 | Ongoing |
| NHIF | Payment of NHIF Deductions | 120,600.00 | Ongoing |
| Committee Expenses | Payment of Committee sitting allowances, transport, conferences | 1,080,000.00 | Ongoing |
| Monitoring & Evaluation/Capacity Building |  |  |  |
| Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 500,000.00 | Ongoing |
| Committee Expenses | Payment of Committee sitting allowances, transport, conferences | 571,226.14 | Ongoing |
| NG-CDFC/PMC Capacity Building | Undertake Training of the PMCs/NGCDFCs on NGCDF Related issues | 1,900,000.00 | Ongoing |
| Emergency | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | Ongoing |
| BURSARY |  |  |  |
| Bursary Secondary Schools | Payment of bursary to needy students in Secondary Schools. | 8,000,000.00 | Ongoing |
| Bursary Tertiary institutions | Payment of bursary to needy students in colleges and universities. | 19,260,218.00 | Ongoing |
| PRIMARY SCHOOLS PROJECTS |  |  |  |
| Eldas Primary School | Renovation of 4no. classrooms (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,400,000.00 | New |
| Eldas Primary School | Renovation of Administration Block (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,000,000.00 | New |
| Eldas primary school | Piping of water from the borehole to the school | 1,400,000.00 | New |
| Eldas Primary School | Construction of Kitchen and Store | 1,500,000.00 | New |
| Eldas Primary School | Purchase and Delivery of 124 number 3-seater desks | 806,000.00 | New |
| Baladweyn Primary School | Additional funds for the Construction of 2no. Classrooms and 2 Vip Toilets to completion. | 800,000.00 | Ongoing |
| Mirgo harun Primary School | Construction of Staff Quarters (2,000,000) and 1 Twin Toilet (300,000 ) | 2,300,000.00 | New |
| Abaq Mathobe Primary School | Construction of 10,000Liters Underground mason water tank. | 1,000,000.00 | New |
| Balatulamin Primary School | Additional funds for the Construction of concrete fence to completion | 700,000.00 | Ongoing |
| Balatulamin Primary School | Renovation of 2no. Classrooms (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 700,000.00 | New |
| Yaqoo Primary School | Construction of 2no. classrooms | 1,4000,000.00 | New |
| SECONDARY SCHOOLS PROJECTS |  |  |  |
| Eldas Secondary School | Construction of 1no. Dormitory | 2,500,000.00 | New |
| Eldas Secondary School | Construction of 2no. Classrooms(1,400,0000) and 2 Twin Toilets(600,000) | 2,000,000.00 |  |
| Elnur Secondary school | Purchase and Delivery of 80no. Double Decker Beds ( 800,000) and Purchase and Delivery of 50no. Lockers and Chairs ( 400,000) | 1,200,000.00 | New |
| Eldas Girls Secondary school | Construction of 4 single rooms for Staffs. | 2,000,000.00 | New |
| Eldas Girls Secondary School | Repair of 500 meters Fence with concrete posts and chain link | 1,500,000.00 | New |
| Eldas Girls Secondary school | Renovation of 2no. Classrooms and 1no. dormitory (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,400,000.00 | New |
| TERTIARY INSTITUTIONS PROJECTS |  |  |  |
| Eldas Technical and Vocational Training Institute | Construction of Eldas Technical and vocational Training Institute | 10,000,000.00 | New |
| SECURITY PROJECTS |  |  |  |
| Eldas Police station | Construction of 6 single rooms for staffs. | 3,000,000.00 | New |
| Eldas Police Station | Construction of Administration block for Eldas DCI Office | 4,500,000.00 | New |
| Eldas Administration Police station | Construction of 16 single rooms for staffs (8,000,000) and 2 door Vip toilets (400,000) | 8,400,000.00 | New |
| Eldas Prison | Construction of Modern Perimeter gate and Security house | 2,000,000.00 | New |
| Masalale Police Station | Construction of Administration block | 3,500,000.00 | New |
| Eldas Deputy County Commissioner’s office | Renovation of Eldas Deputy county Commissioner’s Office (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,500,000.00 | New |
| Basir Police Station | Construction of 2 bedroom house for OCS | 2,000,000.00 | New |
| Waradey Administration Police station | Construction of 4no. staff houses ( 2,000,000) and 1no. Twin toilet (300,000) | 2,300,000.00 | New |
| Assistant County Commissioner Anole | Renovation of Administration block and Residential house (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 2,000,000.00 | New |
| Assistant County Commissioner Tulatula | Construction of 2 bedroom house (2,900,000) and external toilet and bath room(600,000) for the assistant county commissioner. | 3,500,000.00 | New |
| Assistant County Commissioner Tulatula | Construction of10,000m2 concrete Fence and gate | 1,000,000.00 | New |
| GRAND TOTAL |  | 109,040,875.52 |  |

The committee members requested the Fund Account Manager to do the necessary documentation for project proposal approval by NG-CDF board.

MIN 04/12/11/2018 Any Other Business

There being no other business, the meeting was adjourned at 4:30 p.m. with a word of prayer from Mr. Mohamed Gabow Kulow.

Minutes Compiled by;                                                                      Minutes Confirmed by;

(The Secretary)                                                                                 (The Chairman)

Signature………………………………….                                      Signature………………..........

Date………………………………………….                                   Date……………….................

National Government Constituencies Development Fund

THIRD SCHEDULE

CONSTITUENCY PROJECTS SUBMISSION FORM

Constituency No 037 Constituency Name Eldas Financial Year 2018/2019

| Serial | Name of Project | Amount Allocated |
| --- | --- | --- |
| 037/AP1 | Administration/Recurrent | 5,764,437.93 |
| 037/AP2 | Monitoring and Evaluation/Capacity Building | 2,971,226.14 |
| 037/2640200 | Emergency Reserve | 5,738,993.45 |
| 037/2640100 | Bursary | 27,260,218.00 |
| 037/2630204 | Primary School Projects | 13,006,000.00 |
| 037/2630205 | Secondary School Projects | 10,600,000.00 |
| 037/2630206 | Tertiary Institution Projects | 10,000,000.00 |
| 037/2640507 | Security Projects | 33,700,000.00 |
| Total |  | 109,040,875.52 |

Chairman NG- CDF Committee ……………………Signature………………….. Date………………

Fund Account Manager …………………………… Signature…………………….Date………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number 037/AP1

Project Title 6% Administration/Recurrent

Sector Administration

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

The allocation is to cater for CDFC Allowance, staff salaries, vehicle expenses and other administrative

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 5,764,437.93 dated…………………

Amount allocated last financial year 5,818,965.13

Amount allocated this financial year 5,764,437.93

| Project Name | Project Number | Activity | Amount |
| --- | --- | --- | --- |
| Employees Salaries | 4-008-037-2110000-100-2018/19-001 | Payment of staff salaries and gratuity | 3,217,800.00 |
| Goods and Services | 4-008-037-2210000-100-2018/19-002 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 1,264,437.93 |
| NSSF | 4-008-037-2120101-100-2018/2019-003 | Payment of NSSF Deductions | 81,600.00 |
| NHIF | 4-008-037-2120201-100-2018/19-004 | Payment of NHIF Deductions | 120,600.00 |
| Committee Expenses | 4-008-037-2210802-100-2018/19-005 | Payment of Committee sitting allowances, transport, conferences | 1,080,000.00 |
| TOTAL |  |  | 5,764,437.93 |

Person completing form: Name ……………………….. Position Fund Account Manager

Signature…………………… Date………………………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number 037/AP2

Project Title 3% Monitoring & Evaluation/Capacity Building

Sector Monitoring & Evaluation

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To cater for Monitoring and Evaluation of CDF projects and capacity building of CDFC and PMCs in the constituency

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,971,226.14 dated…………………

Amount allocated last financial year 685,146.00

Amount allocated this financial year 2,971,226.14

| Project Name | Project Number | Activity | Amount |
| --- | --- | --- | --- |
| Goods and Services | 4-008-037-2210000-111-2018/19-001 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 500,000.00 |
| Committee Expenses | 4-008-037-2210802-111-2018/19-002 | Payment of Committee sitting allowances, transport, conferences | 571,226.14 |
| NG-CDFC/PMC Capacity Building | 4-008-037-2210700-111-2018/19-003 | Undertake Training of the PMCs/NG-CDFCs on NG-CDF Related issues | 1,900,000.00 |
| TOTAL |  |  | 2,971,226.14 |

Person completing form: Name ……………………… Position Fund Account Manager

Signature…………………… Date………………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number037/2640200

Project Title Emergency Reserve (5% of the fund)

Sector Emergency

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Unallocated amount meant for emergencies that may occur within the Constituency

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 5,738,993.45 dated…………………

Amount allocated last financial year 4,568,965.52

Amount allocated this financial year 5,738,993.45

| Project Name | Project Code | Project Activity | Amount Allocated |
| --- | --- | --- | --- |
| Emergency | 4-008-008-2640200-101-2018/19-001 | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 |
| Total |  |  | 5,738,993.45 |

Person completing form: Name ………………………….. Position Fund Account Manager

Signature…………………… Date………………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number037/2640100

Project Title Bursary

Sector Bursary

Status of projects (tick one) New………………. Extension……………….. On-going…√….. Rehabilitation ………………….

Brief statement on project status at time of submission

Towards Bursary for payment of fees for needy students

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 27,260,218.00 dated…………………

Amount allocated last financial year 21,702,586.20

Amount allocated this financial year 27,260,218.00

| Project Name | Project Code | Project Activity | Amount Allocated |
| --- | --- | --- | --- |
| Bursary Secondary Schools | 4-008-037-2640101-103-2018/19-001 | Payment of bursary to needy student | 8,000,000.00 |
| Bursary to Tertiary institutions | 4-008-037-2640102-103-2018/19-002 | Payment of bursary to needy student | 19,260,218.00 |
| TOTAL |  |  | 27,260,218.00 |

Person completing form: Name ……………………….. Position Fund Account Manager

Signature…………………… Date………………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number 037/2630204

Project Title Primary Education Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions in the primary schools institutions by improving the infrastructure

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 13,006,000.00 dated…………………

Amount allocated last financial year 39,250,000.00

Amount allocated this financial year 13,006,000.00

| Project Name | Project Code | Project Activity | Amount Allocated |
| --- | --- | --- | --- |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-001 | Renovation of 4no. classrooms (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,400,000.00 |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-002 | Renovation of Administration Block (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,000,000.00 |
| Eldas primary school | 4-008-037-2630204-104-2018/2019-003 | Piping of water from the borehole to the school | 1,400,000.00 |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-004 | Construction of Kitchen and Store | 1,500,000.00 |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-005 | Purchase and Delivery of 124 number 3-seater desks | 806,000.00 |
| Baladweyn Primary School | 4-008-037-2630204-104-2018/2019-006 | Additional funds for the Construction of 2no. Classrooms and 2 Vip Toilets to completion. | 800,000.00 |
| Mirqo Harun Primary School | 4-008-037-2630204-104-2018/2019-007 | Construction of staff quarters(2000,000) and 1Vip Toilet(300,000) | 2,300,000.00 |
| Abaq Mathobe Primary School | 4-008-037-2630204-104-2018/2019-008 | Construction of 10,000Liters Underground mason water tank. | 1,000,000.00 |
| Balatulamin Primary School | 4-008-037-2630204-104-2018/2019-009 | Additional funds for the Construction of concrete fence to completion | 700,000.00 |
| Balatulamin Primary School | 4-008-037-2630204-104-2018/2019-010 | Renovation of 2no. Classrooms (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 700,000.00 |
| Yaqoo Primary School | 4-008-037-2630204-104-2018/2019-011 | Construction of 2no. classrooms | 1,400,000.00 |
| Total |  |  | 13,006,000.00 |

Person completing form: Name …………………………………………... Position Fund Account Manager

Signature…………………… Date………………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number 037/2630205

Project Title Secondary School Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions of Secondary schools by improving the infrastructure

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 10,600,000.00 dated…………………

Amount allocated last financial year 14,177,027.00

Amount allocated this financial year 10,600,000.00

| Project Name | Project Code | Project Activity | Amount Allocated |
| --- | --- | --- | --- |
| Eldas Secondary School | 4-008-037-2630205-104-2018/2019-001 | Construction of 1no. Dormitory | 2,500,000.00 |
| Eldas Secondary School | 4-008-037-2630205-104-2018/2019-002 | Construction of 2no. Classrooms (1,400,0000) and 2 Twin Toilets (600,000) | 2,000,000.00 |
| Elnur Secondary school | 4-008-037-2630205-104-2018/2019-003 | Purchase and Delivery of 80no. Double Decker Beds (800,000) and Purchase and Delivery of 50no. Lockers and Chairs (400,000) | 1,200,000.00 |
| Eldas Girls Secondary school | 4-008-037-2630205-104-2018/2019-004 | Construction of 4 single rooms for Staffs. | 2,000,000.00 |
| Eldas Girls Secondary School | 4-008-037-2630205-104-2018/2019-005 | Repair of 500 meters Fence with concrete posts and chain link | 1,500,000.00 |
| Eldas Girls Secondary school | 4-008-037-2630205-104-2018/2019-006 | Renovation of 2no. Classrooms and 1no. dormitory (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,400,000.00 |
| Total |  |  | 10,600,000.00 |

Person completing form: Name ……………………………………… Position Fund Account Manager

Signature…………………… Date………………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number 037/2630206

Project Title Tertiary Institutions Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions of Tertiary Institutions by improving the infrastructure

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 10,000,000.00 dated…………………

Amount allocated last financial year 0.00

Amount allocated this financial year 10,000,000.00

| Project Name | Project Code | Project Activity | Amount Allocated |
| --- | --- | --- | --- |
| Eldas Technical and Vocational Training Institute | 4-008-037-2630206-104-2018/2019-001 | Construction of Eldas Technical and Vocational Training Institute | 10,000,000.00 |
| Total |  |  | 10,000,000.00 |

Person completing form: Name …………………………………. Position Fund Account Manager

Signature…………………… Date………………………

National Government Constituencies Development Fund

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 037 Constituency Name ELDAS County WAJIR

Project Number 037/2640507

Project Title Security Projects

Sector Security

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Projects to ensure proper security in the constituency through establishing Police offices and security fence

Financial year 20171st July To 30th June 2018

Original Cost estimates, in Kshs.33, 700,000.00 dated…………………

Amount allocated last financial year 6, 400,000.00

Amount allocated this financial year 33,700,000.00

| Project Name | Project Number | Activity | Amount |
| --- | --- | --- | --- |
| Eldas Police station | 4-008-037-2640507-113-2018/2019-001 | Construction of 6 single rooms for staffs. | 3,000,000.00 |
| Eldas Police Station | 4-008-037-2640507-113-2018/2019-002 | Construction of Administration block for Eldas DCI Office | 4,500,000.00 |
| Eldas Administration Police station | 4-008-037-2640507-113-2018/2019-003 | Construction of 16 single rooms for staffs (8,000,000) and 2 door Vip toilets (400,000) | 8,400,000.00 |
| Eldas Prison | 4-008-037-2640507-113-2018/2019-004 | Construction of Modern Perimeter gate and Security house | 2,000,000.00 |
| Masalale Police Station | 4-008-037-2640507-113-2018/2019-005 | Construction of Administration block | 3,500,000.00 |
| Eldas Deputy County Commissioner’s office | 4-008-037-2640507-113-2018/2019-006 | Renovation of Eldas Deputy county Commissioner’s Office (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,500,000.00 |
| Basir Police Station | 4-008-037-2640507-113-2018/2019-007 | Construction of 2 bedroom house for OCS | 2,000,000.00 |
| Waradey Administration Police station | 4-008-037-2640507-113-2018/2019-008 | Construction of 4no. staff houses ( 2,000,000) and 1no. Twin toilet (300,000) | 2,300,000.00 |
| Assistant County Commissioner Anole | 4-008-037-2640507-113-2018/2019-009 | Renovation of Administration block and Residential house (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 2,000,000.00 |
| Assistant County Commissioner Tulatula | 4-008-037-2640507-113-2018/2019-010 | Construction of 2 bedroom house (2,900,000) and external toilet and bath room(600,000) for the assistant county commissioner. | 3,500,000.00 |
| Assistant County Commissioner Tulatula | 4-008-037-2640507-113-2018/2019-011 | Construction of10,000m2 concrete Fence and gate | 1,000,000.00 |
| Total |  |  | 33,700,000.00 |

Person completing form: Name ……………………………………. Position Fund Account Manager

Signature…………………… Date………………………

ELDAS

IEBC NUMBER 037

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND

WARD REPORTS

2018/2019 FINANCIAL YEAR

SUBMITTED

NOVEMBER 2018

Introduction or Background

CONSTITUENCY DEVELOPMENT FUND

Background

The National Government Constituencies Development Fund was created by the Constituencies Development Fund Act, 2003 with the primary objective of addressing poverty at grassroots level by dedicating a minimum of 2.5% of the Government ordinary revenue to grassroots development and the reduction of poverty. The fund is managed by the Constituencies Development Fund Board (CDFB)

In January 2013, the CDF Act 2003 (as amended in 2007) was repealed and replaced with CDF Act 2013 that is aligned to the constitution of Kenya 2010.

The enactment of the CDF Act 2015 was mainly aimed to ensure that the law governing CDF is aligned to the Constitution of Kenya 2010, specifically in compliance with the principles of:

transparency and accountability,

separation of powers; and

participation of the people.

 align the operations of the Fund to the new devolved government structure.

- Change of name from Constituencies Development Fund (CDF) to National Government Constituencies Development Fund (NG-CDF).

Key Changes in the CDF Act 2015

- Reduction in size of the CDF Board from eleven to eight members and introduction of a new officer, the Corporation Secretary as secretary to the Board.

- Obviating the role of nominating Bodies in appointment of CDF Board members. Nomination was restricted to competitive recruitment process.

- Separation of roles of the executive vis-à-vis  the Legislature.

- Emphasis on the mandatory role of Project Management Committees

- Submission of Project proposals to the Board by the Chairman of the CDFC.

- Change in size of CDFC resulting in reduction of the maximum number of committee members from sixteen (11) to eight (8).

- Change in the mode of appointment of CDFC members.

- Member of parliament made supervisor of projects rather than member of CDFC

- Names of the persons appointed as members of the CDFC to be published in Kenya Gazette after approval by parliament.

- New structure at ward level

  - ELDAS  CDF

Projects funding in the previous financial year (see PIS)

  - Sectoral analysis of complete and ongoing projects

Brief about projects funded and disbursement of funds

- Number/allocation of completed projects 2017/2018 financial year

| Sector | Ward | Number of completed projects | Cost | Remarks |
| --- | --- | --- | --- | --- |
| Primary Education | Lakoley ward, Eldas Ward, Dela ward and Elnur/tulatual ward | 21 | 39,250,000 | Complete and in use |
| Secondary education | Eldas and Elnur/Tulatula | 6 | 14,177,027.00 | COMPLETE AND IN USE |
| Security | Lakoley,Eldas, and Elnur | 4 | 6,400,000 | Complete and in use |
| Cdf office | Eldas | Nil | Nil | Nil |
| Sports | Nil | Nil | Nil | Nil |
| Environment | Eldas | 1 | 300,000 | Complete |

(b)Number/allocation of ongoing projects 2017/2018 financial year

| Sector | Ward | Number of ongoing projects | Cost | Remarks |
| --- | --- | --- | --- | --- |
| Education | Elnur Tulatula | 1 | 700,000 | Need funding for this financial year |
|  | Eldas | 1 | 800,000 | Need funding for this financial year |
| Security | Nil | Nil | Nil | Nil |

Amount of money used for bursaries, number of beneficiaries and criteria used for 2017/2018 financial year

| Ward | No. of beneficiaries | Amount allocated | Remarks (mention criteria |
| --- | --- | --- | --- |
| Elnur/tulatula Dela Eldas Lakoley | 1,200 | 21,702,586.20 | Forms distributed through location chiefs, available in the NG-CDF office. .needy and bright students considered |

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND ELDAS

P.O BOX 491 -70200 WAJIR

ELNUR/TULATUAL WARD REPORT   ON 5TH November 2018 FOR THE PROPOSAL OF FINANCIAL YEAR 2018/2019 AT TULA TULA CHIEF’S OFFICE

    - LOCATION AND TIME OF THE MEETING.

The Elnur/Tulatula ward meeting was conducted on 5th of November 2018 at Tulatula Chief’s office compound.

The meeting started at 9.30am and ended 12.36 pm

    - MEMBERS PRESENT.

The members present are from the general public, NG- CDF officials, community leaders, women representatives, Deputy county commissioner and the members present include:

MEMBERS PRESENT

- Mohamed Abdullahi Maalim                      - COMMUNITY ELDER

- Haret Dubow hassan                              - Chief   Tula Tula

- Hassan Osman                                         - HEAD TEACHER Tulatula  primary school

- Mohamud A Ibrahim                               -NG- CDFC Chairman.

- Mama Alasa    Musa                                 -WOMEN LEADER/business lady

- Abdirahman mohamud                             -Mirgo harun  PRY SCHOOL.

- MOHAMED HAJI                                           -COMMUNITY ELDER

- Irshad Mohamed                                           -FUND ACCOUNT MANAGER

- Vincent Loctari Lomachar                        - DEPUTY COUNTY COMMISSIONER-Eldas

- Sheikh    Ali Hassan                                           - religious leader

- Adow Shahu Dakat                                              – CDFC member

- Mohamed Noor Abdille                                         – opinion leader

- Shamsa Abdi Ahmed                                              – CDFC member

- Mohamed Gabow Kulow                                        – CDFC member

- Bishara Gaiye                                                            – CDFC member

- Ibrahim m Hussein                                                   – assistant chief mirgo harun

- Habiba Hussein Salat                                               – woman leader

- Omar Abdullahi                                                      – head teacher tulatula secondary school

- Salat Ali                                                                         – chief elnur

WHO GRACED THE OCCASION

The meeting was graced by deputy county commissioner Mr. Vincent Loctari Lomachar. The chairman opened the meeting with a word of  prayer. The chair called the meeting to order at 9.50 am.

1.1.04 COMMENTS BY DEPUTY COUNTY COMMISSIONER.

The Deputy county commissioner informed the members that every year a public forum is conducted in order to comply with the NG-CDF act and the public of Elnur/Tulatula ward to give their priorities to NG CDFC members so that the same can be verified and submitted to the NG-CDF board for funding. The D.C.C officially declared that the meeting is opened and thanked members for attending the meeting.  He asked members of the public present especially women not to shy away to speak.

1.105 COMMENTS BY FUND ACCOUNT MANAGER.

The fund account manager went through the provisions of the CDF act and informed the forum that projects can only be funded if they are not in any way connected to political activities, if they are legal, compliant with the laws of the republic of Kenya, if they are in Eldas constituency and is not connected with any religious activities.

1.1.06 COMMENTS BY CDFC CHAIRMAN.

The CDFC chairman briefed the forums provisions of the CDF act concerning bursary, the chairman informed the members that bursary has an allocations a maximum of 25% of what was allocated and a minimum of that would be decided by the Eldas NG CDFC. He further noted that bursary is open to all members of the constituency and is generally divided into: bursaries for secondary education, bursaries for higher education and funds to organize annual education day.

1.1.07 PROJECTS IDENTIFIED IN THE WARD.

The following are the needs submitted at the forum by the community:

| NO | NAME OF THE PROJECT |
| --- | --- |
|  | Classrooms for at Elnur secondary school, classrooms,and completion of laboratory at elnur secondary, classrooms for mirgo harun and bulla forest pry. Desks for primary schools, staff quarters at mirgo harun primart school, dormitory for tulatula and elnur secondary schools, staff quarters and laboratory at Elnur sec school. |
|  | Administration office at Tulatula DO office |
|  | Chiefs office at mirgo harun and biyaad, |
|  | Fencing of elnur secondary school |
|  | Residential house for ACC Tulatula |
|  | Staff house for Elnur Secondary school |
|  | classrooms for Mirgo harun |
|  | Staff house for mirgo harun primary school |
|  | Electric wiring of elnur primary school |
|  | Fencing of AP camp at Elnur |
|  | Piping of water to Balatul amin pry school |
|  | Renovation of classrooms at Balatulamin primary |

1.1.08 CHALLENGES

The following challenges were identified in terms of project identifications and approval:-

- The cost of the project and how they are ascertained, members identified that wards are of varying distances the cost should be inclusive of the availability of material and water.

- Lack of feedback by CDFC, they noted after the forum the ward officials and the general public be informed of what was submitted to the national board.

1.1.09     WAY FORWARD.

The way forward was to involve the district officer about the distance and availability of water and other material to be involved in the cost. The fund manager informed the forum after approval by the board every member can go access the information in the CDF office.

Signed by;

Irshad Mohamed……………………        Fund Account Manager           Date…………………………

Mohamud A. Ibrahim…………………    NG-CDFC Chairman                Date……………………

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND ELDAS

P.O BOX 491 -70200 WAJIR

DELA WARD REPORT ON 6TH November 2018 FOR THE PROPOSAL OF FINANCIAL YEAR 2018/2019 AT DELA PRIMARY PLAY GROUND

    - LOCATION AND TIME OF THE MEETING.

The Dela ward meeting was conducted On 6th of November at Dela pry school.

The meeting started 8.30am and ended 11.28 pm

    - MEMBERS PRESENT.

The members present are from the general public, CDF members, community leaders, women representatives,

Deputy county commissioner and the members present include;

MEMBERS PRESENT

2.  Salat Ibrahim Haile                      -senior chief Dela

- Mr  Kilimo                                        - HEAD TEACHER Dela  primary school

- Mohamed Noor Abdille                        - opinion leader

- Zeitun Bishar                                            -WOMEN LEADER

- Dela     PRY SCHOOL.

- Osman Mohamed amin                              -COMMUNITY ELDER

- Irshad Mohamed                                                   -FUND ACCOUNT MANAGER

- Mohamud A Ibrahim                                                 - CHAIRMAN CDFC

- Vincent Loctari Lomachar                               - DEPUTY COUNTY COMMISSIONER.

- Asha Bishar Jelle                                             – CDFC member –Secretary

- Bishara Gaiye Ahmed                                           – CDFC member

- Adow Shahu Dakat                                                      – CDFC member

- Roble A Madey                                                            – chief Anole

- Mohamed A Barrow                                             – assistant chief Abdiwaqo

- Hussein Abdullahi                                                     – HM Abdiwaqo pry school

- other members of the public

- Shamsa Abdi                                                           – CDFC member

- Mohamed Gabow Kulow                                            – CDFC member

    - WHO GRACED THE OCCASION

The meeting was graced by deputy county commissioner Mr. Vincent Loctari Lomachar. The chairman opened the meeting with a word prayer. The chair called the meeting to order at 10.15 am.

    - COMMENTS BY DEPUTY COUNTY COMMISSIONER.

The Deputy county commissioner informed the members that every 2 years public forum is conducted in order to comply with the CDF act in generating projects and programs for CDF funding and the public of Dela ward to give their priorities to CDF members so that the same can be verified and submitted to the NG CDF board for funding. The D.C.C officially declared that the meeting is opened asked members not shy away in giving their views.

1.105 COMMENTS BY FUND ACCOUNT MANAGER.

The fund account manager went through the provisions of the CDF act and informed the forum that projects can only be funded if they are not in any way connected to political activities, if they are legaly compliant with the laws of the republic of Kenya, if they are and is not connected with any religious activities. He asked members of the public present to give their views.

1.1.06 COMMENTS BY CDFC CHAIRMAN.

The CDFC chairman briefed the forums provisions of the CDF act concerning bursary , the chairman informed the members  that  bursary has an allocations a maximum of 25% of what was allocated and a minimum  of that would be decided by the Eldas NG CDFC. He further noted that bursary is open to all members of the constituency and is generally divided into: bursaries for secondary education, bursaries for higher education and organizing education day.

1.1.07 PROJECTS IDENTIFIED IN THE WARD.

The following are the needs submitted at the forum by the community:

| NO | NAME OF THE PROJECT |
| --- | --- |
| 1 | Classrooms at Abdi waqo pry school |
| 2 | Dormitory and staff house at proposed Dela Secondary school |
| 3 | Staff house at Abdiwaqo primary |
| 4 | Admin block at abdiwaqo primary |
| 5 | Classrooms, dormitory and laboratory at Anole Secondary School |
| 6 | Muram on Abdiwaqo – kilkiley road |
| 7 | Dormitory, laboratory and staff house at Dela Secondary School |
| 8 | Classrooms at yaqo primary school |
| 9 | Staff house at Yaqo primary School |
| 10 | Chief office at Yaqo centre |
| 11 | Renovation at Anole ACC Administration offices and residential house |
| 12 | Anole Secondary School |
| 13 | Classrooms and water tank at Jigjiga |
| 14 | Water tank at Dela primary |

1.1.08 CHALLENGES

The following challenges were identified in terms of project identifications and approval:-

- The cost of the project and how they are ascertained, members identified that wards are of varying distances the cost should be inclusive of the availability of material and water.

- Lack of feedback by CDFC, they noted after the forum the ward officials and the general public be informed of what was submitted to the national board.

1.1.09       WAY FORWARD.

The way forward was to involve the district officer about the distance and availability of water and other material to be involved in the cost. The fund manager informed the forum after approval by the board every member can access the information in the NG CDF office.

Signed by;

Irshad Mohamed     ……………………    Fund Account Manager      Date……………………………

Mohamud A. Ibrahim ……………………..    NG-CDFC Chairman        Date………………………..

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND ELDAS

P.O BOX 491 -70200 WAJIR

ELDAS WARD   REPORT   ON 7TH November 2018 FOR THE PROPOSAL OF FINANCIAL YEAR 2018/2019 AT ELDAS BARAZA PARK

    - LOCATION AND TIME OF THE MEETING.

The Eldas   ward meeting was conducted in 7th of November at Eldas Baraza park.

The meeting started 9.37am and ended 12.17 pm

1.1.02 MEMBERS PRESENT.

The members present are from the general public, CDF officials, community leaders, women representatives,

Deputy county commissioner and the members present include

MEMBERS PRESENT

  - HUSEIN MADEY                                            -COMMUNITY ELDER

  - Rashid Guthow Hassan                                Senior Chief- Eldas

  - Mr. Wahome                                                  – OCPD – Eldas

  - Mr. Tarus                                                          – APC Eldas

  - Mohamed Gedi                                                – Chief Bulla Shair

  - Ahmed Ali Olow                                        - Assistant chief bulla shair

  - MohamudMudey                                        – Assistant chief Wagberi

  - Rashid Jimale                                                 – chief Kilkiley

  - Adan Boo                                                        – Chief Dadhantalai

  - Mr Abdi Said                                                – Head teacher  Eldas Sec  school

  - Muktar                                                         – Head teacher Eldas Girls Sec School

  - Abdi Abass                                                                 – Head teacher Eldas primary School

  - Bishara Gaiye Ahmed                                   - CDFC OFFCIAL representing  Eldas ward.

  - Irshad Mohamed                                                     -Fund Account Manager

  - Mohamud A Ibrahim                                    - Chairman CDFC

  - Vincent Loctari Lomachar                                - Deputy County Commissioner Eldas.

  - Adow Shahu Dakat                                          – CDFC member

  - Shamsa Abdi                                                 – CDFC member

  - Mohamed Gabow Kulow                             – CDFC member

  - Mohamed Noor Abdille                                    – Opinion leader

  - Asha Bishar Jelle                                      – CDFC member – secretary

  - Ibrahim Khalif Abdullahi                          – CDFC member

    - WHO GRACED THE OCCASION

The meeting was graced by deputy county commissioner Mr. Vincent Loctari Lomachar. The chairman opened the meeting with a word prayer. The chair called the meeting to order at 9.30 am.

    - COMMENTS BY DEPUTY COUNTY COMMISSIONER.

The Deputy county commissioner informed the members that every year public forum is conducted in order to comply with the CDF act and the public of Eldas ward to give their priorities to CDF members so that the same can be verified and submitted to the CDF board for funding. The D.C.C officially declared that the meeting is opened.

1.105 COMMENTS BY FUND ACCOUNT MANAGER.

The fund account manager went through the provisions of the CDF act and informed the forum that projects can only be funded if they are not in any way connected to political activities, if they are legal compliant with the laws of the republic of Kenya, if they are within Wajir east constituency and is not connected with any religious activities.

1.1.06 COMMENTS BY CDFC CHAIRMAN.

The CDFC chairman briefed the forums provisions of the CDF act concerning bursary, the chairman informed the members that bursary has an allocations a maximum of 25% of what was allocated and a minimum  of that would be decided by the Eldas CDFC. He further noted that bursary is open to all members of the constituency and is generally divided into: bursaries for secondary education, bursaries for higher education and organizing education day.

1.1.07 PROJECTS IDENTIFIED IN THE WARD.

The following are the needs submitted at the forum by the community:

| NO | NAME OF THE PROJECT |
| --- | --- |
| 1 | Classrooms & toilets at Wargadud primary |
| 2 | classrooms at Eldas Girls Sec School |
| 3 | Classrooms at Eldas boys sec school |
| 4 | Admin block at Eldas Sec school |
| 5 | Staff houses at Eldas police station |
| 6 | Dormitory at Eldas sec school |
| 7 | Laboratory at eldas sec school |
| 8 | Chief office at Eldas |
| 9 | Fencing and classroom at Dad-hantalai primary school |
| 10 | Classrooms at Jukala primary school |
| 11 | Fencing and classroom at Kilkiley pry school |
| 12 | Chief office at Dad-hantalai |
| 13 | Classroom with toilets at Eldas girls |

1.1.08 CHALLENGES

The following challenges were identified in terms of project identifications and approval:-

- The cost of the project and how they are ascertained, members identified that wards are of varying distances the cost should be inclusive of the availability of material and water.

- Lack of feedback by NG-CDFC, they noted after the forum the ward officials and the general public be informed of what was submitted to the NG CDF board.

1.1.09     WAY FORWARD.

The way forward was to involve the district Works officer about the distance and availability of water and other material to be involved in the cost of projects. The fund manager informed the forum after approval by the board every member can come access the information in the NG CDF office.

Signed by;

Irshad Mohamed …………………… Fund Account Manager      Date…………………………..

Mohamud A Ibrahim ………………… NG-CDFC Chairman          Date……………………..

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND ELDAS

P.O BOX 491 -70200 Wajir

Lakoley Ward   REPORT   ON 8TH November 2018 FOR THE PROPOSAL OF FINANCIAL YEAR 2018/2019 AT Basir Primary School

    - LOCATION AND TIME OF THE MEETING.

The Lakoley ward has the following locations; Masalale, lakoley, Basir, Areswajil and Tito The meeting was conducted on 8th of November at Basir primary School.

The meeting started 9.40am and ended 12.18 pm

1.1.02 MEMBERS PRESENT.

The members present are from the general public, CDFC members, community leaders, women representatives,

Deputy county commissioner and the members present include

MEMBERS PRESENT

- Abdullahi  A Salat                                          Community Elder/ businessman

- Siyad Maalim Hassan                                      Chief Lakoley

- Abdi Abass                                    Head teacher Masalale  primary   school

- Shamsa Abdi                                      -CDFC member

- Halima adan                                                          WOMEN LEADER

- Lakoley Pry  School.

- ADAN AHMED      IMARA                                -COMMUNITY ELDER

- Irshad Mohamed                                                  -Fund Account Manager

- Mohamud A Ibrahim                             - CHAIRMAN CDFC

- Vincent Loctari Lomachar                                    - Deputy County Commissioner

- Adow Shahu Dakat                                     – CDFC member

- Mohamed Noor Abdille                                –  opinion leader

- Bishara Gaiye Ahmed                                  – CDFC member

- Mohamed Gabow Kulow                               – CDFC member

- Asha Bishar Jelle                                   – CDFC Secretary

1.1.03 WHO GRACED THE OCCASION

The meeting was graced by deputy county commissioner Mr. Vincent Loctari Lomachar. The chairman opened the meeting with a word prayer. The chair called the meeting to order at 10.30 am.

    - COMMENTS BY DEPUTY COUNTY COMMISSIONER.

The Deputy county commissioner informed the members that every year  public forum is conducted in order to comply with the CDF act and the public of Lakoley ward to give their priorities to CDF officials so that the same can be verified and submitted to the national board for funding. The D.C officially declared that the meeting is opened.

1.105 COMMENTS BY FUND ACCOUNT MANAGER.

The fund account manager went through the provisions of the CDF act and informed the forum that projects can only be funded if they are not in any way connected to political activities, if they are legal compliant with the laws of the republic of Kenya, if they are within Eldas constituency and is not connected with any religious activities.

    - COMMENTS BY CDFC CHAIRMAN.

The CDFC chairman briefed the forums provisions of the CDF act concerning bursary , the chairman informed the members  that  bursary has an allocations a maximum of 25% of what was allocated and a minimum  of that would be decided by the Eldas CDFC. He further noted that bursary is open to all members of the constituency and is generally divided into: bursaries for secondary education, bursaries for higher education and mocks and assessment

1.1.07 PROJECTS IDENTIFIED IN THE WARD.

The following are the needs submitted at the forum by the community:

| NO | NAME OF THE PROJECT |
| --- | --- |
| 1 | Masalale primary roofing |
| 2 | AP houses at Basir |
| 3 | Classrooms at lakoley |
| 4 | Classrooms at Areswajil |
| 5 | Residential house for OCS Basir Police Station |
| 6 | Classrooms at masalale |
| 7 | Classrooms at Banane |
| 8 | Staff house at lakoley, masalale pry schools |
| 9 | Admin block at areswajil primary |
| 10 | Classrooms at Baqala |

1.1.08 CHALLENGES

The following challenges were identified in terms of project identifications and approval:-

- The cost of the project and how they are ascertained, members identified that wards are of varying distances the cost should be inclusive of the availability of material and water.

- Lack of feedback by CDFC, they noted after the forum the ward officials and the general public be informed of what was submitted to the national board.

1.1.09     WAY FORWARD.

The way forward was to involve the district officer about the distance and availability of water and other material to be involved in the cost. The fund manager informed the forum after approval by the board every member can come access the information in the CDF office.

Signed by;

Irshad Mohamed     …………………… Fund Account Manager       Date…………………………

Mohamud A Ibrahim …………………   NG- CDFC Chairman         Date……………………

Eldas National Government Constituency Development Fund

Project Proposal 2018/2019 Financial Year

Code-list

FINANCIAL YEAR. 1ST JULY 2018 TO 30TH JUNE 2019

| Project Name | Project Number | Original Cost | Cumulative allocation | Project activity | Amount Allocated | Current Status |
| --- | --- | --- | --- | --- | --- | --- |
| Employees Salaries | 4-008-037-2110000-100-2018/19-001 | 3,217,800.00 | 3,217,800.00 | Payment of staff salaries and gratuity | 3,217,800.00 | On-going |
| Goods and Services | 4-008-037-2210000-100-2018/19-002 | 1,264,437.93 | 1,264,437.93 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 1,264,437.93 | On-going |
| NSSF | 4-008-037-2120101-100-2018/2019-003 | 81,600.00 | 81,600.00 | Payment of NSSF Deductions | 81,600.00 | On-going |
| NHIF | 4-008-037-2120201-100-2018/19-004 | 120,600.00 | 120,600.00 | Payment of NHIF Deductions | 120,600.00 | On-going |
| Committee Expenses | 4-008-037-2210802-100-2018/19-005 | 1,080,000.00 | 1,080,000.00 | Payment of Committee sitting allowances, transport, conferences | 1,080,000.00 | On-going |
| Goods and Services | 4-008-037-2210000-111-2018/19-001 | 500,000.00 | 500,000.00 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 500,000.00 | On-going |
| Committee Expenses | 4-008-037-2210802-111-2018/19-002 | 571,226.14 | 571,226.14 | Payment of Committee sitting allowances, transport, conferences | 571,226.14 | On-going |
| NG-CDFC/PMC Capacity Building | 4-008-037-2210700-111-2018/19-003 | 1,900,000.00 | 1,900,000.00 | Undertake Training of the PMCs/NG-CDFCs on NG-CDF Related issues | 1,900,000.00 | On-going |
| Emergency | 4-008-037-2640200-101-2018/19-001 | 5,738,993.45 | 5,738,993.45 | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | On-going |
| Bursary Secondary Schools | 4-008-037-2640101-103-2018/19-001 | 8,000,000.00 | 8,000,000.00 | Payment of bursary to needy students | 8,000,000.00 | On-going |
| Bursary Tertiary institutions | 4-008-037-2640102-103-2018/19-002 | 19,260,218.00 | 19,260,218.00 | Payment of bursary to needy students | 19,260,218.00 | On-going |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-001 | 1,400,000.00 | 1,400,000.00 | Renovation of 4no. classrooms (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,400,000.00 | New |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-002 | 1,000,000.00 | 1,000,000.00 | Renovation of Administration Block (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,000,000.00 | New |
| Eldas primary school | 4-008-037-2630204-104-2018/2019-003 | 1,400,000.00 | 1,400,000.00 | Piping of water from the borehole to the school | 1,400,000.00 | New |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-004 | 1,500,000.00 | 1,500,000.00 | Construction of Kitchen and Store | 1,500,000.00 | New |
| Eldas Primary School | 4-008-037-2630204-104-2018/2019-005 | 806,000.00 | 806,000.00 | Purchase and Delivery of 124 number 3-seater desks | 806,000.00 | New |
| Baladweyn Primary School | 4-008-037-2630204-104-2018/2019-006 | 800,000.00 | 800,000.00 | Additional funds for the Construction of 2no. Classrooms and 2 Vip Toilets to completion. | 800,000.00 | ongoing |
| Mirgo harun Primary School | -008-037-2630204-104-2018/2019-007 | 2,300,000.00 | 2,300,000.00 | Construction of Staff Quarters (2,000,000) and 1 Twin Toilet (300,000 ) | 2,300,000.00 | New |
| Abaq Mathobe Primary School | 4-008-037-2630204-104-2018/2019-008 | 1,000,000.00 | 1,000,000.00 | Construction of 10,000Liters Underground mason water tank. | 1,000,000.00 | New |
| Balatulamin Primary School | 4-008-037-2630204-104-2018/2019-009 | 700,000.00 | 700,000.00 | Additional funds for the Construction of concrete fence to completion | 700,000.00 | Ongoing |
| Balatulamin Primary School | 4-008-037-2630204-104-2018/2019-010 | 700,000.00 | 700,000.00 | Renovation of 2no. Classrooms (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 700,000.00 | New |
| Yaqoo Primary School | 4-008-037-2630204-104-2018/2019-011 | 1,400,000.00 | 1,400,000.00 | Construction of 2no. classrooms | 1,400,000.00 | New |
| Eldas Secondary School | 4-008-037-2630205-104-2018/2019-001 | 2,500,000.00 | 2,500,000.00 | Construction of 1no. Dormitory | 2,500,000.00 | New |
| Eldas Secondary School | 4-008-037-2630205-104-2018/2019-002 | 2,000,000.00 | 2,000,000.00 | Construction of 2no. Classrooms(1,400,0000) and 2 Twin Toilets(600,000) | 2,000,000.00 | New |
| Elnur Secondary school | 4-008-037-2630205-104-2018/2019-002 | 1,200,000.00 | 1,200,000.00 | Purchase and Delivery of 80no. Double Decker Beds ( 800,000) and Purchase and Delivery of 50no. Lockers and Chairs ( 400,000) | 1,200,000.00 | New |
| Eldas Girls Secondary school | 4-008-037-2630205-104-2018/2019-003 | 2,000,000.00 | 2,000,000.00 | Construction of 4 single rooms for Staffs. | 2,000,000.00 | New |
| Eldas Girls Secondary School | 4-008-037-2630205-104-2018/2019-004 | 1,500,000.00 | 1,500,000.00 | Repair of 500 meters Fence with concrete posts and chain link | 1,500,000.00 | New |
| Eldas Girls Secondary school | 4-008-037-2630205-104-2018/2019-005 | 1,400,000.00 | 1,400,000.00 | Renovation of 2no. Classrooms and 1no. dormitory (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,400,000.00 | New |
| Eldas Technical and Vocational Training Institute | 4-008-037-2630206-104-2018/2019-001 | 10,000,000.00 | 10,000,000,00 | Construction of Eldas Technical and Vocational Training Institute | 10,000,000.00 | New |
| Eldas Police station | 4-008-037-2640507-113-2018/2019-001 | 3,000,000.00 | 3,000,000.00 | Construction of 6 single rooms for staffs. | 3,000,000.00 | New |
| Eldas Police Station | 4-008-037-2640507-113-2018/2019-002 | 4,500,000.00 | 4,500,000.00 | Construction of Administration block for Eldas DCI Office | 4,500,000.00 | New |
| Eldas Administration Police station | 4-008-037-2640507-113-2018/2019-003 | 8,400,000.00 | 8,400,000.00 | Construction of 16 single rooms for staffs (8,000,000) and 2 door Vip toilets (400,000) | 8,400,000.00 | New |
| Eldas Prison | 4-008-037-2640507-113-2018/2019-004 | 2,000,000.00 | 2,000,000.00 | Construction of Modern Perimeter gate and Security house | 2,000,000.00 | New |
| Masalale Police Station | 4-008-037-2640507-113-2018/2019-005 | 3,500,000.00 | 3,500,000.00 | Construction of Administration block | 3,500,000.00 | New |
| Eldas Deputy County Commissioner’s office | 4-008-037-2640507-113-2018/2019-006 | 1,500,000.00 | 1,500,000.00 | Renovation of Eldas Deputy county Commissioner’s Office (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 1,500,000.00 | New |
| Basir Police Station | 4-008-037-2640507-113-2018/2019-007 | 2,000,000.00 | 2,000,000.00 | Construction of 2 bedroom house for OCS | 2,000,000.00 | New |
| Waradey Administration Police station | 4-008-037-2640507-113-2018/2019-008 | 2,300,000.00 | 2,300,000.00 | Construction of 4no. staff houses ( 2,000,000) and 1no. Twin toilet (300,000) | 2,300,000.00 | New |
| Assistant County Commissioner Anole | 4-008-037-2640507-113-2018/2019-009 | 2,000,000.00 | 2,000,000.00 | Renovation of Administration block and Residential house (Repair Wall cracks, Repairing and/or Replacing broken Doors and Windows, Remove of all floor cracks and replace, repainting of interior and exterior, Roofing, repainting and labelling) | 2,000,000.00 | New |
| Assistant County Commissioner Tulatula | 4-008-037-2640507-113-2018/2019-010 | 3,500,000.00 | 3,500,000.00 | Construction of 2 bedroom house (2,900,000) and external toilet and bath room(600,000) for the assistant county commissioner. | 3,500,000.00 | New |
| Assistant County Commissioner Tulatula | 4-008-037-2640507-113-2018/2019-011 | 1,000,000.00 | 1,000,000.00 | Construction of10,000m2 concrete Fence and gate | 1,000,000.00 | New |
| TOTAL |  |  |  |  | 109,040,875.52 |  |