## Sheet1
Igembe South | 137367724.14 |  |  | Auki Day Secondary School,Kshs.4,000,0000- Buying of a school bus(62 seater). NG-CDFC to provide proof that the school has committed itself to raise the remaining balance | Issue not cleared
|  | Codelist Memo | 25/2/2020 | Maua KMTC College,Kshs.25,000,000- Construction of storied classroom/ lecture halls ( 600sq.m ) Kshs. 10,800,000, construction of a storied administration block & library ( 600sq.m ) Kshs. 10,800,000, Construction of an ablution block ( 60sq.m ) Kshs. 1,080,000, preparation drawings & BoQs Kshs. 500,000, Preliminaries(4%) Kshs. 950,000, Contingency(5%) Kshs. 870,000. NG-CDFC to submit approval letter from KMTC for the establishment of the college | Issue cleared
|  |  |  | Karurune primary school- 1,500,000- Renovation of 2 classrooms to completion(Roofing, Flooring, plaster, fixing doors & windows, painting). NGCDFC to specify the state to send photos and based on this may revise cost | Issue not cleared
|  |  |  | Akui Day Secondary School 2,000,000- Construction of administration block(foundation & Walling )-8 rooms. NGCDFC to specify capacity and if it is to completion and revise cost. | Issue not cleared