MATUGA

IEBC NUMBER 009

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND

PROJECT PROPOSAL

2018/2019 FINANCIAL YEAR

SUBMITTED

NOVEMBER, 2018

MATUGA NG-CDFC MEETING HELD AT NG-CDF OFFICE ON 03RD NOVEMBER, 2018.

MEMBERS PRESENT

- Mr. Omar N. Mwagaga	   -Member

- Ms. Mercy W. Karanja	   -Secretary.

- Mr.Andrew  Lumunge	  - F.A.M

- Mr. Issack Keter                       - D.C.C

- Mr. Mwachiro N. Mwahanje - Member

- Ms Mariam Ndunge                - Member

- Ms.Mwanamkasi   A. Zani       -Chairlady.

- Mr. Rama M. Gang’ombe	 -Member

- Mr. Abeid S. Mwasaria	 -Member

- Mr. Saidi kazi Mwakazi	 -Member

AGENDA

- Address from the chair.

- Reading and confirmation of the previous minutes.

- Matters arising from the previous minutes.

- Projects proposals 2018/2019 financial year

- Re-allocation of funds. Bahakanda primary school ( ksh.6,000,000)

- A.O.B

MTG/NG-CDFC/MIN 1/03-11-2018: ADDRESS FROM THE CHAIR .

The chairman called the meeting to order and requested Ramadhan Gangombe to open the meeting with a word of prayer. He further congratulated members for being punctual and urged them contribute fully to the days agenda.

MTG/NG-CDFC/MIN 2/03-11-2018: READING AND CONFIRMATION OF THE PREVIOUS MINUTES

The minutes of the previous minutes were read through by the secretary and confirmed to be the true records of what was discussed.

MTG/NG-CDFC/MIN 3/03-11-2018: MATTERS ARISING FROM THE PREVIOUS MINUTES.

No matter arose from the previous minutes..

MTG/NG-CDFC/MIN 4/03-11-2018: PROJECTS PROPOSALS 2018/2019 FINANCIAL YEAR

The Chairman briefed members that the committee is required to submit project proposals for the financial year 2018/2019 soonest possible. He then welcomed the Fund Account Manager to give brief on the 2018/2019 allocations.

The Funds Account Manager briefed the NG-CDFC members that Matuga constituency had been allocated Kshs. 109,040,875.52 from the NG-CDF Board.

The NG-CDFC chairman then asked the secretary to present all the report collected from the public Barazas conducted in all five wards.

After proper scrutiny of the reports the NG-CDF Committee members resolved to allocate the funds to projects as hereunder analyzed;

- STANDING  ALLOCATIONS

| - Emergency fund. | 5,738,993.45 |
| --- | --- |
| - Administration/recurrent Expenses. | 6,198,112.07 |
| - Sports activities - Environmental activities | 2,066,037.00 2,066,037.00 |
| - Monitoring/Evaluation/Capacity Development | 3,099,056.00 |
| - Bursary fund. | 30,000,000.00 |

The total standing allocation was ksh. 49,168,235.52

The total funds to be disbursed to the projects for 2018/2019 financial year will be ksh. 59,872,640.00 The NG-CDFC after thorough scrutinizing of the proposals from the four wards, they anonymously resolved to allocate funds to projects as follows;

| Project Name | Project activity | Amount Allocated |
| --- | --- | --- |
| Mwanamkuu primary school | Construction of 3.No new classrooms to completion- Ksh. 3,000,000.00. Procuring and delivery of 60 pieces of desks- ksh. 240,000.00 | 3,240,000.00 |
| Kidongo primary school | Renovation of 4No. Classrooms (Roofing, plastering and painting) | 2,000,000.00 |
| Lwara Primary school. | Construction of 3.No new classrooms to completion- ksh. 3,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 3,200,000.00 |
| Kizimbani primary school | Construction of 3.No new classrooms to completion- ksh. 3,000,000.00. Procuring and delivery of 40 pieces of desks- ksh. 160,000.00 | 3,160,000.00 |
| Mwele primary school | Construction of 3No. New Classrooms to completion-ksh. 3,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 3,200,000.00 |
| Lunguma Primary school | Construction of 4No. New Classrooms to completion- ksh. 4,500,000.00 Procuring and delivery of 70 pieces of desks- ksh. 280,000.00 | 4,780,000.00 |
| Mwanzwani primary school | Construction of 3No. New Classrooms to completion- ksh. 3,000,000.00 Procuring and delivery of 58 pieces of desks- ksh. 232,000.00 | 3,232,000.00 |
| Nzora primary school | Construction of 2No. New Classrooms to completion- ksh. 2,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 2,200,000.00 |
| Nyando primary school | Construction of 2No. new Classrooms to completion- ksh.2,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 2,200,000.00 |
| Mbweka primary school | Renovation of 2No. Classrooms.( roofing, plastering and Painting) | 1,000,000.00 |
| Deiry primary school. | Procuring and delivery of 40 pieces of desk. | 160,000.00 |
| Lukore Secondary school | Renovation of 4No. Classrooms (Roofing and painting) | 2,000,000.00 |
| Mkomba secondary school | Renovation of 2No. Classrooms (Roofing and painting) kshs. 1,000,000.00 Construction of 2No. of Two door VIP pit latrines to completion- Kshs. 1,000,000.00 | 2,000,000.00 |
| Kirewe secondary school | Construction of a new single laboratory to completion | 3,500,000.00 |
| Mbegani secondary school | Construction of 1No. new Classroom to completion | 1,200,000.00 |
| Burani secondary school | Construction of a new single laboratory to completion. Ksh. 3,000,000.00 Renovation of 3No classrooms.( Roofing, plastering, painting and flooring)- Ksh. 1,000,000.00 | 4,000,000.00 |
| Balozi Makwere secondary school | Construction of 1No. new Classroom to completion | 1,000,000.00 |
| Ziwani secondary school | Renovation of One classroom (painting) – ksh. 200,000. Construction 2door pit latrine to completion- Ksh. 500,000.00 Purchase office furniture-ksh.300,000.00 | 1,000,000.00 |
| Chitsanze secondary school | Construction of 1No. new Classroom to completion | 1,000,000.00 |
| Kiteje secondary school | Construction of a new single laboratory to completion | 3,000,000.00 |
| Mwanambeyu secondary school | construction of a new dormitory to completion | 3,000,000.00 |
| Tiwi Girls secondary school | Completion of a multi-purpose Hall. I.e. co-funding with the school. (Roofing) | 1,000,000.00 |
| Matuga Girls secondary school | Completion of an administration Block. ( Flooring and Painting works) | 2,000,000.00 |
| Ngombeni police post | Construction of a new police post to completion | 2,000,000.00 |
| Tsimba chiefs Office. | Purchase of Land for the Tsimba chief’s office of quarter an acre. | 300,640.00 |
| Matuga constituency ICT Hub | Construction of a New ICT Hub to completion- Ksh. 2,000,000.00. Purchase of 10 tables and 30 chairs for the ICT hub- ksh. 500,000.00 | 2,500,000.00 |
| Kibambani primary school | Construction of 1No. New Classrooms to completion. | 1,000,000.00 |
| Kilindini primary school. | Construction of 1No. New Classrooms to completion. | 1,000,000.00 |
|  | TOTAL FOR THE PROJECTS | 59,827,640.00 |

MTG/NG-CDFC/MIN 5/03-11-2018: RE-ALLOCATION OF FUNDS. BAHAKANDA PRIMARY SCHOOL (KSH.6, 000,000)

Members were informed that there were some funds to be re-allocated to do other projects. The reasons for the re-allocation are outlined here under;

| NO | NAME OF THE PROJECT | ACTIVITY TOBE DONE | AMOUNT | REASONS FOR THE RE-ALLOCATION |
| --- | --- | --- | --- | --- |
| 1. | Bahakanda primary school. | Construction of 1No. Dormitory to completion. | 6,000,000 | A donor has constructed the dormitory to completion. |
|  |  | TOTAL | 6,000,000 |  |

After a lengthy discussion members resolved to re-allocate the funds to the following projects.

| NO | NAME OF THE PROJECT | ACTIVITY TOBE DONE | AMOUNT | RE-ALLOCATED TO | ACTIVITY TO BE DONE. | AMOUNT |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Bahakanda primary school. | Construction of 1No. Dormitory to completion. | 6,000,000 | Bahakanda primary school. | Fencing the school compound with concrete poles and chain link wire with a gate Ksh 4,663,896. Water reticulation and Construction of High level water storage tank. Ksh. 1,336,104. | 6,000,000 |
|  |  | TOTAL | 6,000,000 |  | TOTAL | 6,000,000 |

MTG/NG-CDFC/MIN 6/03-11-2018: A.O.B. .

There being no any other business, the meeting ended at 2pm with a word of prayer from Abeid Mwasaria.

Minutes Prepared by:                                                                Minutes Confirmed by:

Mercy Karanja                                                                    Mwanamkasi A. Zani

NG-CDFC Secretary.                                                                  NG-CDFC Chairperson.

Sign ……………………                                                           Sign………………………

Date……………………                                                            Date……………………...

907

2015                     National Government Constituencies Development Fund                                        No. 30

THIRD SCHEDULE                                                    (s. 15)

CONSTITUENCY PROJECTS SUBMISSION FORM

Constituency No 009 Constituency Name MATUGA Financial Year 2018/2019

| Serial | Name of Project | Amount Allocated |
| --- | --- | --- |
| 009/AP1 | Administration/Recurrent | 6,198,112.07 |
| 009/AP2 | Monitoring and Evaluation/Capacity Building | 3,099,056.00 |
| 009/2640100 | Education Bursary | 30,000,000.00 |
| 009/2630204 | Primary School Projects | 30,372,000.00 |
| 009/2630205 | Secondary School Projects | 24,700,000.00 |
| 009/2211311 | Matuga Constituency ICT Hub Project | 2,500,000.00 |
| 009/2640507 | Security Projects | 2,300,640.00 |
| 009/2640510 | Environmental activities | 2,066,037.00 |
| 009/2640509 | Sports Activities | 2,066,037.00 |
| 009/2640200 | Emergency Reserve | 5,738,993.45 |
| Total |  | 109,040,875.52 |

Chairman NG- CDF Committee …………………… Signature………………….. Date………………

Fund Account Manager …………………………… Signature…………………….Date………………

907

2015               National Government Constituencies Development Fund                              No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/AP1

Project Title 6% Administration/Recurrent

Sector Administration

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

The allocation is to cater for CDFC Allowance, staff salaries, vehicle expenses and other administrative expenses.

Financial year 20181st July To 30th June 2019

Original Cost estimates, in Kshs. 6,198,112.07 Dated…………………

Amount allocated last financial year 5,208,620.00

Amount allocated this financial year 6,198,112.07

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Employees Salaries | 4-002-009-2110000-100-2018/19-001 | Payment of staff salaries and gratuity | 2,700,240.00 | On-going |
| Goods and Services | 4-002-009-2210000-100-2018/19-002 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence. | 1,844,512.07 | On-going |
| NSSF | 4-002-009-2120101-100-2018/2019-003 | Payment of NSSF Deductions | 271,760.00 | On-going |
| NHIF | 4-002-009-2120201-100-2018/19-004 | Payment of NHIF Deductions | 85,600.00 | On-going |
| Committee Expenses | 4-002-009-2210802-100-2018/19-005 | Payment of Committee sitting allowances, transport, conferences | 1,296,000.00 | On-going |
| TOTAL |  |  | 6,198,112.07 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/AP2

Project Title 3% Monitoring & Evaluation/Capacity Building

Sector Monitoring & Evaluation

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To cater for Monitoring and Evaluation of NG-CDF projects and capacity building of NG-CDFC ,NG-CDFC Staff and PMC’s in the constituency

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 3,099,056.00 dated…………………

Amount allocated last financial year 2,604,310.00

Amount allocated this financial year 3,099,056.00

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Goods and Services | 4-002-009-2210000-111-2018/19-001 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 350,000.00 | On-going |
| Committee Expenses | 4-002-009-2210802-111-2018/19-002 | Payment of Committee sitting allowances, transport, conferences | 756,000.00 | On-going |
| CDFC/PMC Capacity Building | 4-002-009-2210700-111-2018/19-003 | Undertake Training of the PMCs/NG-CDFCs on NG- CDF Related issues | 1,993,056.00 | On-going |
| TOTAL |  |  | 3,099,056.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009Constituency Name MATUGA County KWALE

Project Number009/2640200

Project Title Emergency Reserve (5% of the fund)

Sector Emergency

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Unallocated amount meant for emergencies that may occur within the Constituency

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 5,738,993.45 dated…………………

Amount allocated last financial year 4,568,965.52

Amount allocated this financial year 5,738,993.45

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Emergency | 4-002-009-2640200-101-2018/19-001 | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | On-going |
| Total |  |  | 5,738,993.45 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009Constituency Name MATUGA County KWALE

Project Number009/2640509

Project Title 2% Sports Activities

Sector Sports

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Carrying out constituency sports tournament and winning team to be awarded trophies.

Financial year 2018   1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,066,037.00dated…………………

Amount allocated last financial year 1,736,206.00

Amount allocated this financial year 2,066,037.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Constituency Sports Tournament | 4-002-009-2640509-112-2018/19-001 | Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits. | 2,066,037.00 | On-going |
| Total |  |  | 2,066,037.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number009/2640100

Project Title Bursary

Sector Bursary

Status of projects (tick one) New………………. Extension……………….. On-going…√…..Rehabilitation ………………….

Brief statement on project status at time of submission

Towards Bursary for payment of fees for needy students and continuous assessment tests.

Financial year 2018  1st July To 30th June 2019

Original Cost estimates, in Kshs. 30,000,000.00 dated…………………

Amount allocated last financial year Kshs. 21,702,586.00

Amount allocated this financial year 30,000,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Bursary Secondary Schools | 4-002-009-2640101-103-2018/19-001 | Payment of bursary to needy student | 24,000,000.00 | On-going |
| Bursary Tertiary Schools | 4-002-009-2640102-103-2018/19-002 | Payment of bursary to needy student | 6,000,000.00 | On-going |
| TOTAL |  |  | 30,000,000.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/2630204

Project Title Primary School Projects

Sector Education

Status of projects (tick one) New……√…………. Extension……………….. On-going……..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions in the primary schools institutions by improving the infrastructure.

Financial year 2018  1st July To 30th June 2019

Original Cost estimates, in Kshs. 30,372,000.00dated…………………

Amount allocated last financial year 18,764,000.00

Amount allocated this financial year 30,372,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Mwanamkuu primary school | 4-002-009-2630204-104-2018/2019-001 | Construction of 3.No new classrooms to completion- Ksh. 3,000,000.00. Procuring and delivery of 60 pieces desk- ksh. 240,000.00 | 3,240,000.00 | New |
| Kidongo primary school | 4-002-009-2630204-104-2018/2019-002 | Renovation of 4No. Classrooms (Roofing, plastering and painting) | 2,000,000.00 | New |
| Lwara Primary school. | 4-002-009-2630204-104-2018/2019-003 | Construction of 3.No new classrooms to completion- ksh. 3,000,000.00 Procuring and delivery of 50 pieces desk- ksh. 200,000.00 | 3,200,000.00 | New |
| Kizimbani primary school | 4-002-009-2630204-104-2018/2019-004 | Construction of 3.No new classrooms to completion- ksh. 3,000,000.00. Procuring and delivery of 40 pieces desk- ksh. 160,000.00 | 3,160,000.00 | New |
| Mwele primary school | 4-002-009-2630204-104-2018/2019-005 | Construction of 3No. New Classrooms to completion-ksh. 3,000,000.00 Procuring and delivery of 50 pieces desk- ksh. 200,000.00 | 3,200,000.00 | New |
| Lunguma Primary school | 4-002-009-2630204-104-2018/2019-006 | Construction of 4No. New Classrooms to completion- ksh. 4,500,000.00 Procuring and delivery of 70 pieces desk- ksh. 280,000.00 | 4,780,000.00 | New |
| Mwanzwani primary school | 4-002-009-2630204-104-2018/2019-007 | Construction of 3No. New Classrooms to completion- ksh. 3,000,000.00 Procuring and delivery of 58 pieces desk- ksh. 232,000.00 | 3,232,000.00 | New |
| Nzora primary school | 4-002-009-2630204-104-2018/2019-008 | Construction of 2No. New Classrooms to completion- ksh. 2,000,000.00 Procuring and delivery of 50 pieces desk- ksh. 200,000.00 | 2,200,000.00 | New |
| Nyando primary school | 4-002-009-2630204-104-2018/2019-009 | Construction of 2No. new Classrooms to completion- ksh.2,000,000.00 Procuring and delivery of 50 pieces desk- ksh. 200,000.00 | 2,200,000.00 | New |
| Mbweka primary school | 4-002-009-2630204-104-2018/2019-010 | Renovation of 2No. Classrooms.( roofing, plastering and Painting) | 1,000,000.00 | New |
| Deiry primary school. | 4-002-009-2630204-104-2018/2019-010 | Procuring and delivery of 40 pieces of desk. | 160,000.00 | New |
| Kibambani primary school | 4-002-009-2630204-104-2018/2019-011 | Construction of 1No. New Classrooms to completion. | 1,000,000.00 | New |
| Kilindini primary school. | 4-002-009-2630204-104-2018/2019-012 | Construction of 1No. New Classrooms to completion. | 1,000,000.00 | New |
| Total |  |  | 30,372,000.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/2630205

Project Title Secondary School Projects

Sector Education

Status of projects (tick one) New…………√……. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions of Secondary by improving the infrastructure

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 24,700,000.00dated…………………

Amount allocated last financial year 16,328,630.10

Amount allocated this financial year 24,700,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Lukore Secondary school | 4-002-009-2630205-104-2018/2019-001 | Renovation of 4No. Classrooms (Roofing and painting) | 2,000,000.00 | New |
| Mkomba secondary school | 4-002-009-2630205-104-2018/2019-002 | Renovation of 2No. Classrooms (Roofing and painting) kshs. 1,000,000.00 Construction of 2No. of Two door VIP pit latrines to completion- Kshs. 1,000,000.00 | 2,000,000.00 | New |
| Kirewe secondary school | 4-002-009-2630205-104-2018/2019-003 | Construction of a new single laboratory to completion | 3,500,000.00 | New |
| Mbegani secondary school | 4-002-009-2630205-104-2018/2019-004 | Construction of 1No. new Classroom to completion | 1,200,000.00 | New |
| Burani secondary school | 4-002-009-2630205-104-2018/2019-005 | Construction of a new single laboratory to completion. Ksh. 3,000,000.00 Renovation of 3No classrooms.( Roofing, plastering, painting and flooring)- Ksh. 1,000,000.00 | 4,000,000.00 | New |
| Balozi Makwere secondary school | 4-002-009-2630205-104-2018/2019-006 | Construction of 1No. new Classroom to completion | 1,000,000.00 | New |
| Ziwani secondary school | 4-002-009-2630205-104-2018/2019-007 | Renovation of One classroom (painting) – ksh. 200,000. Construction 2door pit latrine to completion- Ksh. 500,000.00 Purchase office furniture-ksh.300,000.00 | 1,000,000.00 | New |
| Chitsanze secondary school | 4-002-009-2630205-104-2018/2019-008 | Construction of 1No. new Classroom to completion | 1,000,000.00 | New |
| Kiteje secondary school | 4-002-009-2630205-104-2018/2019-009 | Construction of a new single laboratory to completion | 3,000,000.00 | New |
| Mwanambeyu secondary school | 4-002-009-2630205-104-2018/2019-010 | construction of a new dormitory to completion | 3,000,000.00 | New |
| Tiwi Girls secondary school | 4-002-009-2630205-104-2018/2019-011 | Completion of a multi-purpose Hall. I.e. co-funding with the school. (Roofing) | 1,000,000.00 | New |
| Matuga Girls secondary school | 4-002-009-2630205-104-2018/2019-012 | Completion of an administration Block. ( Painting works) | 2,000,000.00 | On-going |
| Total |  |  | 24,700,000.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/2640507

Project Title Security Projects

Sector Security

Status of projects (tick one) New………√………. Extension……………….. On-going……..

Rehabilitation ………………….

Brief statement on project status at time of submission

Projects to ensure proper security in the constituency through Construction of a police Post and purchase of land for chief’s office.

Financial year 2018  1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,300,640.00 dated……………

Amount allocated last financial year 2,500,000.00

Amount allocated this financial year 2,300,640.00

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Ngombeni police post | 4-002-009-2640507-113-2018/2019-001 | Construction of a new police post to completion | 2,000,000.00 | New |
| Tsimba chiefs Office. | 4-002-009-2640507-113-2018/2019-002 | Purchase of Land for the Tsimba chief’s office of quarter an acre. | 300,640.00 | New |
| Total |  |  | 2,300,640.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/2211311

Project Title: Matuga Constituency ICT Hubs Project.

Sector Others

Status of projects (tick one) New……√…………. Extension……………….. On-going……..

Rehabilitation ………………….

Brief statement on project status at time of submission

To promote information technology within Matuga constituency.

Financial year 2018  1st July To 30th June 2019

Original Cost estimates, in Kshs2, 500,000.00 dated…………………

Amount allocated last financial year 0.00

Amount allocated this financial year 2,500,000.00

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Matuga constituency ICT Hub | 4-002-009-2211311-108-2018/2019-001 | Construction of a New ICT Hub to completion- Ksh. 2,000,000.00. Purchase of 10 tables and 30 chairs for the ICT hub- ksh. 500,000.00 | 2,500,000.00 | New |
| Total |  |  | 2,500,000.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…05/11/2018………

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 009 Constituency Name MATUGA County KWALE

Project Number 009/2640510

Project Title Environmental activities

Sector Environment

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Purchase and installation of water tanks to various schools within the constituency.

Financial year 2018 1st July To 30th June 2019

Original Cost estimates, in Kshs. 2,066,037.00dated…………………

Amount allocated last financial year 1,200,000.00

Amount allocated this financial year 2,066,037.00

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Environmental Activities. | 4-002-008-2640510-110-2017/2018-001 | Purchase and installation of gutters, tank stands and water tank of 10,000 litres to Dima Primary school, Kirewe secondary school, Boyani primary school and Magwasheni primary @ksh.413,207.40 totaling to ksh.1,652,829.60 Rehabilitation of Nyando natural water spring (construction of water banks, fencing around the springs and planting trees around the springs) - ksh. 413,207.40 | 2,066,037.00 | On-going |
| Total |  |  | 2,066,037.00 |  |

Person completing form: Name …Andrew Lumunge.. Position Fund Account Manager

Signature…………………… Date…15/01/2018………

Matuga National Government Constituency Development Fund

Project Proposal 2018/2019 Financial Year

Codelist

FINANCIAL YEAR..…2018 1ST JULY TO 30TH JUNE……2019

| Project Name | Project Number | Original Cost | Cumulative allocation | Project activity | Amount Allocated | Current Status |
| --- | --- | --- | --- | --- | --- | --- |
| Employees Salaries | 4-002-009-2110000-100-2018/19-001 |  |  | Payment of staff salaries and gratuity | 2,700,240.00 | On-going |
| Goods and Services | 4-002-009-2210000-100-2018/19-002 |  |  | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence. | 1,844,512.07 | On-going |
| NSSF | 4-002-009-2120101-100-2018/2019-003 |  |  | Payment of NSSF Deductions | 271,760.00 | On-going |
| NHIF | 4-002-009-2120201-100-2018/19-004 |  |  | Payment of NHIF Deductions | 85,600.00 | On-going |
| Committee Expenses | 4-002-009-2210802-100-2018/19-005 |  |  | Payment of Committee sitting allowances, transport, conferences | 1,296,000.00 | On-going |
| Goods and Services | 4-002-009-2210000-111-2018/19-001 |  |  | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 350,000.00 | On-going |
| Committee Expenses | 4-002-009-2210802-111-2018/19-002 |  |  | Payment of Committee sitting allowances, transport, conferences | 756,000.00 | On-going |
| CDFC/PMC Capacity Building | 4-002-009-2210700-111-2018/19-003 |  |  | Undertake Training of the PMCs/NG-CDFCs on NG- CDF Related issues | 1,993,056.00 | On-going |
| Emergency | 4-002-009-2640200-101-2018/19-001 |  |  | To cater for any unforeseen occurrences in the constituency during the financial year | 5,738,993.45 | On-going |
| Constituency Sports Tournament | 4-002-009-2640509-112-2018/19-001 |  |  | Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies. | 2,066,037.00 | On-going |
| Bursary Secondary Schools | 4-002-009-2640101-103-2018/19-001 |  |  | Payment of bursary to needy student | 24,000,000.00 | On-going |
| Bursary Tertiary Schools | 4-002-009-2640102-103-2018/19-002 |  |  | Payment of bursary to needy student | 6,000,000.00 | On-going |
| Mwanamkuu primary school | 4-002-009-2630204-104-2018/2019-001 |  |  | Construction of 3.No new classrooms to completion- Ksh. 3,000,000.00. Procuring and delivery of 60 pieces of desks- ksh. 240,000.00 | 3,240,000.00 | New |
| Kidongo primary school | 4-002-009-2630204-104-2018/2019-002 |  |  | Renovation of 4No. Classrooms (Roofing, plastering and painting) | 2,000,000.00 | New |
| Lwara Primary school. | 4-002-009-2630204-104-2018/2019-003 |  |  | Construction of 3.No new classrooms to completion- ksh. 3,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 3,200,000.00 | New |
| Kizimbani primary school | 4-002-009-2630204-104-2018/2019-004 |  |  | Construction of 3.No new classrooms to completion- ksh. 3,000,000.00. Procuring and delivery of 40 pieces of desks- ksh. 160,000.00 | 3,160,000.00 | New |
| Mwele primary school | 4-002-009-2630204-104-2018/2019-005 |  |  | Construction of 3No. New Classrooms to completion-ksh. 3,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 3,200,000.00 | New |
| Lunguma Primary school | 4-002-009-2630204-104-2018/2019-006 |  |  | Construction of 4No. New Classrooms to completion- ksh. 4,500,000.00 Procuring and delivery of 70 pieces of desks- ksh. 280,000.00 | 4,780,000.00 | New |
| Mwanzwani primary school | 4-002-009-2630204-104-2018/2019-007 |  |  | Construction of 3No. New Classrooms to completion- ksh. 3,000,000.00 Procuring and delivery of 58 pieces of desks- ksh. 232,000.00 | 3,232,000.00 | New |
| Nzora primary school | 4-002-009-2630204-104-2018/2019-008 |  |  | Construction of 2No. New Classrooms to completion- ksh. 2,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 2,200,000.00 | New |
| Nyando primary school | 4-002-009-2630204-104-2018/2019-009 |  |  | Construction of 2No. new Classrooms to completion- ksh.2,000,000.00 Procuring and delivery of 50 pieces of desks- ksh. 200,000.00 | 2,200,000.00 | New |
| Mbweka primary school | 4-002-009-2630204-104-2018/2019-010 |  |  | Renovation of 2No. Classrooms.( roofing, plastering and Painting) | 1,000,000.00 | New |
| Deiry primary school. | 4-002-009-2630204-104-2018/2019-010 |  |  | Procuring and delivery of 40 pieces of desk. | 160,000.00 | New |
| Lukore Secondary school | 4-002-009-2630205-104-2018/2019-001 |  |  | Renovation of 4No. Classrooms (Roofing and painting) | 2,000,000.00 | New |
| Mkomba secondary school | 4-002-009-2630205-104-2018/2019-002 |  |  | Renovation of 2No. Classrooms (Roofing and painting) kshs. 1,000,000.00 Construction of 2No. of Two door VIP pit latrines to completion- Kshs. 1,000,000.00 | 2,000,000.00 | New |
| Kirewe secondary school | 4-002-009-2630205-104-2018/2019-003 |  |  | Construction of a new single laboratory to completion | 3,500,000.00 | New |
| Mbegani secondary school | 4-002-009-2630205-104-2018/2019-004 |  |  | Construction of 1No. new Classroom to completion | 1,200,000.00 | New |
| Burani secondary school | 4-002-009-2630205-104-2018/2019-005 |  |  | Construction of a new single laboratory to completion. Ksh. 3,000,000.00 Renovation of 3No classrooms.( Roofing, plastering, painting and flooring)- Ksh. 1,000,000.00 | 4,000,000.00 | New |
| Balozi Makwere secondary school | 4-002-009-2630205-104-2018/2019-006 |  |  | Construction of 1No. new Classroom to completion | 1,000,000.00 | New |
| Ziwani secondary school | 4-002-009-2630205-104-2018/2019-007 |  |  | Renovation of One classroom (painting) – ksh. 200,000. Construction 2door pit latrine to completion- Ksh. 500,000.00 Purchase office furniture-ksh.300,000.00 | 1,000,000.00 | New |
| Chitsanze secondary school | 4-002-009-2630205-104-2018/2019-008 |  |  | Construction of 1No. new Classroom to completion | 1,000,000.00 | New |
| Kiteje secondary school | 4-002-009-2630205-104-2018/2019-009 |  |  | Construction of a new single laboratory to completion | 3,000,000.00 | New |
| Mwanambeyu secondary school | 4-002-009-2630205-104-2018/2019-010 |  |  | construction of a new dormitory to completion | 3,000,000.00 | New |
| Tiwi Girls secondary school | 4-002-009-2630205-104-2018/2019-011 |  |  | Completion of a multi-purpose Hall. I.e. co-funding with the school. (Roofing) | 1,000,000.00 | New |
| Matuga Girls secondary school | 4-002-009-2630205-104-2018/2019-012 | 18,626,634.34 | 20,626,634.34 | Completion of a modern administration Block. ( Flooring and Painting works) | 2,000,000.00 | On-going |
| Ngombeni police post | 4-002-009-2640507-113-2018/2019-001 |  |  | Construction of a new police post to completion | 2,000,000.00 | New |
| Tsimba chiefs Office. | 4-002-009-2640507-113-2018/2019-002 |  |  | Purchase of Land for the Tsimba chief’s office of quarter an acre. | 300,640.00 | New |
| Matuga constituency ICT Hub | 4-002-009-2211311-108-2018/2019-001 |  |  | Construction of a New ICT Hub to completion- Ksh. 2,000,000.00. Purchase of 10 tables and 30 chairs for the ICT hub- ksh. 500,000.00 | 2,500,000.00 | New |
| Environmental Activities. | 4-002-008-2640510-110-2017/2018-001 |  |  | Purchase and installation of gutters, tank stands and water tank of 10,000 litres to Dima Primary school, Kirewe secondary school, Boyani primary school and Magwasheni primary @ksh.413,207.40 totaling to ksh.1,652,829.60 Rehabilitation of Nyando natural water spring (construction of water banks, fencing around the springs and planting trees around the springs) - ksh. 413,207.40 | 2,066,037.00 | On-going |
| Kibambani primary school | 4-002-009-2630204-104-2018/2019-011 |  |  | Construction of 1No. New Classrooms to completion. | 1,000,000.00 | New |
| Kilindini primary school. | 4-002-009-2630204-104-2018/2019-012 |  |  | Construction of 1No. New Classrooms to completion. | 1,000,000.00 | New |
|  |  |  |  |  | 109,040,875.52 |  |