MINUTES OF THE RUIRU NG-CDF COMMITTEE MEETING HELD ON 17TH FEBRUARY 2022 AT THE NG-CDF OFFICE RUIRU AT 10:30AM

PRESENT MEMBERS

- Rachael Macharia               		Chairperson

- Phares Karanja                  		Fund Account Manager

- Mary Kinguku                  		Member

- Paul Kigaa                    		Member

- Felistas Maria Kenyoni           		Member

- Esther Njeri		            	Member

- Boniface Mwaura			Member

- Agnes Wanjiku			Member

- Joseph Mwangi			Member

AGENDA

- Opening of the meeting/preliminaries

- Reading of Minutes of previous meeting

- Resubmissions

- Emergency Requests

- Bursary Awards

- AOB

MIN 1/17/02/2022: Opening of the Meeting/Preliminaries

The meeting started at 10:00am with a word of prayer led by Boniface. The Chairperson then welcomed members to the meeting. She expressed her satisfaction with the projects implementation this far and hoped that the committee will achieve even much more in the few months before the election. She thanked members for working together to serve the community.

MIN 2/17/02/2022:  Reading of Minutes of Previous Meeting

The minutes of the previous meeting were proposed by Esther and seconded by Boniface.

MIN 3/17/02/2022: Resubmissions

Members noted that the Board had not approved our FY 2022/23 project proposal in full.

It was noted that Mwalimu Farm Primary School School Access road project that had not been fully approved could be resubmitted in favour of Kahawa Wendani Primary School which was in dire need of classrooms for standard six in the new academic year. The Estimated cost would be Ksh 3m due to the nature of soil type in that area.

The Fund Manager was requested to give urgent attention to this decision.

MIN 4/17/02/2022: Emergency Requests

Members considered emergency requests in respect of the following and made a decision accordingly.

| No | PROJECT | PURPOSE | AMOUNT |
| --- | --- | --- | --- |
| 1. | Mukuyu Primary School | Renovation of worn out classrooms | 500,000 |
| 2. | Kiratina Primary School | Renovation of worn out classrooms | 200,000 |

MIN 5/17/02/2022: Bursary Awards

Members approved the report of the Bursary Sub Committee in respect of late bursary applicant as per appendix ‘K’ amounting to Ksh. 717,000.

MIN 6/17/02/2022: Adjournment

The meeting ended at midday with word of prayer by Boniface

Minutes Prepared By:  Secretary: Joseph Mwangi

Date……16/11/2021………………….. Sign:……… ………………

Minutes Confirmed By: Chairman:   Rachael Macharia

Date……16/11/2021………………….. Sign:……… ………………

Minutes Endorsed by:   FAM: Phares Karanja

Date…16/11/2021…………………….. Sign:………… ……………