National Government Constituencies Development Fund

Pokot South Constituency

Chepareria Divisional HQs, ACCs Offices, NG-CDF Office

Kapenguria-Lodwar Road, Chepareria

P.O Box 681-30600.

KAPENGURIA, KENYA.

Cell: +254 729 205 889.

Email: cdfpokotsouth@ngcdf.go.ke. | Website: www.ngcdf.go.ke.

POKOT SOUTH NG-CDF

MINUTES FOR POKOT SOUTH NG-CDFC MEETING HELD ON FRIDAY JANUARY 5, 2018 AT NG-CDF –OFFICE CHEPARERIA STARTING AT 10.00 AM. Members Present - Julius Siwareng – Chairperson - Rodah Chemakit Yarangole - Secretary - Festus Kipomet - Fund Account Manager - Evans Ruto Yokito - Member - Rose Cheruto Pkukat - Member - Samson Lowuata Atodonyang -Member - Jacob Lisoreing Ywarangole - Member - Catherine Cherop Tulel - Member - Michael N. John – DCC Rep AGENDA - Preliminaries - Reading of the Previous Minutes - Matters Arising - 2017/2018 Financial Year Project Proposal - A.O.B Min. NG-CDF/PS/132/1/01/2018: Preliminaries The chairperson called the meeting to order at 10:00a.m and asked Rose Cheruto Pkukat to give the opening prayer, the chair requested members to actively contribute to the meeting agenda. Min. NG-CDF/PS/132/2/01/2018: Reading of the previous minutes The secretary read through the minutes of the previous meeting. The minutes were confirmed to be the true copy of the deliberations proposed by Evans Ruto Yokito and seconded by Samson Lowuata Atodonyang. Min. NG-CDF/PS/132/3/01/2018: Matters Arising Min. PS/132/3/12/2017 on election of Chairperson and Secretary of the NG-CDF Committee, Members were informed that the names of the Chairperson and Secretary elected in the previous meeting have been forwarded to the board. Min. NG-CDF/PS/132/4/01/2018: 2017/2018 Financial Year Project Proposal The total allocation for Pokot South National Government Constituency Development Fund for 2017/2018 financial year is kshs 86,810,344.52 The Pokot South NG-CDFCs deliberated on this item at length and resolved that the above amount be spend as follows; - Administration and recurrent expenditure is 6% - kshs 5,208,620.67 - M&E and capacity building – 3% - kshs 2,604,310.13 - Emergency – 5% - kshs 4,568,965.52 - Sports activities - 2% - kshs 1,736,206.00 - Constituency Innovation Hubs (CIH) Project – kshs 4,677,027.20 - Constituency Strategic Plan – kshs 4,000,000.00 - Bursary, mocks and continuous assessment tests –32.5% kshs 28,200,000.00 - Primary School Projects – kshs 14,800,000.00 - Secondary School Projects – kshs 19,300,000.00 - Security Projects – kshs 1,715,215.00. The NG-CDF committees’ attention is drawn to only those projects that are in respect of works and services falling within the functions of the National Government under the constitution of Kenya. The Fund account manager briefed members on the guidelines, preparation and submission of constituency project proposals for the 2017/2018 financial year which among them include the following requirements: - Consultative preparation of projects - Eligible and ineligible projects under the Act - Part funding of NG-CDF projects - Implementation of the Constituency Innovation Hubs Project (CIH) - Priority to ongoing projects - Labeling/branding of constituency projects - Adherence to statutory ceilings - Compliance with Constituency strategic plan and other local and National Development Goals - Construction of NG-CDFC Office - Declaration of Appropriation In Aid - Project submission format - Project coding - Authentication of NG-CDFC Minutes - Timeline for submission The members deliberated and resolved to approve the following projects to be funded in the Financial Year 2017/2018 in all the four wards of Pokot South Constituency. Project name; Project activity; Amount (Kshs); Current Status. Employees Salaries; Payment of staff salaries and gratuity; 2,220,000.00; Ongoing. Committee Expenses; Payment of Committee sitting allowances, transport, conferences; 1,857,820.67; Ongoing. Goods and Services; Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea.; 1,000,000.00; Ongoing. NSSF; Payment of NSSF Deductions; 52,800.00; Ongoing. NHIF; Payment of NHIF Deductions; 78,000.00; Ongoing. Goods and Services; Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence.; 804,310.13; Ongoing. Committee Expenses; Payment of Committee sitting allowances, transport, conferences; 1,100,000.00; Ongoing. CDFC/PMC Capacity Building; Undertake Training of the PMCs/CDFCs on CDF Related issues; 700,000.00; Ongoing. Emergency; To cater for any unforeseen occurrences in the constituency during the financial year; 4,568,965.52; Ongoing. Constituency Sports Tournament; Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits; 1,736,206.00; Ongoing. Constituency Innovation Hubs (CIH) Project; Installation of the system and services comprising of a Satellite Antenna, Router, Digital Access Kit and Digital Ruggedized Tablets, Wi-Fi with outdoor wireless devise complete with 12U cabinet complete with installation accessories at NG-CDFC Office, Batei Educational office, Kabichbich chief’s office and Tapach chief’s office @ Kshs 1,169,256.80 per site; 4,677,027.20; New. Constituency Strategic Plan; Developing Pokot South NG-CDF Strategic plan for 2018 to 2022; 4,000,000.00; New. Bursary Secondary Schools; Payment of bursary to needy student; 20,200,000.00; Ongoing. Bursary Tertiary Institutions; Payment of bursary to needy student; 8,000,000.00; Ongoing. Kodoso Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 2 classrooms; 2,000,000.00; New. Tirken Primary School; Roofing, Plastering, Painting, doors and windows of Dormitory; 800,000.00; Ongoing. Chemarmar Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 800,000.00; New. Chemonges Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 800,000.00; New. Kaptingwo Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 800,000.00; New. Mokowon Primary School; Roofing, Plastering, Painting, doors and windows of 1 classroom; 400,000.00; Ongoing. Pusian Primary School; Plastering, Painting, doors and windows of Dining hall; 400,000.00; Ongoing. Murksian Primary School; Buying School land- 2 Acres; 600,000.00; New. Tonoyon Primary School; Plastering, Painting, doors and windows of 2 classrooms; 600,000.00; Ongoing. Chepkata Primary School; Buying School land- 2 Acres; 600,000.00; New. Kaalotwari Primary School; Renovation of classrooms; Plastering, painting, repair of doors and windows of 4 classrooms; 600,000.00; New. Parua East Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 800,000.00; New. Sebit Primary School; Roofing, Plastering, painting, Doors and Windows of Dining hall; 800,000.00; Ongoing. Tomnyer Primary School; Roofing, Plastering, Painting, doors and windows of 1 classroom; 500,000.00; Ongoing. Nyarkulian Primary School; Renovation of classrooms; Plastering, painting, repair of doors and windows of 5 classrooms; 600,000.00; New. Tapach Primary School; Roofing, Plastering, painting, Doors and Windows of Dining hall; 600,000.00; Ongoing. Kondopilet Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 900,000.00; New. Pchotoy Primary School; Roofing, Plastering, Painting, doors and windows of 1 classroom; 500,000.00; Ongoing. Cheptapesia Primary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 1,000,000.00; New. Chemoril Primary School; Plastering, Painting, doors and windows of 2 classrooms; 400,000.00; Ongoing. Kapchesich Primary School; Plastering, Painting, doors and windows of 2 classrooms; 300,000.00; Ongoing. St. Paul Lomuke Secondary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 2 classrooms; 3,000,000.00; New. Chepukat Mixed Day Secondary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 2 classrooms; 3,000,000.00; New. St. Peters Kapchemogen Secondary School; Foundation, Walling Roofing, Plastering, Painting, doors and windows of 2 classrooms; 2,000,000.00; New. St. Paul Kipkomo Boys Secondary school; Roofing, Plastering, Painting, doors and windows of 2 classrooms; 800,000.00; Ongoing. Kosulol Mixed Secondary School; Roofing, Plastering, Painting, doors and windows of 2 classrooms; 800,000.00; Ongoing. St. Joseph Kaalotwari Mixed Day Sec. School; Roofing, Plastering, Painting, doors and windows of Administration Block; 3,000,000.00; Ongoing. Parua Mixed Day Secondary School; Roofing, Plastering, Painting, doors and windows of Dormitory; 800,000.00; Ongoing. Penon Mixed Day & Boarding Secondary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 2 classrooms; 3,500,000.00; New. Ptop Mixed Day Secondary School; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 1 classroom; 800,000.00; New. Chemolo Mixed Day Secondary School; Roofing, Plastering, Painting, doors and windows of 2 classrooms; 600,000.00; Ongoing. Psiywo Mixed Day Secondary School; Foundation, Walling and Roofing of Administration Block; 1,000,000.00; New. Kipkomo Sub-County AP Camp; Foundation, Walling, Roofing, Plastering, Painting, doors and windows of 2 AP houses; 1,000,000.00; New. Chepareria Divisional Offices; Construction of 3 toilets to completion; 715,215.00; New. GRAND TOTAL; 86,810,344.82. The committee members tasked the Fund Account Manager to do the necessary documentation with the help of the NG-CDFC chair and secretary and forward the Project proposal to the NG-CDF Board for approval. The NG-CDFC members unanimously agreed and all together approved the above proposal for funding in Pokot south NG-CDF kitty in 2017/2018 financial year. Min. NG-CDF/PS/132/5/01/2018: A.O.B The NG-CDFC members approved the following; - The NG-CDF Committee to be paid four days allowances amounting to kshs 188,000.00 during consultative preparation of projects in the four (4) wards of Pokot South Constituency - Payment of the facilitation and other logistics of public participation process to be paid as per the ultimate budget - NG-CDF Committee sitting allowance for the meeting of Kshs.47, 000.00 to be paid. - The Fund Account manager, Chairperson and Secretary to be paid allowances and night outs for the period of projects proposal preparation and submission to the NG - CDF Board. - Adjournment The meeting was adjourned at 3:40pm by a word of prayer from Jacob Lisoreing Ywarangole.