| NG-CDF BOARD | National Government Constituencies Development Fund Board NYAKACH CONSTITUENCY Next to Nyakach sub county DCC Compound P.O Box 169-40111 Pap-Onditi, Kenya Cellphone: Fund Manager 0723 896 642 Chairman 0724 525 425 Email: cdfnyakach@cdf.go.ke ¦ Website:www.ngcdf.go.ke |
| --- | --- |

MINUTES OF THE NYAKACH NG-CONSTITUENCY DEVELOPMENT FUND COMMITTEE MEETING HELD AT THE CONSTITUENCY OFFICES BOARD ROOM ON 21st JANUARY 2020

Present

1. Joel Mc Odongo - Chairman

2. Hellen Were - Secretary

3. Alfred chisaina - F.A.M

4. Henry Odingo - Member

5. Leah Aringo - Member

6. Susan Otieno - Member

7. Cornelius Sangura - D.C.C

8. Nahashon Osenya - Member

9. Justus Ochieng’ - Member

10. Tom Miruka - Member

MINUTE 1/21/1/2020: PRELIMINARIES

The meeting was called to order by the Chairman at 11.00 Am and the quorum confirmed. The word of prayer was then said by Justus Odhoch.

MINUTE 2/21/1/2020: THE MEETING AGENDA

The agenda of the meeting was adopted as follows;

1. Preliminaries

2. Consider projects proposal for the FY 2019-2020

3. Consider ongoing projects

4. Consider any other business

MINUTE 3/21/1/2020: REVIEW OF THE WARD REPORTS

The committee reviewed the wards submissions from the meetings held on 15th October to 17th October 2019 vide the summary report of 18th October 2019. The submissions of other stakeholders like security and sub county educational office were also reviewed. The committee noted with satisfaction that all the five wards were covered during the meetings. The summary report took into account equity and past allocations in the respective wards.

MINUTE 4/21/1/2020: APPROVED BUDGET PROPOSAL FY 2019-2020

The committee after reviewing the ward proposals and the reports recommended the following projects for submission to the board vide the report of 18th October 2019. The constituency has been allocated Kshs 137,367,724.14 by the national board in the current financial year 2019-2020.

The committee also took into account the differences in projects cost in different parts of the constituency. The cost of foundation slabs in the hilly areas costs less by KShs 300,000 bringing about different prices for classrooms and other structures

| S/N | PROJECT |  | PROJECT ACTIVITY | Original cost estimate | Cumulative Allocation | Amount Allocated 2019/2020 (Kshs) | STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | OFFICE ADMINISTRATION |  |  |  |  |  |  |
|  | Employees’ salaries, | Payments of staff salaries & gratuity. |  |  | 0 | 3,200,000.00 | on going |
|  | Goods and services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea |  | 1,988,036.45 | 0 | 1,988,036.45 | on going |
|  | NSSF | Payment of NSSF deductions |  | 48,000.00 | 0 | 48,000.00 | on going |
|  | NHIF | Payment of NHIF deductions. |  | 30,000.00 | 0 | 30,000.00 | on going |
|  | Committee expenses | Payment to committee sitting allowances, transport, conferences |  | 2,976,000.00 | 0 | 2,976,000.00 | on going |
| 2 | MONITORING AND EVALUATION |  |  |  |  |  |  |
|  | Goods and services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea |  | 1,000,000.00 | 0 | 1,000,000.00 | on going |
|  | Committee expenses | Payment of committee field allowances, transport & conferences. |  | 1,621,031.72 | 0 | 1,621,031.72 | on going |
|  | CDFC/PMC Capacity Building | Facilitate training and capacity building of the NGCDFC,PMCs and staff |  | 1,500,000.00 | 0 | 1,500,000.00 | on going |
| 3 | EMERGENCY RESERVE |  |  |  |  |  |  |
| 1 | Emergency reserve | Emergency reserve to meet any unforeseen occurrences |  | 7,198,241.38 | 0 | 7,198,241.38 | New |
|  | SPORTS ACTIVITIES |  |  |  |  |  |  |
| 1 | Sports activities | Facilitate organizing of soccer tournament( Purchase balls, uniforms and support logistics during the events) |  | 2,747,354.48 | 0 | 2,747,354.48 | New |
|  | BURSARY AND SOCIAL SECURITY |  |  |  |  |  |  |
| 1 | Bursary Secondary schools | Pay fees for needy students in secondary schools |  | 16,000,000 | 0 | 16,000,000.00 | on going |
| 2 | Bursary Special schools | Pay fees for needy student in special schools |  | 1,000,000.00 | 0 | 1,000,000.00 | on going |
| 3 | Bursary Tertiary colleges and universities | Pay fees for needy students in tertiary institutions ( colleges and Universities) |  | 25,000,000.00 | 0 | 25,000,000.00 | on going |
|  | ENVIRONMENT |  |  |  |  |  |  |
| 1 | Abwao Primary School | Site prep.,purchase and plant 900 seedlings& nurse for 3 months |  | 100,000 | 0 | 100,000.00 | New |
| 2 | Burkamwana Pry School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 3 | Cherwa Secondary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 4 | Kachan Primary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 5 | Sigoti Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 6 | Kibwon Primary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 7 | Kowire Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 8 | Lisana Secondary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 9 | Lwanda Secondary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 10 | Obuginam Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 11 | Obuora Primary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 12 | Oriang Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 13 | Othith Primary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 14 | Thurdibuoro Sec School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 15 | Thurgem Secondary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 16 | Kandaria Mixed Sec School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 17 | Wasare Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 18 | Bwaja Primary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 19 | Kanyateng Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 20 | Kabondo Secondary School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 21 | Nyabondo Mixed Pry Sch | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 22 | Keyo Nyadundo Pry School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 23 | Nyamarimba Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 24 | Andingo Bware Pry School | Site prep.,purchase and plant 800 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 25 | Nyongonga Sec School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 26 | ApondoKasaye Sec School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 27 | Nyadero Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 28 | Konditi Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 83,156.95 | 0 | 83,156.95 | New |
| 29 | Onyuongo RC Primary Sch | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 100,000.00 | 0 | 100,000.00 | New |
| 30 | Ragen MH Primary School | Site prep.,purchase and plant 900 seedlings & nurse for 3 months |  | 83,157.18 | 0 | 83,157.18 | New |
|  | PRIMARY SCHOOLS |  |  | Original cost estimate | Cumulative Allocation | Amount Allocated 2019/2020 (Kshs) |  |
| 1 | Akado Primary school | Completion of one classrooms (plastering, fittings and painting) The project had been allocated Kshs 400,000 in 2015/16 fy |  | 900,000 | 400,000 | 500,000.00 | on going |
| 2 | Aponde Primary school | Completion of 2 classrooms (plastering, fittings and painting) The project had been allocated Kshs 500,000 |  | 1,200,000 | 500,000 | 700,000.00 | on going |
| 3 | Apondo Kasaye Primary school | Renovation of 3 classrooms (Plastering & painting ) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 4 | Asawo Primary School | Completion three classrooms (Plastering and painting) |  | 2,500,000 | 2,000,000 | 500,000.00 | on going |
| 5 | Bala Primary school | Renovation of two classrooms (Fittings, Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 6 | Bodi Primary School | Renovation of five classrooms (Roofing) |  | 800,000 | 0 | 800,000.00 | Renovation |
| 7 | Bugo Primay school | Fencing of school compound one acre using concrete poles and chain link and erecting of gate |  | 500,000 | 0 | 500,000.00 | New |
| 8 | Cherwa Primary school | Completion of one classrooms (plastering, fittings and painting) Had been given 400,000 |  | 900,000 | 400,000 | 500,000.00 | on going |
| 9 | Holo Primary school | Renovation of two classrooms. (Roofing) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 10 | Kabuya Primary school | Renovation of three classrooms (Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 11 | Kagwel Primary school | Renovation of four classrooms (Plastering and painting) |  | 700,000 | 0 | 700,000.00 | Renovation |
| 12 | Kananda Primary school | Renovation of three classrooms (Plastering and painting) |  | 600,000 | 0 | 600,000.00 | Renovation |
| 13 | Kawili Primary school | Renovation of three classrooms (Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 14 | Keyo Nyadundo Primary school | Plastering and fitting of school administration block comprising of Three offices and staff room |  |  |  | 700,000.00 | on going |
| 15 | Kobong'o Primary school | Completion of office block comprising of two offices and staffroom (Flooring and painting) had been given Kshs 900,000 |  | 1,400,000 | 900,000 | 500,000.00 | on going |
| 16 | Kokungu Primary School | Completion of one classroom (Roofing,fittings, plastering and painting) had been given shs. 400,000 |  | 900,000 | 400,000 | 500,000.00 | on going |
| 17 | Kosogo Primary school | Completion (Flooring and fitting of two classrooms )had been given Kshs.1.2m |  | 1,700,000 | 1,200,000 | 500,000.00 | on going |
| 18 | Kowire Primary School | Completion (Plastering and fittings of 1 classroom) had been given 500,000 |  | 1,000,000 | 500,000 | 500,000.00 | on going |
| 19 | Mbugra Primary school | Renovation of three classrooms (fittings, plastering and painting) |  | 600,000 | 0 | 600,000.00 | Renovation |
| 20 | Ndori RC Primary School | Completion (Roofing of 3 classrooms) had been given shs 1,000,000 |  |  |  | 500,000.00 | on going |
| 21 | Ng'ope Primary school | Completion of one classroom( fix lintel, plaster and fix fittings) had been given kshs 500,000 |  | 1,000,000 | 500,000 | 500,000.00 | on going |
| 22 | Nyabondo Boys Boarding Pri school | completion of 60 bed dormitory( fix lintel and roof) |  | 700,000.00 |  | 700,000.00 | on going |
| 23 | Nyabondo Day Primary school | Renovation of four classrooms (Roofing) |  | 500,000.00 |  | 500,000.00 | Renovation |
| 24 | Nyabondo Mixed Primary School | Renovation of 8 classrooms(cast new floors slabs) |  | 900,000.00 |  | 900,000.00 | Renovation |
| 25 | Nyamarumbe Primary school | Plastering and flooring of 3 classrooms |  | 500,000.00 |  | 500,000.00 | Renovation |
| 26 | Nyalunya Primary school | Flooring and fitting of two classrooms |  | 900,000.00 |  | 900,000.00 | New |
| 27 | Nyawalo Primary school | Completion of one classroom (Roofing, fittings and painting) |  | 1,000,000 | 400,000 | 600,000.00 | on going |
| 28 | Nyong'ong'a Primary school | Completion of hall (Fitting, plastering & painting) |  |  |  | 500,000.00 | on going |
| 29 | Obange Primary school | Renovation of two classrooms (Plastering, Fittings and painting) |  | 600,000 | 0 | 600,000.00 | Renovation |
| 30 | Obuora Primary school | Completion of two classrooms (Roofing and fittings) |  | 1,700,000 | 1,200,000 | 500,000.00 | on going |
| 31 | Olembo Primary school | Completion of two classrooms (Roofing, Plastering, fittings and painting) |  | 1,900,000 | 1,000,000 | 900,000.00 | on going |
| 32 | Onwang'o Primary school | Fencing of one acre school compound and fix gate |  | 500,000 | 0 | 500,000.00 | New |
| 33 | Otho Abwao Primary school | Completion of one classroom, (Plastering, fitting and painting) |  | 1,000,000 | 500,000 | 500,000.00 | on going |
| 34 | Pap Lisana Primary school | Renovation of two classrooms (Plastering, Fittings and painting |  | 500,000 | 0 | 500,000.00 | Renovation |
| 35 | Pundo Primary school | Renovation of three classrooms (Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 36 | Rae Mixed primary School | Renovation of three classrooms (Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 37 | Ragen AIC Primary school | Renovation of three classrooms (Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 38 | Rakwaro Primary school | Renovation of three classrooms (Plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 39 | Ramula Odowa Primary school | Construction of two new classrooms to roof level |  | 2,000,000 | 0 | 1,500,000.00 | New |
| 40 | Rarieda Kokech Primary Sch | Renovation of three classrooms (plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 41 | Sangoro Primary School | Renovation of four classrooms (plastering and painting) |  | 700,000 | 0 | 700,000.00 | Renovation |
| 42 | Soko Primary school | Renovation of three classrooms (plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 43 | St. Aloys Primary school | Completion of two classrooms (Plastering, Fittings and painting) |  |  |  | 600,000.00 | On going |
| 44 | Thurgem Primary school | Completion of three classrooms (Plastering, Fittings and painting) |  |  |  | 700,000.00 | on going |
| 45 | Tulu Primary school | Renovation of three classrooms (plastering and painting) |  | 500,000 | 0 | 500,000.00 | Renovation |
| 46 | Wasare Primary school | Completion of one classroom (Roofing, fittings, plastering and painting) |  | 1,000,000 | 500,000 | 500,000.00 | on going |
| 47 | Nyakach Sub County DEOs office | Renovation of DEOs office comprising of six offices and boardroom (plastering and painting) |  | 900,000 | 900,000 | 900,000.00 | New |
|  | Purchase 2,500 Schools Desks |  |  |  |  |  |  |
| 1 | Kodum Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 2 | Nyaksure Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 3 | Kusa Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 4 | Obugi Nam Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 5 | Pedo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 6 | Onyinge Nazarene primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 7 | Burkamwana Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 8 | Nyabola Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 9 | Konditi Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 10 | Wasare Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 11 | Pap Lisana Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 12 | Kanyateng Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 13 | Kagwel Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 14 | Nduga Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 15 | Urudi Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 16 | Kanyalwal Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 17 | Miruka Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 18 | Rae Mixed Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 19 | Kowire Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 20 | Magunga Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 21 | Ngomo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 22 | Obingo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 23 | Got Onyuongo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 24 | Obuon Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 25 | Michura Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 26 | Sigoti Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 27 | Lwanda Secondary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 28 | Guu Secondary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 29 | Holo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 30 | Ongielore Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 31 | Kabondo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 32 | Odhong Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 33 | Ochol Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 34 | Kananda Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 35 | Kabete Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 36 | Miriu Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 37 | Obuora Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 38 | Apoko Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 39 | Gulmaembe Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 40 | Burkamach Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 41 | Onego Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 42 | Sangoro Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 43 | Apondo Kasaye Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 44 | Ombugo Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 45 | Kobong’o primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 46 | Abwao Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 47 | Mbugra Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 48 | Oriang Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 49 | Nyamanyinga Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
| 50 | Obange Primary School | Purchase of 50 desks @3,200 |  | 160,000.00 | 0 | 160,000.00 | New |
|  | SECONDARY SCHOOLS |  |  |  |  |  |  |
| 1 | Anding'o Opanga Sec school | Completion of Office block comprising of three offices and staff room(Plastering and painting) had been given Kshs 1,172,413.73 |  | 1,772,413.73 | 1,172,413.73 | 600,000.00 | on going |
| 2 | Dirubi Secondary school | Completion of two classrooms (roofing, fittings and plastering) had been given Kshs 800,000 estimated cost is Kshs 1.8m |  | 1,800,000.00 | 800,000 | 1,000,000.00 | on going |
| 3 | Holo secondary school | Cast new floor slab and paint three classrooms |  | 700,000.00 |  | 700,000.00 | Renovation |
| 4 | Kandaria Secondary school | Completion of Storey administration block comprising of five offices and staff room ( walling and casting of suspended slab) had been given Kshs 1.2m. The project is co-funded with the school community. The estimated cost is Kshs 4.5m |  | 2,000,000 | 1,200,000 | 800,000.00 | on going |
| 5 | Lisana Secondary school | Completion of one science Laboratory ( Plastering, Fitting and painting) |  | 1,500,000.00 |  | 1,500,000.00 | on going |
| 6 | Miriu Secondary school | Completion of one classroom (Roofing, fittings, plastering and painting) |  | 1,000,000.00 | 500,000 | 500,000.00 | on going |
| 7 | Moro secondary school | Purchase of 51 seater school bus |  | 7,500,000.00 | 0 | 7,500,000.00 | New |
| 8 | Ndori BC Secondary school | Flooring and painting of laboratory |  | 500,000.00 | 0 | 500,000.00 | on going |
| 9 | Oremo Secondary school | Completion of single science laboratory (plastering, fittings and painting) |  | 500,000.00 |  | 500,000.00 | on going |
| 10 | Sango Buru Secondary school | Purchase of 51 seater school bus |  | 7,500,000.00 | 0 | 7,500,000.00 | New |
|  | SECURITY PROJECTS |  |  |  |  |  |  |
| 1 | Kapsorok police post | Construction of police staff houses to completion. Six units single rooms |  | 3,000,000.00 | 0 | 3,000,000.00 | New |
| 2 | Ngege police post | Purchase one acre land for construction of police post. The estimated cost is Kshs 750,000 |  | 750,000.00 | 0 | 750,000.00 | New |
| 3 | Ngege police post | Complete construction of office block comprising of ten offices, cell and armory and connect to electricity mains (Completion, Kshs1, 500,000; electricity connection, kshs 300,000). Estimated cost is Kshs 6.3m. had been given Kshs 4.5m |  | 6,300,000 | 4,500,000 | 1,800,000.00 | On going |
| 4 | Ngege police post | Construction of police staff houses. Six units single rooms |  | 2,250,000.00 | 0 | 2,250,000.00 | New |
| 5 | Ngege police post | Construct complete 4 door pit latrines |  | 550,000.00 | 0 | 550,000.00 | New |
| 6 | Pap Onditi Police Station | Construction to completion of Administration Police 4 door pit latrines |  | 500,000.00 | 0 | 500,000.00 | New |
| 7 | Tol Police Post | Fencing of one acre plot using concrete poles & chain link |  | 600,000.00 | 0 | 600,000.00 | New |
| 8 | Tol Police Post | Connect police post to electricity mains and internal installations in office block |  | 150,000.00 |  | 150,000.00 | New |
| 9 | Thurdibuoro Chiefs Office | Walling and roofing of Chiefs office |  | 1,261,705.63 |  | 1,261,705.63 | On going |
|  | CONSTITUENCY MOTOR VEHILCE |  |  |  |  |  |  |
| 1 | Constituency office motor vehicle |  | Additional allocation for the Purchase of constituency office motor vehicle NG-CDFC to initiate the process of disposal of old vehicle/ the vehicle was allocated Kshs.4,589,655.17 in 2017/18 f/y | 6,839,655 | 4,589,655 | 2,250,000.00 | ongoing |
|  | GRAND TOTAL |  |  |  |  | 137,367,724.14 |  |

MIN 5/21/03/2020: ON GOING PROJECTS

The committee members having considered most ongoing projects in financial year 2019/ 2020 unanimously agreed that the following list of projects is to be completed in the Financial Year 2020/ 2021;

| S/NO | PROJECT NAME | APPROVED PROJECT ACTIVITY | BALANCE TO COMPLETION |
| --- | --- | --- | --- |
| 1 | Nyabondo day mixed primary school | Construction of 2 classrooms | 1,000,000 |
| 2 | Andigo olasi primary school | Construction of 1 new classrooms | 500,000 |
| 3 | Apoko secondary school | Construction of 1 classroom | 300,000 |
| 4 | Bishop Okumu Secondary school | Flooring, plastering and fitting of tuition block | 1,400,000 |
| 5 | Burkamach Primary School | Construction of 3 classrooms | 2,500,000 |
| 6 | Cherwa Secondary school | Construction of Laboratory | 1,200,000 |
| 7 | Gulmawembe Primary School | Roofing and Plastering of 2 Classrooms | 1,100,000 |
| 8 | Guu Primary School | Plastering and Fitting of 2 Classrooms | 500,000 |
| 9 | Kabondo Boys Secondary Schol | Construction of Dormitory | 1,700,000 |
| 10 | Kandaria Mixed Secondary School | Construction of a storey Administration Block | 2,200,000 |
| 11 | Konditi Primary school | Construction of 1 classroom | 500,000 |
| 12 | Kusa Primary School | Construction of 1 classroom | 600,000 |
| 13 | Magunga Primary School | Construction of 1 classroom | 500,000 |
| 14 | Mbora Secondary School | Construction of a Science Laboratory | 2,200,000 |
| 15 | Mbugra Secondary School | Construction of Administration Block | 1,700,000 |
| 16 | Michura Primary School | Construction of 1 classroom | 500,000 |
| 17 | Miruka Primary School | Construction of 1 classroom | 400,000 |
| 18 | Nyabondo Girls Boarding | Construction of 1 classroom | 500,000 |
| 19 | Nyaksure Primary School | Construction of 2 classroom | 1,500,000 |
| 20 | Nyamanyinga Primary School | Plastering and Fitting of 2 Classrooms | 1,500,000 |
| 21 | Ochwado Primary School | Roofing and Plastering of 1 Classroom | 1,450,000 |
| 22 | Oriang Primary Schol | Construction of 1 classroom | 600,000 |
| 23 | Sigoti Girls Complex | Construction of Dormitory | 1,600,000 |
| 24 | St.Martins Special School | Construction of 1 classroom | 500,000 |
| 25 | St.Patrick Obange Secondary School | Construction of Administration Block | 2,200,000 |
|  | TOTAL |  | 28,650,000 |

MINUTE 6/21/1/2020: CONSIDER ANY OTHER BUSINESS

There being no other business the meeting ended at 1.30PM with a word of prayer by Leah Aringo.