NATIONAL GOVERNMENT CONSTITUENCIES DEVELOPMENT FUND

BOARD SECRETARIAT

PROGRAMMES COMMITTEE PAPER NO.002/2022

PROJECT PROPOSALS FOR 2021/2022 FINANCIAL YEAR, REQUESTS FOR REALLOCATIONS, RESUBMISSIONS, FIELD VISIT REPORTS AND DISPOSAL OF UNSERVICEABLE CONSTITUENCY VEHICLES

10TH MARCH 2022

Introduction

The Committee on Programmes, Performance and Risk Management held its meeting held on 10th March, 2022 and deliberated on the following;

- Resubmission of the Chuka Igamba Ngo’mbe Project Proposals for 2021/2022 financial year

The PPRM Committee in a meeting held on 24th November 2021 deliberated on the Chuka Igamba Ngombe Project Proposal and recommended that all proposed projects pend approval apart from Bursary, Emergency and Administration subject to the NG-CDFC submitting a detailed report on ongoing projects, allocating adequate funds to some proposed projects among other issues.

The NG-CDFC addressed the issues raised by the Committee thereby necessitating a review of the Project Proposal. Management reviewed the proposal and found it to be in compliance with the PPRM Committee’s recommendations, the Act and other guidelines.

Further, Management carried out verification exercise to the Constituency with the aim of ascertaining whether proposed allocations to some projects such as classrooms were adequate.

Management established that most schools were able to construct a classroom at Kshs.500,000 based on previous allocations using labour-based contracts. However, during consultative discussion with officials of the Ministry of Public Works, the Procurement Officer and the National Sub County Accountant it was established that;

- There was minimal supervision of the projects by the Public Works due to inadequate funding thus lack of facilitation for the Sub County Works Officer during supervision of the projects. The Sub County Works officer confirmed that they issue BoQs for the classrooms and other projects based on the amount allocated but normally does not include all the requirements such as electrical installations, ceiling, tiled/terrazzo floors. The Public Works officials confirmed that construction of a standard classroom requires a minimum of Kshs.900,000 and should be implemented through full contract for ease of supervision and accountability.

- The Project Management Committees do not involve the procurement officers during procurement of works rather they carry out procurement of fundi’s and materials on there own which is in contravention of the procurement Act.

The NG-CDFC was therefore advised to engage the technical officers with a view to ensuring allocations to projects are realistic and that the same are implemented in accordance with provisions of the NG-CDF Act, Procurement Act among others. In 2021/2022 Financial Year, the NG-CDFC improved its allocation to classrooms from Kshs.500,000 to Kshs.700,000

See Committee recommendations in Annex I

- Requests for reallocation of funds

The Committee deliberated on requests for reallocations from seventy-nine (79) constituencies and resolved as detailed in Annex II

- Resubmissions for 2010/11, 2011/12, 2016/17, 2017/18, 2018/19, 2019/20, 2020/21 and 2021/2022 Financial Years

The Committee deliberated on forty-three (43) resubmissions and resolved as detailed in Annex III

4.0 Reports on project monitoring in Eldama Ravine, Wajir East and Suba North Constituencies.

The Committee deliberated on projects’ monitoring reports from the Eldama Ravine, Wajir East and Suba North Constituencies; See details in Annex IV

5.0 Requests for disposal of unserviceable Constituency’s vehicles

The Committee deliberated on one request from Mosop Constituency for disposal of unserviceable motor vehicle and resolved as detailed in detailed in Annex V

5.0 Other pertinent matters

- Request for purchase of land by Lunga Lunga Constituency

In the 2018/19 financial year, Lunga Lunga NG-CDF allocated Kshs.5,000,000 for purchase of 5 acres land for Juma Boy Secondary School. The project was conditionally approved subject to the NG-CDFC submitting Land Valuation Report from a Government Land Valuer.

The NG-CDFC submitted 1st valuation report Ref. No. KWL/VAL/19/12 dated 11th November, 2019 from the Directorate of lands, Kwale under the land valuer Agnes K. Ndambu for two plots: KWALE/VANGA/555 & 556 amounting to Kshs.2,000,000. The approximate area for plot 555 was 0.95 Ha and 556 was 0.76 Ha totalling to 1.71 Ha. The properties were inspected on 5th November, 2019. The NG-CDFC was therefore advised to allocate the balance of Kshs.3,000,000 to other projects

Later, the NG-CDFC submitted a new valuation report Ref. No. KWL/VAL.19/12-2 dated 10th January, 2020 for the plots KWALE/VANGA/555.556 and 566(part) amounting to Kshs.4,500,000. The approximate area for plot 555 was indicated as 0.95 Ha, plot 556 was indicated as 0.76 acres and plot 566(part) was indicated as 0.32 acres totalling to 2.03 Ha. The second valuation report was also done by the land valuer Agnes K. Ndambu.  The properties were inspected on 5th November, 2019. Based on the foregoing, management informed the NG-CDFC of the inconsistencies in the valuation reports. The NG-CDFC committed to take up the matter with the valuer for clarification.

In response, the valuer Agnes K. Ndambu wrote a letter Ref. No. KWAL/VAL/22/02 dated 10th February, 2022 indicating that they acted upon the instructions of the Fund Account Manager, NG-CDF Lunga Lunga vide a letter dated 18th January, 2022 and they therefore returned the Open Market Value for purposes of purchase to Kshs.3,500,000. No details of the valued land were provided.

Committee’s Recommendations

The Board to engage an independent valuer from the Ministry of lands (HQs) to independently consider the matter and issue a fresh valuation report to enable the Board make an informed decision.

- Request for authority to utilize funds realized through Appropriation in Aid (AIA) in Endebess Constituency

Section 4(1) (b) of the NG-CDF Act, 2015 as amended in 2016 states that that the National Government Constituencies Development Fund shall comprise of any monies accruing to or received by the Board from any other source.

Further, Section 4(2) provides that all monies allocated under this Act shall be considered as funds allocated to constituencies pursuant to Article 206 (2) (c) of the Constitution to be administered in accordance with the provisions of this Act.

In line with the above provisions, Endebess NG-CDF Committee informed the Board that it had received a grant amounting to Kshs.539,000 from the Embassy of China after the committee made a proposal to the embassy for a support to enable them purchase 52 desktop computers for constituency innovation hub.

The NG-CDF Committee has since declared receipt of the funds to the Board pursuant to the provisions of Section 12 (9) of the Act which states that “any accruing revenues, interest and liabilities from any constituency account shall be declared to the Board together with the annual returns”. The funds were received via cheque number 002077 drawn by the Embassy of the Republic of China.

The Committee has also deposited the cheque into their bank account in line with the provisions of Paragraph 28 (1) of the NG-CDF Regulations 2016 which states that “any accruing revenues, interest and liabilities from any Constituency account realized pursuant to section 12(9) of the Act, shall be declared and deposited in the Constituency bank account.”.

The NG-CDFC is therefore requesting for Board’s approval to use the funds towards the following project: -

Endebess Constituency Innovation Hub, Kshs.539,000- Purchase of 7 desktop computers

Committee’s Recommendations

Recommended for approval upon confirmation of the availability of the funds by the Finance Department and fulfilment of all the financial procedures guiding declaration of AIA.

Annex I

Project Proposals for 2020/2021 financial year

| No. | Constituency name | Allocation (Kshs.) | Compliance to NG-CDF Act and other guidelines | Committee’s Recommendations |
| --- | --- | --- | --- | --- |
|  | Chuka Igambang’ombe | 137,088,879 | All proposed projects complied apart from the following | All proposed projects recommended for approval apart from the following; |
|  |  |  | NG-CDF Office motor vehicle, Kshs.7,260,000- Purchase of office motor vehicle | Pending approval NG-CDFC to initiate the process of disposal of the old constituency vehicle and specify the make of the vehicle to be purchased. NG-CDFC to provide specifications for the proposed motor vehicle |

Annex II

REQUESTS FOR REALLOCATION OF FUNDS

| S/NO | Constituency | CDFC Minutes No/Date | Initial Approved Projects (Where funds are reallocated from) | F/Y | Amount requested for Re-allocation (Kshs.) | Re-allocation Projects and amount | Reasons for reallocation | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Kisumu West | Min 115 of 20/9/2021 | Ogada Primary School- Renovation of Six classrooms ( reroofing, floor terrazzo, wall repairs, painting and decorations and introduction of verandah | 2020/21 | 3,480,000 | Ogada Primary School Kshs.3,480,000- Construction to completion of three classrooms | The classrooms that were to be renovated had poor workmanship hence the project manager advised for construction of new ones | Recommended for approval In 2021/22 financial year the classrooms were allocated additional Kshs.200,000 for completion |
|  |  | Min 116 of 20/9/2021 | Emergency | 2020/21 | 4,708,958 | - South West Chief’s office/Kanyawegi Assistant Chief’s office Kshs.3,458,958- Construction to completion of chief/assistant chief’s office - East Karateng’ Assistant Chief office Kshs.500,000-Construction to completion of a 4 door pit latrine with a urinal to completion with one unit fledged with an access ramp, handrails and a toilet seat for PWD - Huma Girls Secondary School Kshs.500,000-Additional funds for completion of Bio gas/ water reticulation system; Plumbing works at the laundry area (The project has so far received Kshs.3,220,483.5) - Mkendwa Primary School Kshs.250,000- Renovation of administration block and 1 classroom: reroofing of classroom, floor works by fixing terrazzo, glazing and painting of administration block | Unspent balance | Recommended for approval |
|  | Rangwe | Min 004 of 6/12/2021 | Nyopuge Primary School- Construction to completion of 2 classrooms | 2021/22 | 2,000,000 | Nyopuge Secondary School Kshs.2,000,000-Construction to completion of 2 classrooms | The project’s name was erroneously captured as Nyopuge Pry during submission of the project’s proposal | Pending approval NG-CDFC to submit 1st 3rd & 4th schedules |
|  |  |  | Yogo Primary School- Construction to completion of 2 classrooms |  | 2,000,000 | Yogo Primary School Kshs.2,000,000- Renovation of 4 classrooms; | The school has enough number of classrooms | Pending approval NG-CDFC to specify renovation activities and confirm whether project will be done to completion |
|  | Suba North | Min 450 of 25/1/2022 | NG-CDF motor boat- Purchase of fully fitted office motor boat: 4 stroke petrol outboard motors with a boat length of between 5.8m to 6.2m, beam 2.3cm to 5m, draft of 0.2m, hull depth of 1.0m, freeboard of 0.8m, weight of 800kg +/-20kg | 2020/21 | 9,000,000 | - Bursary Secondary Schools Kshs.8,800,000- Payment of bursary to needy students | High cost of the project which the Committee cannot meet at this time. There is also high demand for bursary due to to the ravaging effects of covid 19 pandemic to many livelihoods | Recommended for approval The additional allocation to bursary will not exceed the set limit of 35% allocation per financial year |
|  |  |  |  |  |  | - Wanyama Secondary School Kshs.200,000- Completion of 4 door pit latrine: plastering, painting, branding and publicity sign post |  | Pending approval NG-CDFC to request for change of activity from construction of 6 door pit latrine to 4 doors pit latrine and provide the contract sum NG-CDFC to ensure that one chamber is provided to cater for Persons with Disability In 2020/21 the school was allocated Kshs.400,000 for construction of 6 door pit latrine to completion |
|  |  |  | Constituency innovation hubs | 2017/18 | 2,338,513.60 | - Usao Primary School Kshs.1,000,000- Fencing of 1,200 metres perimeter school compound using angle bar and chain link - Usungu Primary School Kshs.600,513.60- Renovation of 2 classrooms: reroofing, plastering, painting, floor works, branding and publicity sign post - Bursary Secondary Schools Kshs.738,000- Payment of bursary to needy students | There is no building for hosting the hubs | Recommended for approval The additional allocation to bursary will not exceed the set limit of 35% allocation per financial year |
|  | Embakasi East | Min 02 of 15/2/2022 | Bursary secondary schools | 2021/22 | 1,333,968 | Bursary Tertiary Institutions Kshs.1,333,968- Payment of bursary to needy students in universities and colleges | There is high number of applicants in tertiary institutions thus the need for more funds | Recommended for approval |
|  | Rongo | Min 6 of 20/12/2021 | St Jonathan Secondary School - Renovation of 4 Classrooms to Completion; Floor Screed, Roof Patching, Glazing, Plastering and Rendering, Filling Gables, Fixing Fascia Board, Painting and Decoration | 2021/22 | 1,000,000 | St Jonathan Primary School Kshs.1,000,000- Completion of 4 Classrooms started by the community: | The project was erroneously capture as St. Jonathan Secondary School instead of St. Jonathan Primary School | Recommended for approval |
|  |  |  | St Patricks Kamgundho Mixed Secondary School -Drilling and Equipping of Borehole Drilling Work done to completion | 2021/22 | 2,600,000 | Kamondi Primary Kshs.2,600,000- Drilling and Equipping of Borehole; drilling work to be done to completion | A similar project has been implemented by the Migori county Government and will serve the same community | Recommended for approval |
|  |  |  | Banda Mixed Secondary School- Drilling of borehole and equipping to completion | 2020/21 | 4,380,000 | Banda Primary School Kshs.4,380,000- Drilling of borehole and equipping to completion | Banda Primary School and Banda Mixed Secondary School are neighboring schools. Geological survey report indicates that water can only be found in Banda Primary School | Recommended for approval |
|  | Starehe | Min 7 of 8/10/2019 | Sports- Carry out Constituency Sports Tournament and the winning teams/schools to be awarded with trophies, balls, and games Kits equipment. | 2018/19 | 2,180,817 | Mariakani Primary School Kshs.2,180,817- Leveling of school ground; removal of black cotton soil, refilling with red soil and planting of grass in the school field (120 by 120 metres) | Unspent balances | Recommended for approval |
|  |  | Min 4 of 8/10/2021 | - Islamia Primary School- Purchase of 150 Lockers and chairs (Kshs.600,000) Renovation of 9 no. classrooms (glazing of windows, change of doors, repair of walls and floor screeding) Kshs.2,640,758.00 - Emergency | 2020/21 | 3,240,758 7,192,206.90 | River Bank Secondary School Kshs.10,432,964.90- Construction of 10 door ablution block with 2 chambers catering for persons with disability (Kshs.5,102,814.90), renovation of 8 classrooms; reroofing, glazing of windows, external and internal finishes (Kshs.2,650,450), conversion of a hall to a laboratory: reroofing, galzing of doors, windows, external and internal finishes, tiling of floors, installation of laboratory worktops and mechanical works-sinks and plumbing (Kshs.2,679,700) | - The school got a donor to complete the works - Unspent balance | Pending approval NG-CDFC to submit evidence that the works at Islamia Primary School were done by a donor and also confirm whether the funds are adequate to complete the proposed projects at River Bank Secondary School |
|  |  | Min 5 of 25/2/2022 | NHIF Social Security Programe- To cater for health insurance cover for 300 vulnerable people | 2020/21 | 1,800,000 | Bursary Secondary Schools Kshs.1,800,000- Payment of bursary to needy students | There are increased cases of needy persons that require bursary assistance. | Recommended for approval |
|  |  |  | NHIF social security programe- To cater for health insurance cover for 600 vulnearable people each at kshs.6,000 | 2021/22 | 3,600,000 | Bursary Secondary Schools Kshs.3,600,000- Payment of bursary to needy students |  |  |
|  |  | Min 8 of 10/1/2022 | Emergency | 2018/19 | 5,738,993.45 | Dr. Agrrey Pry Sch Kshs.5,738,993.45- Additional funds for renovation of 5 classrooms and a hall; removal of asbestos and reroofing (Kshs.1,795,256), renovation of 10 classrooms and a 600 students capacity school hall; removal of asbestos, disposal and reroofing, floor screeding, repair of walls and painting | Unspent funds | Pending approval NG-CDFC to submit contract documents The project had received Kshs.2,000,000 for the ongoing renovation works |
|  | Ruaraka | Min No.4 of 27/1/2022 | - Ngomongo Police Staff Houses- Additional funds for the construction of six units (one bedroom each unit) of police houses - Drive-Inn Primary School- Additional fund for the completion of the hall - Daniel Comboni Primary School- Purchase and supply of 100 school Wooden Metal Lockers and chairs @ Ksh. 6,000.00 per set - Mathare North Primary School - Additional funds for construction of a perimeter wall 400 meters around the school - Strategic plan | 2017/18 2018/19 2020/21 2018/19 2017/18 | 424,138 2,895,791 2,500 636,885 181,034 | - Mathare North Primary School, Kshs.3,322,429- Renovation of 4 classrooms; tiling of the floor, plastering, replacement of steel windows and doors, glazing, replacement of roofing and ceilings, painting internally and externally and electrical works). - Baba Dogo Secondary School, Kshs.817,919- Additional funds for proposed construction of a ramp from ground to 2nd floor; clearing the area, removing cotton soil, excavation of trenches, walling and slabbing (project was allocated Kshs.2m in 2021/22 f/y) – | Unspent balances | Recommended for approval |
|  | Banissa | Min 3 of 3/02/2022 | Choroqo Primary School – Construction of Kitchen and store to completion | 2020/21 | 1,200,000 | Choroqo Primary School Kshs.1,200,000– Renovation to completion of 4 classrooms: repairing floor cracks, roofing works, replacing broken doors and windows, painting works and labeling | Change of activity by the school in consideration of deplorable condition of existing classes. | Recommended for approval |
|  |  |  | Chief Haji Mohamed Primary - Construction of Kitchen with Store to completion | 2021/22 | 1,200,000 | Chief Haji Mohamed Primary School Kshs.1,200,000 – Renovation to completion of 3 classrooms (Repairing floor cracks, roofing works, replacing broken doors and Windows, painting works and labeling) | Change of activity by the school in consideration of deplorable condition of existing classes. | Recommended for approval |
|  |  |  | Hullow Location Chiefs Office - Construction of 2 Room Office Block to Completion | 2021/22 | 1,200,000 | Banisa Mixed Secondary School Kshs.1,200,000 – Renovation to completion of 3 classrooms (Repairing floor cracks, roofing works, replacing broken doors and Windows, painting works and labeling) | Lack of ideal public land for construction of the chief’s office | Recommended for approval |
|  | Mandera West | Min 03 of 7/02/2022 | Kubdishan Primary School – Construction of One Classroom to completion Kshs.950,000 and 2 door pit latrine to completion Kshs.300,000 | 2020/21 | 1,250,000 | Kubdishan Primary School – Construction to completion of 30 M3 Underground Water Tank | The school has serious water challenges and pupils are forced to fetch water from the village | Recommended for approval |
|  |  |  | Takaba Girls Secondary School – Construction of 50 Students Capacity Computer Laboratory (Computer Hall, Office & Store) to completion | 2021/22 | 3,000,000 | Takaba Day Secondary – Renovation to completion of Science Laboratory (Kshs.1,400,000) and 4 number classrooms; Repairing floor cracks, roofing works, replacing broken doors and windows, painting works and labeling (Kshs.1,600,000) | Takaba Girls has enough classrooms and therefore converted one classroom as a Computer Laboratory and Takaba Day Secondary has classes and science laboratory in deplorable condition and therefore needs urgent attention | Not recommended for approval There was no indication that Takaba Girls Secondary School no longer required the funds NG-CDFC to implement the project as initially approved and allocate funds to the proposed project in 2022/2023 financial year |
|  |  |  | Dandu Primary - Construction of Two Number Classrooms to completion | 2021/22 | 1,900,000 | Takaba Boys Secondary - Renovation to completion of 5 classrooms (Repairing floor cracks, roofing works, replacing broken doors and Windows, painting works and labeling) | Mandera County Government has constructed classes at Dandu Primary and therefore the need has been alleviated | Pending approval NG-CDFC to provide verifiable evidence indicating that the County Government constructed classrooms in Dandu Primary School |
|  |  |  | Kubihalo Primary School - Construction of 30 M3 Underground Water Tank to completion | 2021/22 | 1,200,000 | Kubihalo Primary School - Renovation to completion of 5 classrooms: Repairing floor cracks, roofing works, replacing broken doors and windows, painting works and labeling | The school has challenges of Classes as most are in deplorable condition and unconducive for learning | Recommended for approval |
|  | Kwanza | Min 4 of 24/12/2021 | Milimani Primary school, Kshs.1,400,000-Renovation of four classrooms | 2020/2021 | 1,400,000 | Milimani Primary school, Kshs.1,400,000-Construction to completion of 2 new classrooms | Assessment and recommendations done by the public works Transport and Infrastructure shows that the colonial building was unworthy repairing since it was badly damaged. | Recommended for approval The project has so far received Kshs.200,000 |
|  |  |  | St. Monica Girls Secondary school, Kshs.1,600,000-Construction to completion of 2 classrooms | 2020/2021 | 1,600,000 | St. Monica Girls Secondary school, Kshs.1,600,000- construction of Storey tuition block of 8 classrooms-substructure works: trench excavation, strip foundation, hardcore and murram blinding. | Insufficient land and the increasing enrolment. | Recommended for approval The project was allocated Kshs.9m in 2021/22 financial year and the estimated cost was Kshs.15 million FAM confirmed that the design is inclusive of an access ramp |
|  | Kiminini | Min 3 of 15/2/2022 | Emergency | 2020/2021 | 1,400,000 | Misemwa Primary school, Kshs.1,400,000- Renovation of 3 classrooms: roofing, plastering, flooring, painting, fixing of doors and windows. | Unspent funds | Recommended for approval |
|  | Kesses | Min 94 of 21/9/2021 | Hill school Secondary, Kshs. 7,000,000-Purchase of 51seater school bus | 2019/2020 | 300,000 | Hill school Secondary, Kshs.300,000- Construction of school bus shed | Unspent balance upon bus purchase | Recommended for approval |
|  |  | Min 104 of 26/10/2021 | - Constituency sports tournament - Constituency sports tournament - Constituency sports tournament | 2017/2018 2018/19 2019/20 | 1,686,206 2,066,038 2,603,389 | - Rural Electrification under REREC matching fund program in three areas: Mugundoi A, kaptumo C and Budalangi at Kshs.5,000,000 | Unspent funds | Recommended for approval A letter from REREC Ref: REREC/CEO/T/18/EW dated 27th October, 2021 has been submitted indicating that REREC will match a similar contribution of Kshs.5m to make it Kshs.10m towards installation of electricity transformers/electrification under the matching programme |
|  |  |  |  |  |  | - Tulwet Primary school, Kshs.1,355,633-Drilling of a borehole |  | Pending approval NG-CDFC to submit certified cost estimates |
|  |  |  | Tulwopngetuny Primary school, Kshs.1,000,000-Renovation of 5 classrooms to completion; floor repair, plastering, fixing window panes and painting | 2020/2021 | 1,000,000 | Tulwopngetuny Primary school, Kshs.1,000,000-Renovation of 5 classrooms: re-roofing, fixing window panes, fascia board and painting to completion. | The school board of management has repaired the floor and walls | Recommended for approval |
|  | Turkana North | Min 4 of 16/1/2022 | Napetet Primary School-Construction of two classrooms to completion (Kshs.2,400,000), equipping with 30 desks at Kshs.150,000 and construction of two door pit latrine to completion at Kshs 350,000 with one door accessible to Persons With disability | 2021/2022 | 2,900,000 | Natete Primary School, Kshs.2,900,000-Construction of two classrooms to completion (Kshs.2,400,000), equipping with 30 desks at Kshs.150,000 and construction of two door pit latrine for male students to completion at Kshs.350,000 with one door accessible to Persons With disability | The name was erroneously captured as Napetet Pry Sch during submission of the projects proposal | Recommended for approval |
|  | Loima | Min 4 of 16/1/2022 | Kangalita Primary School- Construction of one classroom to completion | 2021/2022 | 1,300,000 | Kotaruk Primary School, Kshs.1,300,000 Construction of one classroom to completion | The projects amounts and activities were erroneously captured during the submission of the projects proposal | Recommended for approval |
|  |  |  | Kotaruk Primary School-Construction of two classrooms to completion |  | 2,300,000 | Kangalita Primary School, Kshs.2,300,000- Construction of 2 classrooms to completion |  |  |
|  | Kajiado Central | Min. 03 of 7/02/2022 | Ilmolelian Primary school- Purchase of 60 double decker beds. | 2019/20 | 500,000 | Ilmolelian Primary school, Kshs.500,000- Purchase of 30 metallic double decker beds at Kshs.480,000 and transportation at Kshs.20,000. | High market cost of the beds which is currently at Kshs.16,000 | Recommended for approval |
|  |  | Min No.3 of 23/12/2021 | - Kikelea Primary School- Construction of one classroom to completion. - Intinyika Primary School- Construction of one classroom to completion. - Naboisho Primary School- Construction of one classroom to completion. | 2021/22 | 1,100,000 1,100,000 1,100,000 | Bursary Secondary School, Kshs.3,300,000- Payment of bursary to needy students. | The specific schools had least pressure for classrooms. | Not recommended for approval The letters submitted by the schools revealed that they require the funds for the construction of the classrooms as had initially been proposed The request was discussed by the PPRMC in its meeting held on 18th January, 2022 but was pending approval subject to NG-CDFC submitting evidence that the primary schools had enough classrooms. The NG-CDFC submitted letters from the 3 schools indicating as follows: - Intinyika Primary School’s letter indicated that the school accepted the reallocation of funds to cater for bursary for needy students as per the NG-CDF’s request. They however requested the NG-CDFC to honour its promise to allocate back the funds in 2022/23 for construction of classrooms and also consider them for construction of teachers’ quarters. - Naboisho Primary School’s letter indicated that they had been requested to surrender their allocation of a classroom to allow for bursary and were further requesting the NG-CDFC to honor their agreement of allocating funds to the project in 2022/23 Financial Year - Kikelea Primary School’s letter indicated that they had received a request to allow for reallocation of funds with a promise that they will be allocated in the next financial year but had requested the NG-CDFC to honor their word. |
|  | Laikipia West | Min. 06 of 8/02/2022 | Munyaka Girls Secondary School- Construction of one classroom to completion. | 2020/21 | 1,150,000 | Munyaka Secondary School, Kshs.1,150,000- Construction to completion of one classroom. | Munyaka Girls Secondary School is a new school and has not yet been registered. Furthermore, one classroom would not sufficiently serve the purpose of a new boarding high school. | Recommended for approval |
|  | Gilgil | Min 412/2021 of 22/12/2021 | Mbombo Primary School- Renovation of two classrooms (Change of roof, ceiling, flooring with tiles, plastering, painting, vrc for veranda extension, doors and windows) to completion. | 2021/22 | 1,000,000 | Mbombo Primary School, Kshs.1,000,000- Construction to completion of one classroom. | Renovation of classrooms had been done by an NGO (Build Africa). | Recommended for approval The NG-CDFC has submitted minutes from the school confirming the change of activity |
|  |  |  | Mugaa Primary School - Tree planting | 2017/18 | 77,586.20 | Mugaa Primary School, Kshs.77,586.20- Construction of a school gate. | The school could not plant trees since it lacks a gate hence animals grazing around would destroy the trees once planted. | Recommended for approval The NG-CDFC has submitted minutes from the school confirming the change of activity |
|  |  | Min No.382 of 12/10/2021 | Gilgil NG-CDF Office- Purchase of a NG-CDF Vehicle (make - Land Cruiser toyota, 10-seater, short chassis) | 2020/21 | 8,000,000 | - Kanyawa Primary School, Kshs.500,000- Construction of 4 door pit latrine - Nyondia Chiefs Office, Kshs.300,000- Construction of 3 door pit latrines to completion - Shelter Police Post, Kshs.300,000- Construction of 3 door pit latrines to completion - Munanda Police Station, Kshs.800,000- Construction of 2 units staff house (foundation, walling and roofing) phase one - Kasambara Primary School, Kshs.2,800,000- Construction of two classrooms for PWDs; foundation, walling, roofing, plastering, painting, windows, window panes and doors, branding, electrical works, ceiling, tiles and external finishes at Kshs.2,200,000, construction of 4 door special pit latrine at Kshs.500,000 and purchase of 24 chairs and 6 tables at Kshs.100,000 to completion. - Muthaiti Secondary School, Kshs.1,200,000- Construction of one classroom; foundation, walling, roofing, plastering, painting, windows, window panes and doors, branding, electrical works, ceiling, tiles and external finishes at Kshs.1,100,000 and purchase of 20 lockers at Kshs.100,000 - Gilgil TTI, Kshs.2,100,000- Guttering of the TTI building with steel gutters at Kshs.1,800,000 and purchase of 3- 10,000 litres water tanks at Kshs.300,000 | The purchase of the vehicle is not urgent at the time. | Not recommended for approval NG-CDFC to procure the vehicle as earlier proposed and allocate funds to the proposed projects in 2022/23 financial year Information provided is that the NG-CDFC will allocate funds towards purchase of the vehicle in 2022/23 Financial Year a clear indication that the vehicle is a priority to the Constituency. The request was deferred by the PPRM Committee on 24th November, 2021 subject to NG-CDFC; - Submitting a report from the Mechanical engineer on the current condition of the old vehicle and specifying the year of manufacture. - NG-CDFC confirming if the Sub-County Education Office has been notified about the donation of the old vehicle. The NG-CDFC has submitted the vehicle mechanical inspection report indicating that the Land rover GKB 430H (Year of Manufacture: 2014) is in good shape and its economical to repair at an estimated cost of Kshs.186,450. The NG-CDFC has also submitted a letter from the Ministry of Education (Sub-County Education Office) ref: MOE/GIL/GEN/Vol.3/48 dated 19th January, 2021 requesting the NG-CDFC to provide it with the official vehicle so as to be able to visit schools during its routine work. In 2020/21 financial year, the Constituency had requested to purchase a new motor vehicle, which was approved upon initiation of the disposal process of the old one. The proposed method of disposal of the vehicle was through donation to the Sub County Education Office. Up to date, the donation has not been done. The NG-CDFC has indicated that currently, the motor vehicle is not a priority since there were projects that required urgent intervention. It was also confirmed that the old motor vehicle was still being used and that the purchase of a new one would be considered in 2022/23 financial year. |
|  | Kuresoi North | Min. 4 of 16/12/2021 | Bureti Primary School- Construction of 2 classrooms to Completion | 2021/22 | 1,300,000 | Bureti Primary School, Kshs.1,300,000- Renovation to completion of 6 classrooms; roofing, flooring, plastering, fixing doors, windows, fascia board and painting. | The BOMs of the schools indicated that the classrooms were in bad state and needed renovations to make them conducive for learning. | Pending approval NG-CDFC to confirm whether the allocated amount will be adequate to complete the proposed works. The NG-CDFC has submitted minutes from the schools confirming the change of activities |
|  |  |  | Songo Primary School-Construction of 2 units pit latrines @ 3 doors at Kshs.200,000 per unit to Completion with provision of one door for the physically challenged persons |  | 400,000 | Songo Primary School, Kshs.400,000- Renovation to completion of 4 classrooms; plastering, flooring, fixing doors, windows, fascia board and painting. |  |  |
|  | Mogotio | Min.9 of 6/01/2022 | Mogotio day secondary school- Construction of a 40-student science laboratory to lintel level. | 2020/21 | 800,000 | Mogotio day secondary school, Kshs.800,000- Construction of one new classroom. | Increased enrolment due to government policy on 100% transition and need to ensure social distance to control the spread of COVID-19 | Recommended for approval The NG-CDFC submitted minutes from the school indicating that the school urgently needs a classroom to accommodate the new form 1 students who will be joining the school. |
|  |  |  | Kisanana secondary school- Construction of a new dormitory. | 2018/19 | 1,000,000 | Kisanana secondary school, Kshs.1,000,000- Construction of one new classroom to completion |  | Recommended for approval The NG-CDFC has submitted minutes from the school indicating that the school has dire need of a classroom. |
|  |  |  | Bursary Tertiary institutions - Payment of bursary to needy students in tertiary institutions | 2021/22 | 4,000,000 | Revision books, Kshs.4,000,000- Purchase of 1573 copies of Top-grade predictor encyclopaedia 8 at Kshs.699 each and 1694 copies of Top-grade predictor composition at Kshs.399 in 121 primary schools as per the attached list and purchase of 10 Top-Grade Predictors for Mathematics at Kshs.695, English at Kshs.690, Kiswahili at Kshs.690, Physics at Kshs.695, Chemistry at Kshs.695, Biology at Kshs.695, Geography at Kshs.680, Business Studies at Kshs.685, History at Kshs.685, Agriculture at Kshs.680 and CRE at Kshs.680 for 29 secondary schools | Need to improve academic performance in primary and secondary schools. | Not recommended for approval Reallocation of funds away from the bursary kitty goes against the Board’s policy on bursary NG-CDFC to prioritize acquisition of revision books in 2022/23 Financial Year as a separate project The NG-CDF guidelines on administration of bursary stipulates that the Board considers bursary scheme as an important grant targeting the poorest segment of the society hence NG-CDFCs are encouraged to always allocate funds towards the scheme. The guidelines further advises the NG-CDFCs to avoid reallocating funds meant for the programme to other projects The NG-CDFC has provided list of the schools for which books are to be bought |
|  |  |  | Molosirwe secondary school- Construction of a new administration block-4 rooms up to lintel level. | 2019/20 | 600,000 | Molosirwe Secondary School, Kshs.1.200,000-Completion of boys’ dormitory; flooring, plastering, internal fixing and fixing of doors and windows. | The school resolved to prioritize completion of a dormitory rather than starting a new administration block. | Pending approval NG-CDFC to specify the estimated cost of the project The dormitory project was allocated Kshs.600,000 in 2018/19 financial year. |
|  |  |  | Molosirwe secondary school- Completion of a 3 roomed administration block; roofing and fixing doors and windows. | 2020/21 | 600,000 |  |  |  |
|  |  |  | Rosoga secondary school - Completion of the laboratory-painting and plastering and finishings. | 2018/19 | 600,000 | Rosoga secondary school, Kshs.600,000- Construction of a new 10 door latrine block for girls. | The school completed the laboratory. | Pending approval NG-CDFC to submit verifiable evidence showing that the laboratory is complete. NG-CDFC to confirm if the latrine block will cater for the needs of PWDs. The NG-CDFC has submitted minutes from the school indicating that the sanitation facilities were needed as the population had increased |
|  | Westlands | Min 17 of 17/2/2022 | Kihumbuini Primary School- Construction of perimeter wall | 2017/18 | 400,000 | Kihumbuini Primary School Kshs.400,000- Rehabilitation of 4 toilets; painting, lighting, replacement of broken doors, installation of handwashing points and tiling | Unspent balance | Recommended for approval The perimeter project had been allocated Kshs.2,000,000 but realized a saving of Kshs.400,000 |
|  |  |  | Hospital Hill Primary School- Construction of Library from slab, stair case and ramp to completion. | 2019/20 | 3,500,000 | Hospital Hill Primary School Kshs.3,500,000-Additional funds for construction of 300 metre perimeter wall | The school received donor funding and constructed the library | Recommended for approval The project was allocated Kshs.2,000,000 in 2021/2022 Financial Year and the estimated cost had been provided as Kshs.5,500,000 |
|  |  |  | Hospital Hill High School- Construction of 256 capacity dormitory on 1st floor with a slab | 2020/21 | 1,442,680 | Hospital Hill High School Kshs.1,442,680- Completion of 128 capacity dormitory on ground floor in co-funding with Ministry of Education: fitting of windows and doors, painting, electrical works, plumbing, screeding and tiling | Unspent balance | Recommended for approval The ground floor dormitory project was allocated Kshs.5 million in 2019/20 The NG-CDFC has also indicated that the MoE allocated Kshs.6 million towards the project The estimated cost has been indicated as Kshs.16,000,000 |
|  |  |  | Karura Forest Primary School- Rehabilitation of 3 classrooms The school had been allocated Kshs.2,701,206 for rehabilitation of 3 classrooms. Upon completion, the project realized a saving of Kshs.700,000 | 2017/18 | 700,000 | Karura Forest Primary School Kshs.700,000- Renovation of 3 classrooms; painting, replacing broken windows and tiling of floor | Unspent balance | Recommended for approval |
|  | Ijara | MIN: CDFC. 040/03/2022 | Ijara District Education Headquarters - Construction of 7 rooms administration offices to completion | 2020/2021 | 4,000,000 | Ijara Deputy County Commissioner – Additional funds to commence the construction of 3 Bedrooms self-contained staff houses and 2 roomed servant quarter, Kitchen, sitting room and inbuilt toilet with provision for PWD | The emergence of insecurity in Ijara District that requires the stability of the DCC. | Pending approval The staff houses project was allocated Kshs.3,890,10 in 2020/21 Financial Year NG-CDFC to submit certified BoQs |
|  |  |  | Dabara Matam Primary School - Construction of 2 number classrooms to completion (Kshs. 1,750,000) purchase of 30 desks (kshs. 150,000) | 2020/2021 | 1,900,000 | Ijara Technical Institute, Kshs.1,900,000 – construction to completion of 6 door toilets with two chambers to cater for PWDs and septic tank to completion. | School has not been registered to a full primary school, upgrading to be done from ECD to a new primary school later next year and may be considered for funding in the next financial | Recommended for approval |
|  |  |  | Doi Primary School - Construction of 2 number classrooms to completion (Kshs. 1,850,000) purchase of 30 desks (kshs. 150,000) and 2door toilets with septic (ksh, 500,000) to completion | 2020/2021 | 2,500,000 | Ijara NG-CDF Offices, Kshs.2,500,000 – Renovation to completion of 4 offices and one Boardroom: re-flooring, re-plastering, fixing of floor tiles, reroofing, and Painting | School has few students since other students moved to town schools. | Recommended for approval |
|  |  |  | Hulugho boys secondary school – Construction of administration block | 2020/2021 | 3,000,000 | Hulugho boys secondary school – Renovation to completion of 6 classrooms: repair of roofing, flooring, wall plastering, painting, fixing doors and windows, fussier boards, and verandars | Change of activity due to dilapidated status of the classrooms, the school management requested for renovation of 6 classrooms instead of construction of administration block. | Recommended for approval |
|  |  |  | Hulugho sub-county- Supply of office furniture | 2020/2021 | 2,500,000 | Hulugho Sub- County – Renovation to completion of administration block comprising of 5 offices: repair of roofing, flooring, wall plastering, painting, fixing doors and windows and fussier boards | Change of activity from purchase of furniture to renovation administration block comprising of 5 offices. The proposed offices are in deplorable state | Recommended for approval |
|  |  |  | Garabey primary school - Construction of two classrooms Ksh.1, 750,000.00 and purchase of 30 desks ksh.150, 000.00 to completion |  | 1,900,000 | Garabey primary school, Kshs.1,900,000 – Renovation to completion of 5 classrooms: repair of roofing, flooring, wall plastering, painting, fixing doors and windows, fussier boards, and verandars | Change of activity. Due to dilapidated status of classrooms, the school management requested for renovation of 5 classrooms instead of construction of administration block. | Recommended for approval |
|  | Baringo South | Min 4 of 10/2/2022 | Bekibon Mixed day secondary school -Drilling of water borehole | 2018/19 | 2,500,000 | Bekibon primary school, Kshs.2,500,000-Drilling of water borehole | The school’s name was erroneously captured during submission. | Recommended for approval |
|  |  | Min 4 of 12/1/2022 | Loitip Girls Secondary school-Drilling of a water borehole. | 2019/20 | 2,500,000 | Loitip Girls Secondary school, Kshs.2,500,000-Water piping and building of two masonry tanks. | The probability of getting clean water was minimal since the school sits on a geothermal belt. There are existing boreholes within the area which were drilled and abandoned due to salinity. There exists an 11- inch OL-ARABAL pipeline that can be created and water used | Pending approval NG-CDFC to split cost for the proposed activities, specify capacity of the tanks and length of the pipes to be installed |
|  |  |  | Kampi ya samaki primary school-Renovation of 2 classrooms to completion: keying, flooring, fixing of new fascia boards, painting works and branding. | 2020/21 | 300,000 | Kampi ya samaki primary school, Kshs.300,000- Construction to completion of 2 door pit latrine for boys with one door for Persons with disabilities. | The school lacks teachers’ toilets and the amount allocated for renovation is not adequate to complete the renovation activities. | Recommended or approval |
|  | Kipkelion East | Min No. 2 of 11/02/2022 | Bursary Secondary Schools | 2021/22 | 2,985,059 | - Primary Schools Revision Books, Kshs.3,636,249- Purchase of 4551 copies of KCPE revision combined encyclopaedia books (top grade) at Kshs.799 each for candidates in 108 primary schools. - Secondary Schools Revision Books, Kshs.348,810- Purchase of 462 copies of Top-grade predictor mathematics, English, Kiswahili, Physics, Chemistry, Biology, Geography, Business studies, History, Agriculture and CRE each at Kshs.755 for 42 secondary schools | Unspent balances after the beneficiaries have been awarded bursaries in both day and boarding schools. | Not recommended for approval Reallocation of funds away from the bursary kitty goes against the Board’s policy on bursary NG-CDFC to prioritize acquisition of revision books in 2022/23 Financial Year as a separate project The NG-CDF guidelines on administration of bursary stipulates that the Board considers bursary scheme as an important grant targeting the poorest segment of the society hence NG-CDFCs are encouraged to always allocate funds towards the scheme. The guidelines further advises the NG-CDFCs to avoid reallocating funds meant for the programme to other projects NG-CDFC can therefore prioritize the revision books in 2022/23 Financial Year as a separate project |
|  |  |  | Social Security Programmes -NHIF- Provision of medical insurance cover for the vulnerable families |  | 1,000,000 |  | The social security programmes beneficiaries reduced to 167 from 333 | Pending approval NG-CDFC to confirm that there are no existing beneficiaries that would be affected by the withdrawal of the funds NG-CDFC to submit 1st schedule and correct 3rd schedule. NG-CDFC to submit a letter from the Ministry of Education, Science & Technology confirming that the proposed books are recommended for revision and that they are not provided by the Ministry of Education. NG-CDFC to further provide names of the secondary schools for which the revision books will be bought. |
|  | Konoin | Min No. 5 of 11/1/22 | Kipkorir salat Boys Secondary School- Levelling of school field - 1200 square metres hilly field to be levelled and ramped including planting of grass | 2021/22 | 1,900,000 | Satiet Primary School, Kshs.1,900,000- Levelling of school field - 1200 square metres hilly field to be levelled and ramped including planting of grass | The school land title deed is still under Satiet Primary School though the field is used by Kipkorir salat Boys Secondary School. | Recommended for approval |
|  | Eldama Ravine | Min No. 6 of 24/09/2021 | St Mary’s Boito Secondary School- Construction of 40 student capacity library up to roofing level | 2020/21 | 1,200,000 | St. Mary’s Boito, Kshs.1,200,000 - Erection of a library on an existing one storey building. | - | Pending approval. NG-CDFC to provide clear description of project’s activity and specify the reason for change of the project’s activity. |
|  |  | Min No. 7 of 12/1/2022 | St Patrick’s Shimoni Primary School- Construction of 6 door toilets | 2020/21 | 380,000 | St. Patrick’s Shimoni Primary School, Kshs.380,000- Refurbishment of 2 semi-permanent classrooms: repairing floors, fixing of windows, window panes and doors and replacement of old timber. | Toilets have been constructed by a well-wisher, they are complete and in use. | Not recommended for approval Not recommended for approval NG-CDFC to construct permanent classrooms rather than refurbishment of semi-permanent ones NG-CDFC should therefore allocate the funds to another viable project within the school |
|  | Kilgoris | Min No.4 of 15/12/2021 | Embolioi Primary School- Construction of one classroom to Completion. | 2020/21 | 1,300,000 | Embolioi Primary School, kshs.1,300,000- Purchase of 3 acres of land inclusive land processing fee. | The school does not have land and is currently being housed in the local KG church | Pending approval NG-CDFC to confirm ownership of the school through submission of registration certificate NG-CDFC to submit land valuation report from a government land valuer, land search and a copy of title deed. The NG-CDFC has submitted a land valuation report done by a private valuer, that is, Adomag Valuers and Associates. The report indicates that the land is 2.51 hectare and is valued at Kshs.1.8 million |
|  | Kuresoi South | Min No. 6 of 15/2/20 22 | Amalo Girls Secondary School- Construction of a Girls Section; Construction of 2 classrooms to completion. (The school wants to establish a separate wing for female learners within the same institution). | 2021/22 | 2,000,000 | - Completion of 6 No. administration office - Arorwet Secondary School, Kshs.1,100,000- Completion of 6 No. office administration block; tiling of the floor, painting and electrical wiring. The project has so far received Kshs.2 million - Tinet Mixed Secondary School, Kshs.1,100,000- Completion of 6 No. office administration block; tiling of the floor, painting and electrical wiring. The project has so far received Kshs.2 million - Tendwet Secondary School, Kshs.1,100,000- Completion of 6 No. office administration block; tiling of the floor, painting and electrical wiring. The project has so far received Kshs.2 million - Kapngorot Secondary School, Kshs.1,100,000- Completion of 6 No. office administration block; tiling of the floor, painting and electrical wiring. The project has so far received Kshs.2 million - Kapkwen Secondary School, Kshs.1,500,000- Phase 1 construction of 6 no. office administration block; substructure works, walling, RC frame and roofing works. - Aoon Primary School, Kshs.1,300,000- Construction to completion of 1 classroom. | The school decided not to proceed with establishment of a girls’ section. | Pending approval NG-CDFC to provide clear reasons for the reallocation of funds. |
|  |  |  | Chigamba Police Post- Construction of 3 room staff quarters to completion at Kshs. 1,000,000, Construction of staff pit latrines and shower cubicles to completion, i.e. Two door pit latrine and One door pit latrine for persons with disability and 2 door shower cubicles at Kshs. 450,000 and Purchase and installation of 5,000 litre water tank at Kshs. 50,000. |  | 2,000,000 |  | There’s an existing land tussle in the area. | Recommended for approval |
|  |  |  | Tach Asis Primary School – Keringet- Construction of 1 No. classroom to completion. |  | 1,000,000 |  | The school was closed because the land had been demarcated as forested area. | Pending approval NG-CDFC to submit verifiable evidence confirming the closure of the school. |
|  |  |  | Milimet Assistant Chiefs Office- Construction of 2 roomed assistant chiefs office to completion. |  | 700,000 |  | The newly established sub location has not been gazzetted. | Pending approval NG-CDFC to specify the estimated cost of the Kapkwen Secondary School’s administration block. NG-CDFC to also justify the allocation of Kshs.1.3 million for construction of 1 classroom at Aoon Primary School since construction of a classroom in the constituency ranges between Kshs. 750,000 and Kshs.1 million as per the 2020/21 and 2021/22 financial years’ allocations. |
|  |  |  | Kenya Medical Training College Keringet- Construction of 2 classrooms to completion. |  | 2,000,000 |  | Funds allocated are not sufficient for establishment of the institution. | Not recommended for approval NG-CDFC to reallocate the entire allocation of Kshs.5,600,000 if the project is no longer tenable otherwise implement project as approved. The KMTC project was allocated Kshs.5,600,000 for purchase of 2.3 Acres at Kshs.3,600,000 and Construction of 2 classrooms to completion at Kshs.2,000,000 |
|  |  | Min No.3 of 15/11/21 | - Kaber Primary School- Purchase of one acre of land - Kaber Primary School- Purchase of two acres of land. | 2017/18 2019/20 | 400,000 1,000,000 | Kabeer Primary School, Kshs.1,400,000- Construction of 1 classroom to completion at Kshs.1,000,000 and 1 classroom to reinforced concrete frame level (substructure, walling and reinforced concrete frame) at Kshs.400,000. The classroom was allocated Kshs.600,000 in 2021/22 financial year for completion works. | Pieces of land to be purchased have caveats on them. | Recommended for approval. |
|  |  |  | Chepkosigen Primary School- Purchase of one acre of land. | 2019/20 | 600,000 | Chepkosigen Primary School, Kshs.600,000- Construction of 1 classroom to roofing level The classroom was allocated Kshs.400,000 in 2021/22 financial year for completion works. |  | Recommended for approval. |
|  | Bahati | Min No.2 of 18/1/2022 | Emergency | 2019/20 | 458,700 | Kagoto Primary School, Kshs.2,200,907- Additional funds towards supply and installation of a solar powered borehole pumping system and casting of reinforced concrete foundation, installation of 30,000 litres steel panel tank and construction of water kiosk within the school. | Unspent funds | Recommended for approval The project was allocated Kshs.1,850,000 in 2021/22 financial year. |
|  |  |  | Emergency | 2020/21 | 1,742,207 |  |  |  |
|  |  |  | - Githioro Police Station- Construction of a Police Station With 3 cells, Armory and 3 Offices -1st Phase (Foundation, Walling and Roofing. - Bahati Police Station- Purchase of furniture for The Modern Police Station Constructed by NG-CDF-10 Executive Chairs, Airport Seats- Waiting Area, 5 Executive Tables, Curtain Blinds For 5 Offices. - Kiamaina Officer Commanding Police Division (OCPD) Headquarters- Purchase of Furniture for The OCPD Headquarters Office Constructed By NGCDF-5 Executive Chairs, Airport Seats- Waiting Area, 2 Executive Tables, And One Office Cabinet. | 2021/22 | 2,000,000 1,000,000 | Bahati Youth Centre- Studio, Kshs.2,500,000- Equipping the youth centre studio at Kiamaina ICT centre; fixing soundproof membranes, table, chair, professional sound mixer, digital audio work station, HP computer, music keyboard, professional recording microphones, studio speakers and headphones. | There is a standoff between the NG-CDF and Ministry of interior after a fully constructed Lanet Police station was defaced, branding erased and currently not in use. Same challenges faced in other stations, that is, Bahati and Kiamaina hence no project implementation can be done. | Recommended for deferral The PPRM Committee to hold a consultative meeting with the NG-CDFC and other stakeholders with a view to resolving the issues surrounding the projects NG-CDFC to provide information on how the studio will be managed and sustained NG-CDFC to change the project name to Kiamaina ICT centre since the project has been approved as such. NG-CDFC to specify the unit for each item to be purchased and their associated costs Allocation of additional Kshs.1,000,000 towards bursary would not exceed the 35% ceiling for 2021/22 financial year |
|  |  |  |  |  | 500,000 | Bursary Secondary Schools, Kshs.1,000,000- payment of bursary to needy students. |  |  |
|  | Belgut | Min No.4 of 13/12/2022 | - Borborwet Secondary School- Purchase of 50-seater Hino school bus. - Getumbe Secondary School- Purchase of 50-seater Hino school bus. | 2021/22 | 350,000 350,000 | Belgut Resource Centre, Kshs.400,000- Purchase of 500 top grade books at Kshs.799 per book. | Savings after the purchase of buses | Recommended for deferral NG-CDFC to provide information on the management structure of the Centre Management to visit the Constituency with the aim of holding consultative discussion with the NG-CDFC and other stakeholders so as to get a way forward on how the centre would be put to use without offending the NG-CDF Act given that community libraries/facilities fall under the County Government functions. Management via a circular dated 15th July, 2021 requested all the constituencies to compile and submit a report on project that are complete but not in use. Belgut Constituency complied with this and submitted Belgut Resource Centre as one of the projects that are complete but not in use and indicated that the project is situated in place that is not secure. |
|  |  |  |  |  |  | Chemamul A Primary School, Kshs.300,000- Spring protection, completion of piping work and refurbishment of 100,000 cubic masonry tank: filling cracks, reinforcement and painting. |  | Pending approval NG-CDFC to specify the estimated cost of the project and provide clear description of the project The project has so far received Kshs.500,000 |
|  |  |  | - Finlays Flower I Primary School-Purchase of 213 revision books. - Finlays Flower II Primary School- Purchase of 180 revision books. | 2018/19 | 100,000 100,000 | Itembe Primary School, Kshs.200,000- Additional funds for full purchase of 0.4 acres of land. | The schools were closed by the Multinational, Finlays Tea after employees were declared redundant thus cheques could not be issued. | Pending approval NG-CDFC to submit the correct 3rd schedule. The project has so far received Kshs.950,000 |
|  |  | Min No.3 of 27/1/22 | Bursary Tertiary Schools- Payment of bursary to needy students in various colleges and universities | 2021/22 | 5,000,000 | Bursary Secondary Schools/Day School, Kshs.5,000,000- Payment of bursary to needy students. | There was an increased number of applicants in secondary schools as compared to the previous year. | Recommended for approval |
|  | Emurua Dikirr | Min No.4 of 15/2/2022 | Bursary Tertiary Institutions- Payment of bursary to needy students in Tertiary and University Institutions. | 2021/22 | 7,000,000 | Bursary Secondary Schools, Kshs.7,000,000- Payment of bursary to needy students in secondary schools. | There was a high number of secondary school students that require bursaries. | Pending approval NG-CDFC to submit the correct 1st schedule. |
|  |  | Min No.5 of 15/2/2022 | Cheramgoi Girls’ Secondary School- Construction of 1 classroom to completion. |  | 1,200,000 | Cheramgoi Girls’ Secondary School, Kshs.1,200,000- Completion of a 150 students’ capacity dormitory; plastering, floor screeding, fixing of window panes, doors and painting. | The project’s activity was wrongly captured as construction of classroom yet the funds were meant for completion of the dormitory. | Pending approval NG-CDFC to submit contract documents and specify on the exact capacity of the dormitory. The project was proposed for funding in 2019/20 financial year in which it was allocated Kshs.3.5 million for completion of a 100-students’ dormitory (plastering, electricity works, floor, plumbing, and painting). It was further allocated Kshs.700,000 in 2021/22 financial year for completion of 150 students’ capacity dormitory (plastering, floor screed, fixing window panes, doors and painting). The request is however still pending approval subject to the NG-CDFC giving more information in regards to funding and cost of the project to completion. When the project was submitted for additional funding in 2021/22 financial year, the NG-CDFC specified its estimated cost as Kshs.4.3 million which has since been revised to Kshs.4.7 million. |
|  |  | Min No.6 of 15/2/2022 | - Emurua Dikirr Technical Training Institute- Purchase and installation of 1.2 KM water pipes - lkerin Mixed Secondary School- purchase of 51-seater school bus - Angaset Primary School- Purchase and installation of 1.2 KM water pipes - Kapkoros Primary School- Purchase and installation of 1.2 KM water pipes - Mogondo High School- Purchase and installation of 1.2 KM water pipes - Cheramgoi Girls Secondary School- Purchase and installation of 1.2 KM water pipes - Motosiet Primary School- Purchase and installation of 1.2 KM water pipes - Kelonget Secondary School- Purchase and installation of 1.2 KM water pipes - Takitech Secondary School- Purchase and installation of 1.2 KM water pipes. | 2019/20 | 300,000 2,300,000 300,000 300,000 300,000 300,000 300,000 300,000 300,000 | Kurangurik KMTC, Kshs.4,700,000- Drilling and equipping of a borehole | Due to COVID-19 Pandemic, reopening of schools will have to be done as per the directives of the Ministry of health, but the tertiary institutions do not have water supply. | Pending approval NG-CDFC to submit certified cost estimates for the borehole The request was declined by the Board in its meeting held on 1st December, 2020. NG-CDFC was advised to prioritize the project in 2020/21 financial year to allow for implementation of the initial projects since the Kurangurik KMTC was not yet operational at the time. The NG-CDFC has now appealed the Board’s resolution by indicating that the NG-CDFC funded projects at Kurangurik KMTC had been done to completion with enrolment of students and learning currently on. However, learning and other related activities in the institution could not continue due to lack water Ilkerin Mixed Secondary School bus project had been allocated Kshs.7,000,000 in 2019/20 financial year. However, Kshs.4,700,000 was reallocated towards drilling of a borehole at Emurua Dikir TTI thus leaving a balance of Kshs.2,300,000 |
|  | Jomvu | Min No. 6 of 17th June, 2021 | 1. Emergency 2. Emergency | 2019/20 2016/17 | 6,698,241 204,377 | - Amani Primary School, Kshs.600,000- Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set - Kwa Jomvu Primary School, Kshs.600,000- Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set - Kibarani Primary School, Kshs.600,000- Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set - Miritini World Bank Primary School, Kshs.900,000- Purchase of 150 sets of lockers and chairs @Kshs.6,000 per set - Maganda Primary School, Kshs.1,800,000- Purchase of 300 sets of lockers and chairs @Kshs.6,000 per set - Kajembe High School, Kshs.600,000- Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set - Miritini Secondary School, Kshs.600,000- Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set 8. Mreroni Secondary School, Kshs.600,000- Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set | Unspent funds | Recommended for approval |
|  |  |  |  |  |  | - Jomvu Girls High School, Kshs.602,618-Purchase of 100 sets of lockers and chairs @Kshs.6,000 per set |  | Pending approval NG-CDFC to justify allocation of the extra Kshs.2,618 above the estimated cost of the lockers and chairs |
|  |  | Min No 7 of 24th September, 2021 | Jomvu Kuu sublocation- Laying pipes for fresh water | 2013/14 | 1,000,000 | - Miritini Assistant County Commissioner’s office, Kshs.170,000- Connection to the KPLC main Electricity - Miritini Administration police, Kshs.170,000- Connection to the KPLC main Electricity | Unutilized funds from PMC account that were transferred back to the constituency account | Recommended for approval |
|  |  |  |  |  |  | Jomvu Kuu Administration Police Units, Kshs.660,000- Construction of a septic tank, Kshs.490,000 and connection to KPLC main Electricity Kshs.170,000 |  | Pending approval NG-CDFC to specify capacity of the septic tank |
|  |  |  | Mwamlai borehole, Kshs.650,000- Drilling and development. of borehole | 2014/15 | 603,800 | - Jomvu Kuu Administration Police Units, Kshs.113,800- Floor tiling for 2No. Administration Police Units comprising of a sitting room, bedroom, kitchenette and washroom - Jomvu Kuu Assistant County Commissioner’s Office, Kshs.490,000- Additional funds for extra reinforcement due to the sloppy, inaccessible and unstable land (Kshs.320,000) and connection to KPLC main Electricity (Kshs.170,000) | Unutilized funds from PMC account that were transferred back to the constituency account | Pending approval NG-CDFC to clarify how Kshs.46,200 was spent, as the amount approved for Mwamlai borehole was Kshs.650,000 NG-CDFC to submit instructions from the Sub County Works officer for the extra works for Jomvu Kuu Assistant County Commissioner’s Office & Administrative Police units which had been funded to completion. The project was allocated Kshs.4,600,000 in 2019/20 for Construction to completion of 2No. Administrative Police units each comprising sitting room, bedroom, kitchenette and washroom |
|  | Garsen | Min No.3 of 25/01/2022 | - Galana Sabaki Boarding primary School- Construction of 3 classrooms to completion - Galana Sabaki Boarding primary School- Construction 800metre of school perimeter fence to completion using concrete posts. - Galana Sabaki Boarding primary School- Construction of 1 dormitory to completion with capacity of 100 pupils 4. Galana Sabaki Boarding primary School- Construction of 2No 2door VIP toilets to completion | 2020/21 | 3,600,000 2,000,000 2,700,000 1,200,000 | - Bursary Secondary Schools, Kshs.3,124,104.77- Payment of bursary to needy students - Bursary Tertiary Institutions, Kshs.1,000,000- Payment of bursary to needy students - Sports Tournament, Kshs.1,575,895.23- To provide funds for promotion of sports talent in the constituency through organizing sports tournaments and awarding winning teams with trophies and games training kits | Internal wrangling within the project management committee and inter-county border rows with claims that the proposed site is in Magarini constituency of Kilifi county while others claim that it’s part of Garsen constituency in Tana River County. This issue has caused delay in the project implementation. | Pending approval NG-CDFC to submit written confirmation that Galana Sabaki Boarding Primary School is a newly proposed school and that no works have been undertaken NG-CDFC to submit correct 1st, 3rd and 4th schedules capturing the correct financial year The additional allocation of funds to bursary kitty will not exceed the set limit of 35% allocation per financial year Approval of the reallocation to bursary by the PPRMC was based on the fact that Galana Sabaki Boarding Primary School was a newly proposed school. |
|  |  |  |  |  |  | - Onjila Primary School, Kshs.800,000- Renovation of 1 classroom to completion: roofing, flooring, fitting windows and door, plastering and painting - Chamwanamuma Primary School, Kshs.800,000- Renovation of 2 classrooms to completion: roofing, flooring, fitting windows and doors, plastering and painting |  | Pending approval NG-CDFC to justify disparity in allocation of funds for similar renovation activities NG-CDFC to submit correct 1st, 3rd and 4th schedules capturing the correct financial year |
|  |  |  |  |  |  | Garsen NG-CDF Office, Kshs.1,200,000- Repair of office perimeter fence chain-link (800 meters) using wooden posts |  | Pending approval NG-CDFC is advised to use either concrete or metal bars NG-CDFC to submit correct 1st, 3rd and 4th schedules capturing the correct financial year |
|  |  |  |  |  |  | Garsen Police station, Kshs.500,000- Construction of 1 No. 3-door toilet |  | Pending approval NG-CDFC to confirm if the toilet will cater for PWDs and confirm whether it is a pit latrine or flush toilet NG-CDFC to submit correct 1st, 3rd and 4th schedules capturing the correct financial year |
|  |  |  |  |  |  | NG-CDFC Office equipment, Kshs.300,000- Purchase of office equipment: 2 laptops core 19, 32GB, 1 TbSSD, win 10, Touch4K FHD @Kshs.140,000 and 1 TB external storage @Kshs.12,000 |  | Pending approval NG-CDFC is advised to provide clear description of the project and correct the allocation |
|  | Mvita | Min No. 68 of 18/1/2022 | Bursary Tertiary Institutions- Payment of bursary to needy students in tertiary and vocational institutions | 2021/22 | 15,275,000 | Revision books, Kshs.15,275,000- Supply and delivery of 13,000 revision books for secondary schools @235/= totaling to Kshs.3,055,000 and 26,000 revision books for upper Primary @235/= totaling to Kshs.6,110,000, 26,000 revision books for Lower primary @235/ totaling to Ksh6,110,000 | The committee noted that the revision books have greatly improved performance for the year 2020 exams | Not recommended for approval Reallocation of funds away from the bursary kitty goes against the Board’s policy on bursary NG-CDFC to prioritize acquisition of revision books in 2022/23 Financial Year as a separate project The NG-CDF guidelines on administration of bursary stipulates that the Board considers bursary scheme as an important grant targeting the poorest segment of the society hence NG-CDFCs are encouraged to always allocate funds towards the scheme. The guidelines further advises the NG-CDFCs to avoid reallocating funds meant for the programme to other projects The tertiary bursary vote had been allocated Kshs.28 million hence reallocating Kshs.15 million will leave a balance of Kshs.13 million for distribution to the needy students NG-CDFC to give clear reasons for reallocation of funds NG-CDFC to specify the names of the secondary and primary schools, specify the revision books to be purchased and the number to be supplied to each school. NG-CDFC to further submit a letter from the Ministry of Education, Science & Technology confirming that the proposed books are recommended and that they are not provided by the Ministry of Education. |
|  | Machakos Town | Min No.3 of 24/01/2022 | New NG-CDFC Office Equipping, Kshs.2,500,000- Purchase of office furniture-executive desks 4pcs@60,000=240,000, executive chairs 4pcs@40,000=160,000, reception counter 1.8Meter@56,000, reception bench 4 seater 5pcs@30,000=150,000, reception 3 seater sofa 4pcs@70,000=280,000, 1.2Meter office desks with 3 drawers 5pcs@30,000=150,000, office chairs 10pcs@20,000=200,000, visitor chairs 20pcs@5,000=100,000, metal cabinets 10pcs@35,000=350,000, boardroom conference table 3.2Meter 10seater=120,000, conference chairs 10pcs@5,000=50,000, conference hall | 2020/21 | 2,000,000 | Bursary Secondary schools, Kshs.2,000,000- Payment of bursary to needy students | Overwhelming bursary needs | Recommended for approval Allocation of additional Kshs.2,000,000 towards bursary will not exceed the 35% ceiling for bursary vote for 2020/21 financial year |
|  |  |  | Kiima Kimwe Police Post- Construction of 3 roomed Police Post to completion. | 2019/20 | 1,000,000 | Bursary Secondary schools, Kshs.1,000,000- Payment of bursary to needy students | The implementation of the Police post was becoming a challenge as the administration police department was merged to the Kenya Police service and as such the administration police was not required | Recommended for approval Allocation of additional Kshs.1,000,000 towards bursary would not exceed the 35% ceiling for bursary vote for 2019/20 financial year |
|  | Magarini | Min 4 of 27/10/2021 | Songerako Primary School- Construction of 2 classrooms to completion | 2021/22 | 2,400,000 | Mtsangamali Primary School, Kshs.2,400,000- Construction of 2 classrooms to completion | Mtsangamali primary school is more needy. Students are learning in make shift classrooms. Serengeko primary school received assistance through emergency funding in 2020/21 financial year | Pending approval NG-CDFC to submit a letter from Songerako Primary confirming they no longer require the funds. |
|  |  |  | Yedhi Primary School- Renovation of 6 classrooms; Column drilling and erection, ring beam, re-roofing, plastering, floor works, fixing of windows, doors, painting and decoration (phase 1) | 2021/22 | 3,186,453.24 | - Chasimba Primary School, Kshs.2,400,000-Construction of 2 classroom - Kambi Ya Waya Secondary School, Kshs.500,000- Construction of 1 No 2door toilet block, with one cubical catering for PLWDs 500,000 - Mamburi Primary School, Kshs.286,453.24- Full renovations of 3 classrooms (introduction of columns, demolition of weak walls, construction of new walls, construction of ring beam, roofing, plastering, flooring, fixing doors, windows, painting, construction of verandah and decoration) Phase II | Students at Chasimba primary school are learning in very poor conditions the school needs the urgent assistance. Renovations at Yedhi primary school will be funded through the emergency. | Not recommended for approval There is no evidence that Yedhi Primary School no longer requires funds. |
|  |  |  | Sports Activities- Carrying out sports tournaments where the winning teams will be awarded with balls, uniforms and trophies (Kshs.500,000.00) and purchase of uniforms, trophies, balls, Jerseys and equipment (Kshs.1,500,000.00) | 2021/22 | 2,000,000 | Kanyumbani Primary School, Kshs.2,000,000-Construction of 2 classrooms: foundation, walling, roofing, windows, doors, flooring and plaster works | Kanyumbani primary school has a shortage of classrooms and students learn in make shift classrooms. The 2,000,000 allocated for sports in 2020/21 has not been utilized yet and yet to be disbursed from the NGCDF Board. | Recommended for approval The estimated cost of construction of the 2 classrooms is Kshs.2,400,000 and Kshs.400,000 has been allocated through reallocation of funds from Marafa which is before the committee for deliberation. |
|  |  |  | A J Kingi Primary School- Construction of 1 No. 2 Door Pit Latrine to completion (one cubicle will be designed to cater for Persons With Disability with ramp, holding rails and other supporting accessories) | 2021/22 | 500,000 | A J Kingi Secondary School, Kshs.500,000- construction of a1 No 2-door pit latrine to completion (One chamber be designed to cater for PWDs with ramp, holding rails and other supporting accessories) | The name of the institution was erroneously captured as A J Kingi primary school instead of A J Kingi secondary school | Pending approval. NG-CDFC to confirm whether the institution has pit latrines that caters for all genders inclusive of PWD |
|  |  |  | Mambrui Primary School- Renovation of 2 classrooms (Re-Roofing) to completion | 2020/21 | 500,000 | Mambrui Primary School, Kshs.500,000- Full renovation of 3 classrooms (introduction of columns, demolition of weak walls, construction of new walls, construction of ring beam, roofing, plastering, flooring, fixing doors, windows, painting, construction of verandah and decoration Phase 1 | The classrooms are in very poor condition and they require full renovation hence the need to change activity to full renovation. | Pending approval. NG-CDFC to submit certified cost estimates for the proposed renovation works Management to carry out verification visit to ascertain the status of the initial and newly proposed projects The proposed renovation works of 3 classrooms has been allocated a total of Kshs.2,778,550 translating to Kshs.926,183 per classroom A new classroom in the constituency costs Kshs.1.2 million Additional Kshs.592,097 has been allocated to the project through reallocation of funds from emergency which is before the committee for deliberation. |
|  |  |  | Marafa Secondary School, Kshs.5,000,000- Completion of school library (super walling, plastering, roofing, flooring and painting) | 2018/19 | 1,800,000 | Mambrui Primary School, Kshs.1,400,000- Full renovation of 3 classrooms (introduction of columns, demolition of weak walls, construction of new walls, construction of ring beam, roofing, plastering, flooring, fixing doors, windows, painting, construction of verandah and decoration Phase II | Savings after completion of the library |  |
|  |  |  |  |  |  | Kanyumbuni Primary School, Kshs.400,000- Additional funds for construction of 2 classrooms: finishes painting and decoration |  | Recommended for approval |
|  |  |  | Ng’andu Primary School- Construction of a 4-door toilet block | 2018/19 | 1,000,000 | Sogorosa Primary School, Kshs.1,000,000- Construction to completion of 1 No. 2-door pit latrine with one chamber catering for PWDs with ramp, holding rails and other supporting accessories | The toilet block at Ng’andu Primary School was funded in 2020/21 financial year. Sogorosa Primary School has no toilet at all and requires urgent assistance | Pending approval NG-CDFC to revise cost for the construction of 1 No. 2-door pit latrine |
|  |  |  | Emergency | 2019/20 | 1,968,097 | Bomani Primary school, Kshs.1,376,000- Completion of full renovation of 5 classrooms (introduction of columns, demolition of weak walls, construction of new walls, construction of ring beam, roofing, plastering, flooring, fixing doors, windows, painting, and decoration | Unspent funds | Pending approval NG-CDFC to submit contract documents The information availed is that the project was started using emergency funds for 2020/21 financial year where Kshs.3,100,000 was allocated which brings total allocation to the project to Kshs.4,476,000 translating to Kshs.895,200 per classroom |
|  |  |  |  |  |  | Mambrui Primary School, Kshs.592,097- Full renovation of 3 classrooms (introduction of columns, demolition of weak walls, construction of new walls, construction of ring beam, roofing, plastering, flooring, fixing doors, windows, painting, construction of verandah and decoration Phase II |  | Pending approval. NG-CDFC to submit certified cost estimates for the proposed renovation works Management to carry out verification visit to ascertain the status of the initial and newly proposed projects The proposed renovation works of 3 classrooms has been allocated a total of Kshs.2,778,550 translating to Kshs.926,183 per classroom A new classroom in the constituency costs Kshs.1.2 million |
|  | Kitui Central | Min No.7 of 16/12/2021 | Ithiani Chiefs Office- Construction of Chiefs Office and Latrine to completion(3 Rooms & 2 Doors Pit latrines) to completion (One pit latrine is for the Persons with disability) . | 2021/22 | 1,000,000 | Ithiani Chiefs Office, Kshs.1,000,000- Construction of two rooms (One big one which will serve as a boardroom and a smaller one which will serve as the chief’s office to completion.) | Change of design as requested by the Chief. | Recommended for approval |
|  | Kibwezi West | Min No.5 of 29/11/2021 | Bursary Tertiary Institutions- Payment of bursary to needy students in tertiary institutions | 2021/22 | 10,000,000 | Bursary Secondary School, Kshs.10,000,000 - Payment of bursary to needy students in secondary schools | With the 100% transition of pupils from primary schools to secondary schools, the enrolment in the secondary schools had increased and it was noted that the most of students were needy and there was high need for more funds. | Recommended for approval |
|  | Kathiani | Min 6 of 27/1/2022 | Kenol Security Post- Construction of a new office to completion-5 spacious rooms | 2020/21 | 1,000,000 | Kenol Police Post, Kshs.1,000,000- Construction of staff houses | Construction of staff houses had been necessitated by the insecurity in the area and thus needs to have officers reside within the police post. | Pending approval NG-CDFC to specify the capacity and number of units to be constructed and the estimated cost The NG-CDFC has further submitted a letter from the Kenol Police Post PMC dated 24th November, 2021 requesting for the change of activity as the surrounding community had joined hands to build the office |
|  | Kitui Rural | Min No.5 of 1/2/2022 | Kaondu Primary School- Construction of ablution block 8 door & urinal | 2019/20 | 800,000.00 | Kaondu Primary School, Kshs.800,000- Completion of an administration block with 4 rooms and a big staffroom: roofing, shuttering, plastering and flooring | The school has enough sanitary facilities and they want to complete am administration block initiated by the NG-CDF | Recommended for approval The administration block was allocated Kshs.400,000 in 2016/17 financial year |
|  |  |  | St. Lukes Yatta Boy's Secondary School- Construction of 15 students’ capacity computer laboratory | 2020/21 | 700,000 | St Lukes Yatta Boys Secondary School, Kshs.700,000- Purchase of 10HP Desktop computers with core 13, 4 GB Ram, Hard disk 250 GB, monitor 19” at a cost of Kshs.70,000 per computer | The project was completed using funds from the ministry | Recommended for approval The NG-CDFC has submitted photos and a letter dated 8th February, 2022 from the school confirming that the computer laboratory was done using the maintenance and improvement funding from the Ministry of Education |
|  |  |  | St. James Matulani Secondary School- Completion of 100 students’ capacity dormitory: plastering, flooring, installation of doors and windows & painting to complete | 2020/21 | 700,000 | St James Matulani Secondary School, Kshs.700,000- Construction of a septic tank | The dormitory is complete and in use | Pending approval NG-CDFC to specify capacity of the septic tank The NG-CDFC has submitted a letter dated 3rd February, 2022 from the school confirming that the dormitory is complete. |
|  |  |  | Kivuuni Primary School- Construction of an Administration block to completion comprising of 3 offices and 1 staff room | 2021/22 | 1,500,000 | Kivuuni Primary School, Kshs.1,500,000 -construction a five-door pit latrine to completion at Kshs.550,000 and fencing the 2050 meters school compound with chain link and concrete posts at Kshs.950,000 | There has been an increase of population in the school which has led to the need of sanitary facilities for both boys and girls as well as insecurity in the school due to trespassing by both animals and human beings hence the need for fencing | Pending approval NG-CDFC to confirm whether the pit latrines will cater for the PWDs |
|  | Tigania East | Min No. 05 of 17/2/2022 | Kamithega secondary school- Construction of one standard classroom to completion | 2020/21 | 90,000 | Kamithega secondary school, Kshs.90,000- Purchase and delivery of 25 lockers and 25 chairs | Unspent balance after completion of the project | Recommended for approval |
|  | Central Imenti | Min No. 04 of 19/11/2021 | Kirigara primary school- Landscaping of the school playing field to completion; levelling, compacting and planting of grass to a field of approximately 65 metres by 110 metres. Cost differs depending on terrain. | 2020/21 | 1,770,000 | Matetu Primary School, Kshs.1,770,000- Landscaping of the school playing field to completion; levelling, compacting and planting of grass to a field of approximately 65 metres by 110 metres. Cost differs depending on terrain. | The area football team had requested for field landscaping but it was opposed by the school Management. | Not recommended for approval There was no evidence indicating that Kirigara primary school no longer required the funds The project was approved for the school not football team |
|  |  |  | Mbajone primary school -landscaping of the school playing field to completion; levelling, compacting and planting of grasses of approximately 65 metres by 110 metres. Cost differs depending on terrain. | 2020/21 | 1,830,000 | Manthi Primary School, Kshs.1,830,000- Landscaping of the school playing field to completion: levelling, compacting and planting of grass to a field of approximately 65 metres by 110 metres. Cost differs depending on terrain. | The area football team had requested for field landscaping but it was opposed by the school Management. | Not recommended for approval There was no evidence indicating that Mbajone primary no longer required the funds The project was approved for the school not football team |
|  |  |  | Sports Activities- Purchase sports equipment, carry out Constituency Football Sports tournament and the winning teams/schools to be awarded with trophies, balls, goal nets and games kits | 2019/20 | 2,747,354.48 | Katheri Primary School, Kshs.3,950,000- Landscaping of the school playing field to completion; levelling, compacting and planting of grass to a field of approximately 80 metres by 110 metres. The terrain of the field is very sloppy. Cost differs depending on terrain. | Distribution of sports equipment bought in 2017/2018 and 2018/2019 still ongoing. The committee found it prudent to improve the sporting facilities as requested by the management of the schools. . | Pending approval. NG-CDFC to Submit certified cost estimates for the projects. |
|  |  |  | Sports activities- Purchase sports equipment, Carry out Constituency Football Sports tournament and the winning teams/schools to be awarded with trophies, balls, goal nets and games kits. | 2020/21 | 1,202,645.52 |  |  |  |
|  |  |  | Sports activities- Purchase sports equipment, Carry out Constituency Football Sports tournament and the winning teams/schools to be awarded with trophies, balls, goal nets and games kits | 2020/21 | 1,539,132.06 | Kauthene Primary School, Kshs.1,539,132.06- Landscaping of the school playing field to completion; levelling, compacting and planting of grass to a field of approximately 65 metres by 110 metres. Cost differs depending on terrain. |  |  |
|  |  |  | Mpindi primary school - Construction of one classroom to completion. | 2017/18 | 700,000 | Karii Primary School, Kshs.700,000- Renovation of three classrooms: plastering, flooring, shuttering and re-roofing to completion. | The land on which the school is situated is in dispute. | Pending approval NG-CDFC to submit verifiable evidence indicating that the land in which the Mpindi primary school classroom was to be done is in dispute |
|  |  |  | Ntonyero Mixed Day Secondary School- Installation of cabros pavements from the administration block to the classrooms. | 2019/20 | 500,000 | Ntonyero Mixed Day Secondary School, Kshs.500,000- Construction of four roomed administration block extension: foundation and slab. | The school has lately experienced deployment of new teachers thus the demand for extension of the administration block. | Pending approval NG-CDFC to specify the estimated cost of the administration block and provide a plan on how they intend to fund it to completion |
|  |  |  | Kiria Primary School- Renovation of three classrooms i.e. flooring, plastering, painting and roofing to completion. | 2020/21 | 600,000 | Kiria Primary School, Kshs.600,000- Renovation of six classrooms: re-roofing to completion | The school requested the NG-CDFC to carry out re-roofing of the leaking classrooms. | Recommended for approval. |
|  |  |  | Ucheru primary school- Connecting the school with piping water from a distance of about 5km from the main source | 2019/20 | 600,000 | Ucheru primary school, Kshs.600,000- Renovation of six classrooms: re-roofing to completion. | The school was denied connection to the water project. | Recommended for approval. |
|  | Maara | Min No. 05 of 11/8/2021 | - Maara NG-CDFC Office-Phase one construction of NG-CDFC Office - Maara National Government Constituency Development Fund Office- Construction of a ten roomed office block with boardroom to completion . | 2017/18 2020/21 | 6,476,421 8,523,579 | - Mugona primary school, Kshs.700,000- Renovation of six classrooms; flooring, plastering internally, fixing four doors and fixing six windows to completion. - Maguma primary school, Kshs.700,000-Renovation of six classrooms-fixing two doors, three window panes, flooring and plastering to completion. - Igakiramba primary school, kshs.1,300,000- Renovation of five classrooms; re-roofing, fixing doors and windows, fixing of window panes and painting, flooring and plastering to completion - Kauni primary school, kshs.1,200,000-Renovation of four classrooms; re-roofing, fixing eight windows, flooring and plastering to completion. - Kariakomo primary school, kshs.1,000,000- Renovation of six classrooms; flooring, plastering ,fixing of windows and window panes, painting and fixing of verandah to completion. - Kanoro primary school, kshs.800,000-Renovation of six classrooms-painting, fixing doors, fixing window panes, plastering, flooring and painting to completion. - Karigini primary school, kshs.776,421- Construction of one classroom from foundation to completion by demolishing a previous condemned classroom. - Karigini Primary school, Kshs.623,579- Construction of one classroom from foundation to completion by demolishing a previously condemned classroom. - Ngaita primary school, kshs.800,000- Renovation of three classrooms-External painting, fixing verandah floor, fixing five windows with panes, plastering, fixing floor and columns on a verandah to completion. - Kabui primary school, kshs.1,000,000-Renovation of three classrooms; re-roofing, plastering and fixing floor to completion - Nkundi primary school, kshs.700,000- Renovation of four classrooms: re-roofing of two classrooms, fixing windows and window panes to completion. - Kagongo gaceke primary school, kshs.700,000-Renovation of three classroom- flooring, plastering, fixing window panes, painting doors to completion. - Makuri primary school, kshs.1,200,000- Renovation of eighteen classrooms: re-roofing of three classrooms, fixing of doors, fixing of windows and window panes, fixing steel columns on a verandah. - Nturiri primary school, kshs.1,000,000- Renovation of eleven classrooms: re-roofing of four classrooms, fixing of doors and window panes and plastering to completion. - Kieganguru primary school, Kshs.1,000,000- Renovation of thirteen classrooms; re-roofing, fixing of doors and windows, fixing of window panes, steel brushing of external walls. - Nkangani assistant chief’s office-kshs.200,000- Additional funds for construction of an office block with four rooms; plastering, flooring and painting to completion (The project was allocated Kshs.1,000,000 in 2020/21) - Muragara assistant chief office, kshs.200,000-Additional funds for construction of an office block with four rooms; plastering, flooring and painting to completion. The project was allocated Kshs.1,000,000 in 2020/21) - Weru assistant chief office, kshs.200,000-Additional funds for construction of an office block with four rooms; plastering, flooring and painting to completion. The project was allocated Kshs.1,000,000 in 2020/21) - Kithare assistant chief office- kshs.200,000-Additional funds for construction of an office block with four rooms; plastering, flooring and painting to completion. The project was allocated Kshs.1,000,000 in 2020/21) - Gaichau assistant chief office- Kshs.200,000-Additional funds for construction of an office block with four rooms; plastering, flooring and painting to completion. The project was allocated Kshs.1,000,000 in 2020/21) - Majira Police Post-Kshs.500,000-Construction of an office block with two rooms from foundation to completion. | Dispute in the area earmarked land for construction of the office and lack of alternative land where the office can be constructed | Recommended for approval |
|  | Buuri | Min No. 04 of 31/1/2022 | Michogomone Primary School-Construction of 1 classroom to completion | 2018/19 | 600,000 | Kironya Primary School, Kshs.600,000- Construction of a classroom to completion | An error occurred during the submission of proposal where the community refers to the area as Michogomone but the school is registered under the name Kironya Primary School. | Recommended for approval |
|  | South Imenti | Min No. 77 of 15/11/2021 | Gakuuni Primary School-Construction of 5 door pit latrine and urinal to completion | 2020/21 | 650,000 | Gakuuni Primary School, Kshs.650,000-Renovation of 3 classrooms: wall plastering, flooring, fixing new doors and windows, painting and installation of verandah to completion. | The parents intervened and did six doors pit latrine and urinal facility as an emergency need | Recommended for approval. The NG-CDFC has submitted a letter from the school confirming that parents had done a sanitation facility in the school |
|  |  |  | St. Martins Ngongo Secondary School- Construction of 5 doors boys flush toilets to completion |  | 500,000 | St. Martins Ngongo Secondary School, kshs.500,000- construction of five doors boys pit latrine to completion | The school does not have a septic tank. | Pending approval NG-CDFC to confirm whether the pit latrine will be user friendly and accessible to PWDs. The NG-CDFC has submitted a letter from the school request for change of the project’s activity |
|  |  | Min No. 66 of 28/10/2021 | - Bursary Secondary Schools - Bursary Tertiary Institutions | 2021/22 | 6,000,000 6,000,000 | Burie King’ori Primary School, Kshs.800,000 -Construction of 14 doors modern flush toilets with two doors reserved for persons with disability, laying foundation, superstructure walling and roofing | Need for more funding for projects that the committee had committed to various institutions that they would in the 2021/22 financial year. | Not recommended for approval Reallocation of funds away from the bursary kitty goes against the Board’s policy on bursary NG-CDFC to prioritize acquisition of revision books in 2022/23 Financial Year as a separate project The NG-CDF guidelines on administration of bursary stipulates that the Board considers bursary scheme as an important grant targeting the poorest segment of the society hence NG-CDFCs are encouraged to always allocate funds towards the scheme. The guidelines further advises the NG-CDFCs to avoid reallocating funds meant for the programme to other projects |
|  |  |  |  |  |  | Geeto Primary School, kshs.600,000-Renovation of 4 classrooms- wall plastering, flooring and verandah |  |  |
|  |  |  |  |  |  | Kamuringi Primary School, kshs.500,000- Construction of a computer laboratory from foundation to completion to serve 20 pupils per session |  |  |
|  |  |  |  |  |  | Kianyaga Primary School, kshs.1,000,000-Construction of 2 doors staff pit latrines to completion at kshs.200,000 and procure228 pupils desks for kshs.800,000 |  |  |
|  |  |  |  |  |  | Kiithwa Primary School, Kshs.1,000,000-Construction of a 16 doors modern flush toilet block-foundation, walling, and roofing with two doors catering for people with disability |  |  |
|  |  |  |  |  |  | Kithunguri Primary School, Kshs. 650,000-Construction of a modern flush toilet block with 16 units-foundation, superstructure and walling with two doors for people with disability |  |  |
|  |  |  |  |  |  | Machikine Primary School, kshs.400,000-Completion of a classroom; -casting of floor slab, wall plastering, fixing of doors and steel casement windows, floor screed, key pointing and verandah (started by PTA who did foundation to roofing level at kshs. 300,000) |  |  |
|  |  |  |  |  |  | Nyaagi Primary School, Kshs.650,000-construction of an administration block 25 feet by 20 feet; laying foundation and superstructure walling to roofing level. |  |  |
|  |  |  |  |  |  | Tharu primary School, Kshs.600,000-Construction of 10 doors modern flush toilets; laying foundation and superstructure walling with two doors catering for PWDs |  |  |
|  |  |  |  |  |  | Yururu Primary School, Kshs.700,000-Renovation of 3 classrooms; re-roofing to completion |  |  |
|  |  |  |  |  |  | St. Elizabeth Primary School, Kshs.500,000-Renovation of 3 classrooms: wall plastering, flooring, verandah and window replacement |  |  |
|  |  |  |  |  |  | Rurama Primary School, kshs.500,000-Rennovation of 3 classrooms: wall plastering, flooring, verandah and window replacement |  |  |
|  |  |  |  |  |  | Gitine Day Secondary School, Kshs.650,000-Construction of a computer room; foundation, superstructure walling, roofing, fixing of doors and casement windows, wall plastering, floor screeding and key pointing to serve 20 students |  |  |
|  |  |  |  |  |  | Machikine Girls Secondary School, Kshs.700,000- Renovation of a dining hall with a capacity of 300 students and a kitchen with one serving point; flooring, upgrading 20 tables by coating with plain sheet and painting work. |  |  |
|  |  |  |  |  |  | Abogeta West Assistant County Commissioner’s Office, Kshs.750,000-Extension of an ICT room to the existing Assistant County Commissioner’s office from foundation to completion. |  |  |
|  |  |  |  |  |  | Gikui Chief’s Office, Kshs.1,200,000-Construction of chief’s office with 2 rooms; foundation, walling, roofing, plastering flooring, key pointing, ceiling, electricity installation and painting to completion. |  |  |
|  |  |  |  |  |  | Mitunguu Police Station, Kshs.800,000-Construction of 3 door flush toilets to the 3 cells and a 12 cubic meters septice tank to completion for an established station |  |  |
|  | Mt Elgon | Min No. 6 of 15th November 2021 | Planting of trees in the following schools @ Kshs 270,000 each: Chepkoya Primary, Kamarang Primary, Kaptum Secondary, Kibumet Primary, Kimaswa Primary, Kimerin Primary, Kimkung SDA Primary, Kipkama Primary, Kipsabula Primary and, Toroso Mixed Secondary. For each school the following trees will be planted: Pischovia 200 pcs @ Ksh.300 each, Nandi flame 160pcs @ Ksh.300 each, Blue gum 240 pcs @Kshs 50 each, Whistling pine 200 pcs @ Kshs 375 and Elgon teak 200 pcs @ Kshs 375 each | 2021/22 | 2,700,000 | Planting of trees in the following schools @ Kshs 100,000 each: Chepkoya Primary, Kamarang Primary, Kaptum Secondary, Kibumet Primary, Kimaswa Primary, Kimerin Primary, Kimkung SDA Primary, Kipkama Primary, Kipsabula Primary, Toroso Mixed Secondary, Cheskaki Special, Cheskaki FYM, Tuiyombei Primary, Chepkui Primary, Kewabrang Primary, Kamabus Primary, Chepkowo Primary, Kapondi Kabero Primary, Chesinende Primary, Bukonoi Primary, Cheptais SDA Primary, Kaboriot Primary, Chebombai Primary, Kimorong primary, Chebukat Primary, Kapsikei Primary and Mt Elgon TTI For each school the following trees will be planted: Pischovia 74 pcs @ Ksh.300 each, Nandi flame 60pcs @ Ksh.300 each, Blue gum 86 pcs @Kshs 50 each, Whistling pine 74 pcs @ Kshs 375 and Elgon teak 74 pcs @ Kshs 375 each | Need to widen coverage of afforestation in schools for clean and sustainable environment to contribute to acceleration of government commitment to increase forest cover and to mitigate effects of climate change | Recommended for approval |
|  | Endebess | Min 28 of 7/10/2021 | Mubere primary school-Purchase and Installation of 5000 litre water tank and gutters for water harvesting | 2020/21 | 100,000 | Mubere primary school, Kshs.100,000- Purchase and Installation of 3000 litre water tank at Kshs.50,000 and sub-massive motor pump and piping at Kshs. 50,000. | The school has already drilled the borehole and the management’s priority is to pump the water. | Recommended for approval |
|  | Uriri | Min 5 of 10/01/2022 | Siala Primary School- Construction of 1 classroom to completion | 2020/21 | 1,000,000 | Marungu Primary School Kshs.1,000,000- Construction of 1 classroom to completion | The schools are pre-primary institutions and their area of establishment are not government owned parcels of land | Recommended for approval |
|  |  |  | Oria Primary School-Construction of 1 classroom to completion |  | 1,000,000 | Rae Kondiala Primary School Kshs.1,000,000- Construction of 1 classroom to completion |  |  |
|  | Alego Usonga | Min 09 of 30/07/2021 | Ulafu Secondary school- Completion of 49 students laboratory block started by PTA (Roofing, finishes to wall and floor, fixing of windows, doors and painting works) | 2020/21 | 1,110,780 | Ulafu Secondary School Kshs.1,110,780- Completion of a library block started by PTA; Roofing, finishes to wall and floor, fixing of windows and doors and painting works. | The project was erroneously captured during submission of the projects proposal for 20/21 financial year | Recommended for approval |
|  |  | Min 05 of 10/01/2022 | Sirongo oware primary school- Construction of 1No. classroom to completion | 2018/19 | 1,000,000 | Sirongo Oware Primary School Kshs.89,500- Completion of 1No classroom; wall plastering, fittings of windows and doors, construction of ramps and louver vent blocks | Lack of adequate funds to complete the ongoing classroom which was started by the PTA | Pending approval NG-CDFC to clear reasons for reallocation of funds from the initial classroom |
|  | West Mugirango | Min 2 of 07/01/2022 | NHIF Social Security programme | 2021/22 | 3,000,000 | Bursary Tertiary Institutions Kshs.3,000,000- Payment of bursaries for needy students in Tertiary Institutions and vocational Institutions | There is a high number of needy students in tertiary Institutions hence the Committee found it a priority than the social security Programme | Recommended for approval |
|  |  |  | Senator Kebaso Secondary School- Additional funds for completion of the 1000 capacity multipurpose hall walling , flooring, plastering wiring, and painting |  | 3,300,000 | St. Peter Nyaisa Secondary School Kshs.3,300,000- Additional funds for completion; roofing, shuttering, plastering, flooring, wiring and painting of the 300 students capacity multipurpose hall and Kshs.600,000 for tables and seats | The outstanding balance for completion of the project is Kshs.4,300,00. Since there is an outstanding balance of Kshs.800,000, it cannot be completed. The school is non-committal on the completion of the project | Not recommended for approval Reallocation of funds from an ongoing project is against section 46 (2) of the NG-CDF Act. As per the report on ongoing projects submitted by NG-CDFC, the Multipurpose hall at Senator Kebaso Secondary School required an outstanding balance of Kshs.3.3m to ensure its completion. It was initiated in 2016/17 financial year and has so far received Kshs.2,200,000 |
|  | Bomachoge Borabu | Min 07 of 19/2/2022 | Bursary Secondary School | 2021/22 | 4,000,000 | - Omobera SDA Primary School Kshs.3,000,000- Re-construction of 3 dormitories burnt down by electric fault - Riamangata Primary School Kshs.1,000,000- Re-roofing of 8 classrooms blown off by the strong winds | Emergency funds for 2021/22 financial year is exhausted hence the Committee resolved to reallocate bursary funds in order to address the emergency concerns | Not recommended for approval Reallocation of funds away from the bursary kitty goes against the Board’s policy on bursary NG-CDFC to prioritize acquisition of revision books in 2022/23 Financial Year as a separate project The NG-CDF guidelines on administration of bursary stipulates that the Board considers bursary scheme as an important grant targeting the poorest segment of the society hence NG-CDFCs are encouraged to always allocate funds towards the scheme. The guidelines further advises the NG-CDFCs to avoid reallocating funds meant for the programme to other projects |
|  | Muhoroni | Min No.5 of 11/01/2022 | Mutwala Girls Secondary School- Fencing of 500m perimeter wall Kshs.550,000 and erecting a steel gate 4m wide x 2.5m high Kshs.100,000 | 2020/2021 | 650,000 | Mutwala Girls Secondary School, Kshs.650,000- Renovation of 4 classrooms: floor tiling, painting and repair of cracked walls | NG-CDFC confirmed that the land to be fenced still has technical issues and therefore the administration has not found a solution to it. | Recommended for approval A letter from the school requesting for the change of activity has been submitted |
|  | Lang’ata | Min no.3 of 1/2/2022 | - Uhuru Gardens primary school- Rehabilitation of a 430 sm access road and the parade area to completion; repairing of the damaged surface and replacement of the same with hardcore, supplying and spreading quarry dust blinging to the driveway, fixing 60mm thick cabro, compacting to seal all the gaps in the cabro and marking of the parking with road paint - Kenya Medical Training College, Karen- Field leveling, planting of Kikuyu grass and installation of two goal posts - NHIF social security programme- Provision of NHIF Medical Cover to 300 vulnerable persons Emergency | 2020/2021 | 1,6000,000 1,450,000 1,800,000 403,355.45 | Bursary Tertiary institutions, Kshs.13,353,355.45- Payment of bursary to needy students in colleges, universities and tertiary institutions. | There is high demand of bursary | Not recommended for approval Allocation of additional Kshs.13,353,355 would exceed 35% bursary ceiling for 2021/2022 financial year since implementation will be carried out within the financial year In 2020/21 Financial Year, the NG-CDFC allocated Kshs.30.8 million |
|  |  |  | Madaraka Primary School- i) Renovation of six classrooms on first floor to completion; (Replacement of the entire roof, terrazzo flooring, interior and exterior walls painting, replacement of windows and replacement of wooden doors with steel doors) each @ 600,000.00 = Kshs.3,600,000.00. ii) Construction of access road 950 sm, parade area and car park with cabro; Excavation of black cotton soil, backfilling, compaction, Hand-packing, Spreading quarry dust, sanding and Laying of 60mm cabro @ Kshs.4,500,000 |  | 8,100,000 |  |  |  |
|  | Dagoretti North | Min No.4 of 08/12/2021 | Emergency | 2021/2022 | 7,192,207 | Kilimani Police Station, Kshs.7,192,207- Construction of a perimeter fence around police station | The station is busy and normally holds terror suspects among other prisoners who are of interest to the State. Therefore vulnerable to terror attack considering the events that are happening in the country and neighbouring countries. | Not recommended for approval Reallocation of funds from the emergency kitty before the expiry of the financial year is against section 8 (1) of the Act which provides that “ A portion of the Fund, equivalent to five per centum (hereinafter referred to as the "Emergency Reserve") shall remain unallocated and shall be available for emergencies that may occur within the Constituency” The proposed activity is not emergency in nature hence against section 8 (3) of the NG-CDF Act, 2015 as amended in 2016 Further, the project had land dispute on its boundary which necessitated the NG-CDFC to request for change of project’s activity from construction of perimeter wall to construction of ablution block. The Board in its meeting held on 27th September, 2021 deliberated on the request and approved it A letter Ref: C/GEN/5/11/VOL.VI/189 dated 22nd November, 2021 has been submitted indicating that the station is busy and normally holds terror suspects among other prisoners who are of interest to the State. The letter further states that the station is vulnerable to terror attack considering the events that are happening in the country and neighbouring countries. |
|  | Bureti | Min No. 10 of 14/01/2022 | Ngesumin Chiefs Office- Construction of Chiefs Office to completion (Foundation, Walling, Windows, Flooring and Roofing). | 2018/19 | 599,685.76 | Sugutek Primary School, Kshs.599685.76- Renovation to completion of three classrooms: Plastering, fixing of doors and windows & painting. | The project could not be implemented due to land succession dispute challenge. | Recommended for approval. |
|  |  | Min No. 4 of 3/01/2022 | - Ngesumin Chiefs Office- Purchase of 1 Acre Land - Constituency Innovation Hubs Project (CIH)- Establishment of four innovation hubs in partnership with ministry of ICT through Telkom kenya at (i)Bureti recourse centre (ii)chemosot TTI (iii)roret youth centre (iv)Kapkatet resource centre | 2018/19 2017/18 | 160,000 1,000,000 | Tegat Primary School, Kshs.470,000- Renovation to completion of one classroom; Plastering, fixing of doors and Windows & Painting. | - Land succession dispute challenges. - The project is no longer a priority to the community. | Pending approval NG-CDFC to revise cost of the project |
|  |  |  |  |  |  | Kaptebengwet Primary School, Kshs.440,000- Final payment for purchase of 0.45 acres land inclusive land processing fee. |  | Recommended for approval The project was allocated Kshs.1,200,000 in 2020/21 financial year. NG-CDFC had submitted a land valuation report indicating that the value for a 0.45-acre piece of land costs Kshs.1,800,000 inclusive developments. NG-CDFC has also submitted sale agreement indicating that the owner of the land is wiling to sell it at kshs.1,575,000 |
|  |  |  |  |  |  | Kitait Primary School, Kshs.250,000- Final payment for purchase of 0.35 acres land. |  | Pending approval NG-CDFC to confirm how they intend to raise the balance of Kshs.130,000 for one-off purchase of the land. The NG-CDFC has submitted land valuation reporting indicating that the land is 0.35 acres valued at Kshs.690,000 and has no encumbrances. The NG-CDFC has also submitted a sale agreement indicating that the owner is willing to sell it at Kshs.680,000 |
|  |  |  | Kitait Primary School, Kshs.300,000- Land purchase 0.3 Acre to completion. | 2019/20 | 300,000 | Kitait Primary School, Kshs.300,000- Purchase of 0.35 acres of land. | The actual size of the land to be purchased was found to be 0.35 acres after the survey and not 0.3 acres as earlier proposed. |  |
|  |  | Min No. 4 of 7/02/2022 | Kipkerieny Secondary School- Land Purchase 0.5 Acre to completion | 2019/20 | 800,000 | Kipkerieny Primary School, Kshs.800,000- Renovation of Eight classrooms; Plastering, glazing and Painting. | Land succession dispute challenges. | Recommended for approval. |
|  |  | Min No. 10 of 23/02/2022 | Lalwat Primary School- Land purchase 0.35Acre to completion | 2019/20 | 700,000 | Lalwat Primary School, Kshs.700,000- Purchase of 1 acre piece of land including processing of title deed. | The school convinced the land owner to sell them 1 acre and not the earlier agreed 0.35 acres so that school can get enough playing ground for the students. | Recommended for approval The project was also allocated Kshs.1,970,000 in 2019/20 financial year. The NG-CDFC has submitted land valuation report indicating that the land is valued at kshs.2.6 million and has no encumbrances |
|  |  | Min No. 4 of 1/03/2022 | Kaproret Day Secondary School- Land purchase 2.6 Acre-Final payment | 2019/20 | 3,200,000 | Kaproret Day Secondary School, Kshs.3,200,000- Completion of four classrooms storey building; casting of suspended slab, flooring, glazing, fixing of doors and painting. | The school experienced challenges with the land seller who refused to receive the final payment arguing that the value had gone up. | Recommended for approval. The project was allocated Kshs.2.5 million in 2020/21 financial year |
|  | Cherangany | Min 8 of 16/2/2022 | Ekegoro Secondary School- Completion of two classrooms-plaster, flooring, windows and doors, paining and labelling | 2017/18 | 500,000 | Ekegoro Secondary School, Kshs. 500,000-constrcution of two door pit latrines for girls to completion. | The school was allocated Kshs.600,000 in 2019/20 for completion of the same classrooms. | Pending approval NG-CDFC to confirm whether the pit latrine will be user friendly and accessible to PWDs |
|  |  |  | Bursary tertiary institutions | 2021/22 | 6,881,199.01 | Bursary secondary schools, Kshs.6,881,199.01-Payment of bursary to needy students in secondary schools | There was high number of secondary school bursary applicants as compared to students in tertiary institutions. | Recommended for approval |
|  | Subukia | Min No. 3 of 3/02/2022 | NG-CDF Office- Construction of constituency office to completion | 2018/19 | 3,550,000 | NG-CDF Office, Kshs.1,250,000-Final payment for purchase of 0.25 hectares of land. | The NG-CDFC has not acquired the land for construction of the office. | Recommended for deferral Management to seek guidance of the Legal Services Department upon which the matter will be brought for discussion at the Board NG-CDFC to submit correct 1st and 3rd schedules. NG-CDFC has submitted land valuation report indicating that the land was valued at Kshs.3.8 million and has no encumbrances Further, attached a letter from the ministry of lands and physical planning dated 20th September, 2021 indicating the valuation of the land is Kshs.3.8 million and offer price from the vendor is Kshs.4,250,000 NG-CDFC was advised to note that they can negotiate purchase of the land to below or above valuation figure as long as it is within the margin of not more than 10% of the value. The project was allocated Kshs.3 million in 2018/19 financial year for purchase of 0.25 hectares of land. |
|  |  |  |  |  |  | Ndungiri Primary School, Kshs.1,300,000- Renovation to completion of 8 roomed administration block; flooring with tiles, plumbing works, construction of extra walls, plastering and painting. |  | Not recommended for approval As per the Board’s circular dated 26th August, 2021, constituencies that have not constructed offices were advised to set aside funds for construction of NG-CDF Committee offices. The NG-CDFC is therefore advised to prioritize construction of the office. NG-CDFC to submit correct 1st and 3rd schedules. |
|  |  |  |  |  |  | Subukia Chief’s office, Kshs.1,000,000- Completion of a 3 roomed chief’s office; flooring with tiles, plumbing works, electrical works, painting and construction of extra offices (registry of persons, registry of death/ birth offices and cells). The project has so far received Kshs.1 million |  | Not recommended for approval As per the Board’s circular dated 26th August, 2021, constituencies that have not constructed offices were advised to set aside funds for construction of NG-CDF Committee offices. The NG-CDFC is therefore advised to prioritize construction of the office. NG-CDFC to submit correct 1st and 3rd schedules. |
|  |  | Min No.1 of 18/1/2022 | Wiyumiririe Assistant Chief’s Office- Construction of 3 roomed chief’s office to completion. | 2021/22 | 1,000,000 | Gakingi Chief’s Office, Kshs.1,000,000- Construction of 3 roomed chief’s office. | The initial approved project is complete and in use but was erroneously captured in the proposal | Pending approval NG-CDFC to specify the estimated cost of the project. NG-CDFC has submitted a photo of the complete Wiyumiririe Assistant Chief’s office funded by the NG-CDF |
|  | Kiambaa | Min 04 of 02/02/2022 | Gatatha Primary School -Renovation of 10 classrooms; flooring with tiles, painting of walls and roof to completion | 2021/2022 | 2,000,000 | Gatatha Primary School Kshs.2,000,000- Construction to completion of a 7.8m by 6.2m school kitchen at Kshs.1,187,550; Provision of fascia and rainwater goods for 9 classrooms and purchase of 2 no. 10,000 litres plastic water tanks and construction to completion of concrete water tank platforms at Kshs.812,450 | The change of activity was necessitated by the submitted BQs after consultation with the project management committee and clerk of works | Pending approval NG-CDFC to provide clear reason for change of project’s activity NG-CDFC to split cost for provision of fascia and rainwater goods for 9 classrooms and purchase of 2 no. 10,000 litres plastic water tanks and construction to completion of concrete water tank platforms |
|  |  |  | Kihara Primary School- Renovation of 10 classrooms to completion; flooring with tiles, painting of walls and roof | 2021/2022 | 2,000,000 | Kihara Primary School Kshs.2,000,000-Renovations to completion by terrazzo floor finish in the staffroom, one classroom and all school corridors at Kshs.902,200. Wall plastering and painting externally and internally in 10 classrooms at Kshs.654,815, painting to 10 doors, 10 windows and existing roofing sheets for 10 classrooms at Kshs.442,985 |  | Pending approval NG-CDFC to provide clear reason for change of project’s activity. NG-CDFC to provide clear description of the project’s activity |
|  |  |  | Muongoiya Primary School- Renovation of 10 classrooms: Flooring with tiles, painting of walls and roof. | 2021/2022 | 2,000,000 | Muongoiya Primary School Kshs.2,000,000- Renovations to completion by wall plastering and painting, floor tiles finish and painting to doors and windows of the school hall at Kshs.289,130. External work hardcore and cabro paving in front of 8 classrooms (322 SQ) at Kshs.1,260,870, provision of electricity installation power connection and light fittings in 8 classroom Kshs.450,000 |  | Pending approval NG-CDFC to provide clear reason for change of project’s activity NG-CDFC to provide clear description of the project’s activity |
|  |  |  | Karuri Primary School - Construction of 3 classrooms with a slab to completion | 2021/2022 | 5,000,000 | Karuri Primary School, Kshs.5,000,000 Renovation to completion of 15 classrooms: Painting to the existing roofing sheets and fascia board Kshs.776,660, window glazing and painting to windows Kshs.178,350. Replacement of 2 timber doors with steel casement doors Kshs.129,750. Internal and external walls plaster and painting Kshs.1,341,750.00, hacking existing floor and installation of ceramic floor tiles to 15 classrooms Kshs.2,573,490 |  | Pending approval NG-CDFC to provide clear reason for change of project’s activity |
|  |  |  | Kagongo Police Post Kshs.3,000,000- Construction of reporting office to lintel level at Kshs.1,000,000 and 5 (1 bedroomed) Police residential houses to lintel level at Kshs.2,000,000 | 2020/2021 | 3,000,000 | Kagongo Police Post Kshs.3,000,000- Purchase of 0.033 HA land for the construction of police post Plot no. KIAMBAA/KIHARA/8247 |  | Pending approval NG-CDFC to submit a copy of land search and provide reasons for the change of activity NG-CDFC has submitted a land valuation report by Kiambu District Land Valuer indicating that the land is approximately 0.033 hectares registered in the name of Wainaina Munga on Freehold tenure with no encumbrances. The land is valued at Kshs.3,000,000. A copy of the title deed has also been submitted. |
|  | Ndia | Min 003 of 04/01/2022 | Upper Baricho Primary School - Installation of bakery accessories; oven convection 10 tray tecnodom Kshs.1,593,560, 2 tallboy trollie for oven Kshs.170,000, 2 single bowl sink Kshs.110,000, work top central Kshs.62,200, pastry preparation table Kshs.102,320, 2 dough mixers spiral 60 litres prism Kshs.999,920, bench sheeter Kshs.754,000, square neutral display Kshs.208,000 | 2021/2022 | 4,000,000 | Upper Baricho Primary School Kshs.4,000,000- Renovation to completion of 7 classrooms: Box profile roofing, plastering, flooring, tiling, fixing of metal doors and windows and gutters for water collection. | The priority of the school is a total facelift to enable learners and teachers have a good environment. | Recommended for approval The NG-CDFC has submitted letter from the school requesting for the change of project’s activity. |
|  | Ainamoi | Min No.6 of 15/12/2021 | Torsogek Primary School- Completion of 2 No. classrooms - roofing, internal wall plastering, floor screed, ceiling, door/windows fittings, ceiling painting | 2016/17 | 44,400 | Torsogek Primary School, Kshs.44,000- Renovation to completion of two classrooms; flooring with red oxide. | Unspent balance after implementation of the project | Pending approval NG-CDFC to reduce the scope of works to ensure that the Kshs.44,000 is adequate |
|  |  |  | Bursary Tertiary Institutions- Payment of bursary to needy students in Secondary School | 2021/22 | 8,000,000 | Bursary Secondary School, Kshs.8,000,000- Payment of bursary to needy students in Secondary School | Needy students for secondary schools were more compared to those from tertiary institutions. | Recommended for approval |
|  | Olkalou | Min 01 of 18/02/2022 | - Captain Primary School - Construction of a six door toilet with 1 unit for PWLD to completion - Wiyumiririe Primary School- Renovation to completion of two classrooms: Plastering, painting, iron sheets replacement, flooring and fascia board fixing - Mirangine Primary School -Renovation to completion of four classrooms: Plastering, flooring and iron sheets replacement - Mukindu Primary School- Renovation to completion of three classrooms.: Roof replacement - Gachwe Police Post - Construction of one residential room measuring 12 feet square - Kandutura Police Post-Construction of one residential room measuring 12feet square - Sports activities - Organising sports tournaments and buying balls and uniforms for teams within the constituency | 2021/ 2022 | 900,000 696,000 1,160,000 696,000 638,000 580,000 1,005,200 | Bursary Secondary Schools Kshs.10,500,000 – Payment of Bursary to needy students | - | Not recommended for approval There was no indication that the initial approved projects were no longer required |
|  |  |  | - Mirangine Secondary School -Completion of 500 students capacity dining hall: plastering painting and extension of a kitchen and a small store. - Mawingu Secondary School - Completion of 100 students capacity dining hall: Plastering, painting and extension of a kitchen and a small store. - Mugathika Primary School - Completion of administration block comprising of four offices: Roofing and walls plastering. |  | 1,832,800 1,832,800 1,160,000 |  |  | Not recommended for approval Reallocation funds from ongoing project is against Section 46(2) of the NG-CDF Act 2015 as amended in 2016 |
|  | Kandara | Min 5 of 27/01/2022 | - Mugaa-ini Primary School - Renovation by plastering, roof repairs, fixing metal doors and windows, verandas, painting and tiling of 6 classrooms, hall and office to completion - Mugecha Primary School Kshs.4,403,133 - Renovation by plastering, roof repairs, fixing metal doors and windows, verandas, painting and tiling of 9 classrooms to completion - Thagari Primary School Kshs.4,205,796 Renovation by plastering, roof repairs, fixing metal doors and windows, verandas, painting and tiling of 9 classrooms office and staffroom to completion | 2021/2022 | 3,150,000 4,403,133 4,205,796 | Mugaa-ini Primary School Kshs.4,403,133- Renovation to completion by plastering, roof repairs, fixing metal doors and windows, verandas, painting and tiling of 6 classrooms, hall and office | The amounts allocated to the projects were erroneously interchanged during the projects proposal submission process as the approved amounts do not tally with the amounts in the BoQs. | Recommended for approval |
|  |  |  |  |  |  | Mugecha Primary School Kshs.4,205,796- Renovation to completion by plastering, roof repairs, fixing metal doors and windows, verandas, painting and tiling of 9 classrooms |  | Recommended for approval |
|  |  |  |  |  |  | Thagari Primary School Kshs.3,150,000- Renovation to completion by plastering, roof repairs, fixing metal doors and windows, verandas, painting and tiling of 9 classrooms, office and staffroom |  | Recommended for approval |
|  |  |  | Karigu-ini Secondary School- Construction to completion of 50 capacity students’ science laboratory with slab, reinforced concrete, walling windows, doors and finishes. | 2021/2022 | 4,149,280 | Waitua Secondary School, Kshs.4,149,280- Construction to completion of 50 capacity students’ science laboratory with slab, reinforced concrete, walling windows, doors and finishes. | Waitua Secondary School requires the laboratory to enable registration of the Institution. | Not recommended for approval There was no indication that Karigu-ini Secondary School no longer required a laboratory |
|  | Kiambu Town | Min 4 25/01/2022 | Emergency | 2020/2021 | 2,192,707 | Chief Wandie Primary School Kshs.1,192,707- Additional funds for construction of a Modern kitchen to accommodate 6 energy saving cookers. | Unspent emergency funds | Pending approval NG-CDFC to specify the contract sum of the project and the activities to be undertaken with the allocated amount NG-CDFC to submit correct 4th schedule The project has so far received Kshs.4.5 million |
|  |  |  |  |  |  | Kiamumbi Police Post Kshs.1,000,000- Additional funds for construction of 7 roomed offices for the police with a capacity of hosting 15 Officers. |  | Pending approval NG-CDFC to specify the contract sum of the project and the activities to be undertaken with the allocated amount NG-CDFC to submit correct 4th schedule The project has so far received Kshs.5 million |
|  |  |  | Ngegu Primary School Kshs.2,500,000- Vertical extension of 2 classrooms: Reinforcement of ground floor of existing 2 classrooms & construction of roof slab. | 2021/2022 | 2,500,000 | Ngegu Primary School Kshs.2,500,000- Facelift and renovations of 9 classrooms: tiling, plastering and painting of walls and roof. | The school no longer requires more classrooms following the introduction of new education system in Kenya that is currently set to replace the 8-4-4 education system from class 7 and 8 to lower secondary leaving 8 classrooms unoccupied. | Pending approval NG-CDFC to specify the estimated cost of the renovations works |
|  | Sirisia | Min No 4 of 29/11/2021 | Nasala primary school- Renovation of 3 classrooms: shutters, plastering, painting, flooring to completion | 2020/21 | 1,500,000 | Nasala Primary School, Kshs.1,500,000 – Additional funds for construction of three classrooms. | The classrooms initially meant to be renovated were mud walled and could not be renovated | Pending approval NG-CDFC to specify the activities to be undertaken with the allocated funds. The project was allocated Kshs.1.5 million in 2021/22 financial year |
|  | Webuye East | Min N0. 21 of 23/09/2021 | Emergency | 2018/19 | 2,006,201.38 | Webuye Police Station, Kshs.2,006,201.38– Fencing of 3 acres of land using concrete posts and chain-link plus installation of 2 gates to completion. | Unspent balance | Pending approval NG-CDFC to submit correct 3rd and 4th schedules capturing the correct project amount |
|  | Mumias West | Min No.4 of 15/12/2021 | Musanda Primary School- Installation of 8No. 200W, 24Vsolar panels and storage power batteries, solar panel tower 3M high, associated civil works, water pipeline and submerged solar pumps | 2020/21 | 2,000,000 | Imanga police post, Kshs.1,000,000– Purchase of 2 plots (1/4 acre) including survey, valuation and title processing fee | The feasibility report from works officer indicates that the borehole has a small casing size that cannot fit a big pump intended to deliver water to nine institutions including Musanda Primary School namely: Musanda Secondary, Milimani Girls Secondary, Milimani Primary, Buriya Primary, Lusheya Primary, Eshihaka Secondary, Eshihaka Primary and Musanda Police station (Report attached) | Pending approval NG-CDFC to submit properly compiled minutes capturing correct land sizes NG-CDFC to submit 1st, 3rd and 4th schedules The NG-CDFC has forwarded the land valuation reports indicating that the land to be bought for Imanga police post is ¼ acre and is valued at Kshs.1 million while that of Iyabo Secondary School is 2 acres valued at Kshs.1 million. Both the lands have no encumbrances |
|  |  |  |  |  |  | Iyabo Secondary School, Kshs.1,000,000- Purchase of 2 acres of land including survey, valuation and title processing fee |  |  |
|  |  | Min No.4 of 08/08/2021 | Booker Primary School- Renovation to completion of (2No.) classrooms- (casting of ring beam, wall plate construction, re-roofing, ceiling board fixing, construction of verandah, repair of wall and floor, electrical fittings and painting. | 2020/21 | 1,300,000 | Booker primary School, Kshs.1,300,000- Renovation to completion of 5No. classrooms: Replacement of damaged roofing sheets and ceiling boards with new ones at Kshs.140,000, Repairs to damaged ordinary floor screed to Terrazzo finishes at Kshs.990,000 and painting works to ceiling board area and walls internally to the repaired classrooms at Kshs.170,000. | The roof and ring beam are intact apart from few damaged iron sheets. Major damages are on ordinary floors screed necessitating use of terrazzo. Reduction in scope of activities has increased the no. of classrooms to be renovated from 2 to 5. | Recommended for approval |
|  |  |  | Nyakwaka Primary School- Renovation of (4) classrooms (re-roofing, casting of ring beam, wall plate construction, verandah, repair of walls and floor, electrical fittings and painting). | 2020/21 | 2,000,000 | Nyakwaka Primary School- Construction to completion of 1No. Classroom at Kshs.1,300,000, Construction of 6 door Pit latrine for Girls at Kshs. 550,000, supply of 13 desks at Kshs.50,000 and completion of gate & fence- (Plaster works and painting works to the gate wall) at Kshs.100,000 | The overwhelming school population necessitates need for more new classrooms and sanitary facilities. | Pending approval NG-CDFC to confirm if the pit latrines will cater for PWDs Kshs.450,000 was allocated in 2021/22 financial year for construction of the fence and gate |
|  |  | Min No.4 of 21/02/2022 | - Eshikulu Police Post, Kshs.1,100,000 - Purchase of 2 plots (50x100)-Kshs.660,000. Construction of gate and fence for 0.25 acre land with treated celcured posts and barbed wire- Kshs.440,00 - Sports project, Kshs.2,700,000 - Organizing of football & netball tournaments with participating teams being provided sports kits i.e. balls & uniforms. | 2021/22 2020/21 | 1,100,000 1,000,000 | Mumias Muslim Primary School, Kshs.2,100,000 – Construction of gate and fence (construction of gate wall & pillars to completion and construction perimeter wall –dwarf wall with blocks and spiked grills (110M) fence | - There is another police post within the same ward and the area is sparsely populated with minimal crime rate. The available police post will adequately serve the constituent - The sports funds were not used due to delay in disbursement. | Pending approval NG-CDFC to provide clear description of the proposed project. The estimated cost of the project is Kshs.2,350,000. The NG-CDFC has therefore committed to allocate the balance of Kshs.250,000 in 2022/23 Financial Year |
|  | Nyeri Town | Min 003 of 08/07/2021 | Kahiga Primary School- Renovation of 3 classrooms; roofing, plastering, fabrication of doors and windows, rendering, floor finishing and painting. | 2018/2019 | 1,200,000 | Kahiga Primary School Kshs.1,200,000- Fencing of the school’s 10-acre piece land with concrete poles. | The classrooms were renovated by an N.G.O called KEDOVO, who took over and renovated the whole school. The school letter has also been attached. | Pending approval NG-CDFC to confirm whether the funds are adequate to complete the project |
|  |  |  | Nyaribo Secondary School - Construction of 1 classroom; substructure, walling and roofing to completion Kshs.1,100,000 and purchase 65 desks Kshs.400,000 | 2018/2019 | 1,500,000 | Nyaribo Secondary School Kshs.2,900,000- Construction of 100 students’ capacity dining hall. | The Ministry of Education through Economic stimulus fund (ESP) had constructed two classrooms for the school | Pending approval NG-CDFC to specify the estimated cost of the project |
|  |  |  | Nyaribo Secondary School - Construction Of 1 Classroom to completion at Kshs. 1,200,000 and Purchase of office furniture( (10 chairs and 4 tables) at Ksh. 200,000 | 2019/2020 | 1,400,000 |  |  |  |
|  |  |  | Rware High School- Renovation of 8 classrooms: roofing, plastering, fabrication of doors and windows, rendering, floor finishing and painting to completion | 2019/2020 | 2,500,000 | Rware High School Kshs.2,500,000- Completion of an administration block: Plastering, flooring, doors, windows and roofing. | Renovation works were done by parents | Pending approval NG-CDFC to specify capacity of the administration block NG-CDFC to clarify on who initiated the construction of the administration block The school was allocated Kshs.1.5 million in 2021/22 financial year for rehabilitation of 10 offices administration block; flooring, plastering, painting, to completion. |
|  | Kiharu | Min 04 of 25/01/2022 | Goods and Services (Administration vote) - Repairs and maintenance, printing, stationery, telephone, travel and subsistence, fuel, hospitality, office tea | 2020/21 | 1,300,000 | - Kirogo Primary School, Kshs.1,000,000 - Renovation to completion of 7 classrooms by floor hacking, screeding and tiling, plastering, glazing and painting. - Gituto Primary School Kshs.300,000 - Renovation to completion of 2 classrooms by installation of steel doors to replace wooden ones, plastering, glazing, finishes by keys and moldings. | Unutilized funds due to slow down of NG-CDFC activities as a result of COVID-19 Pandemic | Pending approval NG-CDFC to submit properly compiled minutes |
|  |  |  | Committee Expenses (Administration vote) - Payment of Committee sitting allowances, transport, conferences | 2020/21 | 1,500,000 | - Kiangochi Primary School Kshs.600,000- Renovation to completion of 5 classrooms by floor hacking, screeding and tiling. - Upendo Primary School Kshs.600,000 - Renovation to completion of 5 classrooms by floor hacking, screeding and tiling. - Kagumo Primary School Kshs.300,000- Renovation to completion of 2 classrooms by tilling, glazing and finishes by keys and moldings. |  | Pending approval NG-CDFC to submit properly compiled minutes |
|  |  |  | Goods and Services (Monitoring and Evaluation vote) | 2020/21 | 1,000,000 | - Kambirwa Primary School Kshs.600,000- Renovation to completion of 5 classrooms by floor hacking, screeding and tiling. - Thengeini Primary School Kshs.400,000- Renovation to completion of 3 classrooms by tiling, glazing, finishes by keys and moldings. |  | Pending approval NG-CDFC to submit properly compiled minutes |
|  | Matungulu | Min 06 of 10/01/22 | Katulye Primary School- Construction of 1 classroom to completion | 2020/21 | 1,200,000 | Katulye Secondary School, Kshs.1,200,000 Construction of 1 classroom to completion | Katuyle primary school does not exist | Recommended for approval |
|  |  |  | Nguluni SA Primary School- Construction of 2 classrooms to completion |  | 2,400,000 | Tala SA Primary School, Kshs.2,400,000- Construction of 2 classrooms to completion | Nguluni SA primary school does not exist but the school is registered as Tala SA Primary school in Nguluni area | Recommended for approval |
|  | Changamwe | Min 12 of 3/12/2021 | Kipevu Primary School-Renovations of 9 classrooms (removal of asbestoses-roofing, painting) | 2019/20 | 158,000 | Kipevu primary school, Ksh.158,000-Renovation of water system (servicing of borehole Kshs.50,000, piping Kshs.95,500, WRA fee Ksh.12,500) | Unspent funds after completion of the project | Not Recommended for approval The proposed activities are recurrent in nature hence against the NG-CDF Act |
|  |  | Min 17 of 6/01/2022 | Changamwe Girls Secondary School-Purchase of 6 no 4-drawer steel cabinet @ Kshs32,000 totaling to Kshs.192,000, 10 no visitors fabric chairs @Kshs.15,000 totaling to Kshs.150,000, 2 no executive table @Kshs.60,000 totaling to Kshs.120,000, 2 no high back leather chairs @Kshs.30,000 totaling to Kshs.60,000 | 2021/22 | 500,000.00 | Changamwe Girls Secondary School, Ksh.500,000-Purchase of laboratory equipment (twenty Burettes, ten pipette, conical flash, thermometer, ten beakers 250ml, ten beakers 100ml, 10 Volumetric flask, dropper, twenty tripod stand, 2 Retort stand complete with bos and clamps, forty test tubes with racks, ten test tube holders, five boiling tube wire gauze, ten funnels, Vernier caliper, five micro meter screw gauge, magnet, meter rule, ammeter, voltameter, Ball and ring, pendulum bob, permenet slides, five hand lens, five magnify lens, twenty coneve and convex mirror & lenses, 5 glass prisms, optical pin & soft board and five microscopes | The school is in urgent need of the laboratory equipment | Recommended for approval |
|  | Msambweni | Min 3 of 2/2/2022 | Funzi police post - Renovation of 5 roomed police staff quarters of 5 x 4 metres each, kitchen consisting of a cooking area and store of 8 x 6 metres plus exterior veranda of 8 x 6 metres to (Re-roofing, flooring, plastering, painting, ceiling and electrical Installations to completion). | 2020/21 | 1,500,000 | Mabatani primary school, Kshs.1,500,000 – Construction of one classroom to completion at Kshs.1,200,000 and purchase of sixty desks at Ksh.5,000 per desk. | The renovation of Funzi police post has already been done by a donor | Pending approval NG-CDFC to submit correct 1st and 3rd schedules. |
|  | Rongai | Min No.4 of 1/03/2022 | Salgaa Police Station -Construction of four offices and one holding cell to completion. | 2021/22 | 2,100,000 | Salgaa Police Station, Kshs.2,100,000- Construction of a police station comprising of eight offices, three holding cells and armoury. | The activity was erroneously captured as construction of 4 offices yet the actual plan involves construction of one block comprising of 8 office three holding cells and armoury. | Recommended for approval |
|  | Narok North | Min No.5 of 17/02/2022 | Narok North NG-CDFC Motor Vehicle- Purchase of 10-seater HZJ79R-RKMRS Toyota Land cruiser –hardtop, four door model, 4-wheel drive for office use. | 2020/21 | 10,000,000 | - Oleserian Primary School, Kshs.2,400,000- Construction to completion of two classrooms. - Nairenke Primary School, Kshs.1,200,000- Construction to completion of one classroom. - Olokuseroi Primary School, Kshs.1,200,000- Construction to completion of one classroom. - Makutano Primary School, Kshs.1,200,000- Construction to completion of one classroom. - Naisoya Primary School, Kshs.1,300,000- Purchase of 96 mettalic double decker beds at Kshs.13,541.67 each - Olekenta Primary School, Kshs.1,200,000- Construction to completion of one classroom. - Iltareto Secondary School, Kshs.1,500,000- Construction to completion of one staff house with one bedroom, kitchen and living room. | The quotations received for the vehicle from Toyota Kenya was high amounting to Kshs.10,380,049 and later they became out of stock. As at the moment, the vehicle costs Kshs.11,870,000 as per the government tender document for motor vehicles. | Not recommended for approval All NG-CDFC are required to own a vehicle to facilitate smooth operations especially during monitoring of projects NG-CDFC is advised to consider other models or allocate additional funds for purchase of the vehicle in 2022/2023 financial year. |
|  | Mbeere South | Min No. 600 of 13/07/2021 | Machang’a Secondary School-Roofing of multipurpose hall of 300 sitting capacity. | 2020/21 | 1,050,000 | Machang’a Secondary School, Kshs.1,050,000- Flooring and plastering of a 300 sitting capacity dining hall initiated by parents to completion | Roofing was done by parents due to its urgency. | Pending approval. NG-CDFC to clarify on whether the facility is a multipurpose hall or a dining hall. |
|  |  |  | Ikomenie Primary School-Renovation of 3 classrooms by plastering, painting, flooring and roofing to completion | 2020/21 | 700,000 | Ikomenie Primary School, Kshs.700,000- Construction of one block eight doors pit latrine to completion with two units for person with disability | The school was advised by the Ministry of Works against renovation of the classrooms on technical grounds. | Recommended for approval |
|  |  |  | Nyambori Primary School- Construction of administration block up to roofing level comprising of 2 roomed offices and 1 staffroom. | 2020/21 | 1,500,000 | Nyambori Primary School, Kshs.2,800,000- Construction of two classrooms to completion at Kshs.2,400,000 and a construction of four-door pit latrine with two units for person with disability to completion at Kshs.400,000 | The school has a big problem of classrooms since some pupils are learning under the tree and others are sharing classrooms. | Recommended for approval |
|  |  |  | Nyambori Primary School- Completion of administration block comprising of 2 roomed offices and 1 staffroom; roofing, fixing of doors and windows, glaciers plastering, ceiling, flooring and painting | 2021/22 | 1,300,000 |  |  |  |
|  |  |  | Mayori Primary School-Renovation of 3 classrooms including flooring, plastering and roofing | 2019/20 | 500,000 | Mayori Primary School, kshs.570,000- Renovation of 3 classrooms including flooring, plastering, windows glacier and painting to completion | The allocated amount is not adequate to do renovation of 3 classrooms including roofing, plastering and flooring to completion | Pending approval NG-CDFC to reduce the scope of work to ensure that renovations for each classroom is done one off to completion |
|  |  |  | Mayori Primary School- Renovation of 3 classrooms including flooring and re-roofing to completion | 2020/21 | 70,000 |  |  |  |
|  |  |  | Mutuobare Primary School- Grading of playground and installation of sports facilities and goal posts | 2019/20 | 1,500,000 | Mutuobare Primary School, Kshs.1,500,000- Renovation of 2 classrooms: flooring, plastering and painting to completion at Kshs. 500,000 and fencing of school compound 2 acres with concrete posts and barbed wire at Kshs.1,000,000 | The school does not have enough space to do grading of the playground | Recommended for approval |
|  |  |  | Jeremiah Nyagah Technical Institute-Acquisition of a new Mango juice processing preparation plant machine (palber | 2018/19 | 1,900,000 | Jeremiah Nyagah Technical Institute, Kshs.3,000,000-Proposed construction of a perimeter wall 130 meters | It was impossible to get mango processing unit with the funding of Ksh. 3,000,000 | Recommended for approval. NG-CDFC has submitted BoQ indicating that the project is estimated to cost Kshs.3,055,465 |
|  |  |  | Jeremiah Nyaga Technical Institute-Acquisition of a new mango juice preparation plant machine(palber) | 2019/20 | 1,100,000 |  |  |  |
|  |  |  | Kangungi Primary School- Completion of a 45-student capacity laboratory including installation of gas system and fune chamber (Project was started by parents) | 2021/22 | 1,500,000 | Kangungi Secondary School, Kshs.1,500,000- Completion of a 45-student capacity laboratory initiated by parents: installation of gas system and fume chamber. | There was a typing error for the project name. It should read Kangungi Secondary School not Kangungi Primary School | Recommended for approval. |
|  | Emgwen | Min 4 of 29/2/2022 | St Roberts Arwos Primary School- Purchase of 52-seater school bus | 2019/2020 | 9,762,300 | St Roberts Arwos Secondary School, Kshs.9,762,300- Purchase of 52-seater school bus | Erroneously captured during as primary school during submission of the proposal | Pending approval Management to confirm that St Roberts Arwos Secondary School proposed purchase of the bus during public participation The NG-CDFC has submitted quotation from Isuzu East Africa indicating that the bus costs Kshs.9,762,300 |
|  | Kilifi South | Min 07/03/02/2022 | - Chasimba Chiefs Office- Construction of 1No. 3door pit latrine. - Chonyi Police Station - Purchase of 5000 litres tank @Kshs.45,000 water tank and plumbing work at Kshs.55,000 and construction of 20ft concrete water tank stand/tower to completion. - Kitsoeni Assistant Chiefs office –Construction of assistant chief’s office to completion. - Chonyi Sub-County Education Office – Construction of a modern 2door toilet structure - Shariani Chiefs School– Construction of 1No. 3door latrine. | 2021/22 | 650,000 700,000 2,500,000 940,000 650,000 | Bursary, Kshs.7,500,000 – Bursary for secondary schools needy cases | Due to overwhelming requests for bursary because parents have not been able to pay fees due to the effects of Covid pandemic | Not recommended for approval There was no indication that the initial approved projects were no longer required |
|  |  |  | Mtepeni Primary School-Construction of 2 classrooms, 2No. 3door pit latrines and purchase of 60 desks. |  | 4,060,000 | Gandani Chonyi Primary School, Kshs.1,000,000 – Purchase of revision books for the new Gandini Chonyi Primary School library Shariani Primary School, Kshs.1,000,000 – Purchase of revision books for the new Shariani Primary School library | Urgent need of revision book | Not recommended for approval There was no evidence that Mtepeni Primary School no longer required the classrooms NG-CDFC to allocate funds towards purchase of revision books in 2022/23 Financial Year |
|  | Kabuchai | Min No. 4 of 1/12/ 2021 | Chwele Police Station- Construction of Administration Block (6 offices, male, female & juvenile cells, armoury & exhibit store) to suspended slab. | 2020/21 | 4,400,000.00 | Misiri Primary School- Renovation of eight (8) number classrooms: replacement of roof, shutters, plastering, flooring and painting to completion | The police station does not have adequate land for the construction of offices | Pending approval NG-CDFC to submit verifiable evidence indicating that the police station does not have adequate land for the construction of offices |
|  | Embakasi South | Min 03 of 25/1/2022 | Njenga Primary School- completion of field rehabilitation works by, filling with red soil, plant grass and install new 2 goal posts and mark the field | 2018/19 | 7,000,000 | - Kware Primary School Kshs.3,800,000- Construction of 9 door toilet block (one door reserved for PWD and urinal - Kware Secondary School Kshs.3,200,000- Construction of 9 door toilet block (one door reserved for PWD and urinal | There is a land dispute communicated by the legal department through a letter dated 27th July 2021. | Pending approval NG-CDFC to submit certified cost estimates and assign two units for PWDs to cater for male and female |
|  |  |  | Kwa Njenga Primary School- Construction of a two storey library with a capacity of 300 persons to completion, inside partitioning to get the librarian office, spacious study areas, reception, six washrooms, a computer room and a store. | 2020/21 | 6,000,000 | - Kwa Reuben Secondary School Kshs.3,800,000- Construction of 9 door toilet block (one door reserved for PWD and urinal - Kware Secondary School Kshs.600,000- Additional funds for construction of 9 door toilet block (one door reserved for PWD and urinal; plastering, flooring and painting |  |  |
|  |  |  |  |  |  | - Kwa Reuben Secondary School Kshs.1,600,000-Installation of 30 metres high security mast with 8 electricity powered, 300 watts floodlights, construction of concrete, solid 10 feet deep slab base with anchor bolts (total allocation towards the project amounts to Kshs.4,602,162 |  | Pending approval NG-CDFC to submit certified cost estimates/contract documents |
|  |  |  | Imara Secondary School- Construction of 4 classrooms with a roof slab and stair case Kshs.8,000,000 to completion and construction of two door washrooms to completion Kshs.1,000,000 | 2020/2021 | 9,000,000 | Kware Primary School Kshs.1,549,500- Additional funds for construction of administration block comprising of 5 offices and 8 classrooms; extra works on the substructure, deep excavation, land reclamation and ground beams | Lack of land for implementation of the project | Pending approval NG-CDFC to submit certified issued instructions from the project manager and the contract documents NG-CDFC to request for change of project’s activity for funds allocated in 2019/20 and 2020/21 financial years Management to carry out project verification visit In 2019/20 financial year, the school was allocated Kshs.8,000,000 for construction of 4 classrooms with a roof slab and staircase. In 2020/21, the school was allocated Kshs.5,000,000 for construction of administration block |
|  |  |  |  |  |  | Kware Secondary School Kshs.2,117,225- Additional funds for construction of administration block comprising of 5 offices and 4 classrooms; extra works on the substructure, deep excavation, land reclamation and ground beams |  | Pending approval NG-CDFC to submit certified issued instructions from the project manager and the contract documents NG-CDFC to request for change of projects activity for funds allocated in 2019/20 and 2020/21 financial years Management to carry out project verification visit In 2019/20 financial year, the school was allocated Kshs.8,000,000 for construction of 4 classrooms with a roof slab and staircase. In 2020/21, the school was allocated Kshs.5,000,000 for construction of administration block |
|  |  |  |  |  |  | Kwa Reuben Secondary School Kshs.3,200,480- Additional funds for construction of administration block comprising of 5 offices and 4 classrooms; extra works on the substructure, deep excavation, land reclamation and ground beams |  | Pending approval NG-CDFC to submit certified issued instructions from the project manager and the contract documents NG-CDFC to request for change of projects activity for funds allocated and 2020/21 financial year Management to carry out project verification visit The project was allocated Kshs.9,000,000 in 2020/21 financial year for construction of 4 classrooms with a roof slab, stair case two door washrooms to completion. Additional kshs.4,258,910 was allocated in 2021/22 to complete the project hence totaling to Kshs.13,258,910 |
|  |  |  |  |  |  | Assistant County Commissioner’s Office Kshs.965,578- Additional funds for construction of Assistant County Commissioner’s office; extra works on the superstructure roofing, partitioning and exterior plastering and finishes |  | Pending approval NG-CDFC to clarify when the project was allocated funds NG-CDFC to submit certified issued instructions from the project manager and the contract documents Management to carry out project verification visit |
|  |  |  |  |  |  | AA Villa Police Station Kshs.465,055- Additional funds for construction of AA Villa Police station; extra works on the construction of roofing slab, exterior plastering and finishes |  | Pending approval NG-CDFC to submit certified issued instructions from the project manager and the contract documents Management to carry out project verification visit The project has so far received Kshs.7,300,000 allocated in 2019/20 financial year for construction of reception reporting desk & waiting bay, male/female and juvenile cells, OCPD, Deputy OCPD, OCS, deputy OCS, DCIO, deputy DCIO offices, armory and 4 door toilets |
|  |  |  |  |  |  | Kwa Reuben Secondary School Kshs.702,162- Additional funds for installation of 30 metres high security mast with 8 electricity powered, 300 watts floodlights |  | Pending approval NG-CDFC to submit certified cost estimates/contract documents if the project has already been procured The total allocation towards the project including this request amounts to Kshs.4,602,162 |
|  |  |  | Imara Secondary School- purchase of 200 lockers and chairs | 2021/22 | 1,500,000 | Kware Primary School Kshs.1,500,000- purchase of 200 lockers and chairs |  | Recommended for approval |
|  |  |  | Kwa Njenga Primary School- Construction of concrete terraces on one side of the school playing ground for pupil's spectators to sit on and covering the concrete with wooden materials at Kshs.4,500,000, Construction of two door flush toilets Kshs.1,000,000 and construction of two changing rooms Kshs.2,500,000 under the terraces | 2020/21 | 7,791,112 | - Kware Secondary School Kshs.4,896,000- Installation of 30 metres high security mast with 8 electricity powered, 300 watts floodlights - Kware Primary School Kshs.2,895,112- Additional funds for installation of 30 metres high security mast with 8 electricity powered, 300 watts floodlights (The total allocation towards the project including this request amounts to Kshs.4,898,112) | There is a land dispute communicated by the legal department through a letter dated 27th July 2021. | Pending approval NG-CDFC to submit certified cost estimates/contracts documents if the project has already been procured Kwa Njenga Primary School had been allocated Kshs.8,500,000 in 2020/21 financial year out of which Kshs.708,888 was reallocated to other projects leaving a balance of Kshs.7,791,112 |
|  |  |  | Njenga Primary School- construction of strong room for ICT hub | 2017/18 | 2,000,000 | Kware Primary School Kshs.2,000,000- Additional funds for installation of 30 metres high security mast with 8 electricity powered, 300 watts floodlights (The total allocation towards the project including this request amounts to Kshs.4,898,112) |  | Pending approval NG-CDFC to submit certified cost estimates/contracts documents if the project has already been procured |
|  |  |  | Mombasa Road Police Post- Construction of reception/reporting office and waiting bay Kshs 2,200,000 and a 2 door pit latrine Kshs 100,000 | 2019/20 | 2,300,000 | Kwa Reuben Secondary School Kshs.2,300,000- Additional funds for installation of 30 metres high security mast with 8 electricity powered, 300 watts floodlights (total allocation towards the project amounts to Kshs.4,602,162) |  | Pending approval NG-CDFC to submit certified cost estimates/contracts documents if the project has already been procured |
|  |  | Min 04 of 25/1/2022 | Assistant County Commissioner’s Office, Imara Daima-Construction of four pillars infront of the office to support the 2nd floor slab Kshs.2,000,000, constructing a slab around the building to protect soil erosion Kshs.1,000,000, fixing gutters to direct rain water to the storage tanks Kshs.500,000 | 2020/21 | 3,500,000 | Assistant County Commissioner's office Imara Daima Kshs.3,500,000- Construction of 10 car parking lot at the newly constructed NG-CDF Office | - | Pending approval NG-CDFC to specify reason for change of project’s activity NG-CDFC to submit certified cost estimates Management to carry out project verification visit |
|  | Ijara | MIN: CDFC. 040/03/2022 | Masalani Primary School- Construction of 4 number storey classroom to completion | 2020/21 | 8,000,000 | Sophia Girls Secondary School Kshs.11,000,000- Construction of administration block comprising of 6 offices for Headmaster, deputy, secretary, bursar, staffroom, store, Kshs.5,000,000 and construction of 100 students capacity girls dormitory, Kshs.6,000,000 to completion. | Change of priority by the community and stakeholders in starting a new model school | Recommended for approval |
|  |  |  | Masalani Primary School- Construction of administration block with 6 offices for Headmaster, deputy, secretary, bursar, staffroom, store |  | 3,000,000 |  |  |  |
|  | Kangundo | Min No.2 of 10/01/2022 | Kilindiloni Primary School- Renovation of 4 classrooms to completion new roof truss, new roof covering, flooring (ceramic tiles), fixing of windows, doors, new verandah, internal and external plaster, internal and external painting and electrical wiring | 2021/22 | 1,650,000 | Kilindiloni Primary School, Kshs.1,650,000- Construction of 1 classroom (Kshs.1,200,000) and renovation of staffroom; ring beam, verandah, roofing, trusses, purlins and box profile iron sheets, plastering, key point, red oxide floor, painting, re- installation of electricity | Request from the school | Pending approval NG-CDFC to provide clear reasons for change of project’s activity and provide clear description of the activities to be undertaken |
|  |  |  | Mukuyuni SA Secondary School- Construction of a block of 8 door toilet plus half tiled urinal (Kshs.1,028,970) and construction of a block of 2 door cubicle toilet (Kshs.300,000) | 2016/17 | 128,790 | Mukuyuni SA Secondary School, Kshs.128,790- Construction of metal gate with concrete pillars | Unspent balance after completion of the project | Recommended for approval |

Annex III

Resubmissions for 2010/11, 2011/12, 2016/17, 2017/18, 2018/19, 2019/20, 2020/21 and 2021/2022 Financial Years

- 2010/2011 financial year

| No. | Constituency Name | Initial projects that were given conditional Approval/deferred/declined | Proposed Projects | Activity | Amount Allocated | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- |
|  | Starehe | Mathare 3B Toilet - 4,000,000 - Construction of toilet with a hall upstairs- CDFC to be advised to forward cost estimates from the City Engineer and a letter from City Council consenting to the project being implemented The above proposed project was conditionally approved subject to the CDFC submitting a letter of no objection from Nairobi City Council and certified cost estimates. The requested information was never submitted and the NG-CDFC resolved to resubmit the funds to other viable projects which the Board approved Kshs.2,000,000 towards one project and raised issues on the other but the NG-CDFC did not meet the conditions. The NG-CDFC has now resolved to resubmit the funds to Pangani Police Station | Pangani Police Station | Construction of 280 metres perimeter wall | 2,000,000 | Recommended for approval Cumulatively the project has been allocated Kshs.5,013,001 included in this request |

- 2011/2012 financial year

| No. | Constituency Name | Initial projects that were given conditional Approval/deferred/declined | Proposed Projects | Activity | Amount Allocated | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- |
|  | Starehe | Construction of Hawkers markets at Mabatini- Kshs.900,000 - The above proposed project was conditionally approved subject to the NG-CDFC submitting a letter from the City Council of Nairobi confirming their involvement in the projects and forwarding cost estimates for markets The raised issues were not settled even after the NG-CDFC resubmitting funds to another viable project The NG-CDFC has now resolved to resubmit the funds to Muranga Road Pry Sch and Pangani Police Station | Muranga Road Primary School | Additional funds for construction of 140 metres perimeter wall | 500,000 | Recommended for approval Included in this report is a resubmission of Kshs.2,000,000 towards completion of the project |
|  |  |  | Pangani Police Station | Additional funds for construction of 280 metres perimeter wall | 400,000 | Recommended for approval Cumulatively the project has been allocated Kshs.5,013,001 included in this request |

- 2016/2017 financial year

| No. | Constituency Name | Initial projects that were given conditional Approval/deferred/declined | Proposed Projects | Activity | Amount Allocated | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- |
|  | Starehe | Provision of 4 water tanks of 10,000 ltrs at Pangani shopping centre and two tanks of 10,000 litres at Muthurwa market, Kshs.545,977 The above proposed project was declined since they fall under the county government functions. The NG-CDFC has now resolved to allocate the funds to other viable projects | Pangani Police Station | Additional funds for construction of 280 metres perimeter wall | 545,977 | Recommended for approval Cumulatively the project has been allocated Kshs.5,013,001 included in this request |

- 2017/2018 Financial Year

| No. |  | Constituency Name |  | Initial projects that were given conditional Approval/deferred/declined |  | Proposed Projects |  | Activity |  | Amount Allocated |  | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Eldama Ravine |  | Constituency Environmental Activities Kshs.847,693.20 - To cater for the undertaking of Environmental Impact Assessment (EIA) for the various NG-CDF funded projects in the Constituency. The project was declined on basis that the cost for assessment of the proposed project should be included in the project’s cost hence the resubmission to the alongside project. |  | Kabor Primary School |  | Construction to completion of one classroom. |  | 847,693.20 |  | Recommended For Approval. |  |
| 2 | Nakuru Town East |  | Kiratina Primary School, Kshs.5,000,000.00 - New School (foundation of storey building, four classrooms and administration block) – The project was pending approval subject to NG-CDFC submitting approval letter from the Ministry of Education for the establishment of the school. NG-CDFC was also required to submit land ownership documents The NG-CDFC has now proposed to allocate the funds toward bursary |  | Bursary Secondary Schools |  | Payment of bursaries to needy students in secondary schools |  | 5,000,000 |  | Recommended for approval. The allocation will not exceed 35% limit for bursary vote for the 2017/18 financial year |  |

- 2018/2019 financial year

| No. | Constituency Name | Initial projects that were given conditional Approval/deferred/declined | Proposed Projects | Activity | Amount Allocated | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- |
|  | Eldama Ravine | Kibias Chepterwo Security Road, Kshs.300,000 – Opening up of security road to improve security situation in the area. Conditional Approval. The project was pending approval subject to the NG-CDFC submitting a letter from the DCC confirming that the road is a security road and is meant to improve security situation. | Kiptuno Secondary School | Purchase of digital copy printer for the purpose of printing exams. | 300,000 | Pending approval. NG-CDFC to specify on the model Specifications of the printer. |
|  | Kitutu Chache North | Manyansi D. O. K Secondary. School - Completion of one classroom; plastering, fixing doors and windows and painting – Kshs.500,000 Nyagoto Secondary School -Completion of one classroom; Plastering, fixing doors and windows and painting – Kshs.500,000 Ngenyi Girls Secondary School - Additional funds for completion of two classrooms; plastering fixing doors and windows Kshs.1,000,000 The above proposed project were conditionally approved subject to the NG-CDFC providing clarity on the allocations since they seemed to be on the higher side for completion of classrooms. The NG-CDFC has now resolved to resubmit funds to other viable projects | Manyansi Secondary School | Construction of 40 student’s capacity laboratory; foundation, walling, roofing, plastering, fixing doors and windows | 1,000,000 | Pending approval NG-CDFC to submit BoQs from the Sub County Works Officer for construction of a standard laboratory with all the relevant facilities NG-CDFC to commit in writing that it will allocate additional funds in 2022/23 to facilitate construction of a standard lab which has all the facilities required in a lab NG-CDFC to confirm whether the initial proposed completion works for the classrooms was done |
|  |  |  | Nyagoto Secondary School | Construction of 80 students capacity dining hall from foundation, walling, roofing, plastering, fixing doors and windows | 1,000,000 | Pending approval NG-CDFC to submit BoQs from the Sub County Works Officer NG-CDFC to confirm whether the initial proposed completion works for the classrooms was done |
|  | Starehe | Environment, Kshs.2,067,024 – Purchase and installation of of waste bins in City Pry, Mukuru Pry, Kariokor ECD and Race Course Pry The above proposed project was conditionally approved subject to the NG-CDFC specifying the number of bins to be installed in each school and the amount allocated to each. Th NG-CDFC has now resolved to allocate the funds to other viable projects | Pangani Police Station | Additional funds for construction of 280 metres perimeter wall | 2,067,024 | Recommended for approval Cumulatively the project has been allocated Kshs.5,013,001 included in this request |
|  | Nakuru Town East | Kiratina Primary School- Kshs.10,000,000 – Construction of 12 classrooms at Kshs.1,000,000 each, Construction of administration block, Kshs.3,000,000. The project was pending approval subject to NG-CDFC submitting approval letter from the Ministry of Education for the establishment of the school The NG-CDFC has now submitted the alongside projects for consideration | Bursary Secondary Schools | Payment of bursaries to needy students in secondary schools | 8,000,000 | Recommended For approval The allocation will not exceed 35% limit for bursary vote for the 2018/19 financial year |
|  |  |  | St. John’s primary school | Construction of an administration block of 10 offices to lintel level. | 2,000,000 | Pending approval NG-CDFC to specify the estimated cost of the project |
|  |  | Small industries for the youth and women groups from Kiratina ward. After initial starting the project it will be self-sustaining Kshs.2,500,000- Buying of steel nails machine; Provision of electricity connection and Construction of a go-down. Deferred NG-CDFC to provide clear description of the activities to be undertaken and provide specific name for the project The NG-CDFC to submit a concept note on the objective of the project, the intended beneficiaries and how it would be developed, maintained and sustained NG-CDFC to submit a letter of concurrence from the Ministry of Industrialization for the establishment of the industry and the role the ministry would undertake in the development and management, and sustainability of the industry. The NGCDFC carried a resubmission which 500,000 was resubmitted to Race track primary School but Kshs 2,000,000 was awaiting resubmission,which they have now proposed the alongside project. | Lionhill primary school | Construction of a perimeter wall measuring 285 Metres long by 3.5 Metres high. | 2,000,000 | Recommended For approval |

- 2019/2020 Financial Year

| No. | Constituency Name | Initial projects that were given conditional Approval/deferred/declined | Proposed Projects | Activity | Amount Allocated | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- |
|  | Balambala | Modika Rapid Defence Unit – Kshs.6,247,354.48 Construction of Administration Block comprising of 13 offices and armory The project was pending approval subject to NG-CDFC providing the estimated cost of the project and submit a request letter from the beneficiary institution The NG-CDFC has submitted a letter from the Administration Police Service dated 28th July 2020 requesting for the houses. The NG-CDFC has also | Modika Rapid Defence Unit | Construction of six roomed staff quarters to completion | 6,247,354.48 | Pending approval NG-CDFC to justify allocation of Kshs.6.2 million for construction of six roomed staff houses |
|  | Muhoroni | Aora Ndinya Technical Training Institute Muhoroni Kshs.9,500,000- Drilling and developing borehole of approximately 120 m and provide gravel chips along the casing (1,500,000), Provision of casing for loose soils (Black Cotton soil) from 40m to 120m (500,000), Test pumping for minimum of 24 hours (100,000), Purchase for hybrid pump capacity 3 to 5 cubic meter per hour, motor, drop cables, pipes, control panels and plumbing works (800,000), Installation of steel water tower (200,000), Purchase of water tank (10,000 liters) (100,000), Installation of three phase transformer (1,800,000), Fencing 6 acres of land using Barbed wire (concrete poles) and construction of 2 steel metallic gates Kshs.2,000,000.00, and construction of access road creating access to the TTI (1.5 km) (gravelling and grading) Kshs.2,500,000.00 The above proposed project was pending approval subject to the NG-CDFC submitting a letter from the Ministry of Education Science and Technology confirming that the Constituency is among those to be funded in the 4th phase of the co-funding for construction of Technical Training Institutions. The NG-CDFC has reported that it has been difficult to secure land for the construction of the said project because the proposed site had no title deed. The NG-CDFC has now resolved to allocate funds towards other viable projects | Hon Koyoo Mixed Secondary School-Oroba | Construction of six classrooms (Kshs.6,600,000), construction of ten(10) door pit latrines of which 1 door will cater for PWD (Kshs.2,640,000) and installation of one 10,000 litres water tank, construction of tank base and gutter works and taps for school to help them in rain water harvesting (Kshs.260,000) | 9,500,000 | Pending approval NG-CDFC to provide two units for PWDs in the toilets to cater for both male and female |
|  | Kisauni | NG-CDF Office, Kshs.8,000,000 - Construction of NG-CDF office -receptionist’s office, secretary’s office, FAMs office, MP’s office, Board room, staff offices and toilets. The project was pending approval subject to the NG-CDFC confirming whether they have land for the construction of the office and specifying the estimated cost of the office The NG-CDFC has now resolved to resubmit the funds to other viable projects since the office project was allocated Kshs.10,000,000 in 2021/2022 Financial Year for its construction | Barani Primary School | Additional funds for construction of 6 classrooms storey building to completion | 8,000,000 | Pending approval NG-CDFC to provide certified cost estimate or specify the contract sum The one storey block of 6 classrooms in Barani Primary School was allocated Kshs.5,200,000 in 2019/20 Financial Year In 2021/2022 Financial Year the NG-CDFC allocated Kshs.10,000,000 for construction of the Office after purchase of land at Mjambere Ward |
|  | Samburu North | Lemolog environmental project - Construction of 50 gabions @ksh 20,000 to prevent sheet erosion in lemolog area at Baragoi objective being to control the flow of water that causes cut offs, destruction of roads in those areas – Kshs.1,000,000. The project was pending approval subject to Management carrying out verification visit During the visit, Management advised the NG-CDFC to concentrate on construction of gabions around the school. Management had observed that the problem was rampant in the area and had attracted other financiers. NG-CDFC has therefore revised its proposal to just target the area around the school | Lemolog Primary School | Construction of 50 gabions @ Kshs 20,000 to prevent sheet erosion in lemolog around the areas that lead to schools objective being to control the flow of water that causes cut offs and destruction of roads in those areas | 1,000,000 | Recommended for approval |
|  |  | Ntasate Environmental project - Construction of 75 gabions @ksh 20,000 to prevent sheet erosion in ntasate area at Baragoi objective being to control the flow of water that causes cut offs,destruction of roads in those areas – Kshs 1,500,000. The project was pending approval subject to Management carrying out verification visit During the visit, Management advised the NG-CDFC to concentrate on construction of gabions around the school. Management had observed that the problem was rampant in the area and had attracted other financiers. NG-CDFC has therefore revised its proposal to just target the area around the school | Ntasate Primary School | Construction of 75 gabions @ Kshs 20,000 to prevent sheet erosion in Ntasate baragoi around the areas that lead to schools objective being to control the flow of water that causes cut offs and destruction of roads in those areas | 1,500,000 | Recommended for approval |
|  |  |  | Total |  | 2,500,000 |  |
|  | Kisumu West | Usare Secondary School Kshs.1,300,00.00.Construction of septic tank for the New Administration block. The above proposed project was pending approval subject to the NG-CDFC revising the cost of the project. The NG-CDFC submitted certified cost estimates which indicated that the project will cost Kshs.1,096,425. The Board approved the project leaving unspent amount of Kshs.203,575 which the Committee has now resolved to allocatet to other viable projects | Usare Secondary School | Renovation of administration block: repairing cracks and repainting of the whole building | 203,575 | Recommended for approval |
|  |  | Sianda Secondary School-Kshs.2,050,000.00 - Purchase of furniture for administration block Kshs.750,000- Executive chairs(2), Conference tables (2), staff room chairs(15) Metallic drawers( 2) office cabinets (2) office cupboards( 2) staff room table (2) and staff room lockers (15),construction of extended flash toilet and septic tank for administration block( Kshs 1,300,000). The above proposed project was pending approval subject to the NG-CDFC itemizing the cost of furniture and revising the cost of septic tank The NG-CDFC later on resolved to resubmit the project since the items under furniture had been amended. Approval granted for the projects was Kshs.1,950,000 thus leaving an unspent amount of Kshs.100,000 which the NG-CDFC has now resolved to resubmit to the same institution as additional funds for completion of the septic tank | Sianda Secondary School | Additional funds for construction of septic tank | 100,000 | Recommended for approval The project has so far received Kshs.900,000 while its estimated cost is Kshs.1,000,000 |
| 6 | Kisumu East | Kisumu East Technical Training Institute-10,000,000-Construction of one workshop measuring 11M by 16M, 3 lecture rooms each one measuring 8M by 6M and an office space measuring 5.5Mm by 4.5M all located at ground floor. The project was pending approval subject to the NG-CDFC submitting approval letter from the Ministry of Education, Science and Technology confirming that the Constituency is in the 4th phase of the co-funding for construction of TTIs. The requested information was never submitted. The NG-CDFC has now resolved to allocate the funds to another viable project | Chiga Police Station | Purchase of 1.25 acres land Kshs.3,300,000 and cost of land transfer (Kshs.200,000), construction of one wing of the administration block comprising of OCS, deputy OCS, general crime investigation office, in charge police line office, gender office, interview room, stores, four cells, reception and one strong room and four toilets with one unit for persons with disability; foundation and walling (Kshs.3,500,000) | 7,000,000 | Recommended for deferral Management to seek guidance of the Legal Services Department upon which the matter will be brought for discussion at the Board Though the land valuation indicates that the value of land is Kshs.2.8 million, the NG-CDFC has clarified that the owner of land is selling it at Kshs.3.3 million NG-CDFC to review the size land to 1.1 acres NG-CDFC to submit land title deed NG-CDFC to submit correct 4th schedule matching with the minutes in terms of cost and activities and clarify whether it is a police post or station NG-CDFC has submitted land valuation report from a government land valuer indicating that the proposed (1.1-acre land costs approximately) Kshs. 2,800,000 including its developments Further the certificate of land search has been submitted indicating that the land has no encumbrances and that the type of ownership is absolute |
|  |  |  | Ragumo Police Station | Foundation and walling of administration block comprising of 6 offices of 4m by 4.8m each, 4 toilets with two catering for persons with disability, 2 cells, radio room, 4 toilets for inmates and external 4 door pit latrine (all toilets/latrines have one door for pwd) | 3,000,000 | Pending approval NG-CDFC to specify the estimated cost of the project and clarify whether the building is storey. NG-CDFC to provide the actual activities to be undertaken with the allocated funds The project has so far received Kshs.3,000,000 |
|  | Embakasi South | Environment Activities, Kshs. 2,747,354.48 Installation of 6no 11 meters’ solar mast at Kwa Njenga road. The above proposed project was pending approval subject to the NG-CDFC revising the cost of the project. The NG-CDFC has now resolved to allocate funds towards other viable projects | AA Villa Police Station | Installation of 4no. solar masts | 2,747,355 | Pending approval NG-CDFC to submit certified cost estimates |
|  | Nakuru Town East | Small Scale Industries- Kshs. 8,148,498.24- Small industries leather making machine @ 3,000,000.00 Textile machine @ 2,650,000.00 and Purchase of Printing Equipment @ 3,000,000.00. The project was deferred subject to NG-CDFC submitting a concept note on the objective of the project, the intended beneficiaries and how it would be developed, maintained and sustained. NG-CDFC was also required to submit a letter of concurrence from the Ministry of Industrialization for the establishment of the industry and the role the ministry would undertake in the development and management, and sustainability of the industry. NG-CDFC was also required to submit land ownership documents for the land where the industry would be constructed. A total of Kshs.4,500,000 was resubmitted to other projects namely Maria Veronica Secondary School – Kshs.500,000 and Menengai Intergrated Primary School – Kshs.4,000,000 leaving a balance of Kshs.3,648,498.24. The NG-CDFC has now resubmitted the balance to other projects | NG-CDF Office | Purchase of office equipment (4 HP computers, 8 interoffice telephones, Kyocera printer, 2 32” and 40” television, nokia keypad office phone and 2 HP office laptops) | 2,000,000 | Pending approval NG-CDFC to provide breakdown of cost for each item |
|  |  |  | NG-CDF Office | Renovation and repair works (repainting on the exterior and the interior parts of the office and the roof at Kshs.600,000.00, and repairs for the toilets and fabrication at Kshs.200,000.00) and Renovating and repair works the office ramp at Kshs.348,498.00) | 1,648,498.24 | Pending approval NG-CDFC to provide clear description of activities and correct breakdown of cost. |

- 2020/2021 Financial Year

| No. |  | Constituency Name |  | Initial projects that were given conditional Approval/deferred/declined |  | Proposed Projects |  | Activity |  | Amount Allocated |  | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Subukia |  | Oldonyo Mara Primary School road- Opening Of A New Road 1 KM and maintaining of an existing road 2KMs (Bush Clearing, Grading, Murraming) Of 3 Kilometres-Kshs4,000,000. NG-CDFC to submit a letter from KeRRA confirming that the roads are National Government roads and that they are not in their annual work programme NG-CDFC was also required to submit certified cost estimates Management was also mandated to carry out a verification visit The NG-CDFC has now indicated that the County Government undertook the opening up of the road hence proposed a new road |  | Morro Hill primary school road |  | Bush clearing, murraming, grading and gravelling of 4 kilometres road from Subukia – Morro Hill Primary |  | 4,000,000 |  | Pending approval. Management to carry out project’s verification visit The NGCDFC submitted a letter from KERRA indicating that the road is unclassified and they do not have any budget for the it. The NG-CDFC also submitted cost estimates from KeRRA amounting to Kshs 3,999,995 |  |
|  | Wajir North |  | - Watiti Primary School- Purchase and planting of 500 tree seedling (purchase of seeds (95,000), ganibags (85,000), purchase of soil and fertilizer and pesticides (75,000), purchase of water (65,000), labour (105,000) and maintenance (75,000) - Godoma Primary School - Establishment of tree nurseries for both indigenous and exotic trees to be sustained by the school administration (purchase of seeds (95,000), ganibags (85,000), purchase of soil and fertilizer and pesticides (75,000), purchase of water (65,000), labour (105,000) and maintenance (75,000) - Bute Arid Zone Primary School - Establishment of tree nurseries for both indigenous and exotic trees to be sustained by the school administration (purchase of seeds (95,000), ganibags (85,000), purchase of soil and fertilizer and pesticides (75,000), purchase of water (65,000), labour (105,000) and maintenance (75,000) - NG-CDF Office Compound - Establishment of tree nurseries for both indigenous and exotic trees to be sustained by the school administration (purchase of seeds (95,000), ganibags (85,000), purchase of soil and fertilizer and pesticides (75,000), purchase of water (65,000), labour (105,000) and maintenance (75,000) and Office landscaping (58,040) The NG-CDFC have proposed the alongside projects for consideration |  | Bute mixed Day secondary school |  | Purchase and planting of 500 tree seedlings @Kshs.200, Kshs.100,000, purchase and installation of 10,000 litres plastic water tank, Kshs.138,040 and Construction to completion of 2 door pit latrine with one chamber for Persons with Disability, Kshs.400,000 |  | 638,040.00 |  | Pending approval NG-CDFC to confirm whether the school has other toilet facilities to cater for the needs of PWDs for both male and female |  |
|  |  |  |  |  | Bute Girls secondary school |  | Purchase and planting of 500 tree seedlings @Kshs.200 |  | 100,000.00 |  | Recommended For approval. |  |
|  |  |  |  |  | Funan bua primary school |  | Construction to completion of 2 door pit latrine with one chamber for persons with disability |  | 400,000.00 |  | Pending approval NG-CDFC to confirm whether the school has other toilet facilities to cater for the needs of PWDs for both male and female |  |
|  |  |  |  |  | Bute Arid zone primary school |  | Purchase and planting of 500 tree seedlings @Kshs.200 and purchase and installation of 10,000 litres water tank, Kshs.120,000 |  | 220,000.00 |  | Recommended for approval. |  |
|  |  |  |  |  | Fulo primary school |  | Construction to completion of 2 door pit latrine with one chamber for persons with disability |  | 400,000.00 |  | Pending approval NG-CDFC to confirm whether the school has other toilet facilities to cater for the needs of PWDs for both male and female |  |
|  |  |  |  |  | Malaba primary school |  | Purchase and planting of 500 tree seedlings @Kshs.200 |  | 100,000.00 |  | Recommended For Approval. |  |
|  |  |  |  |  | NGCDDF office |  | Purchase and planting of 500 tree seedlings @Kshs.200 |  | 100,000.00 |  | Recommended For Approval. |  |
|  |  |  |  |  | Bute primary school borehole compound |  | Purchase and planting of 500 tree seedlings @Kshs.200 |  | 100,000.00 |  | Recommended For Approval. |  |
|  |  |  |  |  | Total |  |  |  | 2,058,040.00 |  |  |  |
|  | Matayos |  | Bugengi Special School, Kshs.3,460,000 - Purchase of Land for School Expansion and title processing 2 Acres. The project was pending approval subject to the NG-CDFC submitting a Land Valuation Report from a Government Land Valuer The NG-CDFC submitted a land valuation report indicating that the size of the land is 0.9333 acres and is valued at Kshs.4,140,000. The NG-CDFC has now resolved to reduce the size of land as per the report |  | Bugengi Special School |  | Purchase of Land for School Expansion and title processing 0.9333 acres. |  | 3,460,000 |  | Pending approval NG-CDFC to confirm how they will raise the balance to ensure one off purchase of the land |  |
|  | Konoin |  | Kibomut primary school - Purchase of 0.4 acres of land inclusive of processing title deed - 1,300,000. The project was pending approval subject to the NG-CDFC submitting Land valuation report. The NG-CDFC has indicated that the land succession process has not started yet which hinders the process of buying the land hence the resubmission. |  | Chenacho Primary School |  | Completion of a storey building comprising 4 classrooms: Fixing of 8mm non slip coloured first grade ceramic floor tiles, ceiling and electrical works. |  | 800,000 |  | Recommended For Approval. The project has so far received Kshs.5.2 million as follows; Kshs.4,000,000 in 2018/19 financial year for Construction of storeyed building of 4 classrooms. Further, Kshs.1,200,000 in 2019/20 financial year for Completion of four classrooms storeyed building; Floor, plastering, windows, doors, verandah grills fixing and painting |  |
|  |  |  |  |  | Chepkok Primary School |  | Final payment for purchase of 0.25 acres of land including land processing fee. |  | 180,000 |  | Pending approval. The NGCDFC to submit Change of activity for 2017/2018 and 2020/21 Financial Years to read purchase of 0.25 acres of land NG-CDFC has submitted land valuation report 0.5 acres amounting to Kshs.1,400,000 and land has no encumbrances, copy of title deed and official land search. This translates to 700,000 for 0.25 acres of land. The NGCDFC has allocated a total of Kshs.730,000 inclusive of title processing fee of Kshs.30,000. The project was allocated Kshs.400,000 for purchase of 0.3 acres in 2017/18FY and further Kshs.150,000 in 2020/21FY for the purchase of 0.1 acres and is pending approval subject to NG-CDFC submitting land valuation report. |  |
|  |  |  |  |  | Chemelet Chief’s office |  | Final payment for purchase of 0.1 acres of land including land processing fee. |  | 180,000 |  | Recommended for approval. NG-CDFC has submitted the land valuation report indicating that the land has no encumbrances, and the value of the land is Kshs.300,000 NG-CDFC has also submitted copy of title deed and certificate of official land search. The project was allocated Kshs.150,000 in 2020/21FY for the same piece of land and is pending approval subject to NG-CDFC submitting land valuation report. |  |
|  |  |  |  |  | Konoin Sub-County Director of Education Office |  | Purchase of desktop computer at Kshs.50,000, UPS at Kshs.20,000 and printer at Kshs.70,000 |  | 140,000 |  | Recommended for approval |  |
|  | Kisumu East |  | Koyango Chief’s Office Kshs.2000000-Purchase of 0.6 acre piece of land The project was pending approval subject to the NG-CDFC submitting land valuation report The NG-CDFC has submitted land valuation from a government land valuer, land title deed and a certificate of land search indicating that the land has no encumbrances. However, the submitted land valuation report indicated that the approximate acreage of land was 0.7 acres and not 0.6 acres as initially proposed thus the need to resubmit the project |  | Koyango Chief’s Office |  | Purchase of 0.7 acres piece of land |  | 2,000,000 |  | Recommended for approval |  |
|  | Nakuru Town East |  | - Environmental activity, Kshs.793,288.95- purchase of drain rods to facilitate the unblocking of the toilets 2 for each of the five wards (Kivumbini, Nakuru East, Menengai, Biashara and Flamingo). The project was declined since public sanitation services fall under the County Government functions. - Flamingo Chief's Office-Flamingo Ward, Kshs.278,355.52- Planting of tree nurseries in public institution by the youth groups from all wards. - 58 centre - Biashara Ward, Kshs.278,355.52-Planting of tree nurseries in public institution by the youth groups from all wards. - Kiratina Chief's Office - Menengai Ward, Kshs.278,355.52- Planting of tree nurseries in public institution by the youth groups from all wards. - Kivumbini Ward - at the sewer treatment plant, Kshs.278,355.52- Planting of tree nurseries in public institution by the youth groups from all wards. - Langalanga Chiefs Office - Biashara Ward, Kshs.278,355.52- Planting of tree nurseries in public institution by the youth groups from all wards. - Muguga Chief's camp - Nakuru Town East Ward, Kshs.278,355.52- Planting of tree nurseries in public institution by the youth groups from all wards. - Teachers Chief's office - Menengai Ward, Kshs.278,355.52- Planting of tree nurseries in public institution by the youth groups from all wards. The projects were pending approval subject to NG-CDFC justifying the need for the establishment of tree nurseries in chiefs offices and submit concurrence letters from the institutions confirming that they are able to maintain the tree nurseries once established NG-CDFC was further required to provide a breakdown of how they would utilize the Kshs.278,355.52 for planting of tree nurseries The NG-CDFC has now submitted the alongside projects for consideration |  | Umoja Primary School |  | Construction to completion of a 3 door pit latrines with one Chamber for Persons with Disability |  | 314,063.35 |  | Pending approval NG-CDFC to provide two units for PWDs to cater for male and female |  |
|  |  |  |  |  | St. Mary’s Primary School |  | Construction to completion of a 3 door pit latrines with one Chamber for Persons With Disability |  | 314,063.35 |  |  |  |
|  |  |  |  |  | Lion hill Primary School |  | Construction to completion of a 3 door pit latrines with one Chamber for Persons With Disability |  | 314,063.35 |  |  |  |
|  |  |  |  |  | Nakuru East Mixed Secondary School |  | Construction to completion of 2 blocks of Toilets: one block consists of 6 door pit latrines with one chamber for Persons with disability and a urinal for boys and another block consisting of 8 door pit latrines with one chamber for Persons with Disability for girls |  | 1,799,587.54 |  |  |  |

- 2021/2022 Financial Year

| No. |  | Constituency Name |  | Initial projects that were given conditional Approval/deferred/declined |  | Proposed Projects |  | Activity |  | Amount Allocated |  | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Kisumu West |  | Chulaimbo Secondary School Kshs.8,000,000-Construction of a storey administration block comprising of staff room, 4 HOD offices, Bursar office on ground floor, Boardroom, Principal and deputy principal offices, secretary office, 6 door toilets with 2 doors Persons with disability friendly, machine room and kitchenette on 1st floor, 2 halls (192 square metres) and 6 door toilets with 2 doors Persons with disability friendly on 2nd floor reinforcement of columns and beams, installation of 1st floor and 2nd floor suspended slab (co-funded with the school. foundation works have been done by the school) The above proposed project was pending approval subject to the NG-CDFC submitting certified cost estimates. The NG-CDFC submitted certified cost estimates amounting to Kshs.10,169,488. Review of the stated BQ indicated that the scope of work was only ground floor to completion. The NG-CDFC has now resolved to allocate funds towards the same project by reducing the scope |  | Chulaimbo Secondary School |  | Construction of administration block comprising of staff room, 4 HOD offices and accounts office, 7 door toilets with 2 PWD friendly and staircase on ground floor with a 1st floor suspended slab to completion; reinforced concrete superstructure, walling, fixing windows, doors, flooring with tiles, plastering, painting, electrification general finishes |  | 8,000,000 |  | Recommended for approval The NG-CDFC has stated that the school undertook sub-structure works up to foundation slab |
|  |  | Nakuru Town East |  | - Full Gospel- Hillcrest Secondary- 2,500,000.00-Lion Hill Primary Loop To Oginga Odinga Road- Grading , murraming, gravelling and compacting of road from full gospel- hillcrest secondary- lion hill primary loop to Oginga Odinga Road a distance of 1.5 km - Mirugi Kariuki hospital stage to Maria Veronica and loop to Mburu gichua-1,800,000.00- Grading , murraming, gravelling and compacting of road off Nakuru - Kiambogo Road at Mirugi Kariuki hospital stage to Maria Veronica and loop to Mburu gichua Primary School measuring 1.2 km - Oginga Odinga street- Shadrack Kimalel Road-5,500,000.00- Grading, murraming, gravelling and compacting of road off Oginga Odinga street- Shadrack Kimalel Road measuring 1KM and Construction of drainage channel on both sides of the road @2million each - Nakuru- nairobi Highway at Mediheal Hospital Junction to Hyrax Primary-1,500,000.00- Grading and compacting, murraming and gravelling of road off Nakuru- Nairobi Highway at Mediheal Hospital Junction to hyrax Primary measuring 1KM - Oginga Odinga Streat along Menengai Primary School to Maasai Avenue-600,000.00 Grading , murraming, gravelling and compacting of road off Oginga Odinga Streat along Menengai Primary School to Maasai Avenue a distance of 400 meters - Moi road to Spotslight secondary School-1,350,000.00 Grading , murraming, gravelling and compacting of road off Moi road along Stadium Road Serving Kenyatta Primary School, Langalanga Secondary School, Afraha secondary school, St. Joseph primary school and Nakuru Day secondary to Spotslight secondary School 900m long - Kariba Road - Harambee Khalsa road-656,677.20- Grading, murraming, gravelling and compacting of road off Kariba Road along Harambee Khalsa Primary School to Stadium Road 400m long The above projects were pending approval subject to NG-CDFC submitting a letter from KeRRA confirming that the Roads were National Government Roads and that they were not in KeRRA’s annual work programme The NGCDFC has now submitted the proposed alongside projects for consideration since the roads were identified as County Roads |  | Lenana Primary School- |  | Construction to completion of a perimeter wall measuring 156 Metres long by 3.5 Metres high frontage |  | 1,092,000.00 |  | Recommended For Approval |
|  |  |  |  |  |  | Mirugi Kariuki Primary School |  | Construction to completion of a perimeter wall measuring 118 Metres long by 3.5 Metres high frontage |  | 826,000.00 |  |  |
|  |  |  |  |  |  | Kimathi Primary School |  | Construction to completion of a perimeter wall measuring 291 Metres long by 3.5 Metres high frontage |  | 1,919,000.00 |  |  |
|  |  |  |  |  |  | Nakuru Central Secondary School |  | Construction to completion of a perimeter wall measuring 255.5 Metres long by 3.5 Metres high frontage |  | 1,785,000.00 |  |  |
|  |  |  |  |  |  | Nakuru Mixed Secondary School |  | Construction to completion of a perimeter wall measuring 176 Metres long by 3.5 Metres high 2nd phase |  | 1,242,000.00 |  |  |
|  |  |  |  |  |  | Menengai High School |  | Construction to completion of a perimeter wall measuring 154 Metres long by 3.5 Metres high frontage |  | 1,078,000.00 |  | Recommended For Approval |
|  |  |  |  |  |  | Rhino Primary School |  | Construction to completion of a perimeter wall measuring 240 Metres long by 3.5 Metres high frontage |  | 1,680,000.00 |  |  |
|  |  |  |  |  |  | Mburu Gichua Primary School |  | Construction to completion of a perimeter wall measuring 130 Metres long by 3.5 Metres high frontage |  | 910,000.00 |  |  |
|  |  |  |  |  |  | Kisulisuli Primary School |  | Construction to completion of a perimeter wall measuring 204 Metres long by 3.5 Metres high 2nd phase |  | 1,428,000.00 |  |  |
|  |  |  |  |  |  | Nakuru Primary School |  | Construction to completion of a perimeter wall measuring 270 Metres long by 3.5 Metres high 2nd phase |  | 1,890,000.00 |  |  |
|  |  | Loima |  | Urum Security Camp, Kshs.2,400,000- Construction one block of two single rooms security houses to completion The project was pending approval subject to NG-CDFC submitting a letter from the Deputy County Commissioner communicating the decision of the Subcounty Security Council on the establishment of a new security camp The NG-CDFC has submitted a letter from the Loima Sub-County Police Commander requesting for funding of Police unit within Urum Location due to regular recurrent cross-border cattle raids in the area. The NG-CDFC has now resolved to allocate the funds for construction of 2 blocks of staff houses at Namoru Arengan Boarder Control |  | Namoru Arengan Boarder Control |  | Construction to completion of two blocks of two single rooms each for police officers. |  | 2,400,000 |  | Pending approval. NG-CDFC to submit a letter from the Deputy County Commissioner communicating the decision of the Subcounty Security Council on the establishment of a new security camp at Namoru Arengan Boarder Control |
|  |  | Msambweni |  | Msambweni Youth & Opportunity Centre, Kshs.14,095,000- Completion of youth opportunity center i.e. Conference hall, shops, classrooms, library, staffroom for the following measured works done; walling, fixing windows, roof and roof cover in the main hall, concrete works on ground beam in the ablution block, concrete works on ground beam and windows at the staffroom/administration block, 3 classrooms, library, computer laboratory, studio, exhibition rooms & rest area, corridor Variation works for the following measured works not done; doors, windows, general finishes at the main hall, window grills, boards, workstations and chairs at the staffroom/administration block, window grills and white boards at the library, window grills, computer worktops and chairs, computers and accessories at the computer lab, finishes at the studio, window grills, doors, ceiling finishes at the exhibition rooms & rest area, corridor finishes, gate and guard house finishes, electrical work fittings, cabbro paving, football pitch, water fountain and outdoor lighting Ablution block, computer lab, studio, gate & guard house which entails measured extra works not done. The project was initiated in 2015/16 financial year and has so far received a cumulative allocation of Kshs.60,159,034.48 When the NG-CDFC allocated additional Kshs.12 million for completion of the project in 2019/20 financial year, the Board advised management to carry out verification exercise to the constituency to establish the status of the project. As required by the Board, management carried out verification of the project on 7th October, 2020. During the verification exercise, it was established that it was a mega project which comprised of a 1,500 capacity conference hall, 4 exhibition shops, a waiting area, 120 people capacity library with a store, 3 classrooms, a 20 people capacity laboratory with a store, staffroom, 2 units of ablution block of 4 doors each and a studio. Other works included construction of gate and guard house and external works, which encompass cabro paving, leveling of football pitch, water fountain and outdoor lighting. The team was informed that the main objective of the center was to nurture talents by getting youth engaged in different empowerment activities. The project was managed, on the interim, by a development committee whose membership was drawn from different key stakeholders in liaison with the Ministry of Youth Affairs and Sports. However, to ensure its sustainability and proper management, once complete, the project will be handed over to the Ministry of Youth Affairs and Sports which will give a clear structure for its management. The team noted good workmanship of the project and the pending works were found to include: - Conference hall (fixing of doors, general finishes, electrical works and installation of sound system) - Shops and waiting area (fixing of doors, general finishes and electrical works) - Three classrooms (fixing of doors, general finishes and electrical works) - Library (fixing of doors, general finishes and electrical works) - Computer laboratory and a store fixing of doors and electrical works) - Staffroom (fixing of doors, general finishes and electrical works) - Ablution blocks (fixing of doors, general finishes, electrical works and plumbing works) - Studio (fixing of doors and windows general finishes, room acoustic and insulation and electrical works) - Gate and guard house (general finishes and electrical works) - External works; cabro paving, leveling of football pitch, water fountain and outdoor lighting Based on these findings, the team recommended that the NG-CDFC should: - - Resubmit the project by providing a clear description of activities and pending works; - Submit a project valuation report from public works officer giving quantification of the works done and pending works; - Consider budgeting for equipment required to ensure that the project would be fully operational once complete. (Equipment such as computers and conference chairs among others are not catered in the contract sum). The NG-CDFC complied with the above recommendations and submitted project evaluation report done by Sub-County Works Officer indicating that the project works done at the time of the visit amounted to Kshs.47,744,760 while outstanding works were estimated to cost Kshs.12,159,034.48. The project was therefore estimated to cost Kshs.60.1 million to completion. The NG-CDF Board therefore in a meeting held on 1st December, 2020 approved Kshs.12,159,034.48 to complete the outstanding works. However, in 2021/2022 Financial Year, the NG-CDFC proposed additional Kshs.14,095,000 as a variation of works done and works not done. |  | Msambweni Youth & Opportunity Centre |  | Completion of youth opportunity center i.e. Conference hall, shops, classrooms, library, staffroom for the following measured works done; walling, fixing windows, roof and roof cover in the main hall, concrete works on ground beam in the ablution block, concrete works on ground beam and windows at the staffroom/administration block, 3 classrooms, library, computer laboratory, studio, exhibition rooms & rest area, corridor Variation works for the following measured works not done; doors, windows, general finishes at the main hall, window grills, boards, workstations and chairs at the staffroom/administration block, window grills and white boards at the library, window grills, computer worktops and chairs, computers and accessories at the computer lab, finishes at the studio, window grills, doors, ceiling finishes at the exhibition rooms & rest area, corridor finishes, gate and guard house finishes, electrical work fittings, cabro paving, football pitch, water fountain and outdoor lighting Ablution block, computer lab, studio, gate & guard house which entails measured extra works not done. |  | 14,095,000 |  | Recommended for deferral Contract documents to be reviewed by the Legal services departments and guide the Board on the way forward The project was deferred subject to NG-CDFC justifying the need for additional funds and explaining why the proposed works were not catered for during financial appraisal of the project. The NG-CDFC has indicated that during financial appraisal of the project, the engineer used the contracted BoQ and did not take into consideration extra works that were done by the contractor but were never captured in the contracted BoQ. They have also submitted contract documents showing that the contract sum for the project was Kshs.60,725,880. In addition, the committee has submitted BoQ indicating that the extra works done by the contractor outside the contracted works amount to Kshs.6,212,145. This would bring the total cost of the project to Kshs.66,938,025. In addition, the NG-CDFC has submitted a variation claim from the contractor who has indicated that the project was started six years ago and there are several changes that have taken place from the date the contract was signed. These include changes in market prices, changes in human resource/labor, inflation rates and government policies on fuel, electricity and taxes. According to the contractor, after every year, labor cost increases by at least 18% and materials by at least 10% as published by Job Building Council (JBC). The contractor therefore claims a 10% increase for both labor and materials after every year for payments that ware not done on time. The total claim amounts to Kshs.9,997,908.90 The NG-CDFC had therefore taken this into consideration thereby allocating additional Kshs.14,095,000 to the project instead of Kshs.6,212,145 meant for extra works. |
|  |  | Kangundo |  | Proposed Mikoikoni Secondary School, Kshs.1,100,000- Purchase of 1 acre of land for proposed Mikoikoni Primary School- Pending approval The project was pending approval subject to the NG-CDFC submitting approval letter from the Ministry of Education, Science & Technology approving establishment of the school and land valuation report from Government Land Valuer, copies of certified title deeds and land searches The NG-CDFC has now resolved to allocate the funds to another project. |  | Matithini Secondary School |  | Construction of a kitchen and installation of a boiler |  | 1,100,000 |  | Pending approval NG-CDFC to submit 3rd and 4th Schedules NG-CDFC to specify the estimated cost of the project |
|  | Baringo South |  | - Arabal Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Mukutani Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Ngelecha Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Kapindasum Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Chemorongion Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Kiserian Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Noosukuro Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Rugus Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Kasiela Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Sinoni Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Loosampurpur Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Sokotei Primary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Sokotei Secondary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) - Tuiyotich Secondary School, Kshs. 150,000-Purchase of motorbike (TVS/BOXER with 150cc Engine capacity) The projects were declined because they amounted to personal awards hence inconsistent with the provisions of Section 47 of the NG-CDF Act 2015 as amended in 2016. The NG-CDFC therefore resolved to resubmit the funds to the alongside projects |  | Tuluongoi Secondary school |  | Landscaping to completion of 100m-by-100m school compound :Clearing of shrubs and trees, breaking of stones to ground level, leveling, planting of creepers |  | 400,000 |  | Recommended For Approval |  |
|  |  |  |  |  | Ngarie Secondary school |  | Landscaping to completion of 100m-by-100m school compound :Clearing of shrubs and trees, breaking of stones to ground level, leveling, planting of creepers |  | 500,000 |  | Recommended For Approval |  |
|  |  |  |  |  | Sabor Secondary school |  | Landscaping to completion of 100m-by-100m school compound :Clearing of shrubs and trees, breaking of stones to ground level, leveling, planting of creepers |  | 400,000 |  | Recommended For Approval |  |
|  |  |  |  |  | Kamarura Primary school |  | Construction to roofing level of 1 classroom |  | 800,000 |  | Recommended For Approval |  |
|  | Emuhaya |  | - Ikalikha Primary School-Ekalabala road Kshs.2,690,094.39 - Bush clearance, grading, gravelling & compaction of 2 Km road & Installation of 30 meter culverts of diameter 600mm to completion. - Emalindi –Isanda road,Kshs. - Bush clearance, grading, gravelling & compaction of 1.5 Km road & Installation of 12 meter culverts of diameter 600mm to completion. - 1,907,132.85 The projects were pending approval subject to the NG-CDFC submitting a letter from KeRRA confirming that the roads are National Government roads and that they are not in KeRRA’s annual work programme. Management was also mandated to carry out verification visit The NG-CDFC has now allocated funds to other projects |  | Bursary Secondary Schools |  | Payment of bursary to needy students |  | 3,597,227.24 |  | Recommended For approval |  |
|  |  |  |  |  | Bursary Tertiary Institutions |  | Payment of bursary to needy students |  | 1,000,000 |  |  |  |
|  | Kajiado Central |  | AIC Childcare Centre- Completion of 2,000 Capacity Dining Hall, Plaster Works, Floor, Doors & Windows, Plumbing and Electrical Works and Paint Work, Kshs.1,000,000 The project was declined because it falls under county government function The NG-CDFC has proposed other projects |  | NG-CDF Office furniture and computers |  | Purchase of office furniture: 2 executive desks @80,000 and 5 lowback Executive chairs @20,000 totaling to Kshs.260,000 |  | 260,000 |  | Recommended For Approval |  |
|  |  |  |  |  | NG-CDFC Office |  | Landscaping and tree planting at NGCDF office Approximately 1 acre land: Italian cypress, False Ashok, Thuja, Aucaria, Golden palms and Royal palms, Kshs.100,000, Levelling of one acre ground and removal of shrubs, Kshs.80,000 |  | 180,000 |  | Recommended For Approval |  |
|  |  |  |  |  | NG-CDFC Office |  | Purchase of one laptop HP Elitebook 1030 g2. Intel core i7, 7th generation 8gb RAM 512gb SSD, 13.3’’ 1920 x1080 ,Touchscreen, integrated intel UHD graphics 620,HD webcam, HDMI, blue tooth |  | 150,000 |  | Recommended For Approval |  |
|  |  |  |  |  | Bursary tertiary Schools |  | Payment of bursary |  | 300,000 |  | Recommended For Approval |  |
|  |  |  |  |  | NGCDF Office |  | Refurbishment of 5 door washrooms for ladies and gents, 3 No. flush toilet basins, Kshs.30,000, 2 No. Urinal basins Kshs.16,000, 2 No. handwashing sinks, Kshs.16,000, 2 No. sink mixers, Kshs.5,000, 3 No. union door locks, Kshs.7,500, tiling works for ladies and gents toilets, Kshs.25,000, paint works, Kshs.10,500 |  | 110,000 |  | Recommended For Approval |  |
|  |  |  | NG CDF Office- Planting of Beautification Ornamental trees at the NG CDF Office 20 Italian Cypress @ Kshs.50,000, 30 False Ashok @ Kshs.45,000, 30 Thuja @ Kshs.45,000, 10 Aucaria @Kshs.25,000, 20 Golden Plams @ Kshs.50,000, 20 Royal Palms@ Kshs.50,000, Transport at Kshs.15,000 & Labour at Kshs. 20,000 Grand total 300,000 The project was declined and NG-CDFC advised to use allocation on administration and recurrent expenses to carry out the proposed works The NG-CDFC has allocated the funds to other projects |  | Naibala Primary school |  | Water harvesting at Naibala Primary School through installation of gutters of 1 No. Classrooms, Kshs.100,000, construction of 1 No. tank stands to hold 10,000 litres water tanks @ Kshs.50,000, purchase, delivery and installation of 1 No. 10,000 litres water tank, Kshs.100,000 and construction of concrete hand washing basins, Kshs.50,000 |  | 300,000 |  | Recommended Approval |  |
|  | Kangema |  | Proposed Karichiungu Primary School Kshs.3,940,965 - Purchase of 2 ½ acres of land for proposed Karichiungu Primary school The project was pending approval subject to NG-CDFC submitting an approval letter from the Ministry of Education for the establishment of the school, land valuation report from Government Land Valuer, copy of title deed and official land search The NG-CDFC has proposed the alongside projects for consideration |  | Marimira Assistant Chief’s Office |  | Construction to completion of 3 roomed Assistant Chief’s Office. |  | 2,300,000 |  | Recommended for Approval |  |
|  |  |  |  |  | Nyagatugu Primary School |  | Renovation to completion of 4 classrooms: Reroofing, fixing windows, doors, painting, plastering and flooring. |  | 1,640,965 |  | Recommended for Approval |  |
|  |  |  |  |  | Total |  |  |  | 3,940,965 |  |  |  |
|  | Kisauni |  | Mjambere Secondary School - Construction of six classrooms storey building including ramp (Kshs.13,000,000) and two door flushable toilets and two door toilet for Persons With Disabilities to completion (Kshs.1,000,000) – Kshs.14,000,000 The project was pending approval subject to NG-CDFC submitting approval letter from the Ministry of Education for the establishment of the school The NG-CDFC has submitted a letter from the Sub County Director of Education advising the NG-CDFC to concentrate on the primary schools due to high demand. There was need to complete the Primary Schools before embarking on the secondary school project The NG-CDFC resolved to allocate the funds to Barani Primary School. |  | Barani Primary School |  | Construction to completion of one storey block of six classrooms with five door flushable toilets and three door flushable toilets for Persons With Disability |  | 14,000,000 |  | Pending approval NG-CDFC to provide certified cost estimate of the project and confirm whether the allocation is inclusive of a ramp |  |
|  | Machakos Town |  | REREC, Kshs.2,500,000- Rural Electrification Authority matching facility in the following areas; Katheka kai, Keaa/kaumoni, kiuu, mwania kakinduni, sinai, kyanzasu The project was pending approval subject to the NG-CDFC submitting a letter of concurrence from Rural Electrification and Renewable Energy Corporation (REREC) The NG-CDFC has now resolved to resubmit the funds to other viable projects |  | Bursary Secondary Schools |  | Payment of bursary to needy students in secondary schools |  | 1,500,000 |  | Recommended for approval The allocation of additional Kshs.1,500,000 does not exceed the 35% limit for bursary |  |
|  |  |  |  |  | Kanyongo Secondary School |  | Completion of one classroom started by the school: plastering, painting, fixing windows and doors and casting of first floor slab |  | 1,000,000 |  | Recommended for approval |  |
|  |  |  |  |  | Total |  |  |  | 2,500,000 |  |  |  |
|  | Mavoko |  | Athi-River Secondary School, Kshs.8,200,000- Purchase of 52 Isuzu seater school bus on a one-off purchase The project was pending approval subject to the NG-CDFC submitting a pro-forma Invoice The NG-CDFC forwarded a proforma invoice No. 120780/2021 dated 18th December 2021 from Isuzu indicating the cost of the project as Kshs.7,806,800 The NG-CDFC resolved to allocate the balance of Kshs.393,200 to other viable project |  | Athi-River Secondary School |  | Purchase of 52 Isuzu seater school bus on a one-off purchase |  | 7,806,800 |  | Recommended for approval |  |
|  |  |  |  |  | Bursary Secondary Schools |  | Payment of bursary to needy students in secondary schools |  | 393,200 |  | Recommended for approval |  |
|  |  |  |  |  | Total |  |  |  | 8,200,000 |  |  |  |
|  | Nakuru Town West |  | Cereals Board - Upper hill Estate Roads Kshs.4,700,000- Public Sign Board, Heavy Grading without watering and compaction, Ditch/Mitre drain/Catch water drain excavation, Culvert Cleaning- Fully blocked-600mm dia, Fill in Hard Material and compact, Gravel Patching with watering and compaction of 5kms Roads. The project was pending approval subject to the NG-CDFC submitting a letter from KeRRA confirming that the roads are under National Government and that they are not in KeRRA’s annual work programme, Cost estimates for the roads to be submitted and Management to carry out verification exercise. The NG-CDFC submitted a letter from KeRRA indicating that it’s a national government road and certified cost estimates for the road. Management carried out a verification visit on 17th November, 2021 and established that the road does not lead to any learning institution but connects the cereals Board and private estates which was identified as Upper hill, hence the need for resubmission. The NG-CDFC has proposed the alongside project for consideration |  | Barut- Kigonor Primary Access Roads. |  | Grading, bush clearing, fill in hard material and compact and gravel patching of 5Kms access road. |  | 4,700,000 |  | Pending approval Management to carry out project’s verification visit NG-CDFC has submitted a letter from KeRRA ref: KERRA/NKU/EAST/WEST/VOL.1/43 dated 13th January, 2022 indicating that the road is a national government road and that they are not in KeRRA’s workplan for 2021/22 financial year. Further, the NG-CDFC submitted cost estimates amounting to Kshs.4,709,000. |  |
|  | Turkana North |  | Lokamarinyang- Kanamese Kibish Junction Road, Kshs.10,000,000-Opening and grading of 50 Km security road The project was pending approval subject to the NG-CDFC submitting a letter from KeRRA confirming that the roads are National Government roads and they are not in its annual work plan NG-CDFC was also required to submit certified cost estimates and include gravelling works. The NG-CDFC resolved to allocate the funds to other projects |  | Alagama Primary School. |  | Renovation to completion of two classrooms: roofing, plastering, flooring, fixing of windows and doors and painting |  | 1,400,000 |  | Recommended for Approval |  |
|  |  |  |  |  | Kapedor Primary School |  | Renovation to completion of two classrooms: roofing, plastering, flooring, fixing of windows and doors and painting |  | 1,400,000 |  |  |  |
|  |  |  |  |  | Kaaleng Secondary School |  | Purchase of a 51 Seater Isuzu FRR 90 Semi-Luxury bus. |  | 7,200,000 |  |  |  |
|  |  |  |  |  | Total |  |  |  | 10,000,000 |  |  |  |
|  | Mosop |  | AIC Chebarus Primary School, Kshs.1,900,000- Construction of two classrooms to completion at Kshs.1,780,000 and purchase of 40 desks at Kshs.120,000 . The project was pending approval subject to NG-CDFC submitting registration certificate of the school to confirm its ownership status. The NG-CDFC resolved to allocate the funds to other projects |  | Ndalat Jobs Outreach School for the physically challenged. |  | Additional funds for purchase of 25 seater semi luxury bus with complete wheel chair ramp. |  | 875,000 |  | Recommended for approval Proposed allocation of Kshs.4,983,600 towards purchase of a 25 seater Isuzu Bus was deliberated on by the PPRM Committee on 18th January but was pending approval subject to NG-CDFC confirming whether the bus will be designed and fitted to be user friendly to the physically challenged students. The NG-CDFC has proposed additional allocation of Kshs.875,000 so as to cater for modifications that would make the bus user friendly to the students |  |
|  |  |  |  |  | Kapkatet Primary school |  | Construction to completion of one classroom at Kshs.800,000 and purchase of 40 desks at Kshs.225,000 |  | 1,025,000 |  | Recommended for Approval |  |
|  | Loima |  | Loya primary school, Kshs. 1,650,000-Renovation of 2 classrooms; re-roofing, fixing of doors and windows to completion. The project was pending approval subject to the NG-CDFC revising the cost. NG-CDFC has now resolved to increase the number of classrooms to be renovated and the scope of work |  | Loya primary school |  | Renovation of three classrooms to completion; Plastering, flooring, fixing windows and window panes, fixing steel doors and painting. |  | 1,650,000 |  | Recommended for approval |  |
|  | Aldai |  | Kaptumek Secondary School, Kshs.800,000- Final payment for purchase of a school bus initiated by Board of Management The project was pending approval subject to the NG-CDFC submitting verifiable evidence indicating that the school has raised the balance to ensure one-off purchase of the buses The NG-CDFC has indicated that the school has cleared the bus loan hence resolved to allocate the funds for a different activity in the same school. |  | Kaptumek Secondary School |  | Renovation to completion of 2 classrooms: roofing, wall elongation, flooring and painting |  | 800,000 |  | Recommended for approval |  |
|  | Butula |  | Kenya Medical Training College-Butula Campus, Kshs.20,000,000 - Additional Fund for completion of Two Storey Building for Administration Block, Plastering, flooring, fixing of doors, shuttering, windows, plumbing, mechanical works, piping and wiring for Ground floor and First Floor. The project was pending approval subject to NG-CDFC providing clear description. The NG-CDFC increased the scope of works to include other units while providing detailed description for the project. |  | Kenya Medical Training College-Butula Campus |  | Additional funds for completion of a two-storey building comprising of 4 lecture halls, 4 classrooms, 80 students’ capacity multipurpose hall and 2 units of flash toilets of 4 doors each (for male and female) on the ground floor and 20 students’ capacity computer laboratory, administration block of 4 offices and staffroom, students’ capacity skills laboratory and boardroom on the first floor: Plastering, flooring, fixing of doors, shutters and windows, mechanical works, plumbing works, piping and wiring of the first-floor facilities and branding to completion |  | 20,000,000 |  | Recommended for approval The estimated cost of the project is Kshs.57 million and has so far received Kshs.37 million |  |
|  |  |  | Benga TTI, Kshs.5,000,000 - Fixing of Plumbing and Mechanical works; Piping and wiring to Ground floor Hostels. The project was pending approval subject to NG-CDFC providing clear description. The NG-CDFC reviewed the scope of works while providing detailed description for the project. |  | Benga TTI |  | Additional funding for completion of a storey building of 500 students’ capacity hostel: plumbing works (fixing of cabals pipe and wires) and mechanical works |  | 5,000,000 |  | Recommended for approval The estimated cost of the project is Kshs.42.5 million and has so far received Kshs.37.5 million |  |
|  | Tigania East |  | Mukorone Primary School, Kshs.2,000,000-Grading of 1km access road Mukuanii primary school, Kshs.2,000,000-Grading and Gravelling of 3km school access road The projects were pending approval subject to the NG-CDFC submitting a letter from KeRRA confirming that the roads were National Government roads and that they were not in its annual work plan NG-CDFC was also required to submit certified cost estimates Management was mandated to carry out a verification visit to the proposed roads Management carried out a verification exercise on 17th February, 2022 and confirmed that the Mukorone Primary school access road required opening because the existing road was impassable. Management was able to verify only 1km stretch since the other remaining 2km could only be accessed by foot. Management was informed that during construction at the school, materials are normally carried by people because vehicles cannot pass due the state of the road. The proposed road therefore required opening, grading and gravelling The Mukuanii primary school access road was confirmed to be a County Government Road. Though in bad condition, it could not be funded. Due to the state of the Mukorone Primary School, it was observed that the Kshs.2,000,000 proposed could not undertake meaningful works hence the NG-CDFC was advised to engage the Roads Officer with a view to ensuring that realistic cost estimates were provided to inform realistic decisions. Guided by the Engineers estimates of Kshs.4,579,522.24, the NG-CDFC consolidated the funds to go towards Mukorone primary school access road The NG-CDFC further submitted a letter from KeRRA confirming that the road was unclassified and they are not in its annual work plan. |  | Kangethia-Mukorone Primary School Access Road |  | Heavy bush clearing, cut to spoil in hard material, cut to fill in soft material, cut to spoil in soft, heavy grading with watering and compaction |  | 4,000,000 |  | Pending approval Proposed road works to include gravelling |  |
|  | Ruaraka |  | Proposed Mathare North Secondary school Kshs.21,200,000- Proposed construction of 2 storey building comprising of 30 classrooms, 6 laboratories 50 capacity each, administration block of 4 offices and staffroom, 63 door toilets inclusive of the needs of PWD and school hall (kshs.20,000,000), Purchase and supply of 200 school Wooden Metal Lockers and chairs @ Ksh.6,000.00 per set (Kshs.1,200,000) The project was pending approval subject to the; - NG-CDFC submitting an approval letter from the Ministry of Education, Science & Technology for establishment of the school. - NG-CDFC providing proof of availability of land and ownership documents for construction of the school - NG-CDFC submitting certified BoQs & drawings - NG-CDFC specifying the phase to be undertaken with the allocated funds. The NG-CDFC submitted the following; - A letter of no objection for establishment of TJ Kawang’ Mathare North Secondary School Ref: RDE/NRB/IPR/1/28/VOL.1 dated 22nd November, 2021 from the Ministry of Education (Regional Director of Education). The letter further stated that the Ministry will offer necessary support in registration, staffing and other necessities in curriculum delivery of basic education - Board of Management for Mathare North Primary School minutes of a meeting held on 1st November, 2019. The BOM discussed the matter on establishment of a new school and agreed to donate 2 acres of land for establishment of the secondary school. Further, a public participation report held on 2nd June, 2021 was also submitted. Members present during the meeting comprised of the DCC, ACC, MP, BOM members for Mathare North Primary School and other opinion leaders - Certified cost estimates amounting to Kshs.108,465,700 for construction of 2 storey building comprising of 32 classrooms, 72 door toilets inclusive of PWD, administration block of 4 offices and staffroom and a school hall Review of the stated Bill of Quantities indicated that the scope of work had changed and the project’s name thus the need to resubmit the project. |  | Proposed TJ Kajwang Mathare North Secondary school |  | Construction to completion of 2 storey building comprising of 32 classrooms, 72 door toilets inclusive of PWD, administration block of 4 offices and staffroom and a school hall: clearing the area, removing cotton soil, excavation of trenches, walling, keying, electrical works, slabbing and painting (Kshs.20,000,000) and Purchase and supply of 200 school Wooden Metal Lockers and chairs @ Ksh.6,000.00 per set (Kshs.1,200,000) |  | 21,200,000 |  | Pending approval NG-CDFC to specify the phase to be undertaken with the allocated amount. This is in compliance to section 25 (1) of the NG-CDF Act, 2015 as amended in 2016 which states that “Any funding under this Act shall be for a complete project or a defined phase of a project and may include the acquisition of land and buildings” |  |

Annex IV

Reports on projects monitoring in Eldama Ravine, Wajir East and Suba North Constituencies

- Eldama Ravine Constituency

Eldama Ravine NG-CDF Committee proposed the following projects for funding in 2021/22 financial year:

- Kenya National Library Services, Kshs.10,000,000 - Completion of the Eldama Ravine Library and Offices Project-completion of mechanical works which was partly done and payment of mechanical works already done

- National Government Constituencies Development Fund Committee Office, Kshs.15,000,000 - construction of constituency office to completion

The Board in a meeting held 22nd November, 2021 deferred the proposals subject to;

- The PPRM Committee carrying out project monitoring in the Constituency to facilitate consultative discussions with the NG-CDFC among other stakeholders aimed at getting more information on the NG-CDFC office project to aid informed decision;

- NG-CDFC submitting contract documents and expenditure report to ascertain how Kshs.77,083,688 disbursed by the Board for the construction of the NG-CDF office was utilized.

Background of the project

Construction of Eldama Ravine Constituency Development Fund Committee office was initiated in 2013/14 Financial Year with an allocation of Kshs.5,000,000 to commence construction of the office to house modern Constituency Library facility, Constituency Offices, modern cyber, Uwezo fund Offices, Huduma Office and other critical offices in the Constituency

Over the years, the project received a total of Kshs.77,083,688.61 as per records available at the NG-CDF Board office while an additional allocation of Kshs.8 million proposed in 2020/2021 Financial Year is yet to be approved.

Below is a breakdown of the funding per financial year;

| No. | Financial Year | Approved Activity | Amount allocated |
| --- | --- | --- | --- |
| - 1 | 2013/14 | To commence the construction of a CDF Office that shall house the modern Constituency Library facility, Constituency Offices, modern cyber, Uwezo fund Offices, Huduma Office and other critical offices in the Constituency | 5,000,000 |
| - 2 | 2014/15 | To continue the construction of phase 2 of a CDF Office that shall house the modern Constituency Library facility, Constituency Offices, modern cyber, Uwezo fund Offices, Huduma Offices and other critical CDF activity related offices in the Constituency | 10,000,000 |
| - 3 | 2015/16 | To continue the construction of phase 2 of a CDF Office and library that shall house the modern Constituency Library facility, Constituency Offices, modern cyber, Uwezo fund Offices, Huduma Offices and other critical CDF activity related offices in the Constituency | 15,000,000 |
| - 4 | 2016/17 | To cater for the construction of phase two of the 2 storeyed NG-CDF Offices that houses a modern library facility co-funded with Waitrose Foundation and Kenya National Library Service to improve access to information in the Constituency | 15,000,000 |
| - 5 | 2017/18 | To cater for the completion of phase two of the 2 storeyed NG-CDF Offices (First and Second Floor) that houses a modern library facility- Fitting Tiles, electrical installation works, mechanical and plumbing works, internet trunking, painting, external works amongst other finishing works | 14,000,000 |
| - 6 | 2018/19 | Completion of phase two of the 2 storeyed NG-CDF Offices (First and Second Floor) that houses a modern library facility- Painting, doors and windows, electrical fittings, trunking, mechanical and plumbing works, external works, fencing, gate, parking bay, kitchenette and other works | 10,000,000 |
| - 7 | 2019/20 | Completion of the Eldama Ravine Library and Offices Project-Masonry fence, cabro blocks for parking, landscaping, gate and sentry, mechanical and electrical works, external lighting, smoke detectors and other finishing works | 8,083,688.61 |
|  | Total allocation |  | 77,083,688.61 |

Challenges noted in the Implementation of the Project

During a project monitoring exercise by management in March 2021 it was observed that the building was for the exclusive use of the Kenya Library Services with no space set aside for NG-CDFC office as had been indicated in the Constituency Project Proposals and subsequent approvals.

The three storey building had been set up as a library with book shelves installed, library desks and chairs placed and books arranged in all the floors hence no provision for NG-CDF office. The building had also been clearly labelled as Kenya National Library.

Information provided by the then incoming FAM was that construction of the NG-CDFC office had not commenced and would be done on another piece of land.

The NG-CDFC was housed in a dilapidated rented office with no adequate office space for its operations

A follow up monitoring exercise by the PPRM Committee on 15th December, 2021, highlighted the following challenges in the implementation of the project, specifically with regard to adherence to various legal requirements;

- Change of project’s scope/activities without the approval of the Board;

That the two-storey building had entirely been set up as a National Library and clearly labelled as Kenya National Library. There was neither space set aside for the NG-CDF office nor for all the other offices indicated in the approvals granted by the Board. It was further noted that Eldama Ravine NG-CDFC was operating in a dilapidated rented office with a monthly rent of Kshs.20,000.

It was further established that: -

- The Kenya National Library had already taken over the project and had installed book shelves, library desks, chairs and books arranged on all the floors hence no provision for NG-CDF office. The library was in operation;

- The project had initially been conceived as a three-storey building to be implemented in three phases with 1st phase being the ground floor, 2nd phase being the 1st and 2nd floor while third phase was to involve construction of the third floor to host the NG-CDF offices. The first and the second phases were to host the library and other offices. The arrangement on how the project was to be implemented culminated from a meeting of all relevant stakeholders held in January 2015;

- The contract sum for the first phase of the project was Kshs.19,206,352 while that of the second phase was Kshs.39,598,342, totaling to Kshs,58,804,688;

- The scope of the works was later changed and a two-storey building hosting the Kenya National Library Services was constructed and that the 3rd phase which involved construction of NG-CDF Offices was to be done as a separate building on a space within the KNLS compound;

- The outstanding works for 1st phase of the project included fitting of doors for the ground floor kitchenettes and washroom fittings;

- The outstanding works for the second phase of the project included fittings for the 1st floor washrooms and fixing of doors for the 1st and 2nd floor kitchenets;

The decision to change the scope of works from construction of NG-CDF office housing a library among other offices to construction of a stand alone Kenya National Library was not brought to the attention of the Board as provided for in section  6 (2) of the NG-CDF Act 2015 as amended in 2016 which stipulates that “once funds are allocated for a particular project, they shall remain allocated for that project and may only be re-allocated for any other purpose during the financial year with the approval of the Board.”

- The project was being supervised by a consultant;

- Section 36 (1) of the Act provides that “projects under the Act shall be implemented by the Project Management Committee with the assistance of the relevant department of Government.”

- The NG-CDFC however engaged a private consultant in total disregard to this provision and paid a total of Kshs.11 million, a cost that had not been approved by the Board.

- The NG-CDFC did not enter into an MoU with other partners that were involved in the implementation of the project;

- The project was implemented in partnership with Kenya National Library Services (KNLS) and Waitrose Foundation Limited whereby the Kenya National Library Services (KNLS) provided the land where the project was undertaken while Waitrose Foundation contributed Kshs.5 million which was directly paid to the contractor. Other partners such as the County government and EREF were reported to have pulled out.

- However there was no Memorandum of Understanding that was signed between the partners that were involved in the implementation of the project clearly specifying what role each partner would play.

- Irregular reallocation of funds from other projects to the NG-CDF office/Library project

- The NG-CDFC had made a total payment of Kshs.81,553,367.67 to the project against an allocation of Kshs.77,083,688.61 bringing over expenditure of Kshs.4,469,679.67 amount which was irregularly reallocated from other projects.

- The NG-CDFC indicated that an amount of Kshs.4,469,679.67 was released to the project in anticipation that the Board would approve the Kshs.8 million allocated in 2020/21 financial year;

- The decision to disburse the Kshs.4,469,679.67 to the project management committee (PMC) was occasioned by pressure from different stakeholders including the KNLS Board which had planned to have the project commissioned in January, 2021. However, there was no clarity on the projects from whose votes this amount was drawn.

In view of the forgoing, the PPRM Committee recommended that the NG-CDFC should: -

- Hold a consultative meeting with the KNLS management with the aim of deliberating and agreeing on the following;

- Set aside the ground floor of the two-storey building to be exclusively used as the NG-CDFC office

- Have a conjoined title deed with the KNLS for the land where the project is located.

- Branding of the building using the NG-CDF logo as the financier.

- Vacate and discontinue any relationship with the Consultant and engage services of the Sub County Works officer in adherence to Section 36 of the Act. No further payment should be made to the consultant;

- Draft a memorandum of understanding (MoU) with the KNLS which should specifically indicate the partners involved, the roles of each partner and ownership of the project upon its completion. The draft should be submitted to the NG-CDF Board’s Legal Department for review before any signing is done;

- Submit all the relevant documents pertaining to the project including BoQs, variation reports, procurement documents, drawings and designs, contracts awarded and a record of all the payments made;

- Submit a detailed report on the projects that were directly affected by the expenditure of Kshs.4,469,679.67 that was disbursed to the NG-CDF Office/Library project without the approval of the Board;

- Submit an expenditure report to ascertain the amount spent on the project so far and a breakdown on how the amount was spent;

- Submit details of all the members of the project management committee (PMC) and signatories to the PMC account;

- Engage the Sub County Works Officer in appraising the project through quantification of the value of the works done and the outstanding works;

- Submit a brief of all the partners involved in the project, their roles and contributions and clearly detail the components of the project undertaken by each partner;

- Maintain a properly compiled and updated project file;

- The NG-CDFC to hold a meeting with the former Fund Account Manager and submit a report on the above concerns to the NG-CDF Board not later than 24th January, 2022.

NG-CDFC’s Response

The NG-CDFC responded to the issues raised during the monitoring exercise as follows: -

- Consultative meeting with the KNLS and project’s appraisal

- The NG-CDFC submitted minutes of a meeting held on 2nd February, 2022 which brought together members of PMC, KNLS management and the NG-CDFC;

- It was reported that the KNLS CEO indicated that the KNLS could not divorce itself from the initial agreement they had with the Eldama Ravine NG-CDFC in providing space within the compound for construction of NG-CDF office. He however indicated that it was not possible to set aside space in the building for NG-CDF office since the building was designed as a library and is now fully operational and open to the public. He further indicated that all the floors had been fully occupied;

- Concerning the cojoined title deed of the land between NG-CDF and KNLS, the KNLS CEO indicated that the matter required further consultation with the KNLS Board of directors. He however indicated that Eldama Ravine Library was among the facilities earmarked for transfer to the County Government hence all the data regarding assets of the library had been transferred to the Transition Authority which made it difficult to interfere with the land ownership;

- All the parties agreed that the project should be labeled to reflect NG-CDF as the financier;

- The PMC and the NG-CDFC agreed to discontinue services of the private consultant though the same had not been done as at the time of submitting the report to the Board;

- The NG-CDFC was yet to draft an MoU but intended to discuss the same with the KNLS board of directors before forwarding to the NG-CDF Board;

- Documents relating to the project were not submitted. The NG-CDFC indicated that the documents were submitted to the County Works Officer for purposes of appraising the project. The officer had since requested for more time to analyze the documents before undertaking physical visit to the project.

- List of projects affected by the expenditure of Kshs.4,469,679.67

| s/no | Project name | Project activity | Amount allocated | F/Y |
| --- | --- | --- | --- | --- |
| 1. | Torongo police Post | Completion of 1 no 4 roomed police post offices – plastering walls, cementing floors, doors and windows, painting, keying | 1,100,000 | 2020/21 |
| 2. | Kamelilo Primary school | Construction of one classroom to completion at ksh 700,000 and refurbishment of 3 classrooms floor, roof installation of window glasses, painting, verandah at ksh 300,000 | 1,000,000 | 2020/21 |
| 3 | Arama primary school | Refurbishment of 4 classrooms repairing floors, installation of window glasses, painting verandah, keying | 400,000 | 2020/21 |
| 4. | Kiplombe chiefs Office | Construction of 1 no 4 roomed chief’s office up to roofing level | 800,000 | 2020/21 |
| 5. | Saos chief’s office | Construction of 1 no 4 roomed chief’s office up to roofing level | 800,000 | 2020/21 |
| 6 | Simotwet primary school | Renovation of 4 classrooms plastering walls, cementing floor, repairs of roof, installation of window glasses and painting | 400,000 | 2020/21 |
|  |  | Totals | 4,500,000 |  |

- Summary of expenditure on the project

| S/No. | Paye | Amount Paid (Kshs) |
| --- | --- | --- |
| 1 | Main contractor (Chesrob) | 47,401,215.13 |
| 2 | Electrical works (Femsa) | 10,869,750.00 |
| 3 | Mechanical works (lenova) | 950,275.50 |
| 4 | Buildnett Consultants Ltd | 384,203.60 |
| 5 | Design Infinity Architects (Consultant) | 11,230,196.48 |
| 6 | Kenya Power | 55,855.00 |
| 7 | Nation Media Group | 278,336.00 |
| 8 | National Construction Authority | 96,031.76 |
| 9 | NEMA fees | 23,002.00 |
| 10 | Precise Civil Engineering Ltd | 40,000.00 |
| 11 | Qoolmax Enterprises Ltd | 324,178.20 |
| 12 | Mecol ltd (furniture) | 3,110,836.00 |
| 13 | Logenix International (clearance of books) | 826,988.00 |
| 14 | Project administration | 5,933,500.00 |
| 15 | Unclassified | 30,000.00 |
|  | Total | 81,583,688.61 |

- Members of the Project Management Committee (PMC) and signatories to the PMC account

According to MIN 6/25/06/2014 of the stakeholders meeting held on 25th June, 2014, the following were the PMCs and bank signatories as indicated below;

Members of project management team

| S/ NO | Name | Representation | Contact |
| --- | --- | --- | --- |
|  | Joseph Ayaibei | NGCDFC Chairman | 0723923079 |
|  | Patrick Baruett | Eldama Ravine Education Foundation (EREF) Chairman | 0722741641 |
|  | Juliana Muchai | Resource Mobilization officer KNLS | 0721702983 |
|  | Patrick Mugo | Architect Waitrose Foundation | Left the org. |
|  | Richard Ngeny | Environment and Safety officer Roses | Left the org |
|  | Jeremiah Chepkonga | Project Administrator Roses | 0722284401 |
|  | Francis Nganga | Sub county Public Works Officer | 0722562197 |
|  | Geoffrey Koech | Fund Account manager | 0712990222 |
|  | Samson Macharia | Deputy County Commissioner | Transferred |
|  | Dorcas Kibet | Sub county Administrator | Transferred |

Current active members

| s/ no | Name | Representation | Contact |
| --- | --- | --- | --- |
|  | Joseph Ayaibei | NGCDFC Chairman | 0723923079 |
|  | Patrick Baruett | EREF Chairman | 0722741641 |
|  | Jeremiah Chepkonga | Project Administrator roses | 0722284401 |
|  | John Kipkapto | EREF Representative | 0721566662 |
|  | Josphat Kigen | EREF Representative | 0711327503 |

Bank Signatories

| s/no | Organization | Nominee | ID no |  |
| --- | --- | --- | --- | --- |
|  | NGCDFC Eldama Ravine constituency | Joseph Ayaibei | 0482044 | Current signatory |
|  | Waitrose Foundation | Patrick Mugo | 8840692 | Left |
|  | Edama Ravine Education Foundation | Patrick Boruett | 11291554 | Current signatory |
|  | Kenya National Library Services | Juliana Muchai | 10876528 | Has never signed |

- Partners involved in the project

| s/no | Stakeholder | Role /Contribution |
| --- | --- | --- |
|  | Kenya National library Services | Provision of land for the project, equipping the library with books and equipment, staffing and ensuring project sustainability as well as membership in the project implementation |
|  | Waitrose Foundation | Contributed Kshs.5 million as initial funding for the project, membership in the project implementation team and approval of design tender documents |
|  | Eldama Ravine Constituency Development Fund | Provision of funds for the project, membership in the project implementation team, issue the designs as well as construction tender documents in consultation with project management team and overall coordination of the project implementation |
|  | Eldama Ravine Education foundation | Membership in the implementation team, Funding support |
|  | County Government | Follow up on funding support |

Committee’s recommendations

The matter to be discussed further at the Board level alongside the following recommendations;

- Management to formally write to the Fund Account Manager advising her to stop the process of handing over the project to the County Government by the KNLS.

- NG-CDFC to provide comprehensive report detailing the following;

- What informed construction of the office on a land belonging to the KNLS.

- Who prepared the designs and BQ for the project;

- Who procured the consultant;

- Who handed over the site

- Management to confirm availability of the following;

- Project’s monitoring reports undertaken by the Board and the recommendations therein,

- Audit reports undertaken on the project and recommendations

- Projects implementation status report from the Constituency

- Wajir East Constituency

The PPRM Committee in a meeting held on 18th January 2022 deliberated on projects’ verification report on three proposed roads and resolved that the;

- Fund Account Manager to explain why the NG-CDFC proposed grading works on a 12km stretch C975(5015) Riba -Konton Road (51kms) which was observed to be in good condition during the project verification. The FAM was also required to provide the correct status of the condition of the remaining 39 km road;

- Fund Account Manager explains why the NG-CDFC proposed to allocate funds for grading C975(G5360) Riba -Garsa road (28kms) while the road had already been done as observed during the verification visit;

- Fund Account Manager provides the current status of the condition of E5014 Khorofharar –Ausmudulle (42kms) which management was able to verify only 2kms due to security challenges.

A letter communicating the Committee’s resolutions was done and the FAM filed the following report;

That the Sub County had poor road network with narrow, dusty and rocky roads with more than 300kms poor roads linking to various centres making security operations a difficult process. The poor roads were aiding criminals in burying improvised explosive devices (IEDs) in the dusty and narrow roads. Based on these facts, the Wajir NG-CDFC received requests for funding for grading of the roads through ward forums at public barazas. The NG-CDFC later sought clarification from the Regional Manager, KeRRA on the status of the roads on four specific areas;

- The status of the proposed roads;

- Whether the roads were funded by KeRRA;

- Whether the roads fall under the mandate of National Government through KeRRA;

- The cost estimates of the proposed works.

The Wajir County KeRRA Regional Manager through a letter Ref.No.KeRRA/WAJ/006VOL (249) dated 6th September 2021 (Copy of the letter submitted to the Board) clarified the following;

- That the proposed roads were under KeRRA’s jurisdiction;

- That KeRRA had no maintenance plan for the roads for 2021/2022 Financial Year;

- That funding of the roads would bring about better facilitation, transport and accessibility;

- That they had no objection to the approval and funding of the roads.

Through the said letter, KeRRA provided cost estimates for the proposed works.

The above formed the basis for the NG-CDFC’s proposal.

Status of each road as highlighted by the FAM are indicated in the template below;

| No | Proposed Project (s) | Management Findings during the Visit | PPRM Committee’s Recommendations (18th January 2022) | FAM’s responses |
| --- | --- | --- | --- | --- |
|  | C975(5015) Riba -Konton Road - Grading 51kms to completion – Kshs.8,000,000 | - KeRRA confirmed the road is under their mandate vide letter dated 6th September, 2021 - A post by KeRRA showing spot improvement - Due to insecurity, the management covered only 12km - For the 12km covered, the road was gravelled, compacted and in good condition | Recommended for deferral Fund Account Manager to explain why they proposed grading works on a 12km stretch road which was observed during the verification visit that it was in a good condition. Fund Account Manager to provide the correct status on the condition of the remaining 39 km road | - That the road is within the Kenya-Somali Border and is more than 70kms but only 51kms was earmarked for grading - The condition of the road is deplorable - The road is narrow, sandy, with rocky patches, has deep pitches that need smooth grading - The grading is also aimed at clearing road obstacles including huge boulders, trees and shrubs - The road is dangerous and has led to many deaths as al-Shabaab had made it its hide out while security teams have problems plying the road due to its poor condition. - The 12kms covered by management were within the environs of Riba Town since they could not go further due to security threats. - The 12kms was not part of the 51kms road proposed for funding |
|  | C975(G5360) Riba -Garsa road - Grading 28kms to completion – Kshs.6,000,000 | - The road passes through Riba Girls secondary school - KeRRA confirmed the road is under their mandate vide letter dated 6th September, 2021 - The management covered 28km - The 28km was gravelled, compacted, some sections murramed and in good condition | Not recommended for approval Fund Account Manager to explain why they proposed to allocate funds to a road that had already been done. | - The road is rocky and dusty with deep pitches and in deplorable condition - The road is narrow and dangerous for security operations |
|  | E5014 Khorofharar –Ausmudulle - Grading 42kms to completion – Kshs.7,000,000 | - A post by KeRRA showing spot improvement - Of the 2km, a section was gravelled and in good condition - Management covered only 2km due to insecurity as confirmed by the Deputy County Commissioner - The remaining section was not maintained and was sandy. | Recommended for deferral Fund Account Manager to provide the current status on the condition of the road | - The Road is narrow and dusty with huge gullies making movement of security officials and general public difficult - The condition of the road is deplorable and requires grading to smoothen the surface, ensure proper drainage and removal of obstacles in the road including schrubs, trees and boulders that hinder accessibility of the road - That the 2km highlighted by the Management were within the interjection of the Khorofharar-Kotulo road which is not part of the 42km road that needs grading. That the officers could not go beyond the interjection within Khorofharar town due to security challenges - That the KeRRA notice Boards displayed on the roads did not indicate the activities or service funded but only intended to identify roads within KeRRA’s mandate. |

Committee’s recommendation

- Management to conduct a consultative meeting with the Fund Account Manager, KeRRA officials, Board management team who visited the roads among other key stakeholders with a view to ironing out the issues surrounding the proposed roads works.

- The Board to engage Kenya Rural Roads Authority with a view to holding discussions that enhances partnership in order to address the challenges experienced while deliberating on the proposed roads projects for various Constituencies.

- Suba North Constituency

Introduction

The Board in its meeting held on 22nd November, 2021 deliberated on the projects proposal for Suba North NG-CDF and resolved that all other proposed projects be approved apart from proposed purchase of fifteen (15) security patrol boats projects which were deferred subject to management carrying out project monitoring in the Constituency with a view of establishing the status of previous boats bought through the Fund in terms of ownership (registration), management and sustainability. It was noted between 2018/19 and 2020/21 financial years, the Constituency had allocated funds towards purchase of six (6) patrol boats which were approved by the Board and funds disbursed for implementation of the same.

In view of the above, the management visited the constituency on 5th March, 2022.

Objectives of the Visit

- To establish the status of the previous boats bought through the Fund;

- To establish how the boats were managed and sustained;

- To engage with the various Beach Management Units and get to understand reasons for request of the boats.

Methodology

In order to achieve the above objectives, the team adopted a qualitative approach as this would help in selection of appropriate sample that would be useful in providing the necessary information about the project. The main method that was used in collecting information regarding the conceptualization and implementation of the boats project was in-depth interviews of key stakeholders. The method helped in eliciting individual experiences, opinions and perceptions.  A purposive sampling method was used to select the informants based on the team’s judgement on the most representative or informative ones. The team aimed at conducting 6 in-depth interviews, but only managed to carry out 2 interviews because of time constraints as some of the Beach Management Units were located on the islands.

Background

To achieve its objective, the team held discussions with the chairman of Homabay County Beach Management Units. It was established that the Beach Management Units were governed by the Fisheries Act Cap 378 which was charged with the responsibility to provide for development, management, exploitation, utilization and conservation of fisheries.

The BMU Network was founded in 2007 and reconstituted through a democratic free and fair election process held every four years guided by the legal framework of Fisheries Management and Development Act No. 35 and the BMU Regulation 2007 Gazette Notice 402.

In this legal arrangement, each and every landing site has an Executive Committee whose membership varied from 9 to 15 people elected every four years charged with the responsibility of day to day running of the landing sites. The committee was headed by an executive Chairman pursuant to the Section 25 of the BMU Regulations.

The mandate of the BMU is to strengthen Fisheries Management through cooperation and harmonization of guideline/policies, lobbying and advocacy by identifying and creating collaboration with strategic partners, creating business linkages through marketing and value addition for its members and ensuring proper governance of the BMUs and the BMU Networks at all levels based on the principles and sustainable exploitation of Lake Victoria Fisheries resources and ecosystem management.

Considering that the landing sites also served as entry points, the BMUs worked closely with the Ministry of Interior and Coordination of National Government in matters of security through information sharing, surveillance of the landing sites as well as the Lake.

Whereas Fisheries is a devolved function, fishing still remains a National Government function pursuant to the fourth schedule of the Constitution of Kenya hence Beach Management Unit endeavor working together with the National Government in order to guarantee safety and security of fishermen. The patrol boats are instrumental in surveillance and security of the fishermen and the fishing gears in the Lake, response to cross-border conflict and piracy in the Lake, response to incidences of accidents i.e. search and rescue mission and retrieval of bodies in cases of loss of life.

Suba North Constituency is ranked among the leading fishing sites in the whole Homabay County with a total of 62 beaches. To address the challenges mentioned, the units at the locational level approached NG-CDF Suba North for security patrol boats. A case in point was Kisui Beach Management whose membership comprised of 13 members. To be a member of the unit, one was required to have engaged in day-to-day fishing activities in a particular beach a member and pay a registration fee regardless of his/her origin. The unit cited the above-mentioned challenges as a hindrance towards achievement of their economic activities in the lake. It was also noted that the unit had only approached NG-CDF for funding.

Implementation

The Beach Management Unit executive committee was the project management committee. Once funds were disbursed to the PMC account, the PMC initiated procurement oversighted by the NG-CDFC. The uniqueness of the project was that construction materials mainly wood was imported from Congo due to its durability. Also, boat engines were carefully selected from the genuine dealers.

The team managed to inspect one of the patrol boats previously purchased by NG-CDFC and established that it was in a good condition.

Ownership, Management and sustainability

The main custodian of the boats was the Ministry of Interior and Coordination of the National Government (Deputy County Commissioner) who oversighted matters security at the Sub County level. Beach Management Units were charged with the day to day running of the activities of the boats. In each of the units, there was a Monitoring, Control and Surveillance (MCS) Sub Committee comprising of between 5 to 7 members of the Unit in accordance to the regulation and depending on the relevant unit by-laws. Its main function was to administer the daily activities of the boats by recording the number of times the security patrol boat went into the lake and for what purpose. The same was counter signed by the BMU Ward Chairperson, Sub County BMU Chairpersons and a copy shared with the Deputy County Commissioner. Each unit kept a separate asset register. The unit also maintained an asset register. Further, each unit endeavored to cater for training cost of at least one coxswain and a boat crew who operated the vessel in accordance to the Kenya Maritime Authority Act.

The boats once inspected by the Kenya Maritime Authority were registered with an identification number written on the boat. Currently, the Authority is working on a metallic number plate. It was reported that the cost of registration of one boat was currently Kshs.6,000 hence considerably high from the initial cost of Kshs.600. Sustainability of the project in day to day maintenance, fueling, services, repair and safety/ security of the patrol boats was the responsibility of the BMU/PMC. This was done using the funds solicited by the Beach Management Unit from their membership for purposes of administration and service delivery at the landing sites in accordance to the BMU Regulations and the By-laws.

It was reported that a patrol boat could last up to 7 years before repairs and 4 more years after the 1st repair. The lifespan of the engines was comparable to car’s.

Record keeping

The Project Management Committee’s original files were kept at the Fisheries department at the sub county and a copy of the same was maintained at the NG-CDF Office.

Gaps noted

- Documentation- It was noted that the project files were not with the Project Management Committee. A case in point is the Lwanda Beach Management Unit;

- Absence of Acceptance and Inspection Committee- The NG-CDFC explained that there was no officer at the Sub County to undertake supervision of the boats during construction;

- Branding- the boats were not well labelled;

Management’s Recommendations

- The NG-CDFC was advised to ensure project files were kept in every BMU office;

- NG-CDFC to ensure that the boats are branded using the specifications provided by the Board;

- The Board to formally request the services of the relevant government department in order to ensure that technical officers are deployed to the Sub Counties under which similar programmes were being undertaken. This is to ensure that quality of work;

- NGCDFC to ensure constitution of the acceptance and inspection committee.

Management’s Request

Management requested the PPRM Committee to approve the proposed purchase of fifteen (15) security patrol boats as follows: -

Purchase of 15 complete security patrol boat: 30 feet sessa flat boat, 40 horsepower outboard engine with fuel line, tool kit and branding for each of the following beach management units;

- Takawiri Island Beach Management Unit,

- Mrongo Beach Management Unit,

- Wakula Beach Management Unit,

- Wayando Beach Management Unit,

- Kisaka Beach Management Unit,

- Olambwe Beach Management Unit,

- Mbita Fish Banda Beach Management Unit,

- Kisui Beach Management Unit,

- Ulugi Beach Management Unit,

- Kigoda Beach Management Unit,

- Nyagina Beach Management Unit,

- Dho'Gunda Beach Management Unit,

- Mirunda Beach Management Unit,

- Tabla Beach Management Unit

- Koguna Beach Management Unit

(each boat costs Kshs.700,000) hence totaling to Kshs. 0,500,000

Committee’s recommendations

Recommended for approval

Sampled photos

Lwanda Nyamasare BMU patrol Boat

Kisui Beach Management Unit

Annex V

Report on requests for disposal of old constituency vehicles

| No | Constituency Name | Number of vehicles to be disposed | Vehicles Make, Year Bought, Chassis Number, Year of Manufacture and Registration Number | NG-CDFC’s Resolution | Mechanical Engineers recommendations | Board of Survey Recommendations | Committee’s Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Mosop | 1 | GKA 916U Toyota Hilux Chasis Number: AHTFR22G306028980 Year of Manufacture: 2010 Year Bought: 2010 | The vehicle has become expensive to maintain hence needs to be disposed. | The vehicle is uneconomical to repair at an estimated cost of Kshs.1.2 million | The vehicle to be disposed through open tender at salvage value Kshs.500,000 | Recommended approval |

REPORT CONFIRMED BY:-

Signed...................................  						Signed...................................

Mr. Yusuf Mbuno							Ms. Maria Lekoloto

Chief Executive Officer						Chair, PPRM Committee

Date………………............. 						Date…………….................