|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/No. | Constituency | NG-CDFC Minutes No/Date | Approved Projects | F/Y | Amount Requested ( Kshs.) |  Newly Proposed projects and Amount ( Kshs) | Reasons for reallocation of funds or change of activity | Secretariats Recommendation |
| 1. | Gatanga | Min 11 of 02/08/2022 | Ngatho Chief's Office Kshs.1,000,000- Construction of 3 roomed Office to completion. | 2020/2021 | 1,000,000 | Gatanga courts Kshs.3,500,000- Landscaping of 1 acre courts compound: Gravelling, leveling, cabros works and construction of sheds. | Due to preparation of landscaping for the Gatanga courts since it is inaccessible and the courts were ready to be commissioned and they could not since the landscaping of the area was not accessible. | **Recommended for Approval** |
| Mukarara chief office Kshs.500,000- Renovation of 15 capacity Office for Youth Empowerment Centre; Painting and Key pointing. | 500,000 |
| Mitumbiri assistant county commissioner office Kshs.2,000,000- Construction of a 5 roomed assistant countycommsisioner office: substructure works, walling and roofing. | 2,000,000 |