## Sheet1
Saku | 137367724.14 | Manyatta Daba Primary School-440,000- Completion of classroom -installation of windows, doors and floor-being balance of contract price (Sh.200,000), declined and purchase of 30 metal-frame pupil's desks (sh. 240,000) NB; The contract price was Sh.1.5million in 2018/19 | Issue not cleared
|  | Karare Primary School-1,050,000- Completion of construction of one classroom-roofing, plastering, painting,fixing of door and windows,flooring, (sh. 906,000) and purchase of 18 metal-frame pupil's desks (sh. 144,000). NGCDFC to revise cost to 1.2 | Issue not cleared
|  | Jaldesa Primary School- 920,000- Rehabilitation of 2 classrooms (repair of walls, roof, windows, -sh.600,000) and Purchase of 40 metal-frame pupils desks (sh. 320,000). NGCDFC to revise cost of desks | Issue not cleared
|  | Kituruni Primary School- 1,620,000- Construction of one classrooms to completion (sh. 1,500,000) NGCDGC to revise cost to 1.2 and Supply of 15 metal-frame pupil's desks (sh.120,000) NGCDFC to revise cost of desks | Issue not cleared
|  | Segel Primary School- 800,000- Purchase of 50 metal-frame pupils desks (sh. 400,000) and construction of 1no. 2-door pit latrines to completion (sh. 400,000). NGCDFC to revise cost of desks | Issue not cleared
|  | Moi Girls Secondary School -4,000,000- Construction of Dormitory from foundation to roofing level to accommodate 80 students. NGCDFC to revise cost | Issue not cleared
|  | Dakabaricha Mixed Secondary School- 2,000,000-Construction of one classroom to completion with concrete roof for future expansion (sh. 1,600,000) and puchase of 50 students lockers and chairs (sh. 400,000) revise cost of classrooms and desks | Issue not cleared
|  | Saku High School - 2,700,000- Completion of Dormitory to serve 80 students (internal finishes, floor, paint, fixing of doors and windows, electrical works). NGCDFC to revise cost | Issue not cleared
|  | NG-CDF Office-5,000,000- Completion of construction of NG-CDF Offices storey building -Roofing (Sh. 2,300,000),Fixing of Doors (Sh. 500,000),Fixing of Windows (Sh. 600,000) and Electrical Works (Sh.1,600,000) Number of offices. From description funds allocated are adequate hence no additional funds should be allocated next f/y. NGCDFC to submit Designs and BoQs | Issue not cleared
|  | NG-CDF Motor bike- Purchase of NG-CDF Motor bike (Toyota DT 125cc) - Kshs 600,000 NGCDFC to revise cost | Issue not cleared