KILGORIS

IEBC NUMBER 177

NATIONAL GOVERNMENT CONSTITUENCY DEVELOPMENT FUND

PROJECT PROPOSAL

2017/2018 FINANCIAL YEAR

SUBMITTED

JANUARY 2018

- REPUBLIC OF KENYA

- KILGORIS CONSTITUENCY

| Kilgoris NG-NG CDF Building |  | P.O Box 361-40700 |
| --- | --- | --- |
|  |  | Kilgoris. |
| OFF Kisii - Kilgoris Road, |  | Cell: 0722 405 245 |
| E mail: muange5@yahoo.com |  |  |

MINUTES OF NG CDF COMMITTEE MEETING HELD ON 17THJANUARY, 2017 AT THE KILGORIS CONSTITUENCY BOARDROOM AT 12.30 PM

MEMBERS PRESENT

- Shadrack Kasy Seiyio			                 Chairperson

- Ruth Naiduya Saisi   Member		                Secretary

- Isaac Lemayian Musunkui                                       Member

- Bancy Cherono Korir                                              Member

- David Karuiki Wainaina                                          Member

- Samwel Naikada                                                      Member

- Mary Ampany                                                          Member

- John Megorokini. Kirentuan	              	   Member

- Hassan 	Nuru Muhammed	                      	   DCC

- Gedion Konchella	   	                                      Member of Parliament

- Benson Aseka                                                        District Accountant

AGENDA

- Confirmation Of Previous Meeting Minutes

- NG CDF Projects Proposal For Financial Year 2017/2018 Revision

- A.O.B

PRELIMINARIES

The meeting started with prayers led by the fund account manager. The chair welcomed the members to the meeting and asked them to be ready to deliberate on the meeting’s agenda.

MIN 01/01/2018. CONFIRMATION OF PREVIOUS MEETING MINUTES:

The meeting was started with the word of prayer from Benson Aseka and the Chairman welcomed all members and thanked them for being punctual, he urged members to contribute to the meeting agenda. The secretary read through the minutes of the previous meeting. The minutes were confirmed to be the true copy of the deliberations held by Charles Ndegwa who was seconded by Ann Wacheke.

MIN 02/01/2018: NG CDF PROJECTS PROPOSAL BUDGET FOR FINANCIAL YEAR 2017/2018

The Chairman briefed members that the committee had already submitted the proposals for the financial year 2017/2018 in time but there were changes in the allocation. The funds for each constituency had been scaled downwards to kshs. 86,810,344.83 From kshs. 101,416,090.34 With emergency at kshs. 4,568,965.52. Therefore, members were required to amend the project proposal downwards to comply with the changes.

After lengthy deliberations the NG - NG CDF committee agreed on the following projects to be funded in the Financial Year 2017 –2018 in all the four wards in the Constituency. Priority was given to the ongoing projects.

| Project name | Project code | Allocation | Proposed activity | Status |
| --- | --- | --- | --- | --- |
| Goods and Services 3% | 4-033-177-2210000-111-2017/2018-001 | 887,241.11 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence. | Ongoing |
| Committee Expenses 3% | 4-033-177-2210802-111-2017/2018-002 | 900,000.00 | Payment of Committee sitting allowances, transport, conferences | Ongoing |
| NG CDFC/PMC Capacity Building 3% | 4-033-177-2210700-111-2017/2018-003 | 680,000.00 | Undertake Training of the PMCs/NG CDFCs on NG CDF Related issues | Ongoing |
| Employees’ Salaries-6% | 4-033-177-2110000-100-2017/2018-001 | 1,980,000.00 | Payment of staff salaries, PAYE and gratuity | Ongoing |
| Goods and Services-6% | 4-033-177-2210000-100-2017/2018-002 | 960,000.00 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea. | Ongoing |
| NSSF | 4-033-177-2120500-100-2017/2018-003 | 135,000.00 | Payment of NSSF Deductions | Ongoing |
| NHIF | 4-033-177-2120200-100-2017/2018-004 | 45,000.00 | Payment of NHIF Deductions | Ongoing |
| Committee Allowances -6% | 4-033-177-2210802-100-2017/2018-006 | 1,814,482.00 | Payment of Committee allowances | Ongoing |
| Strategic plan | 4-033-177-2211310-108-2017/2018- 007 | 3,500,000.00 | Implementation of Constituency five year Strategic plan ,holding consultative forums, technical evaluation by consultants, validation, collection of constituency fact sheet data and launching | New |
| Kilgoris NG CDF office | 4-033-177-3110202-108-2017/2018-001 | 2,000,000.00 | Purchase of office furniture & equipment i.e 2executive tables @ksh 56,000, 2executive chairs @ 56,000, 110 conference chairs @ ksh 8,500 (for NG-NG CDFC Hall),3 office tables @ ksh 30,000,3 computers @ ksh 90,000,2 printers @ ksh 50,000, 10high back office chairs @ksh 15,000,photocopier @ ksh 300,000 & projector @ kshs 60,000. | New |
| Emergency | 4-033-177-2640200-101-2017/18-001 | 4,568,965.52 | To cater for any unforeseen occurrences in the constituency during the financial year | Ongoing |
| Constituency Sports Tournament | 4-033-177-2640509-112-2017/18-001 | 1,433,739.00 | Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits | Ongoing |
| Environment | 4-240- 177-2640510-109-2017/2018-001 | 300,000.00 | Purchase & distribution of tree seedlings to various schools, Ilparishe, Shankoe &Poroko primary schools each at ksh.100,000.00 | Ongoing |
| Bursary secondary schools | 4-033-177-2640101-103-2015/2016-001 | 15,000,000.00 | To cater for needy/&bright students in secondary schools | Ongoing |
| Bursary tertiary institutions ,Colleges & universities | 4-033-177-2640102-103-2015/2016-002 | 5,600,000.00 | To cater for needy/&bright students in, tertiary institutions & universities | Ongoing |
| Social security programmes-NHIF | 4-033-177-2120201-103-2016/17-003 | 4,200,000.00 | Payment for NHIF targeting OVC, poor older persons, PWD's, poor widows & widowers & destitute families’ | New |
| Constituency innovation Hub (CIH)at Keiyan | 4-033-177-2211311-111-2017/2018- 003 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Constituency innovation Hub (CIH) at lolgorian | 4-033-177-2211311-111-2017/2018- 004 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Constituency innovation Hub (CIH)at central | 4-033-177-2211311-111-2017/2018- 005 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Constituency innovation Hub (CIH)at Shankoe | 4-033-177-2211311-111-2017/2018- 006 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Narrolong primary school | 4-033-177-2630204-103-2017/18-001 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Enkiwancha primary school | 4-033-177-2630204-103-2017/18-002 | 2,000,000.00 | Construction of two classrooms to completion | New |
| Bokoria primary school | 4-033-177-2630204-103-2017/18-003 | 1,000,000.00 | Construction of six door pit latrines for boys and girls | New |
| Enkoiperiai primary school | 4-033-177-2630204-103-2017/18-004 | 1,000,000.00 | Renovation of 6 classrooms, re-roofing, purchase of two water tanks & gutters | New |
| Sosio primary school | 4-033-177-2630204-103-2017/18-005 | 1,500,000.00 | Completion of three classrooms, plastering, external & internal finishes & painting. | Ongoing |
| Kaptembwa primary school | 4-033-177-2630204-103-2017/18-006 | 1,000,000.00 | Completion of two classrooms, plastering, external & internal finishes & painting. | Ongoing |
| Karda primary school | 4-033-177-2630204-103-2017/18-007 | 1,000,000.00 | Renovation of four classrooms re-roofing, flooring & painting | New |
| Mashankwa primary school | 4-033-177-2630204-103-2017/18-008 | 1,000,000.00 | construction of one classroom to completion | New |
| Shankoe primary school | 4-033-177-2630204-103-2017/18-009 | 1,000,000.00 | Renovation of 8 classrooms , | New |
| Sitoka primary school | 4-033-177-2630204-103-2017/18-010 | 2,500,000.00 | Plumbing works & plastering ,internal & external finishes & painting of dormitory | Ongoing |
| Ildolisho primary school | 4-033-177-2630204-103-2017/18-011 | 2,000,000.00 | Completion of dormitory, plastering, fixing doors & windows, flooring, external & internal finishes & painting | Ongoing |
| Angata primary school | 4-033-177-2630204-103-2017/18-012 | 500,000.00 | Completion of dormitory, plastering ,internal & external finishes & painting | Ongoing |
| Pimbinet primary school | 4-033-177-2630204-103-2017/18-013 | 500,000.00 | Purchase & installation of Two water tanks of each 10,000 lts & gutters for water harvesting & construction of tank stands | New |
| Oldonyo Rok primary | 4-033-177-2630204-103-2017/18-014 | 500,000.00 | Completion of dormitory, internal, external finishes & painting. | Ongoing |
| Mashankwa primary school | 4-033-177-2630204-103-2017/18-015 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting of dormitory | Ongoing |
| Tororek primary school | 4-033-177-2630204-103-2017/18-016 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting | Ongoing |
| Ntulele secondary school | 4-033-177-2630205-104-2017/18-001 | 1,500,000.00 | Completion of four classrooms, plastering flooring, internal & external finishes & painting | Ongoing |
| Olalui secondary school | 4-033-177-2630205-104-2017/18-002 | 2,628,890.00 | Construction of a Dormitory | New |
| Ongata girls secondary school | 4-033-177-2630205-104-2017/18-003 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Remosha secondary school | 4-033-177-2630205-104-2017/18-004 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Enoosaen secondary school | 4-033-177-2630205-104-2017/18-005 | 3,000,000.00 | Construction of a dining hall | New |
| Metunkuar secondary school | 4-033-177-2630205-104-2017/18-006 | 2,000,000.00 | Construction of a Dormitory | New |
| Angata Secondary school | 4-033-177-2630205-104-2017/18-007 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting | Ongoing |
|  | Total | 86,810,344.83 |  |  |

The committee members requested the Fund Account Manager to expedite the necessary documentation for project proposal for approval by NG-NG CDF Board. The committee also requested the Area MP to follow up with the board for speedy approval of the proposal.

MIN: NG CDFC 03/ 01/2018	ADJOURNMENT

There being no other business, the meeting ended at 2.00pm with a word of prayer from Ruth Saisi

Minutes Taken by:

NG CDFC Secretary: Ruth Saisi                                      Sign_______________________

Confirmed by:

NG CDFC Chairman: Shadrack Seiyio                              Sign_______________________

907

2015                     National Government Constituencies Development Fund                                       No. 30

THIRD SCHEDULE                                                    (s. 15)

CONSTITUENCY PROJECTS SUBMISSION FORM

Constituency No 177 Constituency Name KILGORIS Financial Year 2017/2018

| Serial | Name of Project | Amount Allocated |
| --- | --- | --- |
| 177/AP1 | Administration/Recurrent | 4,934,482.00 |
| 177/AP2 | Monitoring and Evaluation/Capacity Building | 2,467,241.11 |
| 177/2640100 | Bursary & Social programs | 24,800,000.00 |
| 177/2630204 | Primary School Projects | 21,500,000.00 |
| 177/2630205 | Secondary School Projects | 16,628,890.00 |
| 177/2211310 | Constituency Innovation Hubs | 4,677,027.20 |
| 177/2211310 | Strategic plan | 3,500,000.00 |
| 177/3110104 | NG-NG CDF office | 2,000,000.00 |
| 177/2640509 | Sports Activities | 1,433,739.00 |
| 177/2640510 | Environmental Projects | 300,000.00 |
| 177/2640200 | Emergency | 4,568,965.52 |
| Total |  | 86,810,344.83 |

Chairman NG- NG CDF Committee: Shadrack Seiyio Signature………………….. Date: 17th January, 2018

Fund Account Manager: Eric Muange                   Signature………………. Date: 17th January, 2018

907

2015               National Government Constituencies Development Fund                              No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 Constituency Name KILGORIS   County: NAROK

Project Number 177/AP1

Project Title 6% Administration/Recurrent

Sector Administration

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

The allocation is to cater for NG CDFC Allowance, staff salaries, vehicle expenses and other administrative

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs. 4,934,482.00dated: 17th January, 2018

Amount allocated last financial year Kshs. 4,913,793.10

Amount allocated this financial year   Kshs. 4,934,482.00

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Employee Salaries | 4-018-177-2110000-100-2017/18-001 | Payment of staff salaries and gratuity | 1,980,000.00 | On-going |
| Goods and Services | 4-018-177-2210000-100-2017/18-002 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea | 960,000.00 | On-going |
| NSSF | 4-018-177-2120101-100-2017/2018-003 | Payment of NSSF Deductions | 135,000.00 | On-going |
| NHIF | 4-018-177-2120201-100-2017/18-004 | Payment of NHIF Deductions | 45,000.00 | On-going |
| Committee Expenses | 4-018-177-2210802-100-2017/18-005 | Payment of Committee sitting allowances, transport, conferences | 1,814,482.00 | On-going |
| TOTAL |  |  | 4,934,482.00 |  |

Person completing form: Name: Eric Muange        Position Fund Account Manager

Signature……………………..Date: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name: KILGORIS	County: NAROK

Project Number 177/AP2

Project Title 3% Monitoring & Evaluation/Capacity Building

Sector Monitoring & Evaluation

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To cater for Monitoring and Evaluation of NG CDF projects and capacity building of NG CDFC and PMCs in the constituency

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 2,467, 241.11 dated 17th January, 2018

Amount allocated last financial year: kshs. 2,456, 896.55

Amount allocated this financial year: kshs.  2,467,241.11

| Project Name | Project Number | Activity | Amount | Status |
| --- | --- | --- | --- | --- |
| Goods and Services | 4-018-177-2210000-111-2017/18-001 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence | 887,241.11 | On-going |
| Committee Expenses | 4-018-177-2210802-111-2017/18-002 | Payment of Committee sitting allowances, transport, conferences | 900,000.00 | On-going |
| NG CDFC/PMC Capacity Building | 4-018-177-2210700-111-2017/2018-003 | Undertake Training of the PMCs/NG CDFCs on NG CDF Related issues | 680,000.00 | On-going |
| TOTAL |  |  | 2,467,241.11 |  |

Person completing form:  Name   Eric Muange    Position Fund Account Manager

Signature…………………… Date: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name: KILGORIS	County: NAROK

Project Number 177/2640200

Project Title Emergency Reserve (5% of the fund)

Sector Emergency

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Unallocated amount meant for unforeseen   emergencies that may occur within the Constituency

Financial year 2017 1st July To 30th June 2018

Original Cost estimates, in Kshs. 4,568,965.52dated: 17th January, 2018

Amount allocated last financial year 4,094,827.59

Amount allocated this financial year   Ksh.   4,568,965.52

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Emergency | 4-018-177-2640200-101-2017/18-001 | To cater for any unforeseen occurrences in the constituency during the financial year | 4,568,965.52 | On-going |
| Total |  |  | 4,568,965.52 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Date: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177		Constituency Name:  KILGORIS		County: NAROK

Project Number 177/2640509

Project Title 2% Sports Activities

Sector Sports

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Purchase of uniform & balls for constituency teams

Financial year 2017   1st July To 30th June 2018

Original Cost estimates:  in Kshs. 1,433,739.00	Dated: 17th January, 2018

Amount allocated last financial year:  Kshs.300, 000.00

Amount allocated this financial year: Kshs.  1,433,739.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Constituency Sports Tournament | 4-018-177-2640508-112-2017/2018-001 | To Carry out Constituency Sports tournament and teams/schools to be given trophies, balls, and sports kits i.e. balls, uniforms in the constituency | 1,433,739.00 | On-going |
| Total |  |  | 1,433,739.00 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature……………………Date: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name:  KILGORIS	County: NAROK

Project Number 177/31110104 Project Title NG-NG CDF OFFICE

Sector: Others

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Purchase of office furniture & equipment

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 2,000,000.00 dated: 17th  January, 2018

Amount allocated last financial year:  Nil

Amount allocated this financial year: Kshs.  2,000,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Kilgoris NG CDF Office | 4-018-177-3110202-108-2017/2018-001 | Purchase of office furniture & equipment i.e 2executive tables @ksh 56,000, 2executive chairs @ 56,000, 110 conference chairs @ ksh 8,500 (for NG-NG CDFC Hall),3 office tables @ ksh 30,000,3 computers @ ksh 90,000,2 printers @ ksh 50,000, 10high back office chairs @ksh 15,000,photocopier @ ksh 300,000 & projector @ kshs 60,000. | . 2,000,000.00 | New |
| Total |  |  | 2,000,000.00 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Dated: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name:  KILGORIS	County: NAROK

Project Number 177/2211311   Project Title: Constituency Strategic plan

Sector: Others

Status of projects (tick one) New……√………. Extension……………….. On-going……..…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Implementation of constituency strategic plan

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 3,500,000.00 dated: 17th January, 2018

Amount allocated last financial year:  Nil

Amount allocated this financial year: Kshs.  3,500,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Constituency Strategic Plan | 4-018-177-2211311-108-2017/2018-001 | Implementation of five year Constituency Strategic plan ,holding consultative forums, technical evaluation by consultant, validation, collection of constituency fact sheet data and launching | 3,500,000.00 | New |
| Total |  |  | 3,500,000.00 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Dated: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name:  KILGORIS	County: NAROK

Project Number 177/2211310   Project:  Title: Constituency Innovation Hubs

Sector: Others

Status of projects (tick one) New……√………. Extension……………….. On-going……..…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Installation of Satellite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 4,677,027.20dated: 17th January, 2018

Amount allocated last financial year:  Nil

Amount allocated this financial year: Kshs.  4,677,027.20

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Constituency innovation Hub(CIH) at Keiyan | 4-018-177-2211311-111-2017/2018- 001 | Installation of satellite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | 1,169,256.80 | New |
| Constituency innovation Hub(CIH) at Lolgorian | 4-018-177-2211311-111-2017/2018- 002 | Installation of satellite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | 1,169,256.80 | New |
| Constituency innovation Hub(CIH) at Central | 4-018-177-2211311-111-2017/2018- 003 | Installation of satellite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | 1,169,256.80 | New |
| Constituency innovation Hub (CIH) at Shankoe | 4-018-177-2211311-111-2017/2018- 004 | Installation of satellite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | 1,169,256.80 | New |
| Total |  |  | 4,677,027.20 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Dated: 17th January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name: KILGORIS	 	County: NAROK

Project Number 177/2640100

Project Title Bursary /Social Security Programme

Sector Bursary

Status of projects (tick one) New………………. Extension……………….. On-going…√….. Rehabilitation ………………….

Brief statement on project status at time of submission

Towards Bursary for payment of fees for needy students

Financial year 2017   1st July To 30th June 2018

Original Cost estimates: in Kshs. 24,800,000.00	Dated: 17th January, 2018

Amount allocated last financial year: kshs   20,474,138.00

Amount allocated this financial year: Kshs. 24,800,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Bursary Secondary Schools | 4-018-177-2640101-103-2017/2018-001 | Payment of bursary to needy students in secondary schools | 15,000,000.00 | On-going |
| Bursary Tertiary institutions(Colleges & Universities) | 4-018-177-2640102-103-2017/2018-002 | Payment of bursary to needy students in colleges and universities | 5,600,000.00 | On-going |
| Social security programme | 4-018-177-2120201-103-2017/2018-003 | Payment for NHIF targeting OVC, poor older persons, PWD's & destitute families | 4,200,000.00 | On-going |
| TOTAL |  |  | 24,800,000.00 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature……………………Date: 17th  January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name:  KILGORIS		County: NAROK

Project Number 177/2630205

Project Title secondary Education Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions in the Secondary schools institutions by improving the infrastructure

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 16,628,890.00   dated:  17th  January, 2018

Amount allocated last financial year:  Kshs. 12,600,000.00

Amount allocated this financial year:  Kshs. 16,628,890.00

| Project name | Project code | Allocation | Proposed activity | Status |
| --- | --- | --- | --- | --- |
| Ntulele secondary school | 4-033-177-2630205-104-2017/18-001 | 1,500,000.00 | Completion of four classrooms, plastering flooring, internal & external finishes & painting | Ongoing |
| Olalui secondary school | 4-033-177-2630205-104-2017/18-002 | 2,628,890.00 | Construction of a Dormitory | New |
| Ongata girls secondary school | 4-033-177-2630205-104-2017/18-003 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Remosha secondary school | 4-033-177-2630205-104-2017/18-004 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Enoosaen secondary school | 4-033-177-2630205-104-2017/18-005 | 3,000,000.00 | Construction of a dining hall | New |
| Metunkuar secondary school | 4-033-177-2630205-104-2017/18-006 | 2,000,000.00 | Construction of a Dormitory | New |
| Angata Secondary school | 4-033-177-2630205-104-2017/18-007 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting | Ongoing |
|  | Total | 16,628,890.00 |  |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Date: 17th  January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name: KILGORIS	 County:  NAROK

Project Number 177/2630204

Project Title Primary School Projects

Sector Education

Status of projects (tick one) New………………. Extension……………….. On-going…√…..

Rehabilitation ………………….

Brief statement on project status at time of submission

To enhancing better learning conditions of primary by improving the infrastructure

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. Ksh. 36,156,896.48dated: 17th January, 2018

Amount allocated last financial year: Ksh. 21,500,000.00

Amount allocated this financial year: Ksh. 36,156,896.48

| Project name | Project code | Allocation | Proposed activity | Status |
| --- | --- | --- | --- | --- |
| Narrolong primary school | 4-033-177-2630204-103-2017/18-001 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Enkiwancha primary school | 4-033-177-2630204-103-2017/18-002 | 2,000,000.00 | Construction of two classrooms to completion | New |
| Bokoria primary school | 4-033-177-2630204-103-2017/18-003 | 1,000,000.00 | Construction of six door pit latrines for boys and girls | New |
| Enkoiperiai primary school | 4-033-177-2630204-103-2017/18-004 | 1,000,000.00 | Renovation of six (6) classrooms, re-roofing, External & internal finishes | New |
| Sosio primary school | 4-033-177-2630204-103-2017/18-005 | 1,500,000.00 | Completion of three classrooms, plastering, external & internal finishes & painting. | Ongoing |
| Kaptembwa primary school | 4-033-177-2630204-103-2017/18-006 | 1,000,000.00 | Completion of two classrooms, plastering, external & internal finishes & painting. | Ongoing |
| Karda primary school | 4-033-177-2630204-103-2017/18-007 | 1,000,000.00 | Renovation of four classrooms re-roofing, flooring & painting | New |
| Mashankwa primary school | 4-033-177-2630204-103-2017/18-008 | 1,000,000.00 | construction of one classroom to completion | New |
| Shankoe primary school | 4-033-177-2630204-103-2017/18-009 | 1,000,000.00 | Renovation of 8 classrooms , plastering ,internal & external finishes & painting | New |
| Sitoka primary school | 4-033-177-2630204-103-2017/18-010 | 2,500,000.00 | Completion ,Plumbing works & plastering ,internal & external finishes & painting of dormitory | Ongoing |
| Ildolisho primary school | 4-033-177-2630204-103-2017/18-011 | 2,000,000.00 | Completion of dormitory, plastering, fixing doors & windows, flooring, external & internal finishes & painting | Ongoing |
| Angata primary school | 4-033-177-2630204-103-2017/18-012 | 500,000.00 | Completion of dormitory, plastering ,internal & external finishes & painting | Ongoing |
| Pimbinet primary school | 4-033-177-2630204-103-2017/18-013 | 500,000.00 | Purchase & installation of Two water tanks of each 10,000 lts & gutters for water harvesting & construction of tank stands | New |
| Oldonyo Rok primary | 4-033-177-2630204-103-2017/18-014 | 500,000.00 | Complete, ,internal & external finishes & painting of dormitory | Ongoing |
| Mashankwa primary school | 4-033-177-2630204-103-2017/18-015 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting of dormitory | Ongoing |
| Tororek primary school | 4-033-177-2630204-103-2017/18-016 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting | Ongoing |
|  | Total | 21,500,000.00 |  |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Date: 17th  January, 2018

907

2015 National Government Constituencies Development Fund No. 30

FOURTH SCHEDULE (s. 16)

PROJECT DESCRIPTION FORM

Constituency No: 177 	Constituency Name:  KILGORIS	County: NAROK

Project Number 177/2640510   Project Title: Environment

Sector: Environment

Status of projects (tick one) New……√………. Extension……………….. On-going……..…..

Rehabilitation ………………….

Brief statement on project status at time of submission

Establishment of Constituency tree nursery

Financial year 2017   1st July To 30th June 2018

Original Cost estimates, in Kshs. 300,000.00 dated: 17th January, 2018

Amount allocated last financial year:  300,000.00

Amount allocated this financial year: Kshs.  300,000.00

| Project Name | Project Code | Project Activity | Amount Allocated | Status |
| --- | --- | --- | --- | --- |
| Environment | 4-018-177-2640510-108-2017/2018-001 | Purchase & distribution of tree seedlings to various schools, Ilparishe, Shankoe &Poroko primary schools each at ksh.100,000.00 | 300,000.00 | New |
| Total |  |  | 300,000.00 |  |

Person completing form: Name Eric Muange   Position Fund Account Manager

Signature…………………… Dated: 17th  January, 2018

KILGORIS

IEBC NUMBER 177

CONSTITUENCY DEVELOPMENT FUND

CODELIST

2017/2018 FINANCIAL YEAR

SUBMITTED

JANUARY 2018

Introduction or Background

  - About NG CDF

The Constituencies Development Fund (NG CDF) was established under the Constituencies Development Fund (NG CDF) Act, 2003, amended in 2007 and repealed by the NG CDF Act of 2013.In 2015, the NG CDF Act of 2013 was declared unconstitutional and a new Act was enacted in 2015, being the National Government Constituencies Development Fund Act, NG-NG CDF Act, 2015. The National Government Constituencies Development Fund (NG-NG CDF) is under the ministry of Devolution and Planning. The objective of the fund is to provide mechanisms for supplementing implementation of the National Government Development Agenda at the Constituency level.

The enactment of the NG CDF Act 2013 was mainly aimed to ensure that the law governing NG CDF is aligned to the Constitution of Kenya 2010, specifically in compliance with the principles of:

- Transparency and accountability,

- Sseparation of powers; and

- Participation of the people.

- The new law was also aimed to align the operations of the Fund to the new devolved government structure.

  - About Kilgoris

Kilgoris Constituency is one of the six constituencies in: Narok County. It covers geographical area of Sq. Km (Approx.) 2,526.00 currently it has a population of 18,417 (2009 Census) It is mainly inhabited by the Maasai and Kalenjin community. Cattle Farming is the main economic activity in the constituency. Kilgoris Constituency is an electoral constituency in Narok County, Kenya. It used to be the only constituency in the former Trans Mara District. The constituency was established for the 1997 elections. The towns of Kilgoris, Emarti and Lolgorian are located in this constituency.

The constituency has six wards namely

Angata

Comprises Oldonyo-Orok, Kondamet, Enkoperiae, Magena, Mashangwa, angata Barikoi, Ngendalel, Chelchel and Siteti sub–Location of Narok County

Shankoe

Comprises Ololchani, Lepolosi, Endonyo Nkopit, Osinoni, Nyasita, Olalui, Ilmeshuki, Mukulelta, Shankoe, Olereko and Enaenyieny Sub–Locations of  Narok County

Kimintet

Comprises Oloololo, Kirindoni, Esoit Naibor, Sitoka, Pusanki, Emarti and Ntulele Sub–Locations of  Narok County

Lolgorian

Comprises Kerinkanne, ololmongi, Kawai, Olkiloriti, Olmotonyi, Lolgorian, Moita, Nkararo, Masurura, Naar-olong and Nentekeny Sub–Locations of  Narok County

Kilgoris central

This covers the town which is also administrative centre called transmara west subcounty.

The committee has a number of challenges, the constituency being vast the issue of project monitoring has been difficult. Secondly the constituency has many poor residents hence the applicants for bursary is overwhelming hence leading to awarding of little to the beneficiaries.

- Projects funding in the previous financial year

Number/allocation of completed projects 2016/2017 financial year

| Sector | Number of completed projects | Cost | Remarks |
| --- | --- | --- | --- |
| Education | 13 | 33,800,000.00 | Complete and in use |
| Security | 5 | 4,329,310.48 | Complete and in use |
| Others | 2 | 3,637,931.00 | Complete and in use |

- Number/allocation of ongoing projects 2016/2017 financial year

| Sector | Number of completed projects | Cost | Remarks |
| --- | --- | --- | --- |
| NG CDF OFFICE Construction | 1 | 2,000,000 | On-going |
| Education | 8 | 10,000,000.00 | - |
| Security | 16 | 23,000,000.00 | - |

- Amount of money used for bursaries, number of beneficiaries and criteria used for 2016/2017 financial year

| Institution | Allocation per Child | Number of Beneficiaries | Amount allocated | Remarks (mention criteria) |
| --- | --- | --- | --- | --- |
| Secondary Schools | 5,000 | 3,800 | 18,883,793.00 | Forms distributed through chief’s, filled, signed by the various institutions and returned by the applicants to the office. There exist 15-18 member ward development sub committees that vet the forms and recommend the beneficiaries. The exercise is supervised by the NG CDFC. The finalized list and the minutes are later forwarded to NG CDFC for ratification and processing of cheques which are forwarded to the beneficiary institutions |
| Tertiary Institutions | 7,500 | 968 | 7,260,000.00 |  |
| Special schools | 15,000 | 168 | 2,520,000.00 |  |
| Total |  | 4,936 | 28,663,793.00 |  |

2.0: Ward meetings

2.1: REPORT OF SHANKOE WARD PRIORITY IDENTIFYING MEETING HELD ON 11th  DECEMBER, 2017 AT SHANKOE  TOWNSHIP

MEMBERS PRESENT

- Shadrack Kasy Seiyio			                       Chairperson

- Ruth Naiduya Saisi   Member		                        Secretary

- Isaac Lemayian Musunkui                                         Member

- Bancy Cherono Korir                                                  Member

- David Karuiki Wainaina                                             Member

- Samwel Naikada                                                          Member

- Mary Ampany                                                              Member

- John Megorokini. Kirentuan	              	              Member

- Hassan Nuru Muhammed	                         	  DCC

- Gedion Konchella	   	                                      Member of Parliament

- Benson Aseka                                                               District Accountant

The meeting was held on 11th December 2017 at Shankoe Centre, Shankoe ward. Members of the Public from Shankoe Ward turned out in large numbers. The occasion was graced by the area M.P Hon Konchella. The M.P informed the members of the public that it is the beginning of another financial year FY 2017/2018 and the public should give priorities of the projects they need to be funded by NG CDF. The Fund Account Manager informed the members of the public that NG CDF will only fund public institutions that will benefit the community. He further went ahead and read the projects that cannot be funded by NG CDF. The NG CDFC Chairman informed the public that the NG CDFC had devolved Bursary vetting to the wards and that in every ward there was a 12 to 18 member bursary subcommittee to vet the applicants in their respective wards and there was there was grass root participation and transparency and helped reduce complains. The leaders were requested to assist the NG CDFC members identify most needy students in the ward and give them first priority especially the orphans. The public mainly prioritized on completion of the ongoing projects in the ward. They also requested NG CDF to give priorities on education i.e building of schools and bursaries.

There were no major challenges noticed in that ward. The area M.P requested the members of the public to work together with the NG CDFC to ensure that funds allocated to the projects will be utilized accordingly. Projects suggested are as:

Ilpashire primary school            Construction of a dormitory

Ilpashire Primary School           Construction of a staff houses

Ikarian Primary School             Construction of a dining hall.

Sitoka Primary School               Construction of two dormitories

Angata Secondary school	Construction of a dormitory

Enkoiperiai primary school   Renovation of 6 classrooms, re-roofing, purchase of two water tanks & gutters

Mashankwa primary school              Construction of one classroom

Josephs Girls Boarding primary School        Completion of a dormitory Painting

Kilgoris DEB Primary                                  Construction of a dormitory

Kilgoris Girls Sec School                           Construction of a dining hall

Olalui Primary School                              Construction of six classrooms

  - Kimintet ward

The meeting was held on 12th   December 2017 at Emarti Shopping Centre. Members of the Public from Kimintet Ward turned out in large numbers. The occasion was graced by the area M.P Hon Konchella. The M.P informed the members of the public that it is the beginning of another financial year FY 2017/2018 and the public should give priorities of the projects they need to be funded by NG CDF. The Member of Parliament also noted the constituency allocation has decreased from ksh 101 million to kshs. 86 million and that they will lobby for increase in the funding for coming years so that development is accelerated. The Fund Account Manager informed the members of the public that NG CDF will only fund public institutions that will benefit the community. He further went ahead and read the projects that cannot be funded by NG CDF. The NG CDFC Chairman informed the public that the NG CDFC had devolved Bursary vetting to the wards and that in every ward there was a 12 to 15 member bursary subcommittee to vet the applicants in their respective wards and there was there was grass root participation and transparency and helped reduce complains. The leaders were requested to assist the NG CDFC members identify most needy students in the ward and give them first priority

M.P requested the members of the especially the orphans. The public mainly prioritized on completion of the ongoing projects in the ward. They also requested NG CDF to give priorities on education i.e building of schools and bursaries.

There were no major challenges noticed in that ward. The area public to work together with the NG CDFC to ensure that funds allocated to the projects will be utilized accordingly. Projects suggested are as:

Ntulele secondary school                   Completion of four classrooms

Bokoria primary school                      Construction of two classrooms

Kilae Primary School                         Construction of one classroom.

Kilgoris Girls Secondary School        Purchase of a school bus

Olgos Sopia Primary School           Construction of a dormitory

Sitoka Primary School                      Construction of two dormitories

Ilookwaya Primary School                 Construction of two Classrooms

Tumpelian Primary School              Construction of staff houses

  - LolgorianWard

- The meeting was held on 13th    December, 2017 at Lolgorian Chief’s office. Members of the Public from Lolgorian Ward turned out in large numbers. The occasion was graced by the area M.P Hon Konchella. The M.P informed the members of the public that it is the beginning of another financial year FY 2017/2018 and the public should give priorities of the projects they need to be funded by NG CDF. The Fund Account Manager informed the members of the public that NG CDF will only fund public institutions that will benefit the community. He further went ahead and read the projects that cannot be funded by NG CDF. The NG CDFC Chairman informed the public that the NG CDFC had devolved Bursary vetting to the wards and that in every ward there was a 12 to 18 member bursary subcommittee to vet the applicants in their respective wards and there was there was grass root participation and transparency and helped reduce complains. The leaders were requested to assist the NG CDFC members identify most needy students in the ward and give them first priority especially the orphans. The public mainly prioritized on completion of the ongoing projects in the ward. They also requested NG CDF to give priorities on education i.e building of schools and bursaries.

There were no major challenges noticed in that ward. The area M.P requested the members of the public to work together with the NG CDFC to ensure that funds allocated to the projects will be utilized accordingly. Projects suggested are as follows:

Enkiwancha primary construction of two classrooms

Motony primary school                                     Fencing school & school gate

Olopikidongoe Primary School                         Construction of a staff house.

Ilkarian Primary School                                     Construction of a dining hall,

Senior Chief Ole Nkoidilla Primary School        Construction of a dormitory

Mosiro Primary School                                      Construction of one  classroom.

Oltumaroi Primary School                                 Construction of one classroom

1.4 Angata Ward

The meeting was held on 14th December 2017 at Gathanji Primary school. Members of the Public from Angata Ward turned out in large numbers. The occasion was graced by the area M.P Hon Konchella The M.P informed the members of the public that it is the beginning of another financial year FY 2017/2018 and the public should give priorities of the projects they need to be funded by NG CDF. The Fund Account Manager informed the members of the public that NG CDF will only fund public institutions that will benefit the community. He further went ahead and read the projects that cannot be funded by NG CDF. The NG CDFC Chairman informed the public that the NG CDFC had devolved Bursary vetting to the wards and that in every ward there was a 12 to 18 member bursary subcommittee to vet the applicants in their respective wards and there was there was grass root participation and transparency and helped reduce complains. The leaders were requested to assist the NG CDFC members identify most needy students in the ward and give them first priority especially the orphans. The public mainly prioritized on completion of the ongoing projects in the ward. They also requested NG CDF to give priorities on education i.e building of schools and bursaries.

There were no major challenges noticed in that ward. The area M.P requested the members of the public to work together with the NG CDFC to ensure that funds allocated to the projects will be utilized accordingly. Projects suggested are as follows:

Enkoiperiai primary school    	Renovation of 6 classrooms, re-roofing, purchase of two water tanks & gutters

Kaptembwa primary school	            Completion of two classrooms

Ongata girls secondary School	Purchase of a bus purchase

Mashankwa primary school	construction of one classroom

Manyatta Primary School Construction of two classrooms

Sosiana Primary School Construction of two classrooms

Tagitech Primary School Construction of two classrooms i.e foundation walling and lintel

1.5 Kilgoris Central Ward

The meeting was held on 15th December 2017 at NG CDF compound. Members of the Public from Central Ward turned out in large numbers. The occasion was graced by the area M.P Hon Konchella The M.P informed the members of the public that it is the beginning of another financial year FY 2017/2018 and the public should give priorities of the projects they need to be funded by NG CDF. The Fund Account Manager informed the members of the public that NG CDF will only fund public institutions that will benefit the community. He further went ahead and read the projects that cannot be funded by NG CDF. The NG CDFC Chairman informed the public that the NG CDFC had devolved Bursary vetting to the wards and that in every ward there was a 12 to 18 member bursary subcommittee to vet the applicants in their respective wards and there was there was grass root participation and transparency and helped reduce complains. The leaders were requested to assist the NG CDFC members identify most needy students in the ward and give them first priority especially the orphans. The public mainly prioritized on completion of the ongoing projects in the ward. They also requested NG CDF to give priorities on education i.e building of schools and bursaries.

There were no major challenges noticed in that ward. The area M.P requested the members of the public to work together with the NG CDFC to ensure that funds allocated to the projects will be utilized

Pimbinet primary school                    Purchase of Two water tanks & gutters

Metunkuar secondary school	            Dormitory construction

Metunkuar secondary school	            Purchase of a bus

Remosha secondary	                        Purchase of a bus purchase

Poroko Special School                      Construction of three classrooms

Shartuka Secondary School             Construction of a dormitory

Ilpashire Primary  School                Construction of staff houses

1.6 Keiyan Ward

The meeting was held on 15th December 2017 at NG CDF compound. Members of the Public from Keiyan Ward turned out in large numbers. The occasion was graced by the area M.P Hon Konchella The M.P informed the members of the public that it is the beginning of another financial year FY 2017/2018 and the public should give priorities of the projects they need to be funded by NG CDF. The Fund Account Manager informed the members of the public that NG CDF will only fund public institutions that will benefit the community. He further went ahead and read the projects that cannot be funded by NG CDF. The NG CDFC Chairman informed the public that the NG CDFC had devolved Bursary vetting to the wards and that in every ward there was a 12 to 18 member bursary subcommittee to vet the applicants in their respective wards and there was there was grass root participation and transparency and helped reduce complains. The leaders were requested to assist the NG CDFC members identify most needy students in the ward and give them first priority especially the orphans. The public mainly prioritized on completion of the ongoing projects in the ward. They also requested NG CDF to give priorities on education i.e building of schools and bursaries.

There were no major challenges noticed in that ward. The area M.P requested the members of the public to work together with the NG CDFC to ensure that funds allocated to the projects will be utilized. Proposed projects are as:

Karda primary	                      Renovation of four classrooms

Enoosaen secondary school	          Construction of a dining hall

Narrolong primary	                      Purchase of a bus purchase

Enoosaen police station	          Construction of a police station

Kaptembwa primary school             Completion of two classrooms

Ongata girl’s secondary school         bus purchase

Oloosentu Primary School              Construction of three classrooms

______________________________			____________________________

Signed (Chairman)			                                     Date: 23/12/2017

SHADRACK SEIYIO

______________________________			____________________________

Signed (Fund Account Manager)				  Date: Date: 23/12/2017

ERIC MUANGE

______________________________			____________________________

Signed (Sub-County Commissioner)			               Date: 23/12/2017

MOHAMMED HASSAN

Kilgoris National Government Constituency Development Fund

Project Proposal 2017/2018 Financial Year

Codelist

FINANCIAL YEAR: 1ST JULY 2017 1ST JULY TO 30TH JUNE, 2018

| Project name | Project code | Original cost | Cumulated allocation | Allocation | Proposed activity | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Goods and Services 3% | 4-033-177-2210000-111-2017/2018-001 | 887,241.11 | 887,241.11 | 887,241.11 | Purchase of fuel, repairs and maintenance, printing, stationery, Airtime, travel and subsistence. | Ongoing |
| Committee Expenses 3% | 4-033-177-2210802-111-2017/2018-002 | 900,000.00 | 900,000.00 | 900,000.00 | Payment of Committee sitting allowances, transport, conferences | Ongoing |
| NG CDFC/PMC Capacity Building 3% | 4-033-177-2210700-111-2017/2018-003 | 680,000.00 | 680,000.00 | 680,000.00 | Undertake Training of the PMCs/NG CDFCs on NG CDF Related issues | Ongoing |
| Employees Salaries-6% | 4-033-177-2110000-100-2017/2018-001 | 1,980,000.00 | 1,980,000.00 | 1,980,000.00 | Payment of staff salaries, PAYE and gratuity | Ongoing |
| Goods and Services-6% | 4-033-177-2210000-100-2017/2018-002 | 960,000.00 | 960,000.00 | 960,000.00 | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea. | Ongoing |
| NSSF | 4-033-177-2120500-100-2017/2018-003 | 135,000.00 | 135,000.00 | 135,000.00 | Payment of NSSF Deductions | Ongoing |
| NHIF | 4-033-177-2120200-100-2017/2018-004 | 45,000.00 | 45,000.00 | 45,000.00 | Payment of NHIF Deductions | Ongoing |
| Committee Allowances -6% | 4-033-177-2210802-100-2017/2018-006 | 1,814,482.00 | 1,814,482.00 | 1,814,482.00 | Payment of Committee allowances | Ongoing |
| Strategic plan | 4-033-177-2211310-108-2017/2018- 007 | 3,500,000.00 | 3,500,000.00 | 3,500,000.00 | Implementation of Constituency five year Strategic plan ,holding consultative forums, technical evaluation by consultants, validation, collection of constituency fact sheet data and launching | New |
| Kilgoris CDF office | 4-033-177-3110104-108-2017/2018-001 | 2,000,000.00 | 2,000,000.00 | 2,000,000.00 | Purchase of office furniture & equipment i.e 2executive tables @ksh 56,000, 2executive chairs @ 56,000, 110 conference chairs @ ksh 8,500 (for NG-NG CDFC Hall),3 office tables @ ksh 30,000,3 computers @ ksh 90,000,2 printers @ ksh 50,000, 10high back office chairs @ksh 15,000,photocopier @ ksh 300,000 & projector @ kshs 60,000. | New |
| Emergency | 4-033-177-2640200-101-2017/18-001 | 4,568,965.52 | 4,568,965.52 | 4,568,965.52 | To cater for any unforeseen occurrences in the constituency during the financial year | Ongoing |
| Constituency Sports Tournament | 4-033-177-2640508-112-2017/18-001 | 1,433,739.00 | 1,433,739.00 | 1,433,739.00 | Carry out Constituency Sports tournament and the winning teams/schools to be awarded with trophies, balls, and games kits | Ongoing |
| Environment | 4-240- 092-2640510-109-2017/2018-001 | 300,000.00 | 300,000.00 | 300,000.00 | Purchase & distribution of tree seedlings to various schools, Ilparishe, Shankoe &Poroko primary schools each at ksh.100,000.00 | Ongoing |
| Bursary secondary schools | 4-033-177-2640101-103-2015/2016-001 | 15,000,000.00 | 15,000,000.00 | 15,000,000.00 | To cater for needy/&bright students in secondary schools | Ongoing |
| Bursary tertiary institutions | 4-033-177-2640101-103-2015/2016-002 | 5,600,000.00 | 5,600,000.00 | 5,600,000.00 | To cater for needy/&bright students in, tertiary institutions & universities | Ongoing |
| Social security programmes-NHIF | 4-033-177-2120201-103-2016/17-003 | 4,200,000.00 | 4,200,000.00 | 4,200,000.00 | Payment for NHIF targeting OVC, poor older persons, PWD's, poor widows & widowers & destitute families | New |
| Constituency innovation Hub (CIH)at Gathanji | 4-033-177-2211311-111-2017/2018- 003 | 1,169,256.80 | 1,169,256.80 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Constituency innovation Hub (CIH)at Gathanji | 4-033-177-2211311-111-2017/2018- 004 | 1,169,256.80 | 1,169,256.80 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Constituency innovation Hub (CIH)at Gathanji | 4-033-177-2211311-111-2017/2018- 005 | 1,169,256.80 | 1,169,256.80 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Constituency innovation Hub (CIH)at Gathanji | 4-033-177-2211311-111-2017/2018- 006 | 1,169,256.80 | 1,169,256.80 | 1,169,256.80 | Installation of Satelite antenna, Router, Digital access kit, Digital ruggedized Tablet, WI-FI with outdoor wireless device complete with 12U cabinet with installation accessories by Telkom Kenya ltd | New |
| Narrolong primary school | 4-033-177-2630204-103-2017/18-001 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Enkiwancha primary school | 4-033-177-2630204-103-2017/18-002 | 2,000,000.00 | 2,000,000.00 | 2,000,000.00 | Construction of two classrooms to completion | New |
| Bokoria primary school | 4-033-177-2630204-103-2017/18-003 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | Construction of six door pit latrines for boys and girls | New |
| Enkoiperiai primary school | 4-033-177-2630204-103-2017/18-004 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | Renovation of six (6) classrooms, re-roofing, External & internal finishes | New |
| Sosio primary school | 4-033-177-2630204-103-2017/18-005 | 1,500,000.00 | 1,500,000.00 | 1,500,000.00 | Completion of three classrooms, plastering, external & internal finishes & painting. | Ongoing |
| Kaptembwa primary school | 4-033-177-2630204-103-2017/18-006 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | Completion of two classrooms, plastering, external & internal finishes & painting. | Ongoing |
| Karda primary school | 4-033-177-2630204-103-2017/18-007 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | Renovation of four classrooms re-roofing, flooring & painting | New |
| Mashankwa primary school | 4-033-177-2630204-103-2017/18-008 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | construction of one classroom to completion | New |
| Shankoe primary school | 4-033-177-2630204-103-2017/18-009 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 | Renovation of 8 classrooms , | New |
| Sitoka primary school | 4-033-177-2630204-103-2017/18-010 | 3,500,000.00 | 1,000,000.00 | 2,500,000.00 | Plumbing works & plastering ,internal & external finishes & painting of dormitory | Ongoing |
| Ildolisho primary school | 4-033-177-2630204-103-2017/18-011 | 6,500,000.00 | 4,500,000.00 | 2,000,000.00 | Completion of dormitory, plastering, fixing doors & windows, flooring, external & internal finishes & painting | Ongoing |
| Angata primary school | 4-033-177-2630204-103-2017/18-012 | 6,500,000.00 | 6,000,000.00 | 500,000.00 | Completion of dormitory, plastering ,internal & external finishes & painting | Ongoing |
| Pimbinet primary school | 4-033-177-2630204-103-2017/18-013 | 500,000.00 | 500,000.00 | 500,000.00 | Purchase & installation of Two water tanks of each 10,000 lts & gutters for water harvesting & construction of tank stands | New |
| Oldonyo Rok primary | 4-033-177-2630204-103-2017/18-014 | 6,500,000.00 | 6,000,000.00 | 500,000.00 | Complete, ,internal & external finishes & painting of dormitory | Ongoing |
| Mashankwa primary school | 4-033-177-2630204-103-2017/18-015 | 6,500,000.00 | 5,000,000.00 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting of dormitory | Ongoing |
| Tororek primary school | 4-033-177-2630204-103-2017/18-016 | 7,500,000.00 | 6,000,000.00 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting | Ongoing |
| Ntulele secondary school | 4-033-177-2630205-104-2017/18-001 | 1,500,000.00 | 1,500,000.00 | 1,500,000.00 | Completion of four classrooms, plastering flooring, internal & external finishes & painting | Ongoing |
| Olalui secondary school | 4-033-177-2630205-104-2017/18-002 | 2,628,890.00 | 2,628,890.00 | 2,628,890.00 | Construction of a Dormitory | New |
| Ongata girls secondary school | 4-033-177-2630205-104-2017/18-003 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Remosha secondary school | 4-033-177-2630205-104-2017/18-004 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | Purchase of 51 seater school bus, Co-funded by PTA | New |
| Enoosaen secondary school | 4-033-177-2630205-104-2017/18-005 | 3,000,000.00 | 3,000,000.00 | 3,000,000.00 | Construction of a dining hall | New |
| Metunkuar secondary school | 4-033-177-2630205-104-2017/18-006 | 2,000,000.00 | 2,000,000.00 | 2,000,000.00 | Construction of a Dormitory | New |
| Angata Secondary school | 4-033-177-2630205-104-2017/18-007 | 6,500,000.00 | 5,000,000.00 | 1,500,000.00 | Completion of a dormitory, plastering ,internal & external finishes & painting | Ongoing |
|  |  |  | Total | 86,810,344.83 |  |  |

COMPILED BY:

ERIC MUANGE

FAM

KILGORISNG-NG CDF