| NG-CDF | National Government Constituencies Development Fund Kilgoris Constituency P.O Box 361-40700 KILGORIS cdfkilgoris@ngcdf.go.ke |
| --- | --- |

MINUTES OF KILGORIS NG-CDF COMMITTEE MEETING HELD ON 1`7TH JUNE, 2019 AT THE KILGORIS CONSTITUENCY BOARDROOM AT 0930 HOURS

MEMBERS PRESENT

- Shadrack Kasy Seiyio			                 Chairperson

- Ruth Naiduya Saisi   Member		                Secretary

- Isaac Lemayian Musunkui                                       Member

- Bancy Cherono Korir                                              Member

- David Karuiki Wainaina                                          Member

- Samwel Naikada                                                      Member

- Mary Ampany                                                          Member

- John Megorokini. Kirentuan	              	   Member

- Eric Muange	   	                                      F.A.M

Absent with apology

Hassan 	Nuru Muhammed	                      	   DCC

AGENDA

- Reading and confirmation of previous minutes

- Matters arising

- Reallocation

- Project reports

- AOB

PRELIMINARIES

The meeting started with prayers led by Mr. Naikada. The chair welcomed the members to the meeting and asked them to be ready to deliberate on the meeting’s agenda.

MIN CDFC 01/06/2019 READING AND CONFIRMATION OF PREVIOUS MEETING

The minutes were read out by Fund Account manager and proposed by Ruth Saisi and seconded by Mr. Naikada as true records of the previous meeting.

MIN CDFC 02/ 06/2019 MATTERS ARISING

There were no matters arising from the minutes of the previous meeting.

MIN: CDFC 03/06/2019	REALLOCATION

The chairman informed the members that it has not been easy to implement the ICT-hub projects at Shankoe, Lolgorian ward, Keiyian Ward and  Kilgoris Centre which were allocated Kshs. 1,169,256.8o each in the 2017/18 FY (totaling to Kshs 4,677,027.20). After deliberations, the members agreed that due to lack of requisite infrastructure for the implementation of the projects, they be reallocated to the following projects.

| Proposed Project | Amount | Activity |
| --- | --- | --- |
| Enkakenya primary school | 650,000 | Completion of a dormitory; ceiling and painting |
| Olmeoshi primary school | 1,200,000 | Construction of one classroom to completion |
| Enoosaen Boys Secondary school | 670,000 | Completion of a multipurpose dining hall; ceiling |
| Kaptembwo primary school | 1,200,000 | Construction of one classroom to completion |
| Kilgoris Vocational and Training centre | 957,027.20 | Completion of two classrooms; fixing of doors and windows, plastering and painting |

The members also deliberated on the on the need to reallocate emergency funds allocated in 2018/19 due to the fact that it has remained unutilized yet the financial year is ending. Based on this fact, it was unanimously agreed that emergency funds for 2018/19 be reallocated to the following projects with effect from 1st July 2019.

- Angata Barrikoi Girls secondary school, Kshs.1,650,000-Completion of staff house (flooring, plastering, fascia board, fixing of doors and windows)

- Shartuka Girls secondary school, Kshs.315,000-purchase and delivery of 20 double decker bed

- Kilgoris Vocational and Training centre, Kshs.642,972.80- Completion of two classrooms; fixing of doors and windows, plastering and painting; painting of 4 classrooms; and ceiling of one classroom.

- Ikarian primary school, Kshs.620,000-purchase and delivery of 40 double decker beds

- Shartuka primary school, Kshs.400,000- completion of two classrooms; roofing, verandah and fixing of doors and windows

- Njipship primary school, Kshs.450,000-Completion of two classrooms; slabbing, flooring, painting, fixing of doors and windows

- DCC’s office (Transmara West), Kshs.1,100,000- Construction of 4 doors flush toilet  with urinal at Kshs 1,000,000 and purchase of 10,000 litres water tank

Due to high number of requests for bursary and lack of guidelines on the usage of social security funds, the members resolved to reallocate Kshs.2,850,000 allocated in 2018/19 FY to Social security programme for Payment for NHIF targeting OVC,  poor older persons, PWD's, poor widows and widowers  & destitute families to  the following projects:

- Doinyo primary school, Kshs.1,200,000-Completion of two classrooms; flooring, plastering, painting, fixing of doors and windows

- Kilae primary school, Kshs.650,000-Completion of one classroom; flooring, plastering, painting, fixing of doors and windows

- Enkiloriti primary school, Kshs. 1,000,000-Completion of two classrooms; flooring, plastering, painting, fixing of doors and windows

MIN: CDFC 04/ 06/2019 ADJOURNMENT

There been no other business the meeting ended at 1230 hours with a word of prayer from Mr. Naikada.

Minutes Taken by:

CDFC Secretary: Ruth Saisi                                      Sign_______________________

Confirmed by:

CDFC Chairman: Shadrack Seiyio                              Sign_______________________

National Government Constituencies Development Fund

FIRST SCHEDULE     (S. 6) (5)

CONSTITUENCY PROJECTS RE – ALLOCATION FORM

CONSTUENCY N0:  177 CONSTITUENCY NAME: KILGORIS FINANCIAL YEAR: 2017/2018

| PROJECT NO. | PROJECT TITLE | AMOUNT ALLOCATED (KSH) | AMOUNT DISBURSED (KSH) | BALANCE (KSH) | UNSPENT TO BE RE – ALLOCATED (KSH) |
| --- | --- | --- | --- | --- | --- |
| 4-033-177-2211311-108-2017/18- 001 | Constituency Innovation Hub (CIH)at Shankoe | 1,169,256.80 | 1,169,256.80 | 00 | 1,169,256.80 |
| 4-033-177-2211311-108-2017/18- 002 | Constituency Innovation Hub (CIH)at Lolgorian Ward | 1,169,256.80 | 1,169,256.80 | 00 | 1,169,256.80 |
| 4-033-177-2211311-108-2017/18- 003 | Constituency Innovation Hub (CIH)at Kilgoris Centre | 1,169,256.80 | 1,169,256.80 | 00 | 1,169,256.80 |
| 4-033-177-2211311-108-2017/18- 004 | Constituency Innovation Hub (CIH)at Keiyian | 1,169,256.80 | 1,169,256.80 | 00 | 1,169,256.80 |
| Total |  | 4,677,027.20 | 4,677,027.20 | 00 | 4,677,027.20 |

Name: Eric Muange  Position: Fund Account Manager

Signature: ………………………………………………      Date: ……………………………..

National Government Constituencies Development Fund

FIRST SCHEDULE     (S. 6) (5)

CONSTITUENCY PROJECTS RE – ALLOCATION FORM

CONSTUENCY N0:  177 CONSTITUENCY NAME: KILGORIS FINANCIAL YEAR: 2018/2019

| PROJECT NO. | PROJECT TITLE | AMOUNT ALLOCATED (KSH) | AMOUNT DISBURSED (KSH) | BALANCE (KSH) | UNSPENT TO BE RE – ALLOCATED (KSH) |
| --- | --- | --- | --- | --- | --- |
| 4-018-177-2640103-103-2018/19-003 | Social security programme-NHIF | 4,000,000 | 4,000,000 | 00 | 2,850,000 |
| 4-018-177-2640200-101-2018/19-001 | Emergency | 5,738,993.45 | 5,738,993.45 | 00 | 5,177,972.80 |
| Total |  | 9,738,993.45 | 9,738,993.45 | 00 | 8,027,972.80 |

Name: Eric Muange  Position: Fund Account Manager

Signature: ………………………………………………      Date: ……………………………..

National Government Constituencies Development Fund

THIRD SCHEDULE ( ss. 25 (6),11 and ,29(1)

CONSTITUENCY PROJECTS SUBMISSION FORM

CONSTUENCY N0:177 CONSTITUENCY NAME: KILGORIS   FINANCIAL YEAR: 2018/2019

Chairman CDFC Committee: SHADRACK SEIYO    Signature: …………………Date: …………

| SERIAL NO. | NAME OF PROJECT | AMOUNT ALLOCATED (Kshs) |
| --- | --- | --- |
| 1 | TERTIARY INSTITUTION | 1,600,000 |
| 2 | SECONDARY SCHOOLS | 2,635,000 |
| 3 | PRIMARY SCHOOLS | 7,370,000 |
| 4 | SECURITY | 1,100,000 |
| TOTAL |  | 12,705,000 |

Name: ERIC MUANGE    Position: Fund Account Manager

Signature: …………………………        Date: ……………………………..

National Government Constituencies Development Fund

FOURTH SCHEDULE					(s. 30)

PROJECT DISCRIPTION FORM

Constituency No: 177 Constituency name: KILGORIS   County: NAROK

Project Number: 104/2630204

Project Title: primary schools

Sector: Education

Status of projects (Tick one)

New………………….Extension………√……….Ongoing……………….

Rehabilitation………………………………………………….

Brief Statement on progress at time of submission:

To improve infrastructure in the named schools

Financial year under reference 1st July 2018 – 30th June 2019

Original Cost Estimates ksh 7,370,000.00Date… …………

Amount allocated last financial year;

Amount allocated this financial year: kshs 7,370,000

| Project Name | Project Number | Project Activity | Amount allocated (Kshs) | Current Status |
| --- | --- | --- | --- | --- |
| Enkakenya primary school | 4-033-177-2630204-104-2018/19-013 | Completion of a dormitory; ceiling and painting | 650,000 | Ongoing |
| Olmeoli primary school | 4-033-177-2630204-104-2018/19-014 | Construction of one classroom to completion | 1,200,000 | New |
| Kaptembwo primary school | 4-033-177-2630204-104-2018/19-015 | Construction of one classroom to completion | 1,200,000 | New |
| Ikarian primary school | 4-033-177-2630204-104-2018/19-016 | Purchase and delivery of 40 double decker beds | 620,000 | New |
| Shartuka primary school | 4-033-177-2630204-104-2018/19-017 | completion of two classrooms; roofing, verandah and fixing of doors and windows | 400,000 | Ongoing |
| Doinyo primary school | 4-033-177-2630204-104-2018/19-019 | Completion of two classrooms; flooring, plastering, painting, fixing of doors and windows | 1,200,000 | Ongoing |
| Kilae primary school | 4-033-177-2630204-104-2018/19-020 | Completion of one classroom; flooring, plastering, painting, fixing of doors and windows | 650,000 | Ongoing |
| Enkiloriti primary school | 4-033-177-2630204-104-2018/19-021 | Completion of two classrooms; flooring, plastering, painting, fixing of doors and windows | 1,000,000 | Ongoing |
| Njipship primary school | 4-033-177-2630204-104-2018/19-018 | Completion of two classrooms; slabbing, flooring, painting, fixing of doors and windows | 450,000 | Ongoing |
| Total |  |  | 7,370,000 |  |

Person completing the form: ERIC MUANGE    Position: Fund Account Manager

Signature: …………………………        Date: ……………………………..

National Government Constituencies Development Fund

FOURTH SCHEDULE					(s. 30)

PROJECT DISCRIPTION FORM

Constituency No: 177 Constituency name: KILGORIS   County: NAROK

Project Number: 104/2630205

Project Title: Secondary schools

Sector: Education

Status of projects (Tick one)

New………………….Extension………√……….Ongoing……………….

Rehabilitation………………………………………………….

Brief Statement on progress at time of submission:

To improve infrastructure in the named school

Financial year under reference 1st July 2018 – 30th June 2019

Original Cost Estimates ksh 670,000.00Date… …………

Amount allocated last financial year;

Amount allocated this financial year: kshs 670,000.00

| Project Name | Project Number | Project Activity | Amount allocated (Kshs) | Current Status |
| --- | --- | --- | --- | --- |
| Enoosaen Boys Secondary school | 4-033-177-2630205-104-2018/19-007 | Completion of a multipurpose dinning hall; ceiling | 670,000 | Ongoing |
| Angata Barrikoi Girls secondary school | 4-033-177-2630205-104-2018/19-008 | Completion of staff house (flooring, plastering, fascia board, fixing of doors and windows) | 1,650,000 | Ongoing |
| Shartuka Girls secondary school | 4-033-177-2630205-104-2018/19-009 | purchase and delivery of 20 double decker bed | 315,000 | New |
| Total |  |  | 2,635,000 |  |

Person completing the form: ERIC MUANGE    Position: Fund Account Manager

Signature: …………………………        Date: ……………………………..

National Government Constituencies Development Fund

FOURTH SCHEDULE					(s. 30)

PROJECT DISCRIPTION FORM

Constituency No: 177 Constituency name: KILGORIS   County: NAROK

Project Number: 104/2630206

Project Title: Tertiary institution

Sector: Education

Status of projects (Tick one)

New………………….Extension………√……….Ongoing……………….

Rehabilitation………………………………………………….

Brief Statement on progress at time of submission:

To improve infrastructure in the named institution

Financial year under reference 1st July 2018 – 30th June 2019

Original Cost Estimates ksh 957,027.20Date… …………

Amount allocated last financial year;

Amount allocated this financial year: kshs 957,027.20

| Project Name | Project Number | Project Activity | Amount allocated (Kshs) | Current Status |
| --- | --- | --- | --- | --- |
| Kilgoris Vocational and Training centre | 4-033-177-2630206-104-2018/19-001 | Completion of two classrooms; fixing of doors and windows, plastering and painting; painting of 4 classrooms; and ceiling of one classroom. | 1,600,000 | Ongoing |
| Total |  |  | 1,600,000 |  |

Person completing the form: ERIC MUANGE    Position: Fund Account Manager

Signature: …………………………        Date: ……………………………..

National Government Constituencies Development Fund

FOURTH SCHEDULE					(s. 30)

PROJECT DISCRIPTION FORM

Constituency No: 177 Constituency name: KILGORIS   County: NAROK

Project Number: 113/2640507

Project Title: Security

Sector: security

Status of projects (Tick one)

New………………….Extension………√……….Ongoing……………….

Rehabilitation………………………………………………….

Brief Statement on progress at time of submission:

To improve infrastructure in the named institution

Financial year under reference 1st July 2018 – 30th June 2019

Original Cost Estimates ksh 1,100,000 Date… …………

Amount allocated last financial year;

Amount allocated this financial year: kshs 1,100,000

| Project Name | Project Number | Project Activity | Amount allocated (Kshs) | Current Status |
| --- | --- | --- | --- | --- |
| DCC’s office (Transmara West) | 4-033-177-2640507-113-2018/19-003 | Construction of 4 doors flush toilet with urinal at Kshs 1,000,000 and purchase of 10,000 litres water tank | 1,100,000 | New |
| Total |  |  | 1,100,000 |  |

Person completing the form: ERIC MUANGE    Position: Fund Account Manager

Signature: …………………………        Date: ……………………………..